Annual Review - Summary Sheet

PROGRAMME TITLE: CSSF Egypt Country Programme
Country/Region:	Egypt/MENA
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID), Ministry of Defence (MOD), Home Office, National Crime Agency
Total Spend:	ODA: £10.26m			Non-ODA: n/a
Start Date: April 2017		End Date: March 2018
Outputs					Score
Economy 1 - UK assistance provided to build line Ministries capacity in support of priority areas of the World Bank's Country Partnership Framework.					A+
Economy 2 - UK funded advice identifies start-ups and supports the improvement of their performance.					B
Education - UK education expertise supporting reform and development of Egypt's inclusive education system.					A+
Governance 1 - UK support provided to train and build capacity of Parliamentarians and Ministry of Local Development (MLD) officials.					B
Governance 2 - UK assesses feasibility of support to civil society.					B
Governance 3 - Women's rights organisations in Egypt, Iraq and Lebanon have increased knowledge and skills to undertake advocacy work.					A
Migration - Egyptian authorities at national level are provided with UK international support to implement stronger migration management systems, including law enforcement response against traffickers and irregular migrants and provide alternatives to those at risk of irregular migration.					A
Security - UK support for Multinational Force and Observers (MFO) Bedouin Employment Programme.					A
Research - Develop a research, monitoring and evaluation programme.					A
Overall output score					A
Outcome Assessment: Outcomes are on course to meet expectation.
Outcome Score: A			Risk: Medium / High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	A	B	A	A
Risk Rating	Med/High	Med/High	Med/High

*output/outcome scores

What support is the UK providing?

The UK provides support across six themes: the economy; education; governance; migration; security and research and analysis.

Economy: The UK provides £15m over four years to support the delivery of technical assistance and analytical work in Egypt, to support Government of Egypt’s (GoE) reform priorities. A three-year £2m project creating skills and jobs for men and women through a partnership with the International Finance Cooperation (IFC) to support start-ups with social impact.

Education: A £200k, two-year technical assistance project supporting the GoE’s reform priorities.

Governance: Three £1.8m, three-year projects supporting, respectively, the strengthening of the Egyptian parliament’s committees, a scoping project on how to improve the effectiveness of civil society’s engagement and advocacy with government, and finally women’s rights organisations and women human rights defenders through a regional approach (Egypt, Iraq and Lebanon).

Migration: The CSSF also supports GoE efforts to combat irregular migration (£1.5m over three years) and protects those vulnerable to irregular migration working through the UN (a three-year £500k project) and Non-Governmental Organisations (NGOs) (two three-year £550k and £350k projects).

Security: £750k over three years to contribute to the employment costs of 200 Sinai Bedouin staff as part of the UK’s support to the Multinational Force of Observers.

Research: A £1.8m three-year project to strengthen analysis and build our evidence base on what works for stability in Egypt, build the capacity of staff and implementing partners on monitoring research and evaluation and undertake a rigorous and independent evaluation of Egypt’s CSSF programme in 2020.

Summary of progress and lessons learnt/actions taken since last review

1. This has been a busy third year for CSSF Egypt. The programme team has continued to systematically develop and build on the previous financial year (2016/17). A tracker of the previous year’s recommendations ensured most key actions were delivered, in particular a Theory of Change refresh with strand-specific refreshes underway, tighter monthly forecasting and reporting and a restructured results framework by intervention pillar.
2. The overall weighted-average score is A, which is a fair assessment of programme’s successes and constraints. Economy outputs overall are impact weighted at 50%, considering resources and staff time. But while Economy output 1 (World Bank) scored an A+, Economy output 2 (Start Egypt) due to delays did not meet expectations, so scored a B. Education (impact weighting 13%) also scored an ‘A+’. Migration, Security and Research all met expectations, thus scored an A, with impact weighting of 13%, 2% and 12% respectively. However, Governance outputs, with an overall impact weighting of 13%, did not meet expectations and have scored a ‘B’.
Key achievements

1. The economy pillar has continued to contribute to enhancing government capacity to deliver economic reforms supporting inclusive growth. The technical assistance (TA) provided by the World Bank through the UK-World Bank Trust Fund has delivered more knowledge products (e.g. evaluations, research, studies, etc.) and capacity building activities than expected. These have actively informed reforms and policies, for example, ensuring better targeting of the conditional cash transfers, benefitting 2.2 million households. Although further improvements to the targeting, conditionality and women’s economic empowerment were identified in a gender audit, it is too early to assess the full impact the Trust Fund’s work as most workstreams are still underway. Similarly, due to delays in contracting and money disbursements the Economy 2 (Start Egypt) project was delayed to the next financial year, although the project appears on track to deliver as expected.
2. The education pillar has provided strategically targeted TA to the Ministry of Education to inform wholesale education reform. The activities are timely and targeted TA demonstrates how a modest amount of funding can have a multiplier effect. In Egypt, the largest school system in the Middle East and North Africa, up to 10 million children are failing to acquire core skills. By bringing together UK education expertise in combination with BEIS’s Newton Fund, Chevening scholarships and the British Council, as well as the Department of International Trade’s business and trade partnerships, British Embassy Cairo (BEC) was able to build trust with key stakeholders, and inform the domestic and World Bank case for major institutional change (including supporting the inclusion of students with special educational needs). This coordinated offer helped unlock US$500m World Bank investment.
3. The governance pillar has continued to adapt to the changing context and actors, as the context is particularly fraught, with mixed success. Notable progress includes work with the Egyptian Parliament’s education committee with the UK being considered a model for major reform, triggering interest from other committees such as health and budget. However, demonstrating results in this space, e.g. due to significant and uncertain time lags between activities and changes, remains particularly challenging. Furthermore, the space for working on civil society remains increasingly constricted. The NGO law imposes severe restrictions on NGOs’ ability to register, operate and access foreign funding. Both the above imply the results framework targets should be adapted to be agile, programmatically useful (i.e. for active programme management) and achievable.
4. The migration pillar has contributed to reducing the risks to vulnerable groups to irregular migration and supporting Egypt’s implementation of smuggling and trafficking legislation. There continues to be a moratorium on migrant boats leaving Egypt to cross the Mediterranean, although causality from CSSF activities is hard to establish. BEC support to two smaller specialised organisations offering support to vulnerable persons has exceeded expectations. But the work with two large established partners to influence Egyptian policy on migration has had mixed success. Although the latter has contributed to good working relations in an area of shared interests, its link to outcome-level milestones lacks evidence. BEC should be encouraged to continue exploring how to strengthen the evidence base and using this to explore how to better integrate the projects with the portfolio of the UK Government’s work.
5. The security pillar continues to support a small livelihoods project in Sinai through the MFO, which is appropriate given the current restrictions of working in this sector. However, the static nature of the target - maintaining levels of Bedouin employment – misses the wider benefits to BEC and the UK Government from this support. BEC should consider how to capture wider non-economic benefits in the results framework.
6. The research and analysis pillar is helping improve the analytical and evidence base of the programme and a 2020 evaluation on progress. The work started late in 2017, but has already made progress in developing an overall workplan and a bespoke programme of support to implementing partners, while an evaluation strategy was delayed. Participants in the workshops on reviewing and refreshing the theory of change have found it useful. BEC should be encouraged to share the lessons learnt from this approach more widely and consider how to future-proof the technical support to implementing partners.
Summary of recommendations for the next year

1. Mainstream Political Influence and Access (PIA): The programme needs a more systematic approach to PIA, to monitor and account for the results it achieves, especially where progress is qualitative (governance). In particular, BEC should develop an output indicator on how the Trust Fund leverages influence and access.
2. Improve coherence across the outputs: Barring a couple of examples, the programme needs to demonstrate better coordination and integration across outputs, including between implementing partners where possible. That being said, BEC should explore how to demonstrate it is maintaining a credible balance between working with the grain in GoE priority areas and testing boundaries and maintaining interventions in spaces in areas where the GoE is less permissive. The security, migration and to a lesser extent governance pillars can and should demonstrably play a greater role in cross-fertilisation. And BEC should consider new cross-cutting projects that might help better integrate the portfolio, such as a strategic communications intervention, especially where it could help advance UK public diplomacy (economy) or could help manage or mitigate public communication risks (education).
3. Using the economy pillar to support the portfolio: Given the transition the Egyptian economy is currently going through and centrality of economic/prosperity projects to the portfolio, BEC should consider more in-depth analysis of the drivers of growth, job creation and poverty diagnosis (drawing on HMG tools and BEC’s forthcoming Economic Development strategy) integrated with the regular Joint Analysis of Conflict and Stability to provide a comprehensive picture for economic development programming in a conflict sensitive manner.