Annual Review - Summary Sheet

PROGRAMME TITLE: CSSF Jordan Internal Security Programme
Country	Jordan (Middle East and North Africa –MENA)
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Home Office (HO)
Total Spend:	ODA: £4.4m[1]			Non-ODA: £0.83m
Start Date: April 2016		End Date: March 2019
Outputs					Score
Core policing - community policing programme established in new Governates.					B
Public Security Directorate (PSD) trained in and provided with relevant skills for Counter Terrorism/other investigations.					C
Internal security agencies trained to respond to critical incidents and multi-agency training delivered.					B
Youth and Community Resilience - Pilot project designed and agreed, procurement process for larger multi-year intervention explored / planned / tendered.					B
New Home Office-led policing project designed and delivering.					A
Outcome: Building Jordanian capability to enhance its own security; and enhancing resilience in the face of regional crises and a protracted refugee presence.					B

Overall output score					B
Outcome Assessment: Overall, the outputs are moderately below the outcome sought at this stage in the programme lifecycle.					B
Outcome Score: B			Risk: Medium/High
[1] The difference between the final annual expenditure (£4.4m ODA and £0.83m non-ODA) and the amount indicated in the Programme Document (£4.m ODA) is accounted for by ‘in year’ reallocations and uplifts of funding to the Jordan Security Sector Project (JSSP) and scoping ahead of a new Police Professionalization Project (P3).

Summary of Programme Performance[2]
[2] Although the CSSF Jordan Internal Security Programme in its current configuration began in 2016-17, previous configurations extend back to 2015-16, which explains the inclusion of previous Annual Review scores.
Year	2015/16	2016/17	2017/18*
Programme Score	A	B	B / B
Risk Rating		M/H	M/H

*output/outcome scores

What support is the UK providing?

The Internal Security Programme (ISP) originated as a capacity building programme for selected Jordanian security organisations to enable them to become more effective at contributing to public safety. The UK wanted to offer agile, tactical responses to an urgent need in the wake of the Arab Spring (e.g. public order policing) and the Syrian crisis (e.g. community policing in Azraq and Zaateri). The challenge for the Jordan Security Sector Project (JSSP), the main project in the programme and its successor, is how broader security sector reform can be achieved. A primary goal is to enable these organisations to respond more effectively to major incidents such as terrorist attacks.

UK support has evolved in response to the operational context and covers a range of activity encompassing community policing, investigative policing skills, critical incident response and countering violent extremism. During 2017/18, a new Home Office led policing project was scoped and now planned for FY 2018/19.

Summary of progress and lessons learnt/actions taken since last review

It is encouraging to record the progression in the British Embassy Amman’s management of the ISP over the past year. A number of issues identified in the 16/17 Annual Review have also been addressed. These include:

Mapping stakeholders - The CSSF team has a clear picture of the range of interests with a stake in policing and security both inside the Embassy and in other delegations. This information has been put to good use throughout the year by assisting both planning and in at least one instance successfully deconflicting two projects planned by the UK and another donor on number plate recognition.

Build closer links with Jordanian partners/co-funding donors to connect policy and programming better, the CSSF team has developed a renewed relationship between the Public Security Directorate and Gendarmerie and the main implementing supplier. An improved system involving greater Embassy participation in stakeholder meetings is now in place for discussing and recording progress. Engagement on the new Home Office (HO) project with the Brigadier in charge of PSD Training who is also the Head of the PSD – British Embassy – UK Police Support Team (UKPST) Internal Committee, has also played a major part in this improvement in the JSSP. This new arrangement should go some way towards improving communication and increasing effectiveness.

Consider having a Security Sector Reform adviser in the CSSF team - This proposal was considered but was not progressed at the time as it was not believed that there was enough of a requirement to justify such a position. The CSSF team will be keeping the item under review and recognise the value such external expertise can bring to programming. During the review period it was noted that the CSSF team have appointed a new strategic policing adviser and have used the services of a conflict adviser.

Consider additional work on Countering Violent Extremism (CVE) - This was recognised and accepted by the CSSF team. However, substantive progress was not made due to the team wishing to base its approach on the Jordanian national plan, which at the time of the annual review was not yet published. The CSSF have also been exploring other ways to support CVE whilst being sensitive to the national context, for example through proposed support to the Jordanian National Action Plan on Women Peace and Security (UN Security Council Resolution 1325).

It is noted that the majority of outputs have scored at level B / C due to a range of delivery factors including a period where there was a two month cessation in programming. The outcome scores have also been assessed as being at level B. The review team wish to emphasise that with additional staff in place in the Embassy coupled with new programme management arrangements for the ISP that there is significant potential for improved delivery and impact over the coming year.

Summary of recommendations for the next year

The programme results framework should be revised to ensure that it includes more coherent outcomes and a set of outputs with realistic milestones for assessing progress. This is already in progress.

With the ISP growing in scope and the need to maximise impact across all of the Embassy’s inputs, the CSSF team should draw in external expertise on how the programme could benefit from access to security and justice reform advice on a drawdown basis.

Map out and better understand across the British Embassy and CSSF team who owns and who is responsible for maintaining and developing the various relationships with the Government of Jordan, beneficiaries, other donors and implementing partners. Have a clear plan to ensure these relationships are monitored and any risks to programme delivery flagged early through the country board.

The CSSF team should take advantage of external Monitoring and Evaluation advice to help understand how to build evidence to demonstrate results and give a better understanding of what is working and what is not.

Gain an in-depth understanding of how training/inputs provided contributes to delivering effective impact against the output aims. This should be reflected in the updated Results Framework as an indicator of success and monitored closely.

Take steps to ensure female participation in training opportunities and that the needs of men, women, boys and girls are considered throughout the programme.