Annual Review - Summary Sheet

PROGRAMME TITLE: Libya CSSF Country Programme
Country:		Libya
HMG Partners		Foreign and Commonwealth Office, Department for International Development, Ministry of Defence, National Crime Agency & Home Office
Total Budget:		ODA: £11.51m			Non-ODA: £70,000
Start Date: April 2017			End Date: March 2021
Outputs					Score
Political pillar	Number of civil society stakeholders demonstrating greater social influence & action, strengthened coalition-building, and community participation.					A+
	Libyan engagement with impartial media platforms to improve users’ awareness and understanding of key Libyan issues increases.					A+
	Training of Libyan journalists, civil society & government communications officers has a positive influence on the Libyan media landscape.					B
	Ability of Ministry of Planning (MoP) to coordinate international donors, identify funding gaps & report progress in key Libyan Government priority areas improves.					B
Security & Stabilisation pillar	Trainer mentors equipped to meet the emerging needs of each Social Peace Partnerships and the delivery of the methodology at the local level.					A
	Support the development of national Explosive Ordnance Disposal (EOD) & Counter-Improvised Explosive Device (C-IED) capacity in eastern Libya					B
	1) Create awareness & behavioural change through Risk Education activities in conflict-affected/vulnerable populations at risk of Explosive Remnants of War (ERW) accidents (Benghazi) / 2) Support the development of Libyan staff in Mine Risk Education (MRE) Capacity.					A
	Support to Stabilisation Facility for Libya (SFL) by making safe the target locations identified by the SFL needs assessment					A
	Coordination between national / international mine action stakeholders led by the Government of Libya, and supported by UN Mine Action Service, is improved avoiding overlaps or gaps in response across Libya.					A
	National capacities are strengthened to carry out, manage and monitor operations and quality assurance assessments					A
	Support rehabilitation of light infrastructure in conflict affected municipalities					B
	Local conflict analysis, facilitation and mediation capacity strengthened					A
	Economic recovery opportunities for Sirte Community (internally displaced people (IDPs)) increased					A
	Sirte communities have increased capacity to address psychosocial support and reconciliation needs					A
	Authorities are making some efforts to solve the sewage crisis.					A
Economic pillar	Supporting more efficient use of public financial resources					A
	Promoting better management of information for policy design & monitoring					B
	Fostering collaboration among agencies and institutions					B
	Consensus building, citizen participation, and empowerment					B
	The Libyan Investment Authority (LIA) undergoes a governance reform					A
Overall output score: A
Outcome Assessment: The programme is performing well, but the way the results framework was drafted means the outcome indicators are too ambitious and arguably unachievable, and the link between outputs and outcome is weak and insufficiently attributable.
Outcome Score: B				Risk: Medium

Summary of Programme Performance

Year	2015/16	2016/17	2017/18*
Programme Score	A	A	A
Risk Rating	High	High	Medium

*output/outcome scores

What support is the UK providing?
In support of National Security Council (NSC) Strategy objectives, the UK Libya team managed a spend of £11.4m across the programme portfolio in FY 17/18 (including cross-programme support costs of £0.6m). Programme pillars:
- Political pillar (£3.95m): to build the capacity of the Government of National Accord (GNA) through technical advisory support and capacity building (international coordination, communications); ensure women’s empowerment through political participation and support to civil society; and expand the influence of impartial and healthy media and journalism.
- Security and Stabilisation pillar (£5.79m): to support stability and recovery through projects around the themes of stabilisation and reconciliation, mine action, and security sector reform.
- Economic pillar (£1.1m): to assist Libya’s public administration, improve its capacity for decision-making, and to develop its ability to implement effective and inclusive economic policies, manage public resource and implement good governance principles.

Summary of progress and lessons learnt/actions taken since last review

Recommendations of 2016/17 Annual Review	Actions taken
Sustain and further strengthen the GNA and donor coordination mechanisms that the UK has helped to set up.	Libya CSSF continues to deliver strong projects which contribute to strengthening the GNA and donor contribution mechanisms.
Improved coordination will have a positive effect across CSSF portfolio. In particular, we recommend improved coordination between United Nations Development Programme (UNDP) & USAID Office of Transition Initiatives (OTI) in their local stabilisation work; between mine action organisations, communities & programme partners; & between the World Bank & UN on economic issues.	Some progress has been made on coordination between UNDP and USAID (OTI) but opportunity costs are still being missed through sub-optimal wider coordination.
Examine the scope for new work in the political strand to support political dialogue at all levels. This could include initiatives such as track 2 mediation, or direct support to UN-led talks.	The political pillar budget was increased significantly in 2017/18. CSSF is supporting a UN project “Promoting Elections for the People of Libya” (PEPOL) & the Peaceful Change Initiative (PCi) Track 2 project has been moved into the political pillar. A political parties development project will start in FY 2018/19
Support to local human security and stability in Libya remains an important objective, both in its own right and as a contribution to wider UK political strategy: this strand of work should be maintained, and expansion considered where feasible. Continuing to support this work in the east and south, as well as GNA-controlled areas, is a worthwhile investment in the future re-integration of Libya.	The Prime Minister gave a commitment at the 2017 UN General Assembly (UNGA) the UK would lead on reconstruction efforts. CSSF is contributing to the UNDP SFL and the USAID Chemonics project. Overall, the programme doubled interest in Mine Action since the last annual review.
Continue to work with International Organization for Migration (IOM) as a gateway to working with the Libyan authorities on migration but taking the same careful approach regarding mitigating risk.	IOM were not used as an implementing partner during this review period.
Include a weighting mechanism in the log frame. Some of the projects had to be downgraded in terms of score because they were grouped together under one output alongside non-implemented projects.	This continues to be an area of need/concern – this was not delivered in the year under review but is being addressed for 18/19
United Nationals Support Mission in Libya (UNSMIL) likely to request a further economist secondment. This should only be considered if clear that there is a plan to make good use of expertise.	A further economist secondment was not agreed for FY 17/18 due to delays from UNSMIL, but has since been agreed for 18/19
In future, if programmes are cancelled or started in-year, it would be appropriate to update the results framework to reflect this fact.	Results framework was overhauled significantly
Consider bringing all advisers together into a single programme to reduce administration time and facilitate benchmarking of their respective costs.	With the introduction of Technical Assistance Facility (TAF), this was no longer a required or appropriate action. Seeking to increase efficiencies & reduce management burden through regular review of staffing structures would be useful.
Establish clear value for money (VFM) indicators and benchmarks across the CSSF portfolio, and consider commissioning independent evaluations of key programmes. An independent monitoring programme should also be considered, with due regard to feasibility and value for money.	This was not delivered during the year although plans exist to focus on VFM in Q2 of 2018/19 as part of a new monitoring, evaluation and learning component and review to include embedding VFM requirements in all implementing partners results frameworks.
Develop a unified results framework and programme document for the Libya CSSF programme as a whole. This unified results framework should include impact weightings for the different outputs.	This has been achieved although there are issues with the results framework [see recommendations].
Ensure that the new civil society programme is up and running as soon as possible.	Delivered.
Continue implementation of the gender strategy, in particular using the CSSF board to look at key emerging issues such as parallel meetings for women and girls, and the use of chaperones.	Continued implementation of the gender strategy which is also in the process of being renewed. Projects such as PCi are starting to tackle issues such as the use of chaperones.

Summary of recommendations for the next year

Programme-wide:
New monitoring and evaluation plans that are being put in place should include a detailed review of the results framework to ensure that:
1. The number of outputs, outcomes and indicators is significantly reduced
2. The metrics used accurately capture “SMART” deliverables at output level
3. A weighting mechanism is introduced to make the scoring of a complex programme more proportionately reflective of the performance of its constituent projects by their size/importance/contribution to outcomes.
4. Consistency of quarterly milestones is improved, using cumulative regular targets, and thereby making progression easier to track.
5. Indicators & targets updated regularly throughout the year in order to ensure early assessment of whether projects are on course for meeting indicators, and can be corrected where necessary
6. More “SMART” metrics developed for outcome statements with an emphasis on achievability
7. Independent monitoring is utilised in order to bridge the evidence gap
1. The board should formally re-assess – and register in a note - whether the current staff structure & grading remains appropriate for size, nature & complexity of the current & planned programme, whilst delivering VFM.
2. Use Joint Analysis of Conflict and Stability (JACS) dissemination sessions with donors /partners as a way to better link risk management and conflict sensitivity, and to seek greater buy-in to an enhanced and shared conflict sensitive approach.
3. Use the JACS analysis to formally re-assess the UK Government’s risk matrix and approach to conflict sensitivity, including a commitment to repeat this on at least a quarterly basis, and document this process.
4. Significantly reduce the number of projects, looking creatively, and drawing lessons from elsewhere should be done as a priority.
5. Establish clear VFM indicators & benchmarks across the CSSF portfolio and consider commissioning an independent VFM review. Consider incorporating VFM into formal reporting to the Country Board.
6. Build more synergies between the projects by hosting implementing partner meetings on at least a quarterly basis in order to share our vision and explore areas for greater collaboration and partnership. Implementers should have a clear understanding of how they fit within the overall programme, including how their own results fit into the results framework, and a shared assessment of risk.
7. It would be beneficial for one individual to be given oversight of all programme spend on all department baselines, to ensure a complete picture is presented to the Country Board.
8. Given the changing context, the Board should agree – and review whenever necessary – a short note outlining their risk appetite by category, and how risk is escalated.
9. The programme team should enhance their efforts to improve the international community’s degree of conflict sensitivity and moving towards common agreed SMART targets in this area. This could include running a series of dissemination sessions with donor/UN/implementing partners on the findings of the JACS and a “so what” session on what the findings mean for programming and what we might collectively want to be doing differently.
10. Terms of Reference (ToRs) for the board should be redrafted, to include: clarity on membership, governance mechanisms, delegated authority to include clarity on the board working on strategic level issues only and when the board would want to be consulted on programming decisions even when below delegated authority levels, frequency of meetings
11. It is recommended the Country Board meetings are reinstated on a monthly basis for a more effective monitoring and evaluation of the programme’s progress.

Project level:
1. The work begun in the last quarter of 2017/18 on sustainability of the El Kul project must be continued, including through fully implementing the recommendations from the Itad (monitoring and evaluation consultants) review.
2. If further activity is agreed on areas currently covered by Government Communications Service International (GCSI), then identifying and agreeing improved VFM metrics must be prioritised, including putting the contract out to open tender.
3. The impact of the Strategic Communications Adviser should be better reflected in the results framework, more clearly linking the contribution of their activity to higher outcomes, as well as the linkages to the outputs of other projects.
4. Recommendations from the UNDP SFL review must be implemented, particularly in the area of unified governance & to give a narrower programming focus with fewer, higher quality outputs.
5. Undertake a review in order to assess the value and impact of the MoD advisers, their contribution to higher CSSF objectives/outcomes and whether appropriate to fund under CSSF.
6. To jointly assess – with USAID - risks well in advance of activity, in order to minimise the likelihood of delays, to adapt the results framework, and manage expectations accordingly.
7. Although UK contributions to the Multi-Donor Trust Fund (MDTF) have ended, the team should work closely with the World Bank to shape discussions with Libyan authorities towards agreement on a 2019 budget & follow up on the longer term impact of capacity building exercises conducted in FY 2017/8.
8. The MDTF board must be influenced in order to improve the operational efficiency of the project, improve the timeliness and quality of reporting, convene and consult with donors on an agreed regular schedule, and address the lack of administrative capacity.	`