Annual Review- Summary Sheet

PROGRAMME TITLE: Championing Our Values
Country/Region:	Multilateral
HMG Partners / (LEAD in bold)	Foreign & Commonwealth Office (FCO), Department for International Development (DFID), Ministry of Defence (MoD), Home Office.
Total Spend :	ODA: £5.47m			Non-ODA: 0
Start Date: April 2016		End Date: March 2020
Outputs					Score
Women’s Political Participation (WPP)1.1: Support to the Burundi Women’s Network for Peace and Dialogue (516 new women mediators and 18 new provincial focal points)					A
WPP 1.2: Identify high potential women for the Senior Women Talent Pipeline (SWTP), assessed through the UN recruitment system, and rostered or selected to positions in peace operations (and receive mediation training).					A
WPP 2.1 OHCHR Preventing Sexual Violence Initiative: Improved early warning system on CRSV, developed through the key UN peacekeeping missions of MINUSMA (Mali), MINUSCA (CAR), UNSOM(Somalia - by strengthening their Monitoring, reporting and analysis, and developing information sharing protocols and other tools .					B
WPP 3.1 Sexual Exploitation and Abuse (SEA): Improved local (communities, victims) understanding of the Secretary-General’s ‘zero-tolerance’ policy on sexual exploitation and abuse as well as on relevant conduct and discipline rules and regulations. (Victims Redress communication project).					A
WPP 3.3 SEA: UN staff accountability strengthened through training and vetting (CDU)					A+
WPP 4.1 Children and Armed Conflict (CAAC): Progress in the implementation of action plans to end and prevent grave violations against children (Afghanistan, DRC, Myanmar, Philippines, Sudan as well as with non-state armed groups					A+
WPP 5: Responsibility to Protect (R2P): Specialised training and technical assistance that strengthens the capacity of government officials and civil society to prevent atrocity crimes in situations where there is a risk of these crimes or where they are ongoing.					A
Conflict Prevention and Human Rights 1: OHCHR better able to manage and utilise human rights information through the development of specialised infographics and materials for UN Security Council.					A
Countering Violent Extremism (CVE) 1: Assisted Member States have ability to develop and implement effective strategic communications framework for PVE					B
CVE 3: United Nations Office of Rule of Law and Security Institutions (OROLSI) adapts its guidance for Peacekeeping missions on the basis of the strategy.					A
CVE 4: Commonwealth governments are supported to develop national action plans to counter violent extremism.					B
Overall output score: A
Outcome Assessment: A
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	A	B	A	A
Risk Rating	Medium	Medium	Medium

*output/outcome scores

What support is the UK providing?
This Championing Our Values programme aims to address issues of conflict and instability in line with UK values. Funding covers a broad range of issues, including:
The UK’s Preventing Sexual Violence Initiative which aims to raise awareness of the extent of sexual violence against women, men, girls and boys in situations of armed conflict and rally global action to end it.
- Women, Peace and Security, ensuring protection and political participation of women in situations of conflict and ensuring gender parity in senior UN roles.
- Using UK expertise and knowledge to counter acts of violent extremism and help the UN and Commonwealth to build sustainable strategies to defeat Daesh and individual acts of extremism.
- Rapid UN-wide response to cases of Sexual Exploitation and Abuse by Peacekeepers including through setting up vetting, improved investigations, prevention policies and ensuring victims are aware of support available to them.
- Supporting the Special Representative of the Secretary-General for Children and armed conflict to engage with countries of concern to prevent recruitment and use of child soldiers.

Summary of progress and lessons learnt/actions taken since last review

The 2017/18 CSSF Multilateral Championing our Values programme strand scored a strong A. This was the second year of the four year programme. There is strong evidence that the programme portfolio made good progress towards demonstrating its clear potential as an effective political tool to address global challenges.

Progress against the FY16/17 Annual Review recommendations has been solid in FY 17/18 and there is strong evidence that the programme team has carried through improved scrutiny and planning of the design and development of the FY 18/19 programme. The team has implemented:

A narrower, more realistic and focussed set of activities by focusing on key UK priorities for example SEA, PSVI and projects supporting the delivery of the UK’s WPS National Action Plan 2018-2022.

Brought forward decision-making on FY 18/19 funding allocations. This practice has led to prompt disbursal of funding and therefore avoided delays to activities.

Identified opportunities with social media teams to highlight the impact from UK funded projects in FCO communications.

Regular assessment of the value of these projects and whether UK funding in these areas represents value for money. Since FY16/17, a number of projects have been discontinued – where delivery or reporting has been poor. Support has been deepened in FY 17/18 and FY 18/19 to support the projects with the greatest potential to deliver results in line with UK priorities.

The results framework, theory of change and risk register have been reviewed in FY 17/18 and lessons taken on board for stronger and revised documents for FY18/19 too – which have been highlighted by the Joint Funds Unit as best practice.

Summary of recommendations for the next year

1. Log frames need to be updated to show progression with detailed and realistic targets for subsequent work plans and included an updated baseline and better defined measurable indicators.

2. Larger interventions need to be reviewed to ensure that UK funding is leading to tangible and long term institutional reforms in practice given the large funding commitment.

3. The programme includes several projects, which fund staff positions that are difficult to fund through the UN’s (core) regular budget. However, this raises questions about whether the outputs and outcomes of these Extra-Budgetary funded posts will lead to institutional change beyond the funding of these individuals. The programme team and policy leads need to ensure that implementers have exit strategies and plans to embed policy reforms i.e. to ensure sustainability of programme results.