Annual Review - Summary Sheet

PROGRAMME TITLE: Middle East Peace Process (MEPP)
Country/Region:	The Occupied Palestinian Territories (OPTs) and Israel (Middle East and North Africa – MENA)
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID), Ministry of Defence (MoD)
Total Spend:[1]	ODA: £7.5m			Non-ODA: £0.41m
Start Date: April 2015		End Date: March 2018
Outputs					Score
More capable, accountable and responsive Palestinian Authority Security Forces (PASF) and security sector; operating in support of the rule of law.					A+
Increased pro-peace interventions from key constituencies.					B
Physical viability of two state solution preserved.					A
Overall output score: A
Outcome Assessment: In 17/18 the CSSF made a contribution towards cross-HMG objectives. Tangible successes were had in challenging circumstances, particularly at project/output level. However, the absence of a programme/policy-wide level Theory of Change makes it difficult to articulate the extent to which the programme contributed towards higher-level objectives. A low ambition and somewhat unrepresentative Results Framework for support to the Palestinian Authority Security Forces skewed the grading slightly more favourably than would have otherwise been the case.
Outcome Score: B			Risk: Medium
[1] Allocation was increased by £0.9m in financial year

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	A	A	A	B
Risk Rating	Medium	Medium	Medium

*output/outcome scores

What support is the UK providing?

The UK provides support to help protect the political and physical viability of a two state solution, which the UK believes represents the best framework to end the occupation and deliver peace for both Israelis and Palestinians. It is complementary to DFID’s broader programme in the Occupied Palestinian Territories (OPTs)

Summary of progress and lessons learnt/actions taken since last review

The programme is delivering well in a politically charged, fast-changing and challenging context. It continues to be relevant, with initiatives that show appropriate responsiveness to changes. However, the strategic objectives as currently stated, and the design of the programme, means no significant work on Gaza has featured this FY. Overall, indicators in the Results Framework do not represent the full scope of the components. The Programme Team has addressed the vast majority of the key recommendations of the last review.

Lessons learnt/actions taken since the last review include:

Direction: Strategic direction was informally reviewed in-country during the year to ensure ongoing alignment with UK Government strategy. A Joint Analysis of Conflict and Stability (JACS) was undertaken to further enable ongoing sense-checking of strategic direction.

Programme governance: Programme governance has been greatly strengthened. The Board has access to more detail on the projects, programme staff and London colleagues are now invited to meetings, and site visits planned. These measures are complemented by monthly meetings of CSSF staff from across FCO, MoD, and DFID.

Flexible programming: Problems with over-programming in the previous FY have been remedied through diligent oversight, and the programme finished the year almost exactly on budget. Projects now focus on identifying scope for uplifts should additional funding become available in-year.

Communications: Board discussions on communications were undertaken in-year, with some conscious decisions made not to recruit specific communications staff. However, this means that the recommendations on communications from last year remain unimplemented.

Advisory support: In 17/18 the team brought in regional, Stabilisation Unit (SU), and local gender expertise. External evaluations have been scheduled for Q1 18/19. SU was also brought in for the JACS. However, the requirement to routinely access conflict and monitoring and evaluation (M&E) advice was not addressed.

Portfolio synergy: In-year decisions and preparations were made to bring the security-related projects together into a more strategic and coherent programme, seeking synergies and coordination. This is particularly commendable given the required involvement of three departments in making that a reality. These changes will come into effect in 18/19.

Conflict sensitivity: Whilst the AR did not identify any significant conflict sensitivity concerns with any particular aspects of the programme, there remains a concern that conflict sensitivity is not sufficiently addressed as a matter of course in the management of projects, or the programme as a whole. Neither the partners nor the Board appear to sufficiently or routinely prioritise conflict sensitivity as an approach.

Summary of recommendations for the next year

Relevance: should continue to be reviewed. Discussions should include whether/how the CSSF programme should address the significant needs in Gaza; and whether the policy/programme is sufficiently flexible and adaptive to changes in the context.

Coherence: Whilst the programme has been rationalised to a smaller number of projects, decisions were made in-year to increase numbers once again for 18/19. This is contrary to recommendations in the previous AR. This decision should be urgently reviewed.

Governance: Review the form and function of the Board to ensure greater engagement at the appropriate levels, inclusive participation in discussions on how projects relate to delivery of policy goals and better management of workloads through delegation of detailed project-level decisions.

Conflict sensitivity: must be more firmly embedded at the project and programme level, including through higher degree of conflict sensitivity challenge and by setting out a more robust process for assessing conflict sensitivity at the programme and project level. Urgent consideration to the recruitment of a full-time Conflict Advisor, either in DFID or BCG (British Consulate General Jerusalem), in order to provide ongoing analysis of the changing context and how programmes can be adapted accordingly, and to ensure a higher prioritisation of conflict sensitivity.

Gender sensitivity: BCG should maintain momentum and the focus on gender through ongoing access to technical support. Consider adopting a gender strategy or action plan, and scheduling regular Board discussion on gender. Seek not only a better disaggregation of results by gender, but aiming to evidence how the content of the projects contributes to enhanced equality.

Communications: Programme contributions should be fully integrated into a single, policy-led comms plan, with regular review for risk and conflict sensitivity.

Value for Money: A systematic look at projects’ economy, efficiency, and effectiveness to ensure that they are delivering in the most VFM manner possible – perhaps either as an internal challenge session or with VFM experts who are external to the team. At the programme level, the assessment should consider whether CSSF funds and staff time have been allocated to the areas which can deliver greatest effect; and the political benefit of the programme.

Risk: the Board should review risk appetite and how risk is escalated, the risk matrix should be reviewed quarterly with named individuals identified as the lead for managing and reviewing each risk.

M&E: The Programme Team should undertake further work to articulate how the strand-level Theories of Change contribute to an overarching Theory of Change. Consider enlisting further, external M&E support – such as from JFU – on a more regular basis e.g. for a quarterly check-in on progress against the Results Framework. Ensure that outputs and outcomes are realistic, measurable, and appropriately calibrated, so that the Results Framework allows a holistic tracking of progress and cover a fuller range of what the projects and the programme are doing (including the less tangible benefits).