Annual Review - Summary Sheet
PROGRAMME TITLE: NORTH AFRICA GOOD GOVERNANCE FUND (NAGGF): REGIONAL COOPERATION FUND (‘The RCF’)
Country/Region:	North Africa (Middle East and North Africa -MENA)
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID)
Total Spend:	ODA: £1.8m			Non-ODA: £0.0m
Start Date: April 2017		End Date: March 2018
Outputs					Score
1.1: Greater collaboration between national and regional research institutions for knowledge transfer and institution building. / 1.2: Quality regional forums/networks or alliances established to discuss transnational issues, or issues which could benefit from a transnational solution or have a transnational impact.					A
2.1: Training is delivered to government officials, researchers, civil society, organisations and citizens. / 2.2: Increased evidence base on transnational issues including, intra-regional trade, climate change and instability, human trafficking and sex-disaggregated data collection. / 2.3: Citizens, organisations and government have access to gender sensitive data on transnational issues to inform advocacy decisions and policy making decisions. / 2.4: Gender sensitive capacity development support is delivered to civil society, military, government, citizens or media.					B
3.1: Increased regional focus of partners programming. / 3.2: Increased donor funds are leveraged to contribute to trust funds that the UK supports on Regional issues in North Africa (NA).					A
4.1 Analytical reports, Technical Assistance (TA) products and knowledge events are held which generate evidence to increase understanding on the barriers to economic opportunities across the Middle East and North Africa (MENA) region.					A
Overall output score					A
Outcome Assessment: For financial year 17/18, the theory of change and results framework (RF) were insufficiently developed to be able to assess and demonstrate outputs leading to outcomes due to the programme being in the early stages of development and it being the first year to separate the RCF and Technical Assistance Facility into two programmes.
Outcome Score: B			Risk: Moderate

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score		C / The RCF was aggregated with the North Africa Good Governance Fund Technical Assistance Facility (TAF) programme	A / B
Risk Rating		Medium-High	Moderate

*output/outcome scores

What support is the UK providing?

The UK provided £1.8 million during 17/18 to deliver activities with the World Bank, European Bank for Reconstruction and Development (EBRD), Carnegie and UNWomen. These activities deliver technical assistance, research, policy advocacy, capacity development and network development in North Africa on a variety of thematic issues.

Summary of progress and lessons learnt/actions taken since last review

Recommendation 1: the NA Strategic Steering Board (NASSB) must play a more proactive role in providing strategic direction and challenge to the NAGGF Regional Programme and wider NA country portfolio, including scrutinising spend, results and risk on at least a quarterly basis. The Board should be supported by a working level Board if necessary.

Progress: the NASSB is more engaged in the RCF but has moved too far into the programmatic space. It is recommended that North Africa Joint Unit (NAJU) work with the Regional Board and the NASSB to ensure that the NASSB is focused strategically and look to move consultation and technical programming reviews out of this space.

Recommendation 2: to support the above, now the NAJU Programme Hub are set up and responsibilities are clear, there must be tight and proactive oversight of finance, risk and results by the Programme Hub across the North Africa region, including the Regional Programme. Recognising the high delivery risk for 2017/18 there is a need for ongoing MENA team support and oversight, though ultimate responsibility for delivery sits with the NAJU Programme Hub and Senior Responsible Owner (SRO) for the North Africa portfolio.

Progress: this has not been fully assessed as part of this review but weekly team meetings are now in place to discuss projects under the RCF and NAJU plan to hire a dedicated finance officer for the RCF and Technical Assistance Facility (TAF). It is critical that this person has a good understanding of FCO financial and procurement processes and systems.

Recommendation 3: if capacity and recruitment remain an issue, the FCO and DFID need to discuss how to resolve this, escalating as necessary.

Progress: NAJU are in the process of hiring various new members of staff and have filled a number of key programme roles this year.

Recommendation 4: the Programme Hub must develop a Value for Money (VFM) plan and implement the Monitoring and Evaluation (M&E) plan, ensuring both are delivered for 17/18.

Progress: there is still no explicit VFM proposition for this programme. This needs to be developed in the near future and well in advance of next year’s AR. This should link to the results framework. M&E is moving forward with a significant opportunity presented by the establishment of a Monitoring, Evaluation and Learning (MEL) contract for North Africa.

Summary of recommendations for the next year

Clarify (refresh) the UK Government’s regional strategic objectives in North Africa to enable effective portfolio design and decision-making, with an increased focus on delivering regional objectives that are aligned with, but not directed by, posts’ own strategic objectives.
- Revisit the programme’s theory of change and results framework in line with strategic objectives in order to be better equipped to demonstrate strategic effect in future (already underway).
- Clarify the role and membership of the North Africa Programme (NAP) and NASS Boards in relation to the delivery of regional strategic objectives through programme activities. In doing so, reconsider the balance between deep consultation with posts on design and approval of individual projects versus the primacy of delivering against genuinely regional objectives (which may not, or never be, high priority for individual posts).
- Carefully consider whether there is sufficient merit in investing further in the World Bank Multi-Donor Trust Fund (MDTF).
- Develop an explicit VfM proposition for the RCF programme portfolio, the assessment of which should be supported by indicators and weightings (of return and risk), with robust and reliable baselines.
- Review staffing model against proposed future structure and streamline where possible to reduce back office costs.
- Take a programme-level approach to cross-cutting issues, drawing on what is set out in the programme document, and appointing leads on gender, conflict-sensitivity and human rights to work with individual project managers/advisors to ensure these issues are thought about in design, implementation and M&E by both HMG staff and implementing partners.
- Ensure an Overseas Security Justice Assessment (OSJA) is in place for the Carnegie project, now that it is clear the programme will be directly engaging with security actors.
- Spend the early part of next FY investing in developing RF indicators that focus in on measuring the likely real world effect of implementing partner efforts, linked clearly to regional objectives as outlined in the programme’s theory of change.
- Ensure that all projects are contributing substantively to the RF and consider closing those that do not fit within the theory of change or the RF, particularly the EBRD project.
- Use the new MEL contract coming online this FY to review the evidence base underpinning the programme’s theory of change and look at opportunities for conducting theory-based, formative evaluation where possible (particularly for higher risk, innovative work where learning would be most helpful).

Annual Review - Summary Sheet

PROGRAMME TITLE: North Africa Good Governance Fund (NAGGF) – Technical Assistance Facility (‘the TAF’)
Country/Region:	North Africa (Middle East and North Africa –MENA)
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID)
Total Spend:	ODA: £1.69m			Non-ODA: £0.0m
Start Date: April 2017		End Date: March 2018
Outputs					Score
TAF has proved the concept of a regional provider to draw down on for expertise, delivery and management of projects against National Security Council (NSC) objectives for North Africa.					A
Overall output score					A
Outcome Assessment: The programme has not yet been able to demonstrate its ability (actual or potential) to catalyse reform in North African countries – but the programme team is taking steps to strengthen the programme’s underlying theory of change (ToC) as well as its monitoring and evaluation systems.
Outcome Score: B			Risk: Medium/Low (Moderate)

Summary of Programme Performance

Year	2015/16	2016/17	2017/18*
Programme Score	N/A	C / The TAF was aggregated with the North Africa Good Governance Fund Regional Co-operation Fund (RCF) Programme	A	B
Risk Rating	N/A	Medium-High	Medium/Low

*output/outcome scores

What support is the UK providing?

The TAF supports delivery of North Africa NSC Strategy objectives and provides a dedicated North Africa-specialised service, enabling rapid access to technical assistance and related support for country partners. Interventions are a mix of short or long term, and both inward looking analysis, scoping and programme design and more externally focused support including training, mentoring and advisory support as well as knowledge exchange. The TAF can also be used to give operational support to posts.

Summary of progress and lessons learnt/actions taken since last review

The team have made considerable efforts to address some of the lessons learned from last year’s Annual Review. The key has been a build-up of programme management capacity throughout 2017/18 – with the current complement of staff being in post by the autumn of 2017. The concept of providing technical assistance to North Africa posts has now been proven and the programme has invested heavily on fixing, testing and strengthening the model for delivery, and rolling this out across the region. Lessons around the coordination between London and posts have been addressed. Further clarity around strategic objectives, roles and responsibilities of this and other regional programme oversight will help drive forward strategic regional programmes that are aligned, but not necessarily pushed by, country/post priorities.

Summary of recommendations for the next year

Strategy
- Clarify (refresh) the UK Government’s regional strategic objectives;
- Refresh the programme’s theory of change and results framework;
- Refresh the TAF’s terms of reference;
- Clarity with supplier on ensuring potential conflicts of interest is avoided.
Delivery
- Ensure the UK Government is an intelligent customer of the TAF;
- Ensure that the TAF model is applied effectively with in-country partners
- Reassess project approval approach;
- Ensure responsibility for addressing cross-cutting issues is clearly understood by all stakeholders;
- Consider portfolio-based approach to risk and relevant Board’s risk appetite;
- Consider a dedicated finance officer within NAJU.
Monitoring and Evaluation
- Increase focus on monitoring the quality of Implementer delivery to build systems to ensure the programme is informed by real world effects;
- Implementer to regularly monitor country contexts, focusing on testing the relevance and applicability of overarching assumptions of ToC;
- Seek technical support from an independent governance advisor to assess whether the TAF model of technical assistance is likely to contribute to sustainable change.