Annual Review - Summary Sheet

PROGRAMME TITLE: Multilateral Strategy UN Peacekeeping Programme
Country/Region:	Multilateral
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Ministry of Defence (MoD), Department for International Development (DFID).
Total Spend :	ODA: £1.61m			Non-ODA: £2.4m
Start Date: April 2016		End Date: March 2020
Outputs					Score
Strengthened UN planning capabilities for UN missions					A
Fully Operational Peacekeeping Capability Readiness System (PCRS) to assess the readiness of member states capabilities is developed					A
Adoption and implementation of measures from Extra Budgetary (XB) funding to UN peacekeeping mandates.					B
Increased number of UK nationals accepted for deployment to UN missions and multilateral HQs					A
Overall output score					A
Outcome Assessment: B
Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	A	B	A	B
Risk Rating	Low	Medium	Medium

*output/outcome scores

What support is the UK providing?

This programme aims to make UN peacekeeping operations more effective and efficient, with more and better capabilities to deal with the challenges of modern peacekeeping. This should contribute to conflict containment, the reduction of violence and ultimately the resolution of conflicts to create the stability necessary for peace to flourish. Specifically, we are providing UK funding as follows:

Improving the effectiveness and efficiency of UN Peacekeeping: this includes a range of Department of Peacekeeping Operations (DPKO) and Department of Field Support (DFS) projects to improve mission planning processes, generate new pledges of troops and equipment, and ensure UN peacekeepers perform at the highest level to deliver challenging mandates.

UN Executive Office for the Secretary General Strategic Planning and Analysis Unit: to strengthen planning capabilities for UN missions.

Deployment of UK military officers to UN field missions and headquarters: to provide UK expertise in support of planning, pledges and performance to make UN missions more effective and better able to fulfil their mandates.

Deployment of UK police officers to UN field missions and headquarters: to build the capacity of local police forces in fragile states.

Summary of progress and lessons learnt/actions taken since last review

In order to assess whether any DPKO HQ outputs funded through the CSSF’s extra-budgetary (XB) funding translate into clear impact in the field, the CSSF has increased its monitoring and evaluation (M&E) processes in FY17/18. This includes a country visit to MINUSMA (the UN mission in Mali) and greater scrutiny of the military deployees’ quarterly reports. There is now some evidence that guidance and management tools are filtering down to field missions; however, a more comprehensive evidence base needs to be collected over the next reporting period.

The FY18/19 Peacekeeping programme has now been narrowed and more realistically targeted towards areas that the UK identified as a priority. These include integrated planning, leadership and training, intelligence, IT communications and the protection of civilians.

We continue to lobby and organise like-minded allies as part of a networked approach, including diplomacy, extra budgetary funding and UK leadership, to ensure DPKO continues to improve the efficiency and effectiveness of peacekeeping operations. The 2017 defence ministerial in Vancouver, led by the Strategic Force Generation Cell, which was originally created with UK seed funding and is now funded almost solely through allied nations, was pivotal in securing 40 new capabilities pledges and over 20 training and capacity building pledges.

The programme team revisited the theory of change, risk register and programme document following last year’s annual review recommendations. The overall ambition has been lowered to become more realistic and aligned to our identified areas of investment, within the programme framework.

In response to the Independent Commission for Aid Impact (ICAI) review, the CSSF has shifted towards a more outcome-focussed evaluation process. In this vein, the programme team reformed their reporting template of reviewers to specifically link activity to impact. As part of the M&E process, a key objective of the visit to MINUSMA was to identify whether guidance and toolkits produced by DPKO HQ were having the desired impact in the field. This more in-depth M&E will continue to take place through FY18/19 in order to gain a broader and more comprehensive evidence base.

Summary of recommendations for the next year

Decide whether to take a broad or more targeted approach: In the case of our support to the DPKO/DFS projects, we should decide whether there are specific areas we need to focus on (the recommendation on being more specific about our objectives – see below – should help).

Create more systematic decision-making processes: Deciding which extra-budgetary projects and deployments to support is at a crucial stage in the programme cycle and should be more formalised and systematic.

Strengthen the working relationship between the programme team and deployments: To ensure a greater connection and improved communication, there should be regular contact between deployees and the programme team, beginning with a pre-deployment briefing.

Improve monitoring and evaluation: Critical to judging the success of the programme is being able to assess whether the various projects that the CSSF sponsors at HQ level are having an impact on the ground to verify DPKO reporting. To this end, we should carry out more country visits or, at the very least, hold VTCs, so that we can gather evidence and conduct a more in-depth evaluation at the mission level.

Ensure that the outcome and output indicators are appropriate, realistic and measurable: Some of the outcome indicators should be revised, they should seek to better measure the quality and achievements of the deployees against our objectives.