 Annual Review - Summary Sheet

PROGRAMME TITLE: Security Capacity Building (SCB)
Country/Region:	Multilateral
HMG Partners / (LEAD in bold)	Foreign & Commonwealth Office (FCO), Home Office (HO), Cabinet Office (CO), Ministry of Defence (MoD)
Total Spend :	ODA: £0.47m			Non-ODA: £2.01m
Start Date: April 2016		End Date: March 2020
Outputs					Score
NATO Output 1: NATO Defence Capacity Building (DCB) Trust Fund (TF) – demonstrable progress in establishment of DCB architecture within NATO					A
NATO Output 2: NATO Baltics Resilience – advise on and implement potential improvements to existing resilience planning across the Baltic States					A
NATO Output 3: NATO Strategic Communications Western Balkans – develop a framework for implementation and coordinating with stakeholders enhancing NATO’s Western Balkans engagement					A
NATO Output 4: NATO Cyber team – strengthening NATO’s cyber deterrence posture					A
NATO-EU Output 5: NATO/EU Hybrid – EU and NATO are implementing and operationalising parallel procedures and playbooks for EU-NATO interaction on hybrid threats (using both formal/informal channels including the European Hybrid Centre of Excellence)					A
EU Output 1: EU Strategic Communications – develop best practice strategic communications approaches in Ukraine that can be replicated across the EEAS network, including media independence programme					A
EU Output 2: EU Common Security and Defence Policy (CSDP) missions function better, making them more effective					A
EU Output 3: EU IcSP DEVCO – Strengthen implementation capacity of EU Delegations and contracting partners, including effective indicators for all EU Counter Terrorism (CT)/Countering Violent Extremism (CVE)/Organised Crime (OC) projects					A
EU Output 4: EU Serious and Organised Crime – links strengthened between CSDP missions and Justice and Home Affairs (JHA) agencies. CSDP missions fully reflect UK security interests.					A
EU Output 5: EU-NATO cooperation: strategic crisis response and exercising					A
OSCE Output 1: Representative on Freedom of Media (RFoM) – provide legal and policy advice to the RFoM and participating States of the OSCE					A
OSCE Output 2: Human Dimension Committee (HDC) – maintaining the Human Dimension Committee as an effective well-functioning element of the OSCE security structure					A
Overall output score					A
Outcome Assessment: A
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2016/17	2017/18*
Programme Score	B	A	A
Risk Rating	Medium	Medium

*output/outcome scores

What support is the UK providing?

- UK deployments to the European Union
- UK deployments to the North Atlantic Treaty Organisation (NATO)
- UK deployment and funding support to the Organisation for Security and Cooperation in Europe (OSCE)

Summary of progress and lessons learnt/actions taken since last review

During the reporting period, the CSSF Multilateral Strategy team (MuSt) monitored and evaluated its projects alongside addressing recommendations of the last Annual Review (FY16/17). The programme considerations can be classified as follows:

FY16/17 Annual review recommendations (Programme Related):

A recommendation from the Annual Review identified the Results Framework (RF) as the key document that unifies and binds policy to practice. It was recommended that more effort is required to ensure full cooperation and coordination between London, UKRep/UKDel and the deployees in the development and implementation of RFs.

This has been addressed by ascertaining deployee objectives for FY17/18, designing the RF collectively to correctly capture the project aims and to forge greater links to the overarching National Security Council (NSC) strategy. Final RFs were also shared with policy leads to ensure London policy teams, UKRep/UKDel, deployees and the Overall, there has been increased engagement with deployees and policy leads, better quarterly reports and alignment of projects with policy objectives.

It was recommended that a more robust system of management and ownership including, pre-deployment checklists, policy/post based line management on the FCO’s internal system, senior countering sign officers within delegations was created. As a result, the MuSt team have engaged in depth with the FCO EU Secondments Lead to agree a set of guiding principles which will form the basis of any new secondments and outline terms and conditions, policy and UKRep/UKDel roles and responsibilities. The MuSt also recommended UKDel to acquire additional resource to manage the growing number of deployees.

The MuSt team was advised to engage with the future FCO team/new secondments unit to consider how secondments to Multilaterals might be factored into posts under the new 3-4 year cycle. As a result, the team has engaged with FCO and Department for Exiting the European Union (DexEU) regarding secondments into the EU and the outcomes have been communicated with deployees and MuSt governance boards. Furthermore, a review of long-term postings has pointed to risks in the deployment lacking a strategic fit over time with the MuSt strategy.

A more comprehensive London-based six-monthly review of MuSt outputs was recommended, to assess the progress against the previous year’s Annual Review recommendations and to obtain a snapshot of emerging issues including fallout from Brexit and with regard progress by deployees towards stated outputs. As a result of this, the MuSt has monitored progress against previous year’s Annual Review recommendations on a quarterly basis. The MuSt conducted a scoping visit to Brussels and Vienna in October 2017 to understand challenges and risks and has continuously engaged with UKRep, DexEU and policy teams regarding Brexit and possible impact on secondments.

FY16/17 Annual review recommendations (Policy Related):

The programme officer should collaborate with UKRep and UKDel to formalise cross-communication of EU-NATO deployees with the aim of improving information sharing and collaboration. There are thematic areas (hybrid threats) where collaborative approaches have proved more difficult given the EU-NATO context and Brexit. The MuSt will continue to monitor these through regular discussions with UKDel/UKRep.

Cross-cutting gender issues should be listed as an overarching component of the reporting requirement and should be listed as a header on the reporting form. All the UK deployees in some way are working within a gender context and this key element should be reported accordingly. Pre-deployment training in gender, human rights and conflict sensitivity should be delivered to all deployees to ensure full understanding and consistency across multilateral deployments.

As the MuSt second UK nationals into the multilaterals, the programme itself does not focus on gender but has gender parity across the deployments. Within their respective projects, the deployees will be guided by their multilateral references to gender issues. The MuSt did not have the resource/capability to deliver this training given timing of deployments. It is the recommendation of the MuSt for training be organised by the host multilateral.

Summary of recommendations for the next year

It is clear from the review that this programme is seen as strategically important to the UK Government. A review should be taken to ensure that the current approach to deployments still links in to CSSF and MuSt strategies and takes account of any changes that are required post-Brexit.