Programme Completion Review - Summary Sheet

PROGRAMME TITLE: Syria Resilience
Country/Region:	Syria (Middle East and North Africa – MENA)
HMG Partners / (LEAD in bold)	Department for International Development (DFID), Foreign and Commonwealth Office (FCO)
Total Spend:	ODA: £26.89m[1]			Non-ODA: 0
Start Date: April 2017		End Date: March 2018
Approved extensions: Yes[2]		Was the programme closed early? Yes
Outputs					Score
Civil Defence - Emergency search and rescue and medical support provided to communities					A
Education - Schools are open and staffed, supported by functioning Education Directorates					A+
Livelihoods - Agricultural activities and other livelihoods opportunities maintained and developed					A
Local governance - Increased capacity and ability of local councils to deliver services					A
Overall output score					A
Outcome Assessment:
FINAL Outcome Score: A			Risk: High/Severe
[1] This programme received a budget uplift during the year in order to increase support to the de-escalation area in Southern Syria.
[2] A number of projects within this programme have been extended in the 18/19 North West Syria Programme. This includes continued support to the Syria Civil Defence, service delivery and local governance.

Summary of Programme Performance[3]
[3] 2016/17 score refers to a review of a previous Resilience programme in the CSSF Syria portfolio.
Year	2015/16	2016/17	2017/18*
Programme Score	N/A	A+	A	A
Risk Rating	N/A	High	High

*output/outcome scores

What support did the UK provide?
The UK provided support under a number of programmes under the resilience strand, including support to livelihoods, education, governance and civil defence. The strand’s intended outcomes included meeting the basic needs of those affected by the crisis, inclusive growth and economic resilience at community level, and strengthened local governance institutions.

 The strand included the following programmes:

Programme name	Baseline
Governance Through Education	DFID
Strengthening Local Governance Structures (Tatweer)	DFID
Syria Livelihoods Intervention Fund (LIF)	DFID
Agricultural Livelihoods Support in Syria	DFID
Syria Civil Defence (SCD) – Batal	FCO
Support to Emerging Local Governance in Syria (Tamkeen)	DFID
Syria Education Programme	DFID

The programmes were delivering in diverse ways including the payment of stipends, provision of agricultural inputs, grants, and the provision of technical assistance.

What results did the programme deliver? Will results be sustained?

The programme delivered varied results across the four strands. The focus of the programmes shifted over time following contextual developments but the strand maintained its stabilisation and core state functions focus. The question of whether results will be sustained is a complex one and depends much on the eventual political settlement. The education outcomes have most likely the highest probability of being sustained.

On the livelihoods projects, there were significant successes in terms of skills development, improved incomes (for some 13,815 individuals), and rehabilitation of agricultural and other infrastructure (e.g. dairy, poultry and fish farms, factories and bakeries).

The earlier Governance Through Education projects provided access to formal education for some 350,000 children in 1200 schools, and to pay almost 10,000 school staff per month in a country with no banking system.

The Syria Civil Defence (SCD) project supported 4,011 male and female volunteers with stipends and 179 centres to provide search and rescue and other critical services to their communities. As of March 2018, 114,507 civilians have been rescued or aided by the White Helmets.

Governance: Tatweer reached 633,460 beneficiaries with improved basic services and provided training to over 1050 individuals, including Protection from Sexual Exploitation and Abuse (PSEA) training to communities, local council and Civil Society Organisation (CSO) members.

What lessons have been learned?

Selected lessons learned during implementation are as follows:

There are inherent risks with doing institutional development in an active conflict setting – particularly with regard to which actors to support - and as such the results cannot ever be guaranteed. In the case of the resilience strand, these risks were known. During the time that the conflict trajectory was moving in favour of the opposition, the recommendations (per the last Annual Review) and subsequent scale up in institutional sustainability-focused interventions were reasonable.

CSSF programming is reliant on effective top-down strategy processes – notably an up-to-date NSC strategy which is revised quickly following a substantial contextual shift. Without this the uncertainty has an impact on the effectiveness of programming. The absence of an updated NSC strategy, in the aftermath of the turning point of the Syrian conflict, has affected this programme.

The context offers a rare opportunity to consider developing an evidence base for the ‘stickiness’ of reforms in active conflict settings – for instance, which factors are likely to result in developmental and institutional gains being maintained in the event of a loss of territory by the conflict party being supported. The CSSF Syria resilience strand offers many such instances of engagement in territory that has since been lost by opposition forces, although capturing sustainability in now regime-held areas will prove challenging, and there is no obvious means of assuring this.

With portfolio-type programmes there is a need to consider programme-level synergies and the most appropriate portfolio composition. With regard to the resilience strand, for instance, there is a strong case that the Stabilisation Response Mechanism (SRM) should have been included as part of the programme. The SRM effectively provided a flexible, shorter term mechanism for funding mini public works projects, adhering to a similar philosophy and similar objectives to the Tamkeen project.

Critically, each of the projects has demonstrated that it is possible in such an environment to deliver support that goes beyond ‘hand-outs’ whether pertaining to agriculture, food aid, or education. Predicating the programme’s work on regime legislation could be a helpful step in maximising the probability of sustainability or at least continuity in the eventuality of losses of territory previously governed by the opposition.

Owing to the challenges of engaging in the fast changing context in Syria, and the value evident when the Education programme was able to draw on local staff, there is a need to maintain a strong cadre of Syrian staff in order to effectively manage and deliver the programme.