Annual Review - Summary Sheet

PROGRAMME TITLE: Western Balkans CSSF Programme
Country/Region:	Western Balkans
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Home Office (HO), National Crime Agency (NCA), Ministry of Defence (MoD), HM Revenue & Customs (HMRC)
Total Spend :	ODA: £15,178,718 (in year uplift of £6.4m)			Non-ODA: £2,220,000
Start Date: April 2017		End Date: March 2018
Outputs					Score
Preventing and countering violent extremism regional programme (multiple projects)					A
Defence deployments and capacity building regional programme (multiple projects)					A/B
Countering organised crime regional programme (multiple projects)					A
Bosnia and Herzegovina country programme (multiple projects)					A+/A
Kosovo country programme (multiple projects)					A
Macedonia country programme (multiple projects)					A
Serbia country programme (multiple projects)					A
Albania country programme (multiple projects)					A
Montenegro country programme (multiple projects)					A
Western Balkans Summit activity (multiple projects)					B
Overall output score					A
Outcome Assessment: B
Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	B	A	A	B
Risk Rating	Low/Med	Med/Low	Medium

*output/outcome scores

What support is the UK providing?

The 17/18 Western Balkans Programme has focused on sub-objectives in the first two pillars of the Western Balkans HMG Strategy.

- Organised crime, CT/CVE (National Security Objective – NSO 1 – Protect our People)
- Strengthening security sector capability, reconciliation, rule of law, corruption and transparency (NSO 2 - Project Our Global Influence)
It is structured around four country and three regional strands. Each has its own portfolio of projects, theories of change and results frameworks with multiple outputs and outcomes. There is no overarching regional theory of change or regional outcome and impact measures.
  1. Kosovo Country Programme Strand
  1. Serbia Country Programme Strand
  1. Bosnia-Herzegovina (BiH) Country Programme Strand
  1. Macedonia Country Programme Strand
  1. Regional Programme Strand – Security (Pillar 2): Defence Deployments and Capacity Building
  1. Regional Programme Strand – Security (Pillar 2): Preventing and Countering Violent Extremism
  1. Regional Programme Strand – Security (Pillar 1): Countering Organised Crime

Summary of progress and lessons learnt/actions taken since last review

Overall the Programme is maintaining year-on improvement in its performance, attributable to the implementation of the recommendations from the last Annual Review, a further reduction in the number of projects, a revised Joint Analysis of Conflict and Stability (JACS), better quarterly reporting, and notably the continued commitment of programme staff. A delivery action plan has focussed on the areas below.

- Monitoring & Evaluation (M&E) including Theories of Change (ToC)
- Governance
- Financial Management
- Secondees & Deployments
- Risk
- Cross-Cutting Themes

M&E advisory support, albeit limited, and workshops have aided the understanding of M&E principles. As a result, revised ToCs and Results Frameworks were in better shape to a certain extent, and have served as a foundation and test of assumptions for tangible Outputs. These tools need further strengthening to enable better articulation and measurement against Outcomes.

The 17/18 programme structure reflects a programme in transition and a number of the weakness have been addressed in the changes that have already been made for FY18/19. Effective processes and engagement have been put in place for stronger financial management (other than with Defence Deployments and Capacity Building Regional Programme Strand). The Programme came in at 4% of the final allocation, compared to an under spend of 8% in FY16/17. The programme received an uplift of 66% to its allocation mid-year.

Performance management of secondees and deployments is being addressed. Risk registers are in place and being monitored effectively, and a Gender Audit of the Programme has taken place. Conflict sensitivity and human rights (with Overseas Security and Justice Assessments (OSJAs) in place) are considered in programme and project design, though this should be in a more systematic manner moving forward.

The Programme Document for FY18/19 has, therefore, been drawn together with engagement from across the Western Balkans network to address the reality of the Programme and its future path. There are still shortcomings in certain areas, namely MoD-led projects and projects badged initially under the Western Balkans Summit. But there is a clear awareness of where strengthening and remedial action needs to be targeted, and the recommendations in this Review reflect that.

Summary of recommendations for the next year

The Western Balkans (WB) region should review its overall structure and more clearly delineate between governance at the regional portfolio level and country and thematic programme level with appropriate documentation to match. Next year there should be multiple annual reviews with a capping paper bringing this together at a regional level.
- The WB Regional Strategy Board should consider requesting that country level documents and theories of change that are owned by Post and set out their manifesto for all programmatic activity in country- both regionally and nationally led are developed. Those countries with larger spend and the potential for scale up should invest in conflict analysis working with the Joint Funds Unit (JFU) and Stabilisation Unit (SU).
- Europe and EU Programmes Unit (EPU) should review roles and responsibilities and look to simplify where possible. In particular clearly setting out the following roles across the Region: Head of Portfolio/ Regional Lead, Strategy SROs (eg chairs of Country Boards, Heads of Programme (Programme SROs) and Project leads (Project SROs).
- EPU should build greater understanding and buy-in for the revised programme structure.
- All activity delivered in-country should be overseen by the Head of Programmes (both regionally and country delivered).
- Review and strengthen Theories of Change on a firmer evidential basis in alignment with the JACS and the new programme structure for FY18/19.
- Flowing from revised Theories of Change, review indicators and milestones for outputs and outcomes in Results Frameworks for the development of realistic revised Results Frameworks in alignment with Western Balkans HMG Strategy and the new programme structure for FY18/19. And strengthen causative links between activity and desired change i.e. outputs and outcomes.
- MoD London to revisit and consider how to approach the regionalisation of defence capacity building support, determining which aspects are appropriate for regionalisation and which are more country specific.
- Review adequacy of programme staffing structures in line with expanding programme in FY19/20 and beyond.
- The Joint Funds Unit (JFU) should look at value for money (VfM) of maintaining a separate Good Governance Fund (GGF), and should be examined as part of the next Spending Review. In the interim greater pooling of resources across the GGF and regional portfolios in which it operates should be encouraged.