Annual Review - Summary Sheet

PROGRAMME TITLE: AFRICAN UNION SUPPORT PROGRAMME
Country/Region:	Africa (Continental)
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID), Ministry of Defence (MoD)
Total Spend :	ODA: £2.04m		Non-ODA: £0
Start Date: April 2015		End Date: Mar 2018
Outputs				Score
The UK and African Union engagement maintained during transition year, while Africa Peace and Security (APS ) multi-year programme is developed and successful close down of legacy project is ensured				B
The African Union Commission Department for Political Affairs (DPA) supported to build it’s capacity in structural preventive diplomacy				A
Overall output score				A
Outcome Assessment: Local Strategy Board signs off APS Multi-Year programme, with strong evidence base, sound theory of change and appropriate management structures.				A
Outcome Score: A				Risk: Med/High

Summary of Programme Performance

Year	2015/16	2016/17	2017/18*
Programme Score	C	B	A	A
Risk Rating	MED/HIGH	MED/HIGH	MED/HIGH

*output/outcome scores

What support is the UK providing?

The UK continues to recognise the African Union (AU) as one of the key institutions for furthering UK objectives in Africa, especially in the area of peace and security. As noted in 2016/17, the AU remains severely constrained in terms of finance, resource and capacity. The team was developing a multi-year programme for Financial Year 2017/18 onwards in order to help address this. However this was unavoidably delayed to FY18/19 following a re-appraisal of our relationship with the AU. So FY 17/18 has been used to plan a better governed and multi-year engagement in FY 18/19 with a stronger evidence base. In order to enable this, the UK continued to provide support to the AU in the following areas:

Joint Financing Agreement (JFAs): the UK made a funding contribution to a European Union led pooled-fund that enables the African Union Peace and Security department and its liaison offices to undertake peace and security-related work.

Conflict Prevention and Structural Preventative Diplomacy: support to the AU Department of Political Affairs (DPA), via the organisation International IDEA, funding a dedicated team of experts to support the DPA with analysis on conflict prevention and preventative diplomacy

Summary of progress and lessons learnt / actions taken since last review

A more focused Results Framework has been developed, as recommended in last year’s Annual Review. This has allowed more specific outcomes to be developed, providing clearer direction to activities. This investment, using evidence-based research, will help a future multi-year programme maximise achievements through both technical support and political engagement.

The programme achieved its outcome. The Local Strategy Board (LSB) was able to sign off the APS Multi-Year programme, with a strong evidence base, a sound Theory of Change and appropriate management structures.

The programme also achieved its two main outputs: it maintained engagement between the AU and UK during this transition year, developed the APS multi-year programme and successfully closed down the 2012/16 legacy project; and supported the AU DPA in building its capacity in structural preventative diplomacy

The review team assess that these results are now more than likely to be sustained and that the conditions have been set for a significant programme to be delivered with the AU in 2018/19.

Summary of recommendations for the next year

A programme such as this needs realistic ambition levels. In particular, outcomes and intentions need to be clear and the methodology for measuring them agreed in advance. In a relationship such as the one with the AU, where the UK Government is working with an existing institution with many international partners involved, establishing the scope of, and how to measure, longer term political impact (or political access and influence (PAI) is key. Future monitoring arrangements should capture both the technical results as well as PAI to convey a more comprehensive (and value for money) based results report.

The LSB needs an active working group and more buy in from its wider stakeholders to be fully effective. The LSB needs to ensure it meets on a regular basis and has the staffing support and mechanisms at programme level to shape effective discussions and make decisions.