Annual Review - Summary Sheet

PROGRAMME TITLE: East Africa Criminality (Criminal Networks and Criminal Justice)
Country/Region:	East Africa (Kenya and Tanzania)
HMG Partners / (LEAD in bold)	National Crime Agency (NCA), Crown Prosecution Service (CPS), Foreign and Commonwealth Office (FCO)
Total Budget: £2.31m	ODA: £2.31m			Non-ODA:
Start Date: April 2017		End Date: March 2020
Outputs					Score
Casework and Operations: Improved capabilities and knowledge of legal operational frameworks among justice system actors in East Africa to investigate and prosecute Serious Crime (SC) threats (in a human rights compliant and gender sensitive manner) and to inform decision-making processes.					A
Tactical Capacity Building: Improved specialist capacity to build stronger criminal cases, and adopt effectively and sustainably to new/improved.					A
Strategic Access and Influencing: Enhanced engagement (formal and informal) between host authorities and the UK on issues relating to SC.					A
Overall output score					A
Outcome Assessment: Progress as expected against outcome: effective and compliant criminal justice systems, capable of working with the UK to tackle serious crime threats to the UK and the region.
Outcome Score: A			Risk: Medium-Low

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	N/A	B	A	A
Risk Rating	N/A	Medium	Medium

*output/outcome scores

What support is the UK providing?

The programme aims to help build capacity of law enforcement and criminal justice systems in Kenya and Tanzania that comply with international law and can work with the UK to tackle serious crime threats to the UK and the region.

The programme deploys technical experts from the NCA and the CPS to work directly with counterparts in Kenya and Tanzania to identify the blockages to successful law enforcement and criminal justice prosecutions of criminal networks.

Through live casework on investigations, prosecution, capacity building they influence policy makers and key operatives across legal ministries, judiciary, prosecution and law enforcement and deliver technical solutions. Police reform is addressed through the Senior Command and Leadership Programme at the Kenya Police Staff College, delivered by the UK College of Policing - to build capacity to improve policing governance in Kenya.

The programme benefits from a strong track record of bilateral law enforcement cooperation between the UK and Kenya and Tanzania and supports the delivery of UK objectives on governance, rule of law and human rights.

Summary of progress and lessons learnt/actions taken since last review

In Kenya, the CPS-delivered work has resulted in a number of successful prosecutions of serious crime cases with links to the UK. A bespoke Mutual Legal Assistance (MLA) project identified areas for improvement in the way requests are drafted and transmitted, and devised guidelines (launched in March 2018) for the Kenyan Central Authority and international partners. This was the first of its kind in the region. Initial results indicate greater use of digital technology to enable witnesses to give evidence via video link at trials. Kenya has used the MLA improvements to share and receive evidence with other jurisdictions, not just the UK.

In Tanzania, CPS work contributed to a number of successful prosecutions of serious crime cases with links to the UK.

The programme team has worked with expert advisers: an independent consultant to improve Value for Money; and with Monitoring and Evaluation consultants to inform the design of future phases of work and ensure that learning is better communicated across NCA and CPS networks. This includes gender and conflict sensitivity assessments.

The programme team has been strengthened, including the provision of administrative support to the programme implementers in Kenya and Tanzania. The programme team now conducts regular visits to Tanzania to pro-actively manage emerging programme management issues and strengthen working relationships with programme delivery staff.

Exit strategies for the programme are being addressed through the new programme documents. This will include greater collaboration with international partners.

Summary of recommendations for the next year

Police reform training in 2018-19 should continue, with a stronger evidence base and more focus on train-the-trainer.

For the programme as a whole, sustainability post-2020 is important. Posts and programme implementers should continue to scope potential avenues for cooperation with partners in the international community and develop a road map, to include milestones and indicators of success. The programme team should engage with DFID to maximise support for the programme, including beyond the 2020 timeframe.

As well as featuring as a major component of the new Theory of Change document for the programme, the Political Access and Influence (PAI) approach should be a priority in the refreshed Results Framework. The Risk Register should be more explicit about the political economy environment in both countries, and how it affects the delivery of the programme.

More should be done to involve posts in the recruitment process for new NCA and CPS officers coming into the programme to ensure continuity of programme delivery.

More can and should be done to highlight the achievements of the programme in both Kenya and Tanzania. This includes the success of the MLA in Kenya which was included in the CSSF global Annual Report for 2017-18