Annual Review - Summary Sheet

PROGRAMME TITLE: East Africa Security Programme
Country/Region:	East Africa
HMG Partners (LEAD in bold)	Ministry of Defence (MOD)
Total Spend:	ODA: £0.1m			Non-ODA: £1.30m
Start Date: April 2017		End Date: March 2020
Outputs					Score
Development of the Kenya Defence Forces (KDF) Counter-IED Capability through improvements to doctrine, policy, force structures and training capacity					B
Regional wildlife authorities have improved capability to counter the Illegal Wildlife Trade in East Africa					A
Overall output score					B
Outcome Assessment: Increased coordination and capability of East African security forces to respond to crisis in the region. Progress less than envisaged.
Outcome Score: B			Risk: Low

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	N/A	A/B	B	B
Risk Rating	N/A	Low	Low

*output/outcome scores

What support is the UK providing?

The programme aims to strengthen the capacity of East African troops to maintain stability in the region through training and information provision. In financial year (FY) 2017/18, the programme focused on three broad areas:

Building the capacity of troops in East Africa to take a stronger lead in managing security threats in an effective and proportionate manner. This includes supporting the regional Counter-Improvised Explosive Devices (CIED) Training Wing to achieve full operating capacity. This will be a key asset to improve the ability of African Union Mission in Somalia (AMISOM) to engage in offensive operations in a high-threat IED environment. CIED Training was also provided for the Kenyan Rural Border Patrol Unit (RBPU)

Building regional security cohesion and political will to ensure continued regional support to AMISOM.

Winding down regional counter Illegal Wildlife Trade (IWT) activities to ensure sustainability and relationships.

Summary of progress and lessons learnt/actions taken since last review

There has been progress in improving awareness within the British Peace Support Team (BPST) of Monitoring & Evaluation requirements, including developing additional monitoring and evaluation mechanisms and improving reporting.

Some progress has been made on raising the focus of civilian advisers’ efforts from the tactical level to a more strategic focus. Overall, the division of roles between civilian advisers and military personnel appeared to have been more clearly communicated with a good level of complementary inputs.

Germany has committed to support infrastructure development of the CIED wing.

The programme successfully completed the draw-down of the Illegal Wildlife Trade project.

Summary of recommendations for the next year

The Local Strategy Board (LSB) should provide direction to develop an exit strategy that ensures sustainability and the continued engagement of the Kenyan authorities, taking into account the importance of the CIED Wing in the relationship.

The Results Framework needs updating to reflect what BPST is and is not doing. It should also disaggregate data along gender lines, allowing BPST to monitor the impact of its activities from a gender perspective. The Risk Register also needs additional work. The Senior Responsible Owner (SRO) should lead the redrafting and it should include wider risks not in the gift of the programme, such as the engagement of the Kenyan authorities and regional participation.

The CSSF and BPST teams need to develop a greater understanding of shared priorities, through more regular meetings. A better match between the short term CSSF objectives and long term strategic goals is required.

Other UK Government stakeholders have used the CIED Wing for training. When this happens there must be clear reporting with outputs agreed in advance and reflected in the Results Framework.