Annual Review - Summary Sheet

PROGRAMME TITLE: CSSF Great Lakes
Country/Region:	Great Lakes (Democratic Republic of Congo (DRC) & Burundi), Africa
HMG Partners (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID)
Total Spend:	ODA: £1.2m / (budget adjusted in year)			Non-ODA: £0.2m
Start Date: April 2015		End Date: March 2020
Outputs					Score
Platforms for political dialogue in Burundi are established and utilised					B
Community peacebuilding groups have strengthened community resilience and community relations with government authorities					A
Enhanced UK understanding of the conflict dynamics in Eastern DRC					B
Improved UK situational awareness of DRC armed forces (FARDC) capacity as well as internal political dynamics					B
Increased capacity of the government of the DRC to mark and log small arms and light weapons					A
Human rights organizations are enabled to exercise their role in promoting and protecting human rights in DRC					A
Appeal of violence among security forces, youth, civil society and political parties during the DRC election period in target areas is reduced					A
Burundian civil society participation in violence monitoring and peacebuilding activities is strengthened, and linked with international efforts to resolve the political crisis.					B
Overall output score					A
Outcome Assessment: The individual projects within the programme are producing results and contributing to UK objectives, but the programme’s outcomes are too ambitious for a programme of this size, so progress against outcomes is limited.
Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	A	A/B	A	B
Risk Rating	Med	Med	Med

*output/outcome scores

What support is the UK providing?

The programme undertakes conflict, security sector reform and human rights interventions in the Democratic Republic of Congo (DRC) and Burundi, working through seven implementing partners and a number of advisors. The collaboration with a broad range of local and international implementing partners offers unique opportunities for building partnerships and innovative programming.

The programme has four policy strands:

- Strengthening peace and reconciliation in eastern DRC through advisory support.
- Support to defence reform within DRC, through a defence reform advisor, and a weapons marking, storage and destruction programme with the Congolese armed forces.
- Support to human rights in the context of elections in DRC, including by increasing dialogue between communities and police ahead of elections-related demonstrations, and providing direct support to human rights defenders.
- Monitoring and responding to conflict risks and supporting the conditions needed to allow for peaceful and fair elections in Burundi by 2020.

Summary of progress and lessons learnt/actions taken since last review

The programme’s strategic board has provided clearer direction for the programme and has begun to develop a more strategic vision for FY18/19; with renewed focus and a smaller number of larger projects.

The team have increased their programme management staffing resources. The team are improving multi-year planning and developing contract break clauses. Early procurement has not taken place for all projects in the 2018/2019 financial year and the team should revisit this for the 2019/2020 financial year. Improved financial management.

The team have worked with a CSSF contracted Monitoring and Evaluation (M+E) unit to strengthen the programme’s Theory of Change, but still need to make improvements to the results framework.

Summary of recommendations for the next year

The team should ensure that the 2018/2019 programme aligns clearly to the revised strategic vision, and prioritise ruthlessly those projects that will contribute to this. They must invest time and resources into developing a comprehensive and usable Results Framework, drawing on the experience of implementing partners and ensuring that the results are realistic and measurable, setting out clear indicators and milestones.

The team should ensure all non-ODA projects fully consider gender in their activities, and set this out clearly in the programme’s strategic case. The team should continue to consider whether re-incorporating a gender equality specific project is appropriate.

The team should invest more time in strengthening relationships with partners over the coming year, including to ensure that forecasting is accurate and consistently updated. Encouraging partners to spend with a flatter budgetary profile earlier in the year will ensure that end of year ODA targets are met.

This review recommends that the Annual Review for 2018/2019 does not anecdotally score outputs where there are weak milestones and that the programme team are held to account if partners are not reporting to the same indicators as the programme documentation.