Annual Review - Summary Sheet

PROGRAMME TITLE: Niger Delta Stability Programme (NDSP)
Country/Region:	Nigeria
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO)
Total Spend :	ODA: £0.96m			Non-ODA: N/A
Start Date: April 2016		End Date: March 2019
Outputs					Score
Security and Governance. Increased dialogue and common understanding between Niger Delta, Federal and State Governments on realistic and achievable objectives for the region leading to greater stability.					A
Economic diversification. Innovative economic diversification strategies in power, agriculture and digital sectors promoted and Niger Delta Development Commission’s capacity strengthened.					A
Oil theft and illegal refining. Improved understanding of bunkering and illegal refining drivers and alternate livelihood mechanisms demonstrated leading to a reduction in numbers of those involved in bunkering.					A
Ogoni clean-up makes progress with support from programming that improves livelihoods					A
Better informed UK Government improves effectiveness of engagement with Federal and State Government, impact of programmes and international collaboration on the Niger Delta.					A
Overall output score					A
Outcome Assessment: The programme has made good progress in a relatively short time. Output activities have been well researched and leveraged to deliver targeted impact. An A+ would be awarded if there was evidence of a clearer approach to market CSSF projects for scaling up.
Outcome Score: A			Risk: High

Summary of Programme Performance
Year	2016/17	2017/18*
Programme Score	A	A	A
Risk Rating	Medium	High

*output/outcome scores

What support is the UK providing?

The programme aims to influence Nigerian decision makers to address important issues of political dialogue, governance and security, economic diversification, oil theft and environmental clean-up in the Delta, particularly in Bayelsa, Delta and Rivers States. The programme uses political economy analysis to help influence the focus of local and international partners and develop buy-in to scale up project activity.

The programme complements DFID’s economic and democracy programmes and other CSSF programmes, including Maritime Security and the Security and Justice Programme (SJRP). The programme uses an implementer, Stakeholder Development Network (SDN), with experience of advocacy work across the Delta Region.

Summary of progress and lessons learnt/actions taken since last review

Some activity previously supported by DFID has been successfully incorporated into the new programme. There is though a need to further enhance DFID/CSSF synergies. The number of programme outputs has been reduced from five to three for FY 18/19. This reflects the recommendation from the 2016/17 Annual Review to avoid overambition. Financial oversight has strengthened over the course of FY 17/18.

The extent to which Nigerian Government policy and initiatives are influenced by CSSF programmes is challenging. It is assessed informally, through the Steering Committee and other interactions between stakeholders. The programme monitors developments closely and remains poised to support any new Federal Government Peace and Security Initiatives. The team has set aside funding for FY18/19 to capture and measure political access and influence better.

There is good dialogue between SDN and the programme Senior Responsible Owner (SRO) and this has enabled British High Commission (BHC) interventions on specific subjects – a good example being the advocacy position of BHC when the cease-fire was in danger of breaking down in November 2017. Sustainability has been factored into the projects of the sub-grantees that SDN is working with, but it is less obvious that the scaling up of successful pilots takes sustainability sufficiently into account. More thought is required to articulate how a successful pilot will be ‘marketed’ for scale-up.

Summary of recommendations for the next year

Establish a clear methodology to develop output activity into sustainable programme outcomes. This requires wider advice and support beyond the programme team and implementer to facilitate future partnerships and transitions. UK Government local governance structures should prioritise this.

Map and analyse other initiatives in the Delta to identify potential pilot opportunities and implementers. This work should incorporate analysis based on an evidence base of past activity, relative success and sustainability as well as community and State/Federal Government buy-in.

FY18/19 quarterly reports should specifically report on ongoing efforts to improve Monitoring and Evaluation (M&E), and how much they inform the selection and development of suitable pilots and partners. As the situation in the Niger Delta develops, a Joint Analysis of Conflict and Stability (JACS) and Serious and Organised Crime Joint Analysis could be useful to frame further programmatic work.

The programme needs to put further focus on Gender. There are some potential quick wins in terms of activity, but the implementer may need support, particularly in achieving the required second-level Gender Equality Marker (GEM2).

The team should consider how much the programme can help support human rights advocacy with the Nigerian military in the Delta. This will be especially important as the programme takes on a Maritime Security element.