Annual Review - Summary Sheet

PROGRAMME TITLE: Sri Lanka CSSF: Delivering increased stability and reducing the risk of a return to conflict
Country/Region:	Sri Lanka
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO) and Ministry of Defence (MoD)
Total Spend :	ODA: £ 2.28m			Non-ODA: 0.18m
Start Date: April 2016		End Date: March 18
Outputs					Score
Police Reform					A
Defence Engagement (DE)					A
Anti-Corruption (ABC)					A
Demining					A+
Inter-faith Dialogue					A
Transitional Justice (TJ)					A
Overall output score					A
Outcome Assessment: Likely contribution towards cross-HMG strategy objectives: the score is an assessment of progress made towards achieving challenging outcomes. That outcomes are so challenging is commendable and sets an example. / With the exception of demining, which has exceeded expectations, the review team’s perception is that the programme outcomes do not at this time meet all expectations. That is not to say that they will not be achieved.
Outcome Score: B			Risk: M

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	A	A	A	B
Risk Rating	L/M	M	M

*output/outcome scores

What support is the UK providing?

The CSSF programme in Sri Lanka is designed to support reconciliation and strengthen democracy and the rule of law to ensure long-term stability, through targeted project activity:

- support to police reform and training based on a community policing approach that is gender sensitive and respects human rights;
- support to the government’s commitment to establishing credible and effective transitional justice mechanisms as part of Sri Lanka’s reconciliation process;
- Clearing 600,000 square meters of mine contaminated land in the North and East enabling the resettlement of Internally Displaced Persons;
- support to community-level mediation of ethno-religious tensions in the Eastern Province;
- strengthening the defence relationship through targeted non-kinetic training and high level dialogue which will support security sector reform and foster greater awareness of the importance of accountability and reconciliation; and
- Sharing UK expertise to strengthen government capability to tackle bribery and corruption.

Summary of progress and lessons learnt/actions taken since last review

There is good evidence of successful programme management processes within the British High Commission (BHC), which coupled with effective monitoring of and engagement with implementing partners has led to the successful delivery of this year’s programme to budget.

Recommendations have been implemented such as the consolidation of the previously numerous police reform strands into one project with one work plan. This rebalancing ensures that the programme continues to be effective and reflect UK Government’s National Security Council (NSC) priority areas for change.

The scope of the programme and networking that takes place provides the UK Government with high level access, visibility and influence on key issues across the island enabling the UK Government to punch well above its weight amongst the international community. This breadth also permits CSSF funding for activity in each of the UK Government’s NSC target areas and there is good evidence that the programme is delivering value for money in this regard.

It is however significant that whilst the programme has been agile and adaptive, overall progress has been affected by the Government of Sri Lanka’s (GoSL) sporadic engagement throughout the previous financial year, which may be further impacted upon as Sri Lanka moves towards the forthcoming Parliamentary and Presidential Elections (2019-2020).

It is therefore vital to maintain and not reduce this sphere of influence if the UK Government is to continue to play such a significant role in supporting reform and bringing about positive change in particular given the remaining window of opportunity to do so.

The project work on demining, District Inter-Religious Committees, and aspects of police reform and transitional justice, are making a significant contribution to gender goals within communities and are being carried out in a conflict sensitive way.

The following recommendations seek to assist the programme team as they work towards its conclusion and together with the Joint Analysis of Conflict and Stability (JACS) are intended to assist with planning for a possible future programme.

Summary of recommendations for the next year

Review and revise the Theory of Change and Results Framework taking into account lessons learnt, potential opportunities and the JACS.
Continue to actively pursue the sign off and implementation of the Police Reform Action Plan.

Consider and prepare for the possibility of a change of momentum or priorities on Police Reform as elections approach, and its potential impact on current and future police programming.

Consider further developing community policing and police accountability through exploring potential relationships between the police and DIRCs.

Continue with, and seek to, enhance demining activity through additional UK funding to assist the Government of Sri Lanka (GoSL) to reach its target of being mine free by 2020.

Review and refresh the Anti Bribery and Corruption (ABC) work stream to explore possible opportunities for partnership working within the International Community and refocus efforts into defined areas seeking to deliver institutional reform.

Continue to effectively, monitor and manage risk in line with the GoSL commitment, the potential for political change and appetite for progress that may impact on programme delivery in particular within the sensitive areas of Transitional Justice, Interfaith Dialogue and Anti-Bribery and Corruption.

Establish a clear understanding of programme reporting requirements and expectations.

Ensure evidence is captured throughout the year and collated within a robust results matrix.

Consider the requirements and feasibility of developing a Gender Equality Marker (GEM) 2 project in line with CSSF policy.