Annual Review - Summary Sheet

PROGRAMME TITLE: Nigeria CSSF Security and Justice Reform Programme (SJRP)
Country/Region:	Nigeria
HMG Partners (LEAD in bold)	Foreign and Commonwealth Office (FCO), Ministry of Defence (MoD), Department for International Development
Total Spend :	ODA: £4.09m			Non-ODA: £0.75m
Start Date: May 2015		End Date: March 2019
Outputs					Score
National Assembly Security and Justice Committee members and clerks supported to understand and effectively exercise their legislative oversight role.					B
Women Peace and Security: Targeted security and justice institutions supported to implement and/or monitor relevant objectives within Nigeria's National Action Plan 1325					A
Increased number of public dialogue and media coverage engaging diverse voices in debate on security and justice reform issues.					A
Civil Society Organisations (CSOs) across Nigeria trained to identify and challenge corruption in the defence and security sector.					C
Targeted accountability mechanisms are supported to be more coherent and effective. Stakeholders are aware of relevant accountability mechanisms and how to access them.					N/A
Democratic policing methods and principles are strengthened around targeted issues within focal policing structures at the local, State and Federal level.					A
Capacity of formal and informal leadership of Nigerian Police built to make evidence based decisions.					A
Platforms for coordination (informal and formal) exist between police and other targeted providers on issues of concern to targeted communities.					A
Nigerian Prisons Service (NPS) supported to improve management and use of prison population data					A
Increased number and quality of legal representation for awaiting-trial prisoners (ATPs) and other administrative and judicial interventions aimed at reducing the duration in custody and number of ATPs in targeted prisons in Nigeria					A
Nigerian Air Force develop and begin to implement an anticorruption strategy.					A
Awareness raising events held with Armed Forces of Nigeria leaders on corruption risks					A
Effective management of the SJRP programme					A
Political engagement across wider UK Government and with Nigerian and international stakeholders					A
Overall output score A
Outcome Assessment: The programme has made identified ‘intermediate outcomes’ that are attributable to programme intervention and there was significant progress in the first year of operation.
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	N/A	A	A	A
Risk Rating		Medium	Medium

*output/outcome scores

What support is the UK providing?

The programme seeks to contribute to security and justice reforms in Nigeria, including more coherent national security structures, and more capable and accountable security and justice institutions.

The programme brings together commercial implementers, local CSO’s, international Non-Governmental Organisations (NGOs) and direct HMG capacity to work in areas across the security sector, including Nigerian government, parliament, the police, defence forces and civil society. The programme is linked, where appropriate, with other UK Government support to the police and judiciary. The programme was designed to build on previous Department for International Development (DFID) security and justice programmes and link to broader DFID governance programmes covering democratic accountability and effective and accountable public service delivery.

Summary of progress and lessons learnt/actions taken since last review

The programme has evolved from a series of stand-alone activities into a more integrated programme taking a flexible and adaptive approach to implementation, and building on lessons from earlier UK programmes.

The main recommendations from last years annual review have been implemented: the design phase and updates to results frameworks (RF) and risk matrixes were completed to allow a contract to be put in place in December 2017; the Local Strategy Board agreed a one year extension to the programme to avoid a cut-off during the 2019 election period; steps were taken to enhance the programme’s contribution to the Women Peace and Security Agenda and plans are in place to develop this further; and consideration was given to establishing a steering committee. The decision not to implement this seems sensible, given the complexity of the programme and relationships between different stakeholders.

The programme has helped build momentum on the need for fundamental reform of security sector financing. The post-election landscape will determine whether this momentum can be carried forward. The programme’s activity in securing community buy-in; supporting legislators to carry out their oversight functions; direct work with the Police at both state and national level as well and placing experts in the Office of the Vice-President (OVP) is maximising the chances of sustainable implementation.

The decision to end the prisons component of the work, and reallocate funds towards higher priorities suggests that the programme is implementing an adaptive approach. This has though made the programme extremely ‘security’ focused and the team could look for opportunities to catalyse and promote justice reforms where appropriate.

Summary of recommendations for the next year

Strategic

Consider a realistic outcome for the programme’s focus in North East Nigeria aligned to the UK Government’s North East strategy and other UK Government programme objectives. The team need to agree what is feasible to promote public safety and security. The National Police Programme should be encouraged to resource this part of the work appropriately.

The programme needs to develop strategies (and contingencies) to keep or regain momentum during the post-election period. This should be considered as part of the regular risk monitoring.

Detailed consideration should be given to the gender elements of the programme, beyond awareness raising of the Women Peace and Security Agenda.

Operational

Review the Results Framework (RF). This is not yet capturing outputs. The number of outputs should be reduced to those which accurately reflect contributions to the intermediate outcomes and which can be clearly communicated to political and other UK Government actors. The number and detail of the indicators for intermediate outcomes should also be reviewed.

Further work is needed with NPP to harmonise the NPP and SJRP RFs, and payment milestones. These should reflect priority areas of work, rather than activities.

Consider, from a value for money (VfM) perspective, the value added of non-resident international partners working with the National Assembly and Nigerian Air Force.