## Annual Review - Summary Sheet

PROGRAMME TITLE: Nigeria Serious and Organised Crime (SOC) Programme
Country/Region:	Nigeria
HMG Partners	National Crime Agency (NCA), Home Office (HO).
Total Spend:	ODA: £3.21M / (budget adjusted in year)			Non-ODA:
Start Date: April 2016		End Date: March 2019
Outputs					Score
Joint Border Task Force (JBTF): the JBTF is capable of conducting effective SOC investigations, acts in compliance with human rights standards and gender sensitivity considerations and prosecutes offenders promptly and effectively in compliance with domestic legislation.					A+
NCA Project INSTINCT: Increase probability of recovering the hostage/s in kidnap investigations safely by providing capacity-building training and mentoring to specialist units.					B
Overall output score: Outputs met expectation					A
Outcome Assessment: Outcomes met expectation
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	B	A	A	A
Risk Rating	Medium	Medium	Medium

*output/outcome scores

What support is the UK providing?

The programme has two areas of activity. The first on corruption and borders; the second on kidnapping. The programme was designed as part of a regional strategy to combat SOC in West Africa, including engagement in Togo and Benin. The principal threats addressed through the programme are human trafficking, corruption, kidnap and extortion, and illicit commodity/drug trafficking.

The programme supports capacity building of the JBTF, a multi-agency task force established in 2015/2016 with CSSF funding, by providing a cross-government team of UK law enforcement mentors led by the NCA. The aim is to build an agile and capable multi-agency operational team, capable of conducting complex investigations into all types of SOC impacting on Nigeria’s borders.

NCA has also built on existing strong relationships with Nigerian law enforcement to deliver capacity building in managing kidnap cases. This aims to increase public confidence in Nigerian law enforcement’s capabilities, and to reduce the risk of harm to hostages and victims.

During FY17/18 the programme was supported by a UK CPS Criminal Justice Advisor, funded under the JBTF project, who delivered training and mentoring on SOC cases to prosecutors and judges to improve case management and outcomes, through increased transparency and accountability.

Summary of progress and lessons learnt/actions taken since last review

Overall, the programme has met expectations, with some additional positive benefits not initially planned. While the NCA lead the projects, they have full support from and integration with other UK Government resources in Nigeria, including engagement from the Home Office, Foreign & Commonwealth Office, Department for International Development, Border Force, and Immigration Enforcement International.

Work delivered in Togo and Benin, has significantly increased the operational ability of officers engaged in countering the threat from drugs and human trafficking by focusing on mentoring law enforcement officers in parallel with the engagement in Nigeria. The project leads have built lasting relationships with Nigerian, Togolese and Beninoise officials. This has also resulted in improved access at senior government levels in each country.

The programme leads have worked more collaboratively. Siloed working, identified as an area for improvement in previous ARs, has ended. This has improved the complementarity of projects. The programme overall has significantly improved the UK’s profile on SOC with the Nigerian government and law enforcement bodies, and had an impact on threats affecting Nigeria and the UK.

Summary of recommendations for the next year

Use the forthcoming Serious Organised Crime Joint Analysis (SOCJA) exercise to inform the programme’s work.

Consider how to improve the programme’s ability to surge trained staff when required. Alternative avenues of securing staff might include retired NCA personnel. The Stabilisation Unit might wish to consider developing an NCA associate cadre.

Further develop and formalise cross project learning, building on that identified through individual projects. This could be developed into a specific objective in future programming.

Continue to build monitoring & evaluation (M&E) expertise, including via a cross-government Nigeria M&E workshop.

The programme has significantly improved its consideration of gender. The team could consider developing a forum to promote support, lesson sharing and development on gender issues across the mentored Nigerian projects, drawing on the empowered and committed female host country staff within the projects.