Annual Review - Summary Sheet

PROGRAMME TITLE: Early Recovery Stabilisation in newly or recently recovered areas
Country/Region:	Somalia
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Ministry of Defence (MoD)
Total Budget:	ODA: £1.10m			Non-ODA: £0
Start Date: April 2016		End Date: March 2019
Outputs					Score
Gender and conflict sensitive approaches to grassroots reconciliation and political negotiations are developed by the Early Recovery Initiative project in collaboration with the African Union Mission in Somalia (AMISOM), Somali Security Forces (SSF), the Federal Government of Somalia (FGS) and other stabilisation actors.					A
Support district level interim community consultation forums in newly recovered areas In South West, Jubaland, Galmudug and Hirshabelle States.					A
Community-driven activities identified and delivered through inclusive participatory processes and supported with a combination of programme funds and assistance of other partners.					A
Overall output score					A
Outcome Assessment: Outcome is on course to meet expectation
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	A	A	A	A
Risk Rating	High	High	Medium

*output/outcome scores

What support is the UK providing?

The programme operates in the early recovery phase that precedes ‘transitional’ stabilisation. It aims to support the foundations for the political settlement and stability to allow the FGS and Federal Member States (FMS) to establish their presence in areas that have been recently recovered by AMISOM and SSF.

The programme consists of: (i) the Early Recovery Initiative (ERI) project, which aims to address local drivers of conflict and deliver improved community cohesion through inclusive community engagement; and (ii) a set of upstream interventions, which entails diplomatic engagement with both local and international actors as well as donors, to influence the overall approach to Early Recovery Stabilisation.

Summary of progress and lessons learnt/actions taken since last review

The programme’s Theory of Change (ToC) and Results Framework (RF) have been updated, and targets and milestones now better measure the programme’s progress. The ERI project has been redesigned and is now aligned to the FGS’s framework for local governance and has been structured around two main interventions: establishing a platform for dialogue between communities, AMISOM and SSF; and establishing community consultation forums in support of developing District Councils and supporting community-led activities.

The programme lead held regular Early Recovery meetings to increase awareness of the programme with other donors and within AMISOM. The team engaged AMISOM leadership to sustain the support given to the programme and to develop more effective communication between sector level and AMISOM Mission Headquarters (MHQ).

The programme strengthened the delivery of joint AMISOM & Somalia National Army (SNA) Civilian Military Co-operation (CIMIC) training and the Pre Deployment Training (PDT) carried out by BPST (A).

The programme supported AMISOM gender training, human rights and “Child Soldier” workshops. It also provided training and development activities in the FMSs to build the capacity of government institutions. Success stories from these trainings and workshops have been featured on Somali media and social media.

Summary of recommendations for the next year

Improve operational synergies between the upstream and downstream work. In order to ensure that the effects of AMISOM and SSF training is felt at the local level and to better synchronise the various sets of activities.

Consider expanding ERI coverage to more remote regions of Jubaland and South West states, increasing the current budget for Community Based Liaison Officers (CBLOs) to hire more.

Ensure all RFs for partners have measurable targets. RFs should also estimate the number of direct and indirect beneficiaries to help provide a measurement of the programme Value for Money (VfM)