Annual Review - Summary Sheet

PROGRAMME TITLE: Somalia Human Rights and Vulnerable Persons’ Programme
Country/Region:	Somalia
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO)
Total Spend :	ODA: £0.4m		Non-ODA: £0
Start Date: April 2015		End Date: March 2018
Outputs				Score
Improved support is in place for victims of sexual violence in Mogadishu, Guriceel and / Galkayo				A+
Project outputs
Strengthened institutional system for prevention, detection, and response to Gender Based Violence (GBV)				A
Improved quality and scope of response services delivered to survivors and children at / Risk				A
Increased knowledge on GBV, awareness raising and advocacy at district, national and international levels				A
Overall output score				A
Outcome Assessment: Improved knowledge about, response to and prevention of / GBV at national and district levels and advocacy at international level
Outcome Score: A				Risk: Medium

Summary of Programme Performance

Year	2015/16	2016/17	2017/18*
Programme Score	B	A+	A	A
Risk Rating	Medium	Medium	Medium

*output/outcome scores

What support is the UK providing?

The programme supported the delivery of the ‘Promoting Rights, Protecting Women’ project which delivered a holistic approach to preventing Gender Based Violence (GBV) in three districts of Mogadishu, and with partner funding, in two additional semi-urban districts.

The programme approached Human Rights and specifically women’s rights issues from the grass-roots level, promoting consensus on the values underpinning Human Rights and so contributing to prevention of gender-based violence and stigma. The project also addressed immediate needs in providing health and social services to survivors of GBV.

Summary of progress and lessons learnt / actions taken since last review

Extensive research by implementing partners helped them learn lessons on developing prevention mechanisms for GBV and community engagement strategies. For example, the lessons from this were used to change the format of community discussions, and to include boys in the project through boys’ clubs. The project is finalising a dialogue guide in English and Somali, ensuring that the lessons learnt from the dialogue process and the community dialogue group are captured and can be shared.

Summary of recommendations for the next year

Analyse more thoroughly the potential causal links between activities, outcomes and intended impact within the Theory of Change.

Develop a capacity building strategy for staff and training participants, ensuring: i) that the targeting of the training is appropriate for the participants, ii) that the activity employs a rigorous monitoring and learning element in order to inform future training, and iii) that appropriate records are kept to inform future activities;

Future activities that incorporate distinct advocacy activities would benefit from having an advocacy strategy;