Annual Review - Summary Sheet

PROGRAMME TITLE: SOMALILAND CSSF PROGRAMME
Country/Region:	SOMALIA
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO)
Total Spend :	ODA: £3.75m			Non-ODA: £0.02m
Start Date: April 2016		End Date: March 2019
Outputs					Score
1. Institutional capacity, accountability, transparency and security of Somaliland justice institutions is strengthened					A
2. Sustainability of counter-terrorism (CT) capacity of Somaliland Police (SLP) is strengthened					B
3. Institutional capacity, accountability and democratic oversight of defence institutions (MoD, Army, and Coastguard) is strengthened.					B
4. Somaliland’s electoral authorities have increased technical capacity and credibility					A
5. Government of Somaliland communications capacity and relationship with media is enhanced					A
Overall output score A					A
Outcome Assessment: the programme is making a contribution to progress in support of the outcome, in particular building capacity in the criminal justice system and on stability around elections. But it is challenging at this stage, given the Theory of Change (ToC) and indicators selected, to be clear whether progress is sustainable or in line with expectations.
Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	B	A	A	B
Risk Rating	Medium	Medium	Medium

*output/outcome scores

What support is the UK providing?

The programme aims, in concert with wider UK diplomatic and development efforts, to improve Somaliland’s capacity to manage its own internal security and become more stable and secure and a more constructive partner on UK Government objectives, including protecting the UK. It consists of two parts:

Security and Justice Sector Reform: targeted, sustainable capacity-building to enable Somaliland to better manage its own internal security in a more transparent and accountable way; and enabling and protecting CT capability thereby helping to reduce the threat to the UK and UK interests. Inputs include technical assistance and other support to the criminal justice system, police, army, Defence Ministry and Coast Guard.

Political Stability: contributing to improved democratic processes, including peaceful and transparent elections via support to the National Election Commission; and capacity building of the Government’s communications function and of the private media.

Summary of progress and lessons learnt/actions taken since last review

The programme has continued to make progress across its two strands. It provided support to free, fair and peaceful Presidential elections in late 2017 developing and facilitating a media Code of Conduct which helped ensure equitable coverage and avoid inflammatory language in the private media. This was voluntarily taken up and followed by the State media. The programme also funded an international election observer mission which provided a valuable independent expert view.

Progress on supporting reform and greater accountability in the security and justice sector was more uneven. Late agreement on contracting the implementer reduced timescales and the elections created a number of uncertainties, risks and delays. Solid progress was made to make the criminal justice system more efficient through a computerised case management system and infrastructure support. Incremental progress was made in building information management capacity and skills in the Coast Guard and in promoting more effective joint working between the Ministry of Defence and the Army. Further support to the police helped embed skills in maintaining public order in a Human Rights compliant way, demonstrated by their effective handling of a number of events around the elections.

Important lessons learned from the previous review included: ensuring longer contracts for implementers; adjusting implementation priorities in response to changes in the context (particularly elections). The management of the programme will be further strengthened by the decision to recruit a UK civil servant Programme Manager.

Summary of recommendations for the next year

Analysis and Evidence: further develop the evidence base by using the conflict analysis and forthcoming Countering Violent Extremism analysis to identify key conflict and instability drivers suitable for CSSF effort and potential impact.

CSSF Priorities: agree with other UK Government stakeholders a clear shared understanding of areas where the CSSF should be the lead UK Government funding tool and areas where it should fund activity in support of wider UK Government priorities.

More Political Focus/Higher Risk Appetite: consider ways to make the political stability strand more politically-attuned, including, potentially, taking more risks.

Portfolio Balance: as part of the above, rebalance the portfolio between Security and Justice (S&J) and wider political stability, consider narrowing the breadth of CSSF-funded interventions on S&J.

Programme Management Tools: review the ToC and identify improved evidence indicators. Also consider more specific outputs to ensure they are fully achievable. Agree the Results Framework in conjunction with the implementers and monitor and update regularly. Consider whether political access and influencing objective(s) should form a distinct part of results.

Monitoring and Evaluation: improve the breadth and sources of monitoring evidence to avoid over-reliance on implementers’ own reporting, including from the UK Government, international partners and more formal but proportionate third party monitoring.

Human Rights: improve reassurance by quickly ensuring that all relevant CSSF programme activity is covered by an up to date Overseas Security and Justice Assistance assessment (OSJA) with the right level of specificity.