Annual Review - Summary Sheet

PROGRAMME TITLE: South Sudan National Conflict Reduction
Country/Region:	South Sudan
HMG Partners (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID)
Total Spend :	ODA: £2.06m / (budget adjusted in year)			Non-ODA: £0.09m
Start Date: Feb 2016		End Date: March 2019
Outputs					Score
High quality expertise provided to key institutions and structures for the monitoring and implementation of the peace agreement which supports increased accountability and enhanced leverage.					A
UK Government has increased capacity to engage strategically in, provide policy leadership to, and influence key actors in support of the implementation of a more inclusive and robust peace agreement					A +
Outcome: UK efforts contribute to the Joint Monitoring and Evaluation Commission (JMEC) and its subsidiary bodies being increasingly able to galvanise a way forward for a revitalised and more inclusive peace process, harnessing the support of regional and international actors.
Overall output score:					A
Outcome Assessment: Progress partially did not meet expectation
Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2016/17	2017/18*
Programme Score	B	A	B
Risk Rating	HIGH	MEDIUM

*output/outcome scores

What support is the UK providing?

The programme provides support to the institutions mandated by the Agreement on the Resolution of the Conflict in South Sudan (ARCSS) which did not have the technical expertise needed to implement and carry out their mandates. Support consists of funding for an implementer to provide technical support to the JMEC and the Ceasefire and Transitional Security Arrangements Monitoring Mechanism (CTSAMM), as well as ad-hoc training courses or activities relating to implementation of the ARCSS.

The programme also provides temporary members of UK Government staff, in both Juba and London, to coordinate internally and engage externally on the ARCSS. This also helps facilitate HMG’s increased engagement with the process, following the events of July 2016.

Summary of progress and lessons learnt/actions taken since last review

The CSSF team has delivered a well-structured and implemented programme, in the most difficult of circumstances.

In response to 16/17 Annual Review recommendations, the team has re-adjusted programme focus and content in light of the policy review prompted by the Joint Assessment of Conflict and Stability (JACS) and planned ahead for FY 18/19, to combine the national and sub national programmes into one to allow greater flexibility.

Through the JACs process and CSSF programme prioritisation, the team has also reviewed the components and overall strategy of the programme, balancing a short versus long run prevention focus, and developed a stronger theory of change.

The programme has also enhanced its policy and programme management support, through stronger Senior Responsible Owner (SRO) oversight and additional administrative support. It has also strengthened governance mechanisms by implementing regular strand board meetings with reviews on key policy decisions. It has also supported greater lesson learning and exchange between the different components of the programmes, through holding joint implementing partner meetings on a quarterly basis.

The programme has also increased its focus on working with / on perpetrators of sexual and gender based violence (SGBV), by prioritising in other areas.

Summary of recommendations for the next year

UK support to the peace process and institutions should for the moment be “no more but no less”. It will be important to see how ongoing peace talks pan out and be nimble – the programme should be designed to support this as much as possible. The UK Government should encourage closer JMEC/CTSAMM ties, and consider carefully any potential future limiting of support to JMEC/CTSAMM for short-term operational reasons.

This AR agrees with the 16/17 recommendation to merge the national and subnational South Sudan programmes. When this happens in FY18/19, programme management needs to be higher level and more strategic. This would also ensure that the CSSF-funded UK Government advisors could focus on their core activities without being drawn into administrative issues. If there are gaps in the CSSF team, additional programme staff should be appointed.

The current Programme Management arrangements work because of the personalities involved and despite the challenges of the geographic spread. As and when platform constraints ease, the Programme Manager should spend more time in Juba.

The programme should retaining the ability to scale up or wind down interventions and develop reserve activities which can be implemented at short notice to take advantage of additional central resources.

The objectives and limitations of UK Government support must be clear in all programme documentation, including the Results Framework to ensure outputs and outcomes are more easily ‘measurable’.

The programme should develop a more robust and sophisticated risk matrix. Duty of care and security plans should be regularly reassessed. Overseas Security and Justice Assistance (OSJA) requirements should be kept under constant review. Implementing Partners must be aware of UK Government sensitivities and OJSA requirements.

The UK Government team should ensure a clearer delineation between CSSF-funded UK Government advisors in JMEC/CTSAMM and those funded from other sources. Care needs to be taken to ensure that these roles are not used to fill other gaps where not appropriate.

Establish more regular meetings between the implementer and the team. These should include policy and managerial leads.