Annual Review - Summary Sheet

PROGRAMME TITLE: South Sudan Subnational Conflict Reduction Programme
Country/Region:	South Sudan
HMG Partners (LEAD in bold)	Department for International Development (DFID), Foreign and Commonwealth Office (FCO)
Total Spend :	ODA: £1.97m			Non-ODA:
Start Date: April 2016		End Date: March 2019
Outputs					Score
Conflict sensitivity programme (Saferworld-led consortium)					A+
Conflict early warning and early response system (Catholic Relief Services)					A
Preventing violence & building safer communities in Wau (Nonviolent Peace Force)					B
South Sudan Council of Churches (Christian Aid)					A
Overall output score					A
Outcome Assessment: Progress broadly met expectations.
Outcome Score: A			Risk: Medium

Summary of Programme Performance (*output/outcome scores)
Year	2015/16	2016/17	2017/18*
Programme Score		B	A	A
Risk Rating		Medium	Medium

What support is the UK providing?

The programme provides support to a range of Non-Governmental Organisations (NGOs) working at the local level with communities to reduce and mitigate violent conflict through (i) conflict prevention, reconciliation and peace building activities, and (ii) conflict mitigation with a special focus on building community resilience and safety through protection, and preventing sexual violence.

Summary of progress and lessons learnt/actions taken since last review

The CSSF team has delivered a well-structured and implemented programme in difficult circumstances. The programme has achieved excellent progress with delivery largely on track and expected results achieved. CSSF funding has helped strengthen local structures for peace dialogue and linkages between communities and state and national level governments on conflict reduction and resolution. There is strong evidence of a positive contribution in reducing violent conflicts at local level and building stronger community relationships. There are concrete results in a number of settings, including examples of Community-Based Reconciliation Mechanisms (CBRMs) resolving conflicts through local peace dialogues and increased participation by women in conflict resolution efforts.

There is evidence of the linkages between the national and subnational CSSF programmes. The programme also works coherently with other interventions by international partners. The subnational programme refresh has used adaptive programming, undertaking the South Sudan Council of Churches (SSCC) pilot and using lessons to develop a larger full year programme. The team have shown flexibility towards implementing partners’ (IP) programme management constraints including by not expanding the Conflict Early Warning and Early Response System (CEWERS) project into new states.

The Conflict Sensitivity Programme (CSP) is an innovative project, and its move to DFID is a good example of using the CSSF to pilot new initiatives. The planning for the Peacebuilding Opportunities Fund (POF) will further the CSSF programme team’s ability to be responsive, flexible, and agile in such a highly challenging context.

This Annual Review validates the 2016/17 recommendation to merge the national and subnational strands.

Summary of recommendations for the next year

While the individual elements of the subnational portfolio are delivering much needed elements of conflict management and reduction, the programme should aim to develop a greater level of connectivity and synergies (e.g. more geographical convergence of activity to “be more than the sum of the parts”). This could include: options for scaling up subnational level efforts; an assessment to bring together parallel efforts through different mechanisms; a review of the Building Safer Communities (BSC) programme. It is hard to see the national to local level linkages that other programmes are able to achieve. Some of its work has a protection of civilians/humanitarian angle, which would sit better within a DFID or other programme.

The Local Strategy Board (LSB) and programme leads have provided good overall governance, oversight and monitoring of activities, results and outputs. The LSB could now shift emphasis to monitoring higher level outcomes and impact. LSB administrative support could be strengthened.

The implementing partners meeting is an excellent initiative. The platform should include policy and managerial leads.

Risk – given the high levels and unpredictability of violence and insecurity, implementers should show they are testing their duty of care responsibilities on a regular basis. The team should also make more of implementers’ exceptionally fine-grained analysis of their areas of operation.