 Annual Review - Summary Sheet

PROGRAMME TITLE: Conflict Resilience and Stabilisation
Country/Region:	Sudan
HMG Partners (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID)
Total Spend :	ODA: £1.97m / (budget adjusted in year)			Non-ODA:
Start Date: April 2017		End Date: March 2020
Outputs					Score
Community initiatives deliver collaborative livelihoods and income generating activities					A
Better administrative, technical and reporting capacity of the African Union High Level Implementation Panel (AUHIP), and a sustainable mechanism for it to be supported					B
Overall output score: A / Given the weighting of the two different components, the programme scores an A.
Outcome Assessment: / There has been more limited progress this year under Outcome (1) progress in implementing a Roadmap for peace in Sudan as well as peaceful cooperation with South Sudan, more on Outcome (2) higher levels of trust between communities in Darfur and the Two Areas, Overall, a B is appropriate: that outcomes moderately did not meet expectation, combined with insufficient evidence to demonstrate the contribution.
Outcome Score: B			Risk: Medium

Summary of Programme Performance *
Year	2015/16	2016/7	2017/18*
Programme Score	B + A	A	A	B
Risk Rating	Medium High	Medium	Medium

What support is the UK providing?

The programme aims to strengthen inclusive conflict management architecture and improve long term stability and peace in Sudan through two main components:

Supporting two United Nations Development Programme (UNDP)-managed programmes: the Darfur Community Peace and Stability Fund (DCPSF), and the Community Security and Stabilisation Fund (C2SP). The programmes aim to build community conflict resilience and stabilisation, with increased trust and confidence between communities, and inclusion of women in peacebuilding, to help pave the way towards recovery in Darfur and the Two Areas (South Kordofan and Blue Nile).

Support to the AU High Level Implementation Panel (AUHIP) to promote progress towards a peace agreement between the Government of Sudan and the armed groups in Darfur and the Two Areas, paving the way for political participation; and promote progress on implementation of the 2013 Cooperation Agreements between Sudan and South Sudan.

Summary of progress and lessons learnt/actions taken since last review

Oversight and governance of the programme has strengthened with good follow-up on the recommendations of the last Annual Review, particularly in relation to strengthening conflict sensitivity and inclusion of women in peacebuilding at the subnational level. There has been progress in developing programme-wide responses on sexual and gender-based violence (SGBV).

The implementation of recommendations by implementing partners has been good in some areas, for example by DCPSF on gender. C2SP has also made good progress in implementing recommendations although it has been slower to respond on gender sensitivity. There has been limited adaptation in the work of AUHIP.

The UK Government has taken advantage of its co-funding of the DCPSF and role on the Steering Committee to leverage stronger implementation, in close cooperation with the other donors. The UK Government has continued to work closely with the team at the AUHIP on national level peace efforts and has a high level of political access. But collaboration with the AUHIP has not adequately translated into delivery. The joint configuration of CSSF and DFID funding highlighted in the last review as placing UK in a strong position to leverage change still needs to be better synchronised.

There has been strengthened complementarity between CSSF work and other UK Government projects at the subnational level (e.g. DFID-funded demining in South Kordofan and livelihoods initiatives in Darfur).

A stronger UK Government political influencing strategy is needed in the context of the UK-Sudan Strategic Dialogue, with clear objectives and targets.

There remains need for stronger portfolio level Theory of Change (ToC), to include linkages between national and subnational level peacebuilding efforts, as well as a more robust and ambitious Results Framework and use of approaches to measure Political Access and Influencing (PAI). Financial management of the programme has been robust. The streamlined programme structure has reduced transaction costs.

Summary of recommendations for the next year

There is a need for stronger UK Government political engagement in support of CSSF activity in order to maximise returns.

Reconsider the use of CSSF vis a vis other UK Government funding with clear criteria on what CSSF should fund and why, and with a transition strategy for CSSF programmes to be “mainstreamed” into DFID funding where appropriate.

Develop a stronger and more ambitious Results Framework which better captures the breadth and depth of what is being delivered, includes a stronger focus on political engagement in support of conflict reduction and peacebuilding objectives on the back of CSSF support, and better incorporating ole of women in peacebuilding.

Continue to build a stronger focus on conflict and gender sensitivity within the programme, including encouraging more transparent conflict analysis by DCPSF and C2SP which can feed into an enhanced HMG understanding of conflict in both Darfur and the Two Areas.

Support AUHIP to have a stronger, outcome-oriented strategy with clear milestones for progress Continue to develop holistic, cross-government approaches to peacebuilding, stabilisation and recovery in Darfur and the Two Areas making catalytic use of CSSF funding.