Annual Review - Summary Sheet

PROGRAMME TITLE: Irma Hurricane Recovery
Country/Region:	Overseas Territories – Anguilla, British Virgin Islands and Turks and Caicos
HMG Partners / (LEAD in bold)	FCO, MOD, DFID
Total Budget: £72m	ODA: £0			Non-ODA: £72m
Start Date: Sept 2017		End Date: March 2018
Outputs					Score
Output 1- Immediate assistance provided to critical national infrastructure, including health and housing infrastructure, where damage poses an immediate threat to economic recovery, public health or general wellbeing					B
Output 2 - Enhanced disaster recovery systems, mechanisms or policy frameworks					A
Output 3 – Immediate needs supported for the restoration of security through capability augmentation, capacity building, infrastructure and policy advice					A
Overall output score					B
Outcome Assessment: Outcomes met (or are on course to meet) expectation
Outcome Score: A			Risk: Medium

Summary of Programme Performance (*output/outcome scores)
Year	2017/18*
Programme Score	B	A
Risk Rating	Medium

What support did the UK provide?

Anguilla, the British Virgin Islands and Turks and Caicos are Overseas Territories that were hit by Hurricanes Irma and Maria in September 2017; there was widespread devastation though limited loss of life. Roads became impassable; potable water production ceased; the electricity grids and communications networks collapsed; ports and the airports were damaged and most government buildings sustained some damage or were destroyed including the executive functions and all services delivery departments. The scale of damage overwhelmed local capacity and no contingency plan (locally or in the UK) was designed to cope with the unprecedented occurrence of two consecutive Category 5 hurricanes. On the islands ‘over 45,000 people, many of whom were British nationals, faced grave danger.
Funded by the CSSF the UK deployed its full range of assets across the military, police, diplomatic and aid staff which supported the local Governments and private sector response. While many lessons have been learned from the initial response comment – sounds like we haven’t done it yet – can we tweak? across the Departments, Crisis Centre and the Territories, it is clear that in all three territories the CSSF enabled the restoration of functioning life much faster and in a more comprehensive manner than would have been possible without it.
In the words of one of the Anguillan partners we spoke to, the CSSF provided “some stability when we really needed it.” These are important real world impacts from the CSSF. Notable outcomes include the restoration of law and order on BVI, restoration of power by mid-December in Anguilla and by January in BVI, capacity augmentation and capacity building across the police and prison services and key infrastructure repairs and upgrades to airports.
There are of course still significant needs – these vary across the islands, and will be addressed in Anguilla and BVI via the £70m recovery fund (also managed by the CSSF) from 2018-2021. The biggest immediate risk is that another hurricane strike – even a Category 3 could be devastating since recovery from the 2017 hurricanes is still underway. Whilst parts of Territories’ infrastructure are already more resilient than prior to Hurricane Irma (notably the airports, police services and electricity grids) a direct hit would set back progress significantly.

Summary of progress and lessons learnt/actions taken since last review

Lesson: The morale boost and confidence provided by UK military support was invaluable. It is however difficult to sustain, and due to the pressing need to deliver quickly, in some areas, UK military resource was not necessarily prioritised to the on the most pressing (military) task, and in some cases was diverted to areas better suited to civilian lead. Recommendation: HMG could consider the most effective way to deploy its range of resources is against the diverse range of tasks required in future Hurricane responses.

Lesson: The ability for the UK to deliver across a range of sectors, including hard security, policing, prisons as well as more traditional humanitarian response sectors was essential to addressing the requirements on the islands. Recommendation: Future responses should assume that the full range of the UK’s capabilities may be required.

Lesson: Humanitarian response approaches, including supplies of water and shelter, cash transfers and restoration of the most critical parts of infrastructure were all important, but could have been better targeted or deployed more efficiently. Recommendation: Lead UK departments and delivery agencies to work with partners, including Disaster Management Departments, the British and local Red Cross organisations to improve mapping and future distribution plans.

Summary of recommendations for the next year (Relevant to the Anguilla & BVI Programmes)

Lesson: The transition of UK funded support from Phase 1 (immediate response) to Phase 2 (recovery) was not executed well with the Task Force deployed in to the region being wound-down after 8 weeks. This resulted in a loss of momentum in recovery. Recommendation: a standard operating procedure for moving from crisis to recovery should be in place for the next hurricane season.

Lesson: Risk management was not as systematic as it could have been and increased risk to HMG, though risk identification and mitigation was impressive. Recommendation: risks registers need to be used as live management documents.

Lesson (Outcome 1): each sector on each Island faced different challenges that had to be overcome iteratively which slowed delivery. Recommendation: across key infrastructure sectors assessments (now complete) need to be factored in to response options and choices to enable faster more effective delivery.

Lesson (Outcome 2): the outputs delivered provide a useful source of material for future response planning and the longer-term recovery programme and some evidence could not be sourced yet (due to delivery in Q4). Recommendation: identify which outputs will be used to support the various projects in the longer-term recovery programme and where necessary use funding from 18/19 to conduct follow-up evaluations of the outcomes of some of the FY17/18 outputs.

NOTE: This review focused primarily on the early recovery programme £15m, but incorporates within it the evidence and conclusions of the Phase 1 review (conducted in February 2018) and covering the remaining £57m.