Annual Review - Summary Sheet

PROGRAMME TITLE: Colombia Peace Process Programme
Country/Region:	Colombia
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO)
Total Spend:	ODA: £11.43m / (an in year uplift of £7.10m to the original budget of £4.60m was received in year)			Non-ODA: N/A
Start Date: April 2015		End Date: March 2020
Outputs					Score
Output 1: Support rural development and reintegration programs to create opportunities for sustainable economic transformation of post-conflict areas					A
Output 2: State security and justice capacity strengthened					A
Output 3: Contribute to promoting reconciliation and effective Government of Colombia (GoC) communications to ensure a public support of peace					A
Overall output score					A
Outcome Assessment: / Outcome: Support the Government of Colombia to address the causes and symptoms of violent conflict – likely to be met
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	A	A	A	A
Risk Rating	Medium	Medium	Medium

*output/outcome scores

What support is the UK providing?

The Colombia Peace Process (CPP) Programme, aims to support the GoC to address the causes and symptoms of violent conflict thereby sustaining trust in and progress towards implementation of the historic peace agreement signed in November between the GoC and the Fuerzas Armadas Revolucionarias de Colombia (FARC). The programme supports more than 20 projects aimed at delivering progress against three intended outputs:

Output 1: Support rural development and reintegration programs to create opportunities for sustainable economic transformation of post-conflict areas; (Priority theme: Rural development)

Output 2: State security and justice capacity strengthened;

Output 3: Contribute to promoting reconciliation and effective GoC communications to ensure a public support of peace.

The programme is implemented by a number of different implementing partners, including the United Nations and its associated agencies, the British Council, and local and international non-governmental organisations (NGOs).

Summary of progress and lessons learnt/actions taken since last review

The programme made important progress towards all three outputs over the last year:

Under output 1, the programme supported the construction of more than 140 small-scale infrastructure projects, providing short-term employment for 1,176 people. It also supported the training of 783 community leaders (22% of which were youth leaders) in negotiation, advocacy, and social participation skills, which will be crucial for their engagement with the GoC’s planned rural development process.

Under output 2, the programme supported the development of the Colombian National Police’s (CNP) ‘National Police Peace-building Model’, a strategy which will help transform the CNP to ensure it contributes to the peace process and is fit-for-purpose in the post-conflict era. It also supported the introduction of local justice systems in 12 municipalities, which will improve communities’ access to justice services.

Under output 3, the programme supported the development of a cross-GoC communications strategy which will enable the GoC to deliver clear co-ordinated messaging on the peace process, rather than disparate (and often conflicting) ones as had occurred to date. It also supported the dissemination of communications campaigns aimed at raising public awareness around the peace process, reaching nearly one million people.

Summary of recommendations for the next year

The programme should consider what the right balance should be between the number and size/scale of the projects it supports going forward, particularly taking into account the new Colombian administration’s approach to the peace process.

The programme should be rationalised to support only those projects that are likely to make a coherent, strategic, catalytic, and sustainable contribution to the intended outcome.

The programme team should revise the results framework through a ‘blank canvass’ approach, which is not constrained by existing projects. Ignoring the current portfolio of projects in the design process will avoid path-dependency.

The results framework should also be designed to capture disaggregated data on gender, age, and disability.

The programme team should capture and articulate, in a single programme level gender strategy, the efforts currently being made to better integrate gender in programme activities.