Colombia Prosperity Fund Programme Annual Review

Cartagena, Colombia, 23 November 2018 – Official launch of the Colombia Prosperity Fund Open Procurement activity: Gloria Alonso, Director of Colombia’s National Planning Department, thanks the United Kingdom and the Prosperity Fund on national television for supporting improved transparency, greater efficiency and reduced corruption in the country’s public procurement system. She is accompanied by Peter Tibber, British Ambassador, Juan David Duque, Director of Colombia Compra Eficiente, and Nicolas Penagos, Country Director for Open Contracting Partnership.
Title: Unlocking Economic Opportunities in Colombia’s Post-Conflict and Conflict-Affected Regions / Review Period: November 2017 – November 2018
Programme Value: £25.5mn		Review Date: 20 November 2018
Programme Code: / PF COB 921001 / PF COB 921002 / PF COB 924001 / PF COB 924002 / PF COB 925001 / PF COB 925002 / PF COB 925003	Start Date: / November 2017	End Date: / March 2022

Summary of Programme Performance
Year	2018	2019	2020	2021	2022
Programme Score	A
Risk Rating	Moderate

Summary of progress and lessons learnt since last review
This is the first Annual Review (AR) of the Colombia PF Programme. Ministers approved the Colombia Prosperity Fund (PF) Programme in November 2017. In the first four months, the British Embassy Bogota, Colombia signed Memoranda of Understanding (MoU) with each of the three main implementing partners: i) Colombia’s Financial Institution for Development of the Regions (Findeter); ii) the Latin American Development Bank (CAF); and iii) Innovate UK (IUK) – the British Government’s agency for the promotion of innovation. During this period, Findeter and CAF also set up new financial processes to receive and administer PF resources. On 1 April 2018, the Colombia PF Programme went live and six of the seven activities commenced operations. The seventh activity (ANI) only began in September 2018 once the new Colombian government was in office.

List of recommendations for the next year
Regional Competitiveness
1. BE Bogota to work closely with CAF to finalise contract with CONFECAMERAS, prepare the second technical assistance ToRs for PF Commercial Framework companies and launch the first projects in Magdalena, Caldas and Valle.
2. BE Bogota should monitor spend on this activity more proactively. If it is affected by further delays, work with CAF to identify and implement remedial actions.
3. Explore how the recent MoU between CAF and UK Export Finance can support the delivery of selected Regional Competitiveness projects.
4. For the Urban Development activity, the original number of projects (three per department and 24 in total) now seems too ambitious. CAF and the BE Bogota should conduct the first three pilots and then revise the target. The reduction in the Urban Development activity from six to four cities was beneficial to the Programme as it focused efforts. The Regional Competitiveness activity should consider if reducing down from eight departments could help focus efforts and improve impact, and ensure the activity remains within budget.
5. Same as the Agri-insurance activity, BE Bogota to spend more time understanding CAF internal approval procedures and to agree with CAF how these add value, and ensure the achievement of targets by agreed milestones. At the same time, CAF should look at what it could do to reduce the time between committee meetings.
6. As the Programme becomes more established, BE Bogota should explore opportunities for further joined up programming between the Conflict, Stability and Security Fund and the Prosperity Fund in post-conflict areas, based on the regional development plans (PDTs in Spanish) of the selected departments.

Open Procurement
1. BE Bogota to work closely with Findeter, OCP and CCE to design the first complementary strand to the activity that allow CCE to ensure full adherence of SECOP II in the PF selected departments.
2. BE Bogota to design second complementary strand with Findeter and OCP that would allow civil society to better engage with and monitor implementation of SECOP II in the selected departments.
3. Revise open procurement and all nested logframe indicators to ensure they are SMART and gender and inclusion priorities are fully integrated.

Corporate Governance of ANI

BE Bogota to work closely with CAF to ensure ToRs for ANI corporate governance reform go out to market as soon as possible.

Rail Development
1. Employ BE Bogota bilateral relations and the rail working group to continue to influence the new Colombian administration on the value and potential of rail and to offer on-going strategic support including on transport project finance in tandem with the rail rehabilitation work.
2. The logframes for rail and urban development need to be revised to better reflect the wider efforts of BE Bogota in building capacity and ensuring projects are ODA compliant, deliverable and will have impact. This includes capturing better the full range of progress and benefits by breaking down the indicators and including, for instance, activities like the development / issuance of ToRs.

Urban Development
1. Revise the next version of the nested and umbrella logframes to say up to 12 urban development projects reflecting the higher cost of each initiative.
2. Use the many lessons learned from the first five urban development projects to improve the processes around the rail and regional competiveness activities as well as the remaining (up to) seven urban development projects.

Agri Insurance
1. BE Bogota and CAF to monitor closely progress and spend on this activity. If it is affected by further delays, the BE Bogota should work with CAF to identify and implement remedial actions.
2. If the SIGRA cost does double, BE Bogota should work with CAF to cut back on one or two of the other parts of this activity, based on agreed criteria of maintaining the aspects most critical to achieving impact and proving the commercial viability of the project.
3. Similar to the CAF Regional Competitiveness activity, BE Bogota to spend more time understanding CAF internal approval procedures and to agree with CAF how these add value, and ensure the achievement of targets by agreed milestones. At the same time, CAF should look at what it could do to reduce the time between committee meetings.

Agri Tech Catalyst Challenge Fund
1. Ongoing testing and education of the beneficiaries is needed to ensure they can and are willing to use the technologies.
2. If resources are secured for a second round of the challenge fund, there is a need to ensure that all the lessons learned from the first one are incorporated especially around gender and inclusion, conflict zones and sustainable crops, and if possible should focus on late stage projects.
List of Acronyms
AGROSAVIA – Colombian Agricultural Research Agency
ANI – National Infrastructure Agency
BC – Business Case
BE Bogota – British Embassy, Bogota, Colombia
CAF – Latin America Development Bank
CCE – Colombia Compra Eficiente (Colombia’s National Procurement Agency)
CIAT – International Centre for Tropical Agriculture
Confecameras – Colombian National Federation of Chambers of Commerce
COP – Colombian Peso
CSSF – Conflict, Stability and Security Fund
DD – Due Diligence
DFID – Department for International Development
DIT – Department for International Trade
DNP – National Planning Department
FCO - Foreign and Commonwealth Office
Finagro – Colombian Agricultural Development Bank
Findeter – Colombian Financial Institution for Development of the Regions
G&I – Gender and Inclusion
IADB – Inter-American Development Bank
ICF – International Climate Fund
IDEAM – Colombian Institute for Hydrology, Meteorology and Environmental Studies
IOPS – International Open Procurement Standards
IPA – Infrastructure and Projects Authority
IUK – Innovate UK
JFU – Joint Funds Unit
KPIs – Key Performance Indicators
L&D- Learning and Development
MoU – Memorandum of Understanding
MREL – Monitoring, Reporting, Evaluation, Learning
NDP – National Development Plan
ODA – Official Development Assistance
OCP- Open Contracting Partnership
PEA – Political Economic Analysis
PF – Prosperity Fund
PFDU – Prosperity Fund Delivery Unit
PPP – Public Private Partnership
RCC – Regional Competitiveness Commission
SECOP II – The Second version of Colombia’s on-line State System for Public Procurement
SIGRA – Risk Information System for the Agriculture Sector
SIP – Sustainable Infrastructure Programme
SRO – Senior Responsible Officer
ToC – Theory of Change
ToRs – Terms of Reference
UPRA – Colombian Unit for Rural Agricultural Planning
VfM – Value for Money
Logframe – Logical Framework

A. Introduction and Context
The Colombian PF Programme aims to support economic development, unlock economic opportunities and drive growth in Colombia’s post-conflict and conflict-affected regions. The Programme will benefit about 3 million people with a focus on women and girls in Colombia’s poorest regions and result in up to £1.99bn of primary benefits to Colombia over 10 years. The potential secondary benefits for international (including UK) businesses, set within the context of a peaceful, prosperous Colombia, are considerable.

The Programme targets seven activities within the three sectors of institutional strengthening; infrastructure; and agriculture:

Institutional Strengthening
1. Regional competiveness: strengthen economic development in Colombia’s regions by improving their competitiveness. Build government capacity in up to 8 regions; deliver up to 24 competitiveness projects and train up to 200 officials in project development and management.
2. Open, public procurement: more transparent, less corrupt public procurement in Colombia’s regions. Build government capacity to implement the International Open Procurement Standards in up to 8 regions and train up to 200 officials in open procurement and its effective implementation.
3. Corporate governance reform of Colombia’s National Infrastructure Agency (ANI): improve ANI’s corporate governance standards in line with UK best practice. Design a new corporate governance model for ANI and pilot it over one year with an evaluation afterwards.

Infrastructure
1. Urban development: strengthen SMART urban development in Colombia’s second tier cities. Build government capacity to implement existing urban master plans in up to 10 cities; deliver up to 30 urban development projects; and train up to 200 officials on SMART urban development.
2. Rail development: support the rehabilitation of Colombia’s narrow gauge rail network. Develop the regulatory framework; complete up to four rail rehabilitation feasibility studies and structure at least two of them for market.

Agriculture
1. Agri-insurance: develop and roll out agri-insurance to Colombia’s smallholders and agricultural micro and small enterprises (MSEs). Create and implement a IT based Risk Information System (SIGRA) to manage and mitigate risk; and provide open data information for policy and agri-insurance planning; design and market agri-insurance products and services in three pilot projects.
2. Agri-Tech Catalyst Challenge Fund: increase productivity and incomes for Colombia’s smallholders and agricultural MSEs through adoption of agri-innovations and technologies from the UK. Through a competitive bidding process, fund up to 10 agri-innovation projects, which either pilot new innovations and technologies or develop the Colombian market for existing ones.

Implementing Partners
Following an early market engagement event in October 2016, the Latin American Development Bank (CAF) was selected to implement the Regional Competitiveness, ANI Reform and Agri-Insurance activities while Colombia’s Financial Institution for the Development of the Regions (Findeter) was chosen to manage the Open Procurement, Rail and Urban Development activities. The Open Contracting Partnership (OCP) is helping Findeter manage the Open Procurement activity. Innovate UK was identified as the best partner for implementing the Agri-Tech Catalyst Challenge Fund with support from the International Centre for Tropical Agriculture (CIAT). The three main partners operate under MoUs with the PF while OCP and CIAT have grant agreements.

Selection of Cities and Regions
For the Regional Competitiveness and Open Procurement activities it was necessary to select eight of Colombia’s 32 departments to include in the Programme. Similarly, for the Urban Development activity, a selection of up to ten intermediate / second tier cities was required. BE Bogota contracted Ernst and Young through an open competition to research which cities and regions would make the best partners based on an agreed set of criteria which included, among others: potential for primary and secondary benefits; track record on economic development and fighting corruption; commitment to working with the UK Government; and historical links with the BE Bogota. The regions selected were Antioquia, Atlantico, Caldas, Cundinamarca, Magdalena, Meta, Santander and Valle del Cauca. The first six cities chosen were Cartagena, Ibague, Manizales, Santa Marta, Valledupar and Villavicencio. However, since this selection, Programme operations in both Cartagena and Villavicencio have been put on hold due to reports of electoral or financial irregularities. Until these are resolved, the Programme is concentrating on the other four municipalities.

Primary and Secondary Benefits
The Colombia PF Programme supports projects and initiatives that reduce poverty and gender inequality through inclusive economic development. Colombia PF Programme projects such as: water and sanitation for communities displaced by Colombia’s conflict; improved public transport for vulnerable populations; and agri-innovations that increase quality, productivity and incomes for smallholders especially women; demonstrate the potential primary benefits.

Colombia’s new National Development Plan has a gender chapter which the PF Programme will help to implement. It says: ‘The evidence shows that Colombian women are disadvantaged in almost all social and productive activities….Our goal is to reduce inequality to a minimum through policies that empower women economically, politically, physically and through education… This plan proposes eight policies to enhance gender equality (p 751):

1. Strengthening the institutionalisation of gender issues
2. Educational and economic empowerment to address gender gaps in the labour market
3. Care and other coordinated actions
4. Political empowerment for women to participate more in decision-making
5. Sexual and reproductive rights
6. The right to a life without violence
7. Rural women
8. Gender equality for peacebuilding.’

The Colombia PF Programme has taken a number of steps to strengthen its gender and inclusion (G&I) focus. In August 2017, a senior social development expert revised the Business Case and MoUs with implementing partners to ensure they contained the right policies and practices reflecting global lessons learned and the UK’s International Development (Gender Equality) Act of 2014. The following month, the same expert helped the PF Team and implementing partners devise a G&I Strategy for the Programme that included capacity building for public and private sector stakeholders. The expert returned to Colombia in May 2018 to assist implementing partners the design of G&I Action Plans which articulate a clear set of commitments to ensure each activity has maximum impact on target beneficiaries. Each of the Agri Tech Catalyst projects are currently designing G&I Action Plans proportionate to their budgets and timeframes.

To support increased market opportunities to and from Colombia, contracts to design projects for the Regional Competitiveness, ANI Reform, Rail and Urban Development and Agri-Insurance activities will be awarded to companies listed in the PF Commercial Framework through a procurement competition. CAF and Findeter will manage the contractual processes for the design contracts (usually feasibility studies). The main secondary benefits from the Colombian PF Programme are opportunities that will arise for international businesses, including UK companies, to construct and / or manage projects resulting from the design / feasibility phase.

In the case of the Agri-Tech Catalyst Challenge Fund, new technologies and innovations will be adapted to support small holder and female farmers improve their production, reduce barriers and increase their incomes. SMEs, NGO’s and university groups will transfer knowledge and technology to their Colombian partners through pilot projects. If successful, the pilot initiatives could expand, be replicated and lead to future and more opportunities. For the Open Procurement activity, we expect to see more transparent, less corrupt, public contracts being awarded to international businesses including UK companies at the sub-national level in Colombia. Preventing resources being corruptly misplaced and assuring that projects will be implemented to benefit the most needed. The secondary benefits are that international businesses including UK companies will benefit from the improved environment and be attracted to bid for resultant contracts. A full description of expected secondary benefits can be found in the Colombia PF Programme Secondary Benefits Plan.

Programme Implementation
Programme implementation began on 1 April 2018. At the time of the AR mission (week of 22 October 2018), the Programme had been running for just over 6 months. During this period, two issues contributed to a partial delay of Programme implementation:

1. a move away from using CAF and Findeter contracting guidelines, as stated in the original MoUs, to a hybrid model that awards project design contracts to companies in the PF Commercial Framework; and
2. to a lesser extent, Colombian general and presidential elections that brought a new administration to power on 7 August 2018.

The latter meant that both BE Bogota and the PF implementing partners had to invest in building new relationships with ministers and senior government representatives to secure buy-in and support that would allow the Colombia PF investments to proceed. As a result, all seven activities only became operational in October 2018. Interest by the new government in the PF Programme has been strongly enthusiastic with several senior representatives requesting that implementation be brought forward where possible. Encouragingly, many elements of the Programme are likely to appear in the new National Development Plan (NDP), for the current presidential term (2018 – 2022).

Monitoring and Evaluation
The Colombia PF Programme Business Case included an overall Theory of Change (ToC), indicative logframe and risk matrix. With support from the Monitoring, Reporting, Evaluation and Learning (MREL) team first visit to Colombia on February 2018, the PF Team and implementing partners CAF and Findeter finalise nested ToCs, logframes and risk matrices for six of the seven activities. The MREL team later worked separately with Innovate UK in London to do the same for the Agri-Tech Catalyst activity. As a result, all of the seven activities have nested TOC, logframes and risk matrices that are being updated quarterly and submitted to the PF team as an annex to the quarterly report.

The MREL team delivered a second visit to Colombia on the middle of August to draft the umbrella logframe. The umbrella logframe will now need to be agreed and finalise with our implementing partners CAF, Findeter and IUK. The visit also helped the MREL team to scope Colombia’s Year 1 evaluation at thematic and programme level and explore potential learning benefits. Since then, BE Bogota and the MREL Team agreed to apply seven Key Performance Indicators (KPIs) also being measured in the wider global PF portfolio. These cover: infrastructure, transport, jobs, foreign direct investment (inwards and outwards), export opportunities and export wins that drive inclusive economic growth in Colombia. Finally, a draft Evaluation and Learning Approach Paper was submitted to BE Bogota on 8 November.

For the purposes of this first AR, progress against the processes leading to the achievement of the main output from each the seven nested logframes is being measured. The impact weighting is based on the value of the activity in the total Programme budget and the risk rating is the average taken from the nested risk matrices for each activity.

Programme Governance Structures
In addition to the weekly PF Team meetings and monthly meetings with the Ambassador (as Senior Responsible Officer), the Colombia PF Programme has three main governance structures that between them measure progress against primary and secondary objectives, review spend, evaluate risk and recommend improvements. These are the Internal Programme Review Group (IPRG), the Private Sector Advisory Panel (PSAP) and the Stakeholder Group (SG) all of which meet every six months. The IPRG is composed of representatives from the UK’s Joints Funds Unit (JFU) and the Prosperity Fund Delivery Unit (PFDU) of the Foreign and Commonwealth Office (FCO). The PSAG is made of businesses from the PF Commercial Framework with presence in Colombia. The SG comprises the three implementing agencies (Findeter, CAF and Innovate UK) and representatives of the Colombian government at the central, departmental and municipal levels. In addition, the Colombia PF Team meets every six months with its counterparts in Brazil, Mexico and London at the Americas PF Regional Conference to harmonise polies and practices at the regional level and to share lessons learned.

Joint Working
The Colombia PF Programme coordinates closely with other UK government funds operating in Colombia such as the PF Global Infrastructure Programme (GIP), the PF Global Trade Programme (GTP), the PF Global Anti-Corruption Programme; the International Climate Fund (ICF) especially on the Sustainable Infrastructure Programme (SIP), the Conflict, Stability and Security Fund (CSSF), the Newton-Caldas Fund for research and innovation and the UK’s Chevening Scholarship Programme. In addition to bi-monthly meetings that include DIT, we recently commenced weekly coordination meetings to enhance collective progress and impact on the UK’s development objectives for Colombia. We are just about to enter into a phase of deeper joint policy and programming work under the UK’s Economic Horizons (EcHo) Programme.

Link to Business Case:	https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/687047/Colombia_BC_WEBREADY.pdf
Link to Log frame:

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment (Primary Purpose)
No primary benefits are expected during the first year of the Programme. However, the basis for securing poverty reduction and gender equality objectives in subsequent years is being laid down now. All projects and activities have clear primary benefit targets. The BE Bogota has invested significantly in communicating these goals and in building up stakeholder capacity to understand and support them.

Annual outcome assessment (Secondary Purpose)

No secondary benefits are expected during the first year of the Programme. However, the Programme team is building the capacity of BE Bogota laying the foundations for securing commercial benefits in Colombia for international business, including UK companies. This includes a comprehensive and proactive secondary benefits plan, the recruitment of a Commercial (Secondary Benefits) Adviser (Non-ODA funded), and regular engagement with PF Commercial Framework businesses.

Overall output score and description

A is the overall output score for the Colombia PF Programme given that four of the seven activities scored A or A+ and that they accounted for 84% of the impact weighting.

Key lessons

PF primary and secondary objectives require substantial socialisation with implementing partners. Findeter, CAF and Innovate UK all required support to understand the poverty, gender and inclusion focus of the Programme. To maximise Programme impact, this support must continue and spread to our wider stakeholders in government and the private sector in Colombia. Similarly, Findeter and CAF needed time and training to understand how the PF Commercial Framework operated and how their procurement procedures could be optimised to attract the widest number of Framework bidders. These investments are important as they can influence whole organisations as was the case with Findeter on gender and inclusion.

The regional competitiveness and urban development design projects are costing about double what was originally budgeted. This is mainly because the average cost of a competiveness project (£150,000) and an urban one (£280,000) was calculated in 2016 from a range of possibilities that included low and high value initiatives. As the Prosperity Team began to engage with cities and regions on their priorities in early 2018, it became clear that higher costing projects were a closer fit with PF primary and secondary benefit objectives. For example, a training centre might cost £150,000 to design and 10,000 beneficiaries over 10 years. A sanitation project, on the other hand, may cost £500,000, but it would reach 500,000 beneficiaries in as early as 3 years thereby offering better value for money (VfM). Another consideration was that fact that commercial companies were less interested in small, fragmented projects preferring larger, technically sophisticated projects that genuinely demonstrated the UK’s added value. With only 11 PF Commercial Framework companies present in Colombia, multiple small projects would run the risk of receiving no bids. In addition, UK visibility and leverage would not be the same with small projects. Finally, the projects selected so far, prioritised by the cities and departments themselves, mostly have prefeasibility studies in place and earmarked resources for their execution. This means the projects are more likely to go ahead and, therefore, that primary and secondary benefits more likely to be secured.

Other reasons that affected project costs include: i) the original Business Case assumed costs based on local Colombian Commercial Framework companies, however, PF Commercial Framework companies will be used (they are more expensive than local Colombian ones, but then they do a better job and poor quality project design is a serious problem in the country); ii) additional PF requirements such as gender and inclusion analyses and action plans and the preparation of inclusive project execution ToRs push costs up (and were not included in original Business Case costs); and iii) implementing partners omitted to include in their budgets an additional 20% on average for project quality assurance costs. As the Annual Review recommendations make clear, the overall number of regional competitiveness and urban development projects proposed in the Colombia PF Programme Business Case and indicative logframe was overly ambitious. Combined with the higher costs, there will be a significant reduction in total projects numbers following the Programme logframe review in early 2019. Estimated benefits associated with these activities will depend on two key factors: i) size of project (capital supported by intervention); and ii2) likelihood of project success.

BE Bogota outreach to the new Colombian government, which came into office in August of this year, has been highly successful at securing commitment to PF objectives and activities. New ministers and directors have been keen for the Programme to advance rapidly and contribute to the country’s economic development. While the BE Bogota has been keen to respond positively, our implementing partners do not have the staffing resources and administrative flexibility to do so. The BE Bogota will work with Findeter and CAF over the next quarter to identify how the Programme can respond more nimbly to government priorities. It is also worth mentioning that the UK’s early engagement with the new administration has resulted in important references in the next National Development Plan. For example, a portion of the Plan’s rail section is the direct result of findings from the recent PF-financed rail conference and rail regulation workshop and the Political Economic Analysis (PEA) of the sector that BE Bogota commissioned.

The commitment of the new Colombian administration to the country’s economic development including through infrastructure, transport and agriculture is clear. However, available financial resources to fund these sectors is limited as is Colombia’s experience with innovative project finance. As demonstrated through large projects like Crossrail, UK financial expertise on transport infrastructure is knowledge that needs to be shared with Colombia. Similarly, the catalytic role of UK Export Finance (UKEF) and that of British investment groups like John Laing, Aberdeen Standard and Ashmore Group operating in Colombia requires further dissemination. The PF Programme should prioritise this learning and relationship building with the new government.

One of the greatest barriers to international and UK companies doing business in Colombia is the inaccurate perception of risk. The PF Programme initiatives, including the Agri-Tech Catalyst mission to Colombia and the challenge fund were both heavily over-subscribed demonstrating that, with the right incentives, businesses will respond with enthusiasm to new market opportunities. A serious risk is that the Department for International Trade (DIT) is not adequately resourced to maximise the commercial opportunities generated by the PF in Colombia. This has been partly rectified with the recruitment through Non-ODA resources of a PF Commercial Adviser in September. Non-ODA resources have been allocated to support and strengthen commercial opportunities link to activities from the PF Colombia Programme. In addition, a new DIT and Prosperity Fund virtual working group has been set up for the Latin America region to coordinate on secondary benefits and new staff have been recruited into the International Directorate of DIT in London to support PF export wins worldwide.

Though not planned for, a de facto inception phase occurred as time was needed to deal with unforeseen challenges right at the start of Programme implementation. An inception phase is good practice for programmes of this nature and, on reflection, should have been included in the design of the Colombia Programme. Inevitably, despite the best planning and preparations, difficulties arise as soon as implementation starts. To provide a cushion between delivery of agreed outputs and such challenges, building a 3 to 6 month inception phase into the Programme is advisable and helps manage results expectations.

Colombia has good standing in international gender rankings because of its good policies and strategies. However, the country does not actively implement them. Neither does Colombia have adequate capacity to implement its own policies or international best practices. BE Bogota has not been able to find qualified gender or social development experts in country to support the Programme. We will need to continue to import UK social development expertise as there is a very high demand for it.

Key actions
 See list of recommendations above.
Summary of changes to the logframe since the last Annual Review

This is the first Annual Review.

## C: DETAILED OUTPUT SCORING

Output Title	Regional Competitiveness / Up to 3 inclusive projects (from the departmental competitiveness plans) designed, structured and ready for investment
Output number per LF		1	Output Score	A - outputs met expectation
Border Risk:		Moderate	Impact weighting (%):	18%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of inclusive projects prioritised by Regional Competitiveness Commissions	Up to 8 gender inclusive projects prioritised (2018/2019)	Three departments (Caldas, Magdalena and Valle) prioritised and piloted during the third quarter of 2018/19. Two more departments (Santander and Atlantico) voluntarily brought forward their first projects to third quarter of 2018/19. The remaining three will be completed by early 2019.
Number of inclusive projects designed and structured	Up to 8 gender inclusive projects designed and structured (2019/2020)	The first five projects will be designed in the fourth quarter of 2018/19 and the remainder at the start of the next financial year (FY).
Number of inclusive projects taken to market	Up to 8 gender inclusive projects taken to market (2019/2020)	Following design of the projects in 2019, the departments have agreed in principle to put them out to market in 2020.

Background
This activity seeks to strengthen economic development in up to eight of Colombia’s departments by improving their competitiveness. The activity has two main parts. The first is building the capacity of the Regional Competitiveness Commissions (RCCs) comprising a broad range of public, private and civil society stakeholders in up to eight departments. While receiving training, the RCCs would update their Competitiveness Plans and prioritise up to three projects for the PF to support. The implementation of this part of the activity is subcontracted to CONFECAMERAS – Colombia’s National Federation of Chambers of Commerce. The second part of the activity is the design and structuring (technical, legal and financial) of up to three competiveness projects per department. These contracts will be made available to companies on the PF Commercial Framework. The types of projects that fit in the competitiveness category include infrastructure, transport, agro-industry, tourism, creative industries and support to small and medium sized enterprises (SMEs). The targeted beneficiaries include vulnerable populations, women and girls, and micro and small enterprises. Given the delay in the CONFECAMERAS contract, CAF and the BE Bogota agreed in June to bring forward three projects (one each in Caldas, Magdalena, and Valle del Cauca) that would act as pilots learning experiences for the RCCs in those departments and the wider activity.

Key Points

In addition to the MoU amendment and the Colombian national elections, a third issue affected progress on this activity. Initially, CAF planned to have a Technical Cooperation Agreement (TCA) with CONFECAMARAS for the capacity building work. CAF submitted a draft TCA to the BE Bogota for approval in May. However, a TCA would have permitted CONFECAMARAS to sub-contract using PF resources, which is not possible. In June, CAF began a process to contract CONFECAMARAS instead. The text of the contract was finalised and approved by the BE Bogota on 12 October 2018. As of the AR Mission, CAF’s legal team were reviewing it. When signed, the contract will allow CONFECAMARAS to commence its capacity building activities during the third quarter. CAF will also prepare a second contract using the PF Commercial Framework to provide additional technical support to the regions (on gender and inclusion for example) that will complement the main contract with CONFECAMARAS.

As described in the Business Case, about 80% of the activities are to build the capacity of the Regional Competitiveness Commissions which comprise officials from the department, private sector, civil society and academia. However, about 80% of the budget for this activity is to cover the costs of the competiveness projects in each department. For this reason, the AR is measuring progress against the first pilot projects in Caldas, Magdalena and Valle and the two additional ones (Santander and Atlantico) that were brought forward. As a result, the score for this activity made it into the A category.

More generally, there is a concern with CAF’s internal approval procedures and its commitment to adhere to timeframes. CAF adhere to rigorous and a high level of professional standards. But the time taken to achieve the agreed objectives seems to conflict with the Programme’s ambitious timetable. A clearer sense needs to be developed jointly between CAF and the Programme team about the trade-offs by following the current approval procedures and the consequences of any further delays to ensure that the benefits outlined in the Programme’s business case are delivered in a timely fashion.

Summary of responses to issues raised in previous annual reviews (where relevant)
This is the first Annual Review
Recommendations
1. BE Bogota to work closely with CAF to finalise contract with CONFECAMERAS, prepare the second technical assistance ToRs for PF Commercial Framework companies and launch the first projects in Magdalena, Caldas and Valle.
2. BE Bogota should monitor spend on this activity more proactively. If it is affected by further delays, work with CAF to identify and implement remedial actions.
3. Explore how the recent MoU between CAF and UK Export Finance can support the delivery of selected Regional Competitiveness projects.
4. As in the Urban Development activity, the original number of projects (three per department and 24 in total) now seems too ambitious. CAF and the BE Bogota should conduct the first three pilots and then revise the target. The reduction in the Urban Development activity from six to four cities was beneficial to the Programme as it focused efforts. The Regional Competitiveness activity should consider if reducing down from eight departments could help focus efforts and improve impact, and ensure the activity remains within budget.
5. Same as the Agri-insurance activity, BE Bogota to spend more time understanding CAF internal approval procedures and to agree with CAF how these add value, and ensure the achievement of targets by agreed milestones. At the same time, CAF should look at what it could do to reduce the time between committee meetings.
6. As the Programme becomes more established, BE Bogota should explore opportunities for further joined up programming between the Conflict, Stability and Security Fund and the Prosperity Fund in post-conflict areas, based on the regional development plans (PDTs in Spanish) of the selected departments.
DETAILED OUTPUT SCORING

Output Title	Open Procurement / Target regional institutions have increased capacity to execute competitive procurement according to international open procurement standards (IOPS)
Output number per LF		2	Output Score	B – outputs moderately did not meet expectations
Risk:		Moderate	Impact weighting (%):	3%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of officials trained	20 per department	Training of officials in first two pilot departments (Caldas and Valle) began in November 2018.
Number of target departments whose officials have received training	2 pilots and then 6 more	In early 2019, training will be replicated in up to six more departments.
Number of officials conducting project procurement according to International Open Procurement Standards (IOPS)	40 by end of project	Measurement of this indicator will commence in mid-2019.
Percentage of IOPS implemented by Departments	To be decided	Measurement of this indicator will commence in late 2019.

Background
This activity will roll out the international open procurement standards (IOPS) from central government to up to eight departments in Colombia. Open Contracting Partnership (OCP), who supported the central government changes via Colombia Compra Eficiente (CCE), Colombia’s National Procurement Agency, will manage the main capacity building activities starting with Caldas and Valle del Cauca departments in the third quarter. Findeter, who has oversight of the activity, will consider how to complement OCP’s work engaging both with CCE and civil society in the selected departments. As more departmental resources are protected through transparency, there will be more beneficiaries of state resources such as vulnerable populations and women and girls. More international businesses will benefit from open tendering procedures that allow them to compete fairly.

Key Points

When designed, this activity was going to be managed and implemented by Findeter in conjunction with external contractors. Subsequently, OCP was identified as the best possible provider given their track record of helping reform and introduce the IOPS to CCE. However, Findeter did not have a mechanism to fund OCP as it is a not-for-profit organisation, located in Washington, DC that only accepts resources in US dollars. Therefore, the BE Bogota agreed to procure OCP’s services through a grant agreement. Developing the proposal and grant agreement while conducting due diligence on OCP was completed in September. OCP are now recruiting a national coordinator to manage the capacity building activities in the first two departments.
CCE were originally going to help design the implementation of this activity in April and May. The new arrangements with OCP put that process on hold. Findeter and the PF Governance Adviser will work with CCE to address their integration into the activity. Over the life of the activity, there will be opportunities to integrate further best practice in procurement into regional and local governments (e.g. governors and mayors, respectively), which depend in part on CCE and Findeter. There will be cost implications, as CCE is responsible for operating and maintaining the on-line Public Contracting System (SECOP II) and for training all public officers in the country. In addition, OCP considers it best practice to ensure active civil society engagement in public procurement. It recommends a second complementary activity that would support a group such as Transparency for Colombia to monitor the implementation of the PF Programme activity in selected departments.

Summary of responses to issues raised in previous annual reviews (where relevant)
This is the first Annual Review
Recommendations
1. BE Bogota to work closely with Findeter, OCP and CCE to design the first complementary strand to the activity that allow CCE to ensure full adherence of SECOP II in the PF selected departments.
2. BE Bogota to design second complementary strand with Findeter and OCP that would allow civil society to better engage with and monitor implementation of SECOP II in the selected departments.
3. Revise open procurement and all nested logframe indicators to ensure they are SMART and gender and inclusion priorities are fully integrated.

## DETAILED OUTPUT SCORING

Output Title	Corporate Governance Reform of ANI / Application by ANI of independent transparent, collective decision-making processes and structures, including gender considerations
Output number per LF		3	Output Score	U – unscored as activity only just started
Risk:		Moderate	Impact weighting (%):	1%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of board meetings with women and men participating	Diagnostics of the current situation of ANI’s corporate governance and recommendations (2019)	The winning contractor for this work will measure the current level of women and men participating in meetings of senior ANI staff, recommend in the new corporate governance model how to have a balanced gender representation and then monitor ANI’s progress over the following two years of implementation.
Number of men and women responsible for making decisions	2 workshops with relevant stakeholders on view of the improvements of ANI’s Corporate Governance (2019/2020)	One workshop each in 2019 and 2020 managed by the contractor.
Number of male and female ANI staff trained in the new Corporate Governance Model	Training workshops held for ANI staff (2019/2020)	Several training workshops managed by the contractor in 2019 and 2020.
Number of minutes of the board meetings published externally	Diagnostics of the current situation of ANI’s corporate governance and recommendations (2019)	Same as first box above.

Background
The Head of Colombia’s National Infrastructure Agency (ANI) is solely responsible for taking all investment decisions worth billions of dollars annually. This activity will review best practice in the UK and other countries to design a new corporate governance model for ANI, pilot it over one year and conduct an evaluation afterwards. The design and implementation contract will be offered to companies in the PF Commercial Framework. Vulnerable populations and women and girls will benefit as state resources for infrastructure are spent as agreed in the budget and international companies will be able to compete in open, fair and transparent procurement processes.

Key Points
As explained in the Colombia Prosperity Fund Business Case (BC), this activity would only commence around September or October 2018 once the new Colombian government was in place. On 7 August, the new administration came into power. In September, the British Ambassador and BE Bogota colleagues met the new Head of the National Infrastructure Agency (ANI) who was enthusiastic about the activity and requested it be implemented as soon as possible. CAF is drafting an Agreement for ANI to sign. This will be followed up by Terms of Reference (ToRs) for a company from the PF Commercial Framework to design, test and monitor a new corporate governance model for the Agency.

Summary of responses to issues raised in previous annual reviews (where relevant)
This is the first Annual Review
Recommendations
BE Bogota to work closely with CAF to ensure ToRs for ANI corporate governance reform go out to market as soon as possible.

## DETAILED OUTPUT SCORING

Output Title	Rail Development / Two most sustainable and profitable rail projects are taken to market
Output number per LF		4	Output Score	A – outputs met expectation
Risk:		Moderate	Impact weighting (%):	24%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of projects selected	At least 4 in Year 1	Four projects have been selected for feasibility or pre-feasibility studies: Bogota – Zipaquira; Tren Multiproposito de Antioquia; Regio Tram Cali; and Tren del Caribe
Number of projects taken to market	At least 2 in Years 2 and 3	ToRs for Bogota – Zipaquira being prepared and Cundinamarca Department is co-funding 15%; Antioquia ToRs scheduled to be prepared in early 2019

Background
Working with the Ministry of Transport, the National Infrastructure Agency (ANI) and the National Planning Department (DNP), this activity aims to catalyse rehabilitation of Colombia’s 3,500 km of existing narrow gauge railways. The Inter-American Development Bank (IADB) has agreed to complete Colombia’s National Rail Master Plan leaving the PF Programme to focus on developing the country’s rail regulatory framework and completing up to four feasibility studies with at least two of them going to market. Vulnerable populations and women and girls will benefit from improved transport links to go to work or school and to export their agricultural produce. Companies will benefit from managing the construction, operation and maintenance contracts, possibly via PPPs, of the rehabilitated railways.

Key Points

Colombia’s new National Development Plan (p 479) says: ‘The Government will prioritise its policy for the reactivation and promotion of rail transport, as part of the development of a national, intermodal system, via the formulation and implementation of the Rail Master Plan, generating conditions that allow the railway to exploit its competitive advantage and promote its integration in the logistics and multi-model transport chains.’

The broader framework for rail in Colombia has improved under the new administration. The new government has established a rail working group comprising Ministry of Transport, ANI, DNP, IADB, Findeter and the BE Bogota. With non-ODA resources, the BE Bogota has already provided a 2 day strategic rail conference and a 2 day rail regulation workshop. Further requests for UK support are likely especially on regulation and on project finance.

This is a key moment in time for Colombia on railways. With strong export growth, insufficient roads and climate change commitments, the potential to revive the rail sector is immense. However, the road lobby is strong and budgets are limited. Now is the time, working closely with other partners, to influence the Colombian government to take a long term strategic decision to invest in the national rail network and integrate it into a genuinely intermodal transport system that benefits the whole country.

The rail feasibility studies will be awarded to companies on the PF Commercial Framework.
Summary of responses to issues raised in previous annual reviews (where relevant)
This is the first Annual Review
Recommendations
1. Employ BE Bogota bilateral relations and the rail working group to continue to influence the new Colombian administration on the value and potential of rail and to offer on-going strategic support including on transport project finance in tandem with the rail rehabilitation work.
2. The logframes for rail and urban development need to be revised to better reflect the wider efforts of BE Bogota in building capacity and ensuring projects are ODA compliant, deliverable and will have impact. This includes capturing better the full range of progress and benefits by breaking down the indicators and including, for instance, activities like the development / issuance of ToRs.

## DETAILED OUTPUT SCORING

Output Title	Urban Development / Up to 3 inclusive projects per city designed and structured, with detailed specifications, ready for investment
Output number per LF		5	Output Score	A – outputs met expectation
Risk:		Moderate	Impact weighting (%):	29%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of inclusive projects identified with ToRs prepared	Up to 24; 8 of these by early 2019 and the balance by late 2020	The first five projects have been identified and the ToRs completed (three sanitation projects in Ibague, Santa Marta and Valledupar; one intelligent transport project in Manizales and one SMART city project in the historic centre of Santa Marta). Before the end of the third quarter of 2018/19, Findeter will prepare a list of financially viable projects that will be prioritised in 2019. The PF will select three of these in early 2019 bringing to eight the number of projects supported. The logframe will be revised in early 2019 meaning that total expected projects will be reduced to up to 12. This change reflects the higher than expected costs and the learning around the potential benefit of targeting fewer larger projects.
Number of inclusive projects designed and structured	Up to 24; 8 of these by mid-2019 and the balance by mid-2021	All projects identified should go out to tender for design and structuring. Five are going out now in the third quarter of 2018/19; three more in the final quarter; and the rest in 2020/2021. As noted above, the logframe will be updated in early 2019 to reduce total projects to up to 12.

Background
Colombia’s largest four cities, Bogota, Medellin, Barranquilla and Cali, have traditionally received the lion’s share of the country’s infrastructure resources and development. However, that is changing. Colombia has a large number of intermediate or second tier cities with between 100,000 and 1 million inhabitants that are experiencing strong post-conflict growth and creating substantial investment opportunities. This activity will build government capacity to implement urban master plans in up to ten cities while delivering up to three urban development projects in each of them. Primary benefits include providing transport and social services such as water and sanitation to vulnerable populations and women and girls. Secondary benefits will be available to companies that win bids to construct or execute the projects designed by the PF.

Key Points
Having selected the first six cities to work in, this activity got off to a head start when the BE Bogota conducted PF and GREAT Commercial Opportunities Road Shows at the beginning of 2018. The first projects meeting primary and secondary objectives for four of the cities were identified quickly. However, the change in the MoU and the national elections brought delays to the activity. An Early Market Engagement Event in July identified a list of requirements that PF Commercial Framework companies would find hard to comply with. This began a two-month consultation process to resolve each of these requirements one by one.

Another important point surfaced while designing the technical notes (fichas) of each project – the price. On average, the design of each project was double that initially described by Findeter in the MoU i.e. about £500,000 instead of £280,000. Findeter provided a written response explaining why the costs had increased: i) more complex types of project; ii) higher cost for international consultants; iii) addition of gender and inclusion analyses as a separate output; and iv) the addition of project execution ToRs as another separate deliverable. In discussions with London, it was agreed that quality was more important than quantity and that the cost benefit analysis calculations would not be updated at this stage given the uncertainty regarding the pipeline.

A further challenge then appeared. Findeter had not included the cost of quality assurance (known as interventoria in Spanish) in the MoU. At first, this was going to be around an additional 10% of the project cost, but in September the figure turned out to be 22%. Again, this was due to the more complex urban development projects that the PF Programme was supporting. Given the new higher costs for each project, a total of 24 initiatives is no longer feasible (the updated target will be up to 12). It is uncertain what impact this will have on the estimated primary / secondary benefits of the activity, and evidence suggests that fewer, but larger, projects have the potential to achieve more than higher numbers of smaller projects. This will need to be monitored closely to ensure ongoing VfM of the final pipeline of projects.

Two of the original six cities selected for this activity – Cartagena and Villavicencio – have dropped out this year due to electoral or financial irregularities. It is intended that they be brought back into the Programme, together with other new cities, after the local elections in October 2019. The new administration will take office in January 2020.
Both the project design contracts and the quality assurance ones (interventorias) will be offered to companies on the PF Commercial Framework.

Findeter has been very receptive to the institutional changes that the Colombia PF Programme has requested. In addition to the procurement amendments described above, Findeter has made significant strides forward in gender and inclusion and in monitoring and evaluation (MREL). On the former, Findeter contracted a full time gender expert who also helps other teams in the bank. This gender mainstreaming, introduced by the PF, helped Findeter become a Green Climate Fund recipient. On the latter, Findeter has requested support to mainstream many of the PF MREL approaches to other parts of the bank. The BE Bogota is currently considering how to do this.

Based on the number of lessons learned between the BE Bogota and Findeter, the AR Mission team believe an A score is justified for this activity.

Summary of responses to issues raised in previous annual reviews (where relevant)
This is the first Annual Review
Recommendations
1. Revise down the next version of the nested and umbrella logframes to say up to 12 urban development projects reflecting the higher cost of each initiative. Re-focus the logframe indicators to account for the quality of the projects selected and how they can be replicated in other cities.
2. Use the many lessons learned from the first five urban development projects to improve the processes around the rail and regional competiveness activities as well as the remaining (up to) seven urban development projects.
## DETAILED OUTPUT SCORING

Output Title	Agri-Insurance / Agriculture Risk Management Information System implemented to better manage risks considering the male and female smallholder needs
Output number per LF		6	Output Score	B – outputs moderately did not meet expectation
Risk:		Moderate	Impact weighting (%):	12%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of public entities participating in the SIGRA information system	10 public entities participating in the SIGRA information system (2018/2019)	The tender for the first stage of SIGRA system is expected to go out to tender during the first quarter 2019. It will be 2019 before any public entities are able to participate.
Number of variables considered in the GeoAGRO system	1 public entity participating in the GeoAGRO system (2019/2020)	The tender for the GeoAGRO system is expected to go out to tender this quarter. It will be 2019 before any public entities are able to participate.
Number of variables that can be cross-referenced to gender (land ownership; crops; etc.)	4 public entities participating in the information system through the develop of risk maps (2019/2020)	Too early to comment on progress as this activity starts in 2019/20.

Background
This activity has four parts:
1. information technology (IT) systems that, among other things, allow for accurate risk assessment of different agricultural activities in diverse geographies across Colombia; these systems are known as SIGRA, GeoAGRO and risk mapping;
2. an education campaign to raise awareness and technical knowledge of agri insurance among public officials, the private sector, academia and agricultural communities;
3. linking Colombia’s meteorological data to the new agri insurance IT systems; and
4. three pilots to test the impact of new agri insurance products and services especially for female smallholders.
Smallholder farmers and micro and small enterprises will benefit from protection against crop and livestock failures while companies will benefit from commercial opportunities to provide agri-insurance products and services, including re-insurance, to previously untapped markets.

Key Points

Colombia’s new National Development Plan (p 323) says Colombia will: ‘Promote productive transformation, agricultural and agro-industrial competitiveness and rural development, creating conditions that stimulate the provision of goods and services, private investment, innovation and entrepreneurship to generate opportunities for growth and well-being of the entire rural population.’ More specifically, there is a reference (p 238) to agri-insurance that Colombia will: ‘Implement strategies to guide the sustainable development of the agricultural sector, including implementation of the Risk Information System for the Agricultural Sector (SIGRA), and the implementation of risks management schemes and instruments.’

A slow initial contract (not PF) to help design the basics of an Risk Information System for the Agriculture Sector (SIGRA) has held this activity back from making progress. During the AR Mission, CAF clarified that it intended to divide the development of SIGRA in to two phases. The first one, to prepare the ToRs for the design of SIGRA, will go out to companies on the PF Commercial Framework during the first quarter of 2019. In the second quarter of 2019, the second ToRs to design SIGRA would then go out to tender. In addition, the overall cost has increased. The final price may be significantly more than the original £1.2m estimate. If this is proven through market testing, to remain within budget, either this activity would need to cut back its ambition by e.g. reducing the PF-funded parts from four to two, or seek out other co-financing options.

On part (i), CAF is preparing the GeoAGRO IT system ToRs and these should be ready for PF Commercial Framework companies in the next two months. The original partner for CAF to work on the risks maps, AGROSAVIA, recently demanded a confidentiality agreement and intellectual rights on the final product. As this is not possible, CAF had to work with the ministry of Agriculture to identify a new partner. That group is UPRA and, if confirmed, the tender for this work should go out to market in 2019.

CAF is developing the other parts of this activity. On part (iii), connecting to the Colombian meteorological system, IDEAM will be the main beneficiary and it plans to submit a proposal. However, based on initial forecasts, this work will cost 50% more than originally planned as the scope of the work has also increased by 50%. Given the large increase in the cost of SIGRA, it is not clear if there will be sufficient PF resources to go ahead with the IDEAM support.

All agri insurance contracts will be made available to companies in the PF Commercial Framework.

As with the CAF Regional Competitiveness activity, internal approval process may be partly responsible for delays in this activity. For example, there are monthly gaps between important committee meetings.

Summary of responses to issues raised in previous annual reviews (where relevant)
This is the first Annual Review
Recommendations
1. BE Bogota and CAF to monitor closely progress and spend on this activity. If it is affected by further delays, the BE Bogota should work with CAF to identify and implement remedial actions.
2. If the SIGRA cost does double, BE Bogota should work with CAF to cut back on one or two of the other parts of this activity, based on agreed criteria of maintaining the aspects most critical to achieving impact and proving the commercial viability of the project.
3. Similar to the CAF Regional Competitiveness activity, BE Bogota to spend more time understanding CAF internal approval procedures and to agree with CAF how these add value, and ensure the achievement of targets by agreed milestones. At the same time, CAF should look at what it could do to reduce the time between committee meetings.

## DETAILED OUTPUT SCORING

Output Title	Agri Tech Catalyst Challenge Fund / Commercial potential of early stage innovations tested in Colombia; results captured through feasibility studies that include impact on female smallholders
Output number per LF		7	Output Score	A+ - outputs moderately exceeded expectation
Risk:		Moderate	Impact weighting (%):	13%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of eligible funding applications received	25 by second quarter 2018/19	50 applications received of which 37 were eligible
Number of proposals above quality threshold as scored by Innovate UK (>70%)	15 by second quarter 2018/19	20 applications scored above 70%
Number of partnerships funded	Up to 10 by final quarter 2018/19 depending on the cost of the initiatives selected as a maximum of £2.6mn is available	8 partnerships worth £2.64mn to be funded

Background
This activity creates partnerships to support technology transfer in agriculture from the UK to Colombia. It specifically targets innovation and new technologies to help improve the quality and production of female smallholders and micro and small enterprises allowing them to increase their income. The challenge fund mechanism permits a wide range of private sector, academic and civil society organisations to compete for PF resources. Projects last for 18 months and will start in January 2019. Those that successfully demonstrate their value have the potential to develop a market in Colombia and produce export wins.

Key Points

This activity has made the most progress. It began with publication of the challenge fund in March, successful campaign events to raise awareness, a heavily over-subscribed mission to Colombia in June, over 400 registrations of interest on the website, submission of 50 proposals of which 16 of these met all the requirements. Initially, targeting both early and late stage projects, as in respectively further and closer to wider deployment of the technology. In total, eight bids (all early stage) were successful in bringing UK innovations to crops such as cocoa, coffee, bananas, tilapia and vegetables. There is now a three-month verification procedure which includes due diligence (DD) of all UK and Colombian partners. There will also be a consultative process to improve the gender and inclusion focus and impact of each initiative.

The organisations winning the PF support have the opportunity to demonstrate how their innovations and new technologies can improve quality and production for smallholder farmers leading to higher incomes for rural communities. At the same time, the organisations partnering in these projects improve their chances of commercial success in Colombia.

Summary of responses to issues raised in previous annual reviews (where relevant)
This is the first Annual Review
Recommendations
1. Ongoing testing and education of the beneficiaries is needed to ensure they can and are willing to use the technologies.
2. If resources are secured for a second round of the challenge fund, there is a need to ensure that all the lessons learned from the first one are incorporated especially around gender and inclusion, conflict zones and sustainable crops, and if possible should focus on late stage projects.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
The first quarterly payment to partners made in March 2018 totalled £1.723m. The second quarter was £2.66mn. To date spend for 2018/19 is £4.38mn (47%) against a forecast of £9.1m. Payments for the third quarter are set to be £4.82m. Overall, the Colombia PF Programme is on target financially.

The main cost driver is the advisory services delivering technical assistance and capacity building activities, either via the implementing partners, or directly through the Programme’s advisers. These costs are managed in three ways: (i) an assessment of Value for Money (VfM) during the initial selection of a delivery partner; (ii) where relevant, implementing partners run competitive tenders through the PF Commercial Framework companies, assessing costs against benchmarks and reducing these where possible; and (iii) contracts and MoUs based on milestone payments contingent on delivery of outputs to ensure services are delivering the expected results.

BE Bogota programme management costs for delivering the Programme are 3.4% of the total budget which is reasonable to effectively manage MoUs and deliver primary and secondary benefits. This percentage includes BE Bogota staff costs (seven of eight staff members are local hires), travel costs associated with Programme implementation and monitoring, and PF-hosted meetings and events.

The key performance challenge for the Programme is the significant increase in scale in programming for BE Bogota. Clear governance and coordination structures are needed, which broadly appear in place. The risk is that, without these, the Programme would under-spend as interventions take longer to reach implementation than planned. This has occurred, partly as implementing partners and BE Bogota establish effective ways of working, but also due to expected (elections) and unexpected (contracting complications) events. On the flip-side, some of the activities could potentially over-programme leading to overspend. Some activities have excelled (Agri Tech Catalyst), others have suffered from delays (Agri-insurance) and complications (Regional Competitiveness).

If an overspend is likely to occur, BE Bogota should explore trimming back on the activities experiencing the most challenges and concentrate on those interventions that have made the most progress towards poverty reduction and gender equality through economic development, as well as new market opportunities (e.g. Agri Tech Catalyst). These risks have so far been managed with an effective Programme Team, combined with regular oversight by the Ambassador as SRO. However, ongoing attention is needed to ensure the Programme’s milestones can be achieved and avoiding any further delays, while maintaining the highest possible standards of governance and transparency. This can be achieved by working closely with implementers and developing trusted relationships with them. The Programme Team should continue to regularly review budget forecasts to maintain Programme momentum and address challenges in real time in consultation with implementing partners.

Changes in Staffing

BE Bogota recruited three new advisers (C4L) for governance, infrastructure and agriculture in February 2018. With non-ODA resources, BE Bogota recruited a Commercial Adviser (C4L) in September 2018 to help lead on securing secondary benefits with oversight of the non-ODA budget. In October, a part time Policy Adviser (C4L) joined the team to help make important links between the Programme and Colombian government policy reforms to improve the business environment, open up trade, reduce corruption and to better integrate gender and inclusion into public sector investments.

BE Bogota also contracted local supplier ARKO Consults for an initial six months to provide gender and inclusion expertise to the Programme on a draw down basis.

VfM performance compared to the original VfM proposition in the Business Case

The Programme started implementation on 1 April 2018. The Programme is still in the early stages with varying levels of progress across the seven activities.

Economy

In October 2016, during the Colombia PF Programme Business Case design phase, BE Bogota received over 100 Expressions of Interest from providers wishing to manage PF activities and resources. From this exercise, BE Bogota received 30 more detailed proposals from potential implementation partners. These proposals were evaluated based on: track record and proven ability to deliver high quality activities, outputs and outcomes; existing relationships with local governments, and Value for Money (VfM). Development banks and UK government institutions have lower management costs than the private sector. These are 10%, 3% and 0% respectively for CAF, Findeter and Innovate UK compared to private sector companies that began at around 15%. Innovate UK decided not to charge any overheads for the Agri Tech Catalyst activity as this was a pilot initiative for them. Findeter was also unusually low as they are only charging for additional staff and travel and not for existing staff who are working on the PF Programme. CAF, while the highest, are still much lower than private sector companies. They are charging for all staff working on the PF including, for example, a highly professional MREL team based in their office in Lima, Peru.

CAF is implementing its three Colombia PF Programme activities with partner institutions willing to co-fund the projects in cash or in kind thus reducing the burden on the Programme. In order to determine the best Value for Money for contracts, CAF and Findeter will consult partners and conduct market studies. The selection and recruitment of consultants will be in accordance with CAF’S procedures, but in accordance with FCO guidelines on price. As flagged in the Regional Competitiveness and Urban Development activities and the Key Lesson section, all PF projects must reduce poverty and gender inequality, contributing to the doubling in expected costs of projects (and consequently reducing the number of projects by half), for the VfM this has meant the Programme team has justified this additional expenditure was worthwhile to ensure the quality of projects with the highest impact.

CAF and Findeter select providers via a competitive process. Budgets for the PF projects go through a price benchmarking processes based on the bank’s experience in the relevant sector. Each step of the contracting process requires a “No Objection” from BE Bogota.

Innovate UK also selects winning bids through a competitive challenge fund process. For the Colombia Agri Tech Catalyst pilot, Innovate UK are not charging overheads to maximise funding for programme delivery. However, this would change if the activity were to have a second phase. In the Agri Tech Catalyst Challenge Fund, winning bidders co-finance their projects between 15 and 75% depending on the size and turnover of the organisation. Typical Return on Investment (ROI) for UK-based projects is £7.30 for every £1 invested, resulting in secondary benefits.

Efficiency

The Programme has experienced several delays in converting inputs into outputs, mainly due to the process of establishing the activities (a de facto inception phase) and now that these have been established should not recur and are not expected to have a material effect on the overall VfM over the Programme’s lifecycle. For instance, while there have been delays in the Regional Competitiveness Commissions (RCCs) prioritising projects, all five RCCs have since the AR mission proposed viable projects, which can be taken forward. Furthermore, although the local/regional elections planned for October 2019 create manageable risks for regional projects, the Presidential and legislative elections earlier in 2018 (and the follow-up work by the embassy in re-confirming support) have ensured the new central government’s interest and support in the PF programme.

The potential impact of the projects selected by the Regional Competitiveness and the Urban Development activities demonstrate how the Programme has met expectations, while the success of the Agri Tech activity in drumming up UK-Colombia partnerships exceeded expectations. However, the selected logframe indicators for some of the larger impact activities (Urban and Rail Development) currently do not reflect the full range of progress or potential results. The Annual Review team would recommend considering how the activities could be further broken down into the process required, which could be done without creating excessive monitoring requirements by, for instance, the rail development activity could focus on the process of developing and issuing of good quality ToRs, rather than just the “number of projects taken to market”. In addition, one of the obstacles the Programme has experienced is the need for specific meetings/events to take place, e.g. an implementing partner’s internal governance processes. Therefore, a potentially useful monitoring tool (rather than a logframe indicator) could be an indicator on the frequency of or time between these events/meetings by activity (while avoiding the pitfall of exclusively focusing on quantitative factors) to be able to monitor how quickly decisions are being turned around.

CAF and Findeter’s activities are designed to have long-term impact and sustainability by building capacity of partner institutions and beneficiaries. Both partners are meeting with relevant officials of the new Colombian government to let them know about their PF work, adapt the activities to the needs of the new administration and to ensure maximum public sector buy-in.

CAF and Findeter will both issue project design contracts accompanied by separate quality assurance contracts (known as interventorias in Spanish). The interventorias ensure resources in the main design contract are spent as agreed in the contract and that the quality of the outputs meet and / or exceed expectations. Moreover, technical teams of CAF and Findeter combined with the selected municipalities and regions will have a supervision role during Programme execution. Innovate UK has similarly robust quality assurance processes that combine Monitoring Officers (MOs), BE Bogota and CIAT. It is the job of each monitoring entity to understand each initiative, suggest how to maximise investments and measure if this is being achieved.

Effectiveness

Progress to date suggests potential for the Programme to still deliver against the business case’s original objectives despite the higher-than-anticipated costs in some outputs’ activities and the consequent shift towards fewer but larger scale projects. The eventual pipeline and the impact of changing the composition of the pipeline is uncertain and it is too early to fully assess effectiveness as actual results (outcomes) are not yet being reported. Several of the activities (Regional Competitiveness, ANI, Open Procurement and Agri Insurance) are still under-going the last few adjustments prior to full implementation. The higher cost of quality inputs will help ensure the outputs’ quality in reducing poverty and gender inequality. If the Programme team is able to utilise the higher quality inputs by working with the implementing partners to support projects that address common issues, while also engaging with potential beneficiaries’ and stakeholders on whether these projects could adapted to fit their context, additional value could be added. There is potential to realise the same level of estimated impact as set out in the original Business Case, but this needs to be monitored closely.

Over the past 9 months, the MREL Team has worked with the BE Bogota and the three main implementing partners CAF, Findeter and Innovate UK to develop and finalise nested ToCs, logframes and risk matrices for all seven activities. With the completion of the umbrella logframe (expected in January 2019), the Programme will be in a strong place to begin to measure success against agreed outcomes. Careful attention is needed on the poverty reduction aspects of the Programme, e.g. jobs indirectly created or cost-savings through improved transport/urban design, to avoid getting lost in the important technical improvements achieved by the activities.

Equity

Building implementing partners’ capacity on gender and inclusion (G&I) has been a core deliverable of the Programme so far, for which BE Bogota should be recognised. Integrating G&I in a systematic way into their programme management is improving the capacity of implementing partners beyond the Programme’s life. It will be important to assess progress in future evaluations ensuring that lessons learnt and successes are celebrated.

To ensure G&I was fully integrated into programme delivery, workshops for the implementation partners’ understanding and capacity were delivered. In addition, a G&I expert reviewed all the initial Programme documentation (Business Case, MoUs, and draft logframes), prepared a G&I Strategy and then later helped the partners create G&I Action Plans for the CAF and Findeter activities. Meanwhile, BE Bogota is supporting the eight Agri Tech Catalyst projects to design G&I Action Plans proportionate to the size and timeframe of each initiative.

All of this work strategically underpins the rest of the Programme. Each of the three main partners now have clear understandings of the G&I Framework and can fluently articulate the differences between minimum compliance / voice, empowerment / choice and transformation / control. This broadly has translated into a G&I mainstreaming from a focus to female smallholders in the Agri Tech activity to “inclusion” being a key criterion for project selection for Regional Competitiveness. While there is still room for improvements in achieving a level of specificity in logframe indicators for how the activities are affecting or will affect G&I, it is still early in the Programme’s lifecycle and there is scope to fine tune these measurements. The Programme Team can draw on the support of local and international G&I consultants to achieve this in the next few months.

In terms of procurement, all CAF and Findeter design projects must include a new deliverable which is a G&I analysis and action plan which covers stakeholder engagement. This is the first time either development bank have undertaken such a promise. Senior officials from the municipalities and regions will participate in the G&I analysis work to ensure that the follow-on project execution / construction adheres to the findings of the design work this embedding G&I best practice and priorities into Colombian government entities. Findeter have recruited a full time G&I expert who is also advising, for the first time, other non-PF policy and programme work of the bank. CAF has a G&I unit in Venezuela, but are looking to hire a specialist in Colombia as a result of the PF partnership. BE Bogota has a small additional budget (£160,000) to support G&I capacity building and will use these resources to further enhance the G&I competencies of implementing partners and government stakeholders.

Assessment of whether the Programme continues to represent value for money

The Programme is only six months into implementation, but has made strong progress to deliver the outputs identified in the Business Case across the three pillars over 2019-20: institutional strengthening (e.g. feasibility studies on projects improving regional competitiveness; 22% Programme impact weighting), infrastructure improvements (e.g. inclusive Urban development solutions and feasibility studies on sustainable rail projects; 54% Programme impact weighting) and Agriculture benefits (e.g. agri insurance and agri-tech; 25% Programme impact weighting).

The Programme has experienced a de facto inception phase, therefore expectations on short-term delivery timelines have needed to be adjusted. For instance, the ambition for the Urban Development and Rail Development activities were clearly set too high early on. And while there have been unexpected delays from contracting issues, key outputs (Regional Competitiveness and Urban Development) were meeting expectations on identifying potential projects and activity is expected to pick up over the next six months (e.g. all RCC prioritised projects have since been identified). Although the process of establishing an umbrella/programmatic logframe is still being finalised (due January 2019), it is important that BE Bogota builds on this to develop VfM indicators that can highlight how effectively the Programme is delivering all 4Es.

Quality of financial management

Implementing partners are paid on a quarterly basis based on an agreed activities and milestones. Implementing partners are responsible for providing quarterly impact and financial reporting. The quality of technical and financial reporting improved significantly between the first and second quarters as the three main partners responded to BE Bogota’s request for more comprehensive presentation of information. Partner’s financial management has also improved over the same period. As development banks, CAF and Findeter receive quarterly payments in advance while Innovate UK, CIAT and OCP, as not for profit organisations, are quarterly in arrears.

Date(s) of last narrative financial report(s)	Reports are due on a quarterly basis
Date(s) of last audited annual statement(s)	Due end of June 2019

E: RISK
Overall risk rating: Moderate
Overview of Programme risk in order of priority and likelihood
1- Change of government in 2018 (national elections) and 2019 (local elections) alters security situation and reduces support for implementation of programme. New leaders with new agendas may no longer be aligned with those of the PF Programme.

- Secure MOUs with key government and local partners covering long term delivery of the programme
- Develop relationships with future local and national leaders
- PF remains a cross BE Bogota priority with consistent messaging during bilateral engagements

Update: The new Colombian administration is more private sector-oriented than the previous one and has engaged with BE Bogota and PF Programme enthusiastically requesting that timelines for activities be brought forward if possible.

2 - Under-performance of implementing partners results in non-delivery of agreed targets. During MoU negotiations, CAF, Findeter and Innovate UK committed themselves to the PF objectives and delivery targets, but challenges arising during implementation may affect their appetite for progress.

Establish comprehensive MoU covering all expected activities, results and milestones. Rigorously review implementation of MoU agreements on a monthly or more frequent basis. Ensure MoUs have break clauses, independent audits and M&E mechanisms in place to improve performance or end the partnership.

Update: Some activities had a slow start (Regional Competitiveness, Open Procurement and Agri Insurance), but we are working much closer with implementers to resolve delays in those three activities and drive momentum.

3 - Corruption / fraud in one of our interventions cause reputation damage and derail the programme. At the start of the Programme implementation phase, the mayors of two prioritised cities were in the press for financial and / or electoral irregularities.

We, and implementing partners, employ: (i) robust due diligence during partner selection; and (ii) strong governance and proactive programme oversight to manage each intervention. MoUs will build in break clauses and milestone payments that would allow termination.

Update: The inclusion of the cities of Villavicencio and Cartagena in the Urban Development activity are on stand-by until the irregularities there have been resolved.

4 - Major economic downturn in either UK or Colombia reduces the capacity or appetite for UK business to invest in Colombia. Following the financial crisis of 2008 and the subsequent oil price crash, UK investments in Colombia contracted, but are expanding again now.

Use flexible and adaptive programming to respond to downturn. Ensure programme delivers primary benefits that help to insulate from global economic trends.

Update: Not an issue.

5 - Failure to secure secondary benefits (commercial opportunities) as links between Programme and benefits are indirect. The execution of projects (i.e. the secondary benefits) could go to any national or international businesses.

Targeting sectors with high potential and select delivery modalities to maximise UK exposure to these sectors. Leverage relationships through MoU agreements to secure wider opportunities alongside programme delivery. Additional staffing in BE Bogota to exploit relationships and opportunities opened up by Programme.

Update: Colombia PF Programme Secondary Benefits Plan is on schedule and progressing well. Too early to say if planned secondary benefits will materialise or not.

Outstanding actions and recommendations from risk assessment - None
F: COMMERCIAL CONSIDERATIONS
Delivery against planned timeframe

The Colombia PF Programme began implementation on 1 April 2018. The original CAF and Findeter MoUs, signed in November 2017, had to be amended in mid-2018 to allow both implementers to use the PF Commercial Framework to procure suppliers. The seven activities are either on track or close to being on track.

Performance of partnership(s)

BE Bogota has strong, amiable working relationships with all three implementing partners, CAF, Findeter and Innovate UK. We meet around every two weeks in person or by phone. CAF’s internal approval processes, while comprehensive and robust, do take much longer than the PF Team had expected. A priority going forward with CAF is to better understand these processes, work to bring them forward where possible and plan activities bearing in mind the timeframes that CAF operates.

Changes in the Delivery Plan

Originally, Findeter was going to manage all aspects of the Open Procurement activity. Open Contracting Partnership (OCP) was subsequently identified as the ideal agency to implement the procurement capacity building in the regions. However, being based in the USA and unable to accept payments in Colombian pesos, BE Bogota took over the relationship with OCP and developed a project proposal and grant agreement with them. Currently, it is still planned for Findeter to manage the remaining two complementary activities with Colombia Compra Eficiente and local civil society.

Asset monitoring and control

The Programme is not generating any assets nor is expected to later on.

G: Business Environment
How has the business community and business environment responded to the programme?

We have built strong relations with host market influencers and decision makers over the past 2 years. Several Colombian ministries and agencies and many international business, including those from the UK contributed to the design of the bilateral PF Programme. As part of Programme implementation, we work directly with the Ministries of Transport and Agriculture, the National Planning Department, the Presidency, the National Infrastructure Agency and sub-national governments on regional competitiveness, rail, urban development, agri-insurance and agri-innovation. Substantial private sector interest has been generated in Colombia PF projects at the PF Commercial Framework Launch and the Colombia Infrastructure Road Show in London (co-funded with non-ODA resources).

What role has non-ODA spending played in promoting programme objectives?

Non-ODA has played a pivotal role in raising awareness of the PF Programme with public and private sector in Colombia and the UK. It has created many opportunities for building partnerships between the two countries, building the capacity of UK companies to compete fairly for tenders in Colombia, and communicating, including with social media, to a large audience of government, companies, academia, civil society and the press.

More specifically, we have promoted PF commercial opportunities through:

1. Non-ODA activities and events which include outreach to relevant sectors (infrastructure, agriculture, financial services) in the UK via Road Shows, inward missions, supplier events and training and workshops (UKEF, winning public sector contracts, etc.).

2. Advertising all PF-generated contract opportunities (up to 50 of them) to the PF Commercial Framework companies on Bravo, directly with those already operating in Colombia and amongst wider DIT, Chambers of Commerce and ProColombia networks.

3. Our new Colombia PF Communications Strategy that includes in both English and Spanish: brochures, banners, one-page briefings, PPT presentations, videos on YouTube, DIT webinars, case studies, partners’ websites and social media.

Non-ODA resources have helped us raise awareness of wider commercial and trading opportunities between the UK and Colombia. In several cases, those resources attracted new companies to visit Colombia and better understand those opportunities first hand. Some of events used to achieve these objectives over the past few months include:

- Colombia Infrastructure Road Show in London In May
- Agrofuturo: three-day exhibition and conference in August where we brought 10 new UK companies to attend the event
- Early Market Engagement event with over 100 participants in Bogota in July
- Rail conference in joint with Ministry of Transport to influence the development plans of the Government and to showcase UK capabilities in the rail sector in September.
- Two-day rail workshop for the Ministry of Transport, Ministry of Finance, ANI, FDN and DNP in October
- Colombia Infrastructure Conference and Partnering Workshop in November with at least 7 new UK companies planning to attend

H: MONITORING & EVALUATION
Evidence and evaluation
The MREL team visited Colombia in February 2018 and worked with the PF Team and implementing partners CAF and Findeter to finalise nested Theories of Change (ToCs), logframes and risk matrices for six of the seven activities. The MREL team are working with Innovate UK to do the same for the Agri-Tech Catalyst activity. The Team returned to Colombia in August to conclude initial technical assistance (TA) to the Programme and to help PF staff and implementing partners prepare baselines and commence reporting in the Prospero monitoring system. A draft Approach Paper on Evaluation and Learning was submitted to BE Bogota for comments on 8 November. An umbrella logframe workshop with all three implementing partners took place on April 2019, documents will be public once finalised.

Monitoring progress throughout the review period
In addition to the governance structures, fortnightly meetings and quarterly reports, BE Bogota staff have visited about half of the cities and regions with projects, and meet government stakeholders in Bogota on a regular basis. Monitoring systems for the first six months of the Programme have worked well. As MREL engagement increases and project activity starts producing data and feedback, there will be an uptick in monitoring work.