Prosperity Fund Business Case
Mexico Bilateral Programme:
Stimulating Opportunities for Productivity and Growth and Tackling Market Failures

Locations of possible Prosperity Fund interventions in Mexico

MEXICO PROSPERITY FUND PROGRAMME
STIMULATING OPPORTUNITIES FOR PRODUCTIVITY AND GROWTH AND TACKLING MARKET FAILURES
Contents

## Acronyms
APF – Agile Programming Fund
Banxico – Central Bank
CONAVIM – National Commission to Prevent and Eradicate Violence Against Women
CONEVAL – National Council for the Evaluation of Social Policy
COPARMEX – Mexican Employers’ Association
CPTPP – Comprehensive and Progressive Agreement for Trans-Pacific Partnership
DAC – Development Assistance Committee
DFID – Department for International Development
DIT – Department for International Trade
EoI – Expression of Interest
FCO – Foreign and Commonwealth Office
FEVIMTRA – Specialised Prosecution Office for Violence against Women and Human Trafficking
Fintech – Financial Services Technology
FTE – Full Time Equivalent
GVA – Gross Value Added
GDP – Gross Domestic Product
HMA – Her Majesty’s Ambassador
HMG – Her Majesty’s Government
HMT – Her Majesty’s Treasury
IFC – International Finance Corporation
MCO – Mexican Institute for Competitiveness
IMF – International Monetary Fund
INEGI – National Institute of Statistics and Geography
IPA – Infrastructure and Projects Authority
ITT – Invitation to Tender
KPI – Key Performance Indicators
MNC – Multi-National Company
MORENA – National Regeneration Movement
MoU – Memorandum of Understanding
MREL – Monitoring, Reporting, Evaluation, Learning
MSMEs – rural micro, small and medium enterprises
NAFTA – North American Free Trade Agreement
NPV – Net Present Value
OBIEE – Oracle Business Enterprise Edition
ODA – Official Development Assistance
OECD – Organisation for Economic Cooperation and Development
OGD – Other Government Department
OSJA – Overseas Security and Justice Assistance
PAN – National Action Party
PBR – Payment by results
PEMEX – Mexican Petroleum
PF – Prosperity Fund
PO – Purchase Order
PPP – Public Private Partnership
PPP – Purchasing power parity
PRD – Party of the Democratic Revolution
PRI – Institutional Revolutionary Party
PSVI – Preventing Sexual Violence in Conflict Initiative
P2B – Peer to Business
P2P – Peer to Peer
P2P – Purchase to Pay
SESNSP – Executive Secretariat of the National System of Public Security
SDG – Sustainable Development Goal
SLA – Service Level Agreements
SME – Small and medium-size enterprises
SoR – Statement of Requirements
SRO – Senior Responsible Officer
ToC – Theory of Change
UN – United Nations
VfM – Value for Money
WB – World Bank
WHO – World Health Organisation
WTO – World Trade Organisation
MEXICO PROSPERITY FUND 2017-2023 PROGRAMME
STIMULATING OPPORTUNITIES FOR PRODUCTIVITY AND GROWTH AND TACKLING MARKET FAILURES
Executive Summary
Now is a unique point in time to invest in Mexico to help embed the economic advances of the past years and to support the newly elected government reduce poverty. Mexico is an emerging market, currently 15th largest in the world[1], and is growing - by 2030 Mexico might be the 9th largest economy in the world and the 7th by 2050[2]. The Mexican Government has an ambitious vision for a future Mexico with a strong focus on social inclusion and reducing corruption. There is a window of opportunity to support Mexico at a time of change, making strategic interventions which will help alleviate poverty and advance the UN’s Sustainable Development Goals (SDGs). This programme will also help to strengthen the UK’s relationship with Mexico as it emerges as one of the world’s leading economies; building a partnership that will further the UK’s international political, security and economic priorities.
[1] “World Development Indicators database”, World Bank, April 2017, http://databank.worldbank.org/data/download/GDP_PPP.pdf
[2] “The Long View: How will the global economic order change by 2050?”, PwC, 2017, https://www.pwc.com/gx/en/world-2050/assets/pwc-the-world-in-2050-full-report-feb-2017.pdf

While Mexico represents significant opportunities for growth it also has a sizeable wealth gap and significant levels of poverty. Despite having a Gross Domestic Product (GDP) of about $1 trillion[3], around half the population in Mexico live in poverty (including 20 million children); with 3% of people living in extreme poverty according to the World Bank (2014), although national figures put this at a higher figure of 9.5%[4]. Gender inequality is also an issue since poverty disproportionately affects women and girls. In combination with the poverty rate and a wider understanding of development outcomes in Mexico, the data suggests that Mexico has a significant issue with inclusive growth in particular.
[3] World Economic Outlook Database, International Monetary Fund, 2017, http://www.imf.org/external/pubs/ft/weo/2017/01/weodata/weorept.aspx?sy=2015&ey=2022&scsm=1&ssd=1&sort=country&ds=.&br=1&pr1.x=68&pr1.y=14&c=273&s=NGDPD&grp=0&a=
[4] “Informe de pobreza en México”, CONEVAL, 2014, http://www.coneval.org.mx/InformesPublicaciones/Documents/Informe-pobreza-Mexico-2014.pdf

As the UK exits the European Union and Mexico adjusts to its changing relationship with the U.S. , there is an opportunity to strengthen the bilateral relationship. The UK’s trade and investment relationship with Mexico is modest but growing; UK total current account earnings in Mexico reached £3.2bn in 2015[5], and there is a significant opportunity to tap into this emerging market. Nevertheless, capitalising on these benefits will be challenging – Mexico’s market visibility in the UK still needs to develop significantly.
[5] “UK Balance of Payments, The Pink Book: 2016”, Office for National Statistics, 2016 https://www.ons.gov.uk/economy/nationalaccounts/balanceofpayments/bulletins/unitedkingdombalanceofpaymentsthepinkbook/2016#toc

The Presidential election in 2018 has seen the first election of a National Regeneration Movement (MORENA) government on an anti-corruption and social inclusion ticket. Initial engagement with the new government suggests the programme is aligned with their priorities. To mitigate risk from the changing political environment the programme will take a geographical approach via engagement with state and municipal level governments across our targeted regions which have been identified to maximise impact and ensure deliverability, rolling out innovative pilots and transferrable programmes.

The £60 million programme will focus on the Energy, Future Cities, Financial Services and Anti-Corruption and Rule of Law sectors with the aim of reducing poverty and gender inequality in Mexico, complemented by other global Prosperity Fund Programmes. At the same time improved economic development and the opening of new markets will present opportunities for international and UK businesses.

The Mexico Prosperity programme supports the 2015 UK Aid Strategy and is in line with the Department for International Development’s Economic Development Strategy which recognises trade as an engine for poverty reduction and the importance of the programme’s priority areas in propelling economic development and advancing the UN’s SDGs. In 2015 the National Security Council identified Latin America, and Mexico in particular, as vital partners in delivering the UK security strategy[6].
[6] National Security Strategy and Strategic Defence and Security Review 2015

What will we deliver?
The programme will aim to deliver change in the following sectors which have been identified due to their ability to deliver primary (poverty reduction) and secondary (opportunities for international businesses) benefits alongside their strategic fit with Mexico’s vision for change and the UK’s ability to help shape that change in areas where the UK has strong expertise:

- Energy: Highest value sector for the Mexican economy (£28m)
- Future cities: Greatest opportunity for inclusive growth (£11m)
- Financial services: Greatest potential for impact across the economy (£11m)
- Anti-Corruption and Rule of Law: Biggest brake on economic growth (£10m)

What are the expected results?

Through targeting niche interventions, the programme will complement the work of the Mexican Government and other donors to maximise impact. It will help make progress towards the vision for Mexico, helping to reduce poverty and improve economic development in specific areas where the UK can best support with world-class expertise. It is estimated that the programme will deliver benefits to Mexican economy equating to £886m.

In addition, prosperity interventions will open up new markets and deepen existing ones with international business, including UK business able to benefit from overall growth of markets. It is estimated that the programme will deliver secondary benefits to UK businesses equating to an additional £462 million of exports to 2026.

How will the programme be delivered?
The programme will be delivered through four commercial contracts to enable a strategic approach across the interventions identified for each strand, deliver value for money through economies of scale and maximise impact in line with the programme’s objectives and theory of change. These contracts will allow for a level of flexibility and the ability to capitalise on short windows for influencing government policy in Mexico. These contracts were procured in 2018, with the following suppliers winning the competitive tender process : DAI Europe (for both the Energy and Financial Services strands), PwC (Future Cities) and PA Consulting (Anti-corruption and Rule of Law).

Strategic Case
### Socio-economic Context
#### Introduction

Mexico’s economic prospects remain bright compared to the wider Latin American region, even at a time when the Mexican economy continues to face complex external challenges. As an emerging market, private consumption continues to grow as a result of low inflation, low unemployment, rising real wages and large remittances. Mexico has maintained steady growth in spite of a number of considerable challenges. These include persistently low oil prices, a normalisation of U.S. monetary policy, and a slowdown in global trade and economic growth. The International Monetary Fund (IMF) predicted annual growth of 1.7% in 2017 and 2% in 2018, against a 3.5% contraction in Brazil and 0.5% contraction in Latin America as a whole last year.[7]
[7] Perspectivas de la Economía mundial al día, actualización de las proyecciones centrales”,IMF, 2017, https://www.imf.org/external/spanish/pubs/ft/weo/2017/update/01/pdf/0117s.pdf

The sections below set out the trends and challenges Mexico faces across the domestic and international political and economic environment.
#### Domestic socio-political context

Mexico is a federation with a presidential system. There are three levels of government: federal, state and municipal. The President is the head of state, government and military. There are four main political parties: the National Action Party (PAN), centrist conservative party; Institutional Revolutionary Party (PRI), centre-left party which held power for 71 years; and left-wing Party of the Democratic Revolution (PRD). MORENA, an emergent party, founded in 2015, was elected at the federal level in July 2018. Since 2015, independent candidates have been able to run for office.

Lately, local politics have been heavily influenced by external factors, most importantly, the final sign-off of USMCA (the new NAFTA). Given that Mexico’s political system is divided into Federal, State and Municipal levels and to deliver effective impact for the objectives of the Prosperity Fund (PF) the programme will need to coordinate with each level of government. Designing activities in the geographic areas where it can have the greatest impact given the shifting political context throughout the life cycle of the programme.
#### International Political Context

Over the past years Mexico has sought a bigger role on the international stage. The change in U.S. government policy has made this more challenging, but at the same time increases Mexico’s need to achieve greater international status. The UK and Mexico are close friends and key partners in international fora such as the United Nations (UN), G20 and World Trade Organization (WTO). Mexico is becoming more active regionally, including through the Pacific Alliance (with Colombia, Chile and Peru) and the Comprehensive and Progressive Agreement for Trans-Pacific Partnership (CPTPP).

Mexico shares our values around political openness, free trade and human rights; and has been a vital ally on climate change and international development.

Mexico’s Economic Landscape

Mexico is the 15th largest economy in the world – whilst the 11th largest by purchasing power parity (PPP) – and the second largest economy in Latin America, following Brazil.[8] In 2017, there was a slight economic slowdown; GDP remained at 2.1% compared to 2.3% in 2016.[9] Expanding its production by diversifying industries has been key to Mexico in order to show resilience to negative externalities and to keep on growing. Nowadays, not just the hydrocarbons sector drives the economy, but other major sectors like automotives (4m cars produced in 2018, making it the 7th largest automobile producer in the world), services, trade, real estate, construction, transportation and tourism (with the country receiving more than 39m tourist in 2017). Mining supports the economy with 4% of its GDP (largest world silver producer), although most of the mines are under foreign ownership. Mexico is among the largest producers of coffee, sugar, corn, orange, avocado and lime worldwide. Livestock and fishing are also important economic activities in the food sector. Mexico is also the 5th largest producer and the largest exporter of beer in the world.[10]The country is among the world’s leading mineral producers, including silver, fluorite, zinc and mercury. Its oil and gas reserves are one of its most valuable assets: Mexico is in the top 20 list of countries globally in terms of proved crude oil reserves.
[8] “Data Bank World Bank: Gross domestic product 2015 PPP”, World Bank, 2017, http://databank.worldbank.org/data/download/GDP_PPP.pdf
[9] “Sistema de Información Económica”, Banco de México, 2017 http://www.banxico.org.mx/SieInternet/consultarDirectorioInternetAction.do?accion=consultarCuadro&idCuadro=CR142&locale=es
[10] “Complejidad del Producto Rankings”, OEC, 2015, http://atlas.media.mit.edu/es/rankings/hs92

Whilst Mexico’s economy is comparable in size to the economy of Spain, its population is larger by 161%. Consequently, GDP per capita is an order of magnitude lower, at an estimated $9,600 USD in 2018. According to the IMF, Mexico’s GDP per capita is among the lowest in the Organisation for Economic Cooperation and Development (OECD).[11]
[11] “El cambiante panorama de la economía mundial”, Fondo Monetario Internacional, 2017, https://www.imf.org/external/spanish/pubs/ft/weo/2017/update/01/pdf/0117s.pdf

Despite shocks, domestic demand was the main driver of Mexican growth, supported by credit expansion and an increase in remittances from expatriate workers. Structural reforms support an environment of low inflation and strong credit expansion, which could lead to increases in real wages and employment. The sharp depreciation of the Mexican peso further increases the competitiveness of Mexico’s non-oil exports.

##### Unemployment/labour force
##### Mexico’s labour market faces structural challenges although unemployment is low. The unemployment rate in Mexico is low and has dropped considerably in the recent years, going from 5.27% in 2010 to 3.43% in 2017.[12] In addition, few jobseekers have remained unemployed for more than a year, as the long-term unemployment rate was is 2% in 2018, being the second best in the OECD countries.[13]
[12] “Encuesta Nacional de Ocupación y Empleo (ENOE), población de 14 años y más de edad”, Instituto Nacional de Estadística y Geografía, INEGI, 2014, http://www3.inegi.org.mx/sistemas/infoenoe/default_conapo.aspx?s=est&c=26227
[13] “Long-term unemployment rate”, Organisation for Economic Co-operation and Development, OECD, https://data.oecd.org/unemp/long-term-unemployment-rate.htm

The labour market still faces several structural challenges; as according to the National Institute of Statistics and Geography (INEGI, 2014)[14] more than half of the employed population works for small and micro businesses or is employed in the informal economy; there are low levels of productivity, approximately 60% of the population earns less than three minimum wages[15]; and the youth unemployment rate (7.7%)[16] remains almost double the total average unemployment rate.
[14] INEGI. “Encuesta Nacional de Ocupación y Empleo (ENOE), población de 14 años y más de edad” http
[15] In 2015, the real minimum wage established in Mexico (around MXN$70 per day) was below the welfare line determined by CONEVAL to determine poverty thresholds. This means that those who earned a minimum wage lived in income poverty. Such wages were insufficient to purchase food and the most basic services, such as education and health. In the urban sector, for a family of two members earning two minimum wages to overcome poverty, the minimum wage would have had to increase 146.6%. In Mexico, around 20 million people earn between one and two minimum wages.
[16] “Youth unemployment rate”, Organisation for Economic Co-operation and Development, OECD, https://data.oecd.org/unemp/youth-unemployment-rate.htm#indicator-chart

Conclusion

Mexico’s GDP growth may remain low in 2019 (1.5%-2.5%), mainly due to investment and low consumer confidence levels in the wake of uncertainties about the future, both internal and external. However, the economy could benefit from the fiscal stimulus expected in the U.S., which would increase the demand for Mexican imports and some other domestic policies that might enable consumption. Private investment in the energy sector is expected to generate activity that would partially compensate for the budget cuts in public investment related to oil; however, industrial production will remain tied to U.S. activity. A more stable depreciation of the Mexican peso will continue to support foreign trade activities, with a limited transfer to domestic prices, nevertheless the pressure coming from monetary policy in the US and uncertainty around new government policies might complicate the inflation’s conversion towards Banxico’s target (3% ±1%).

 Poverty Analysis
Mexico is defined by the OECD as an Official Development Assistance (ODA) eligible country. According to the World Bank (2016) 2.5% of the population in Mexico live in extreme poverty However, national poverty line data (almost 50% of people below the nationally recognised poverty line[17]) together with inequality figures and a wider understanding of development outcomes, suggests that Mexico has a significant issue when it comes to inclusive growth in particular. The National Council for the Evaluation of Social Policy (CONEVAL) has its own multidimensional poverty figures that define extreme poverty. Defined as lacking the necessary income to satisfy basic needs but also as the lack in access to three or more social development rights: an ideal level of education, healthcare, social security, adequate nutrition, adequate housing characteristics and social cohesion. With this definition, in 2016, 7.6% of the population (9.4 million people) live in extreme poverty.
[17] Medición de pobreza a nivel nacional 2016. CONEVAL

From the 1950s to 2000, Mexico’s poverty rate fell from 80% to 50%, largely as a result of an increase in urbanisation. But since 2000, the poverty rate has barely moved. In 2016 it was 43.6% – and more recent figures published by Mexico’s National Institute of Statistics, though lower have been criticised for using a questionable methodology. Under more reliable OECD data, Mexico’s projected poverty rate would continue to remain high even under strong economic growth. And in the event that economic reforms or the global economy falter, they could rise further. Part of the problem is stubbornly high rates of informal economy (currently 58%).

The main causes and effects of poverty in Mexico are deeply rooted. These include: the informal economy, poor quality public education and health systems (which negatively impact on people’s employability and wider social mobility), endemic corruption, poor infrastructure, inefficient government institutions, and a lack of innovation (reducing productivity growth). Combined, these severely limit economic and social opportunities for Mexicans, where nearly 5% of the workforce is unemployed, in particular those at the base of the pyramid.

There is a longstanding narrative around ‘two Mexico’s’. On the one hand, there is an industrialised, competitive, productive, and globally integrated economy in the states bordering the U.S. and in the central corridor. On the other hand the economy in the south of the country is dominated by more traditional, small scale, less productive firms in the informal sector. At an aggregate level, and despite Mexico being the second largest economy in Latin America, poverty remains a sizable issue. Mexico is the second most unequal country of the 35 advanced economy members of the OECD, after Chile. In fact, 38% of the national income is held by the top 1%.[18] Moreover, inequality in the population, as measured by the Gini coefficient, has seen little improvement over the past 10 years – disposable income inequality is 0.46 compared to the OECD average of 0.31.
[18] Credit Suisse, 2016

Age is also a factor in the poverty demographic in Mexico. More than 20 million children live in poverty and more than 4.65 million live in extreme poverty, according to Fusion, the UN Children’s Fund. Mexico also has one of the highest old-age poverty rates in the OECD. Approximately 66% of citizens over 65 years (8.6 million Mexicans) do not have access to a pension and 25% live in poverty.
#### The impact of poverty in Mexico

Poverty and inequality in Mexico have two further negative effects. First, they act as a drag on broader economic growth, resulting in reduced saving, investment and consumer demand. Second, they are associated with higher violence, crime and social exclusion. The lack of employment opportunities, especially for the young population, has stimulated the market in Mexico for criminal activities such as drug and human trafficking, kidnapping and extortion. This is particularly evident in the states of Guerrero and Michoacán (Pacific states along the drug routes to the U.S.), and on the border with the U.S. The current Mexican Government is expected to continue to prioritise poverty reduction, albeit with different programmes and initiatives.

Gender Equality Context
Key Facts / Labour Force / In 2016, 45% of working age women formed part of the labour force, compared to 80% of working age men[19] / Women represent 40% of those employed in the non-agricultural labour force[20] / In 2020, women are projected to be 38% of the total labour force (22,704,200)[21] / Leadership / Women have a low participation rate in leadership roles and make up only 7% of board seats in companies[22] / Only 15% of firms have women in top management roles [23] / Women represent only 23% of senior-management positions[24] / Women earn only 60% of men's salaries[25] / Education / Only 29% of women in Mexico are enrolled in tertiary education[26] / In 2012, the percentage of women graduates in specific undergraduate degree programs included: / 11.2% in engineering, construction, manufacturing / 4.9% in sciences / 49.6% in social sciences, business, and law[27]
[19] “Labor force participation rate, female (% of female population ages 15+)”, The World Bank ,2013 http://data.worldbank.org/indicator/SL.TLF.CACT.FE.ZS
[20] “Labor force participation rate, female (% of female population ages 15+)”, World Bank ,2013, http://data.worldbank.org/indicator/SL.EMP.INSV.FE.ZS?locations=MX
[21] "EAPEP-1990-2020, Economically Active Population, Estimates and Projections (6th Edition, October 2011)”, Data for All Countries, 2020, Mexico, International Labour Office,” LABORSTA, 2011
[22] “The Global Gender Gap Report 2015”, The World Economic Forum, 2015, http://reports.weforum.org/global-gender-gap-report-2015/economies/#economy=MEX
[23] “The Global Gender Gap Report 2015”, The World Economic Forum, 2015, http://reports.weforum.org/global-gender-gap-report-2015/economies/#economy=MEX
[24] “Women in Eastern Europe Point the Way to Senior Management”, Grant Thornton, Women in Business 2015, 2015 https://www.grantthornton.global/en/press/press-releases-2015/women-in-business-2015/
[25] The Global Gender Gap Report 2015, The World Economic Forum, 2015 http://reports.weforum.org/global-gender-gap-report-2015/economies/#economy=MEX
[26] The World Economic Forum, The Global Gender Gap Report 2015: Mexico, http://reports.weforum.org/global-gender-gap-report-2015/economies/#economy=MEX
[27] UNESCO, Percentage of Female Graduates by Field of Study, Education, 2012, Mexico, UNESCO Institute for Statistics http://uis.unesco.org/

According to the 2017 Global Gender Gap Index, Mexico ranks overall as just the 81st most gender-equal country in the world out of 144 benchmarked countries. The index is built using a set of sub-indexes, and Mexico ranks 124th in economic participation and opportunity, 53rd in educational attainment, 58th in health and survival and 34th in political empowerment.[28] It is well established that when women are educated and employed, economies grow and development outcomes are improved[29], and while Mexico has made significant progress in recent years in protecting women’s rights and advancing gender equality, there are challenges that are still to be addressed. Mexico has made a series of significant developments in moving towards greater protection for women and girls. UN Women reports the following progress in Mexico in the advancement of women’s rights and gender equality:
[28] World Economic Forum. (2017). Global Gender Gap Report 2017. Retrieved June 25, 2018 from https://www.weforum.org/reports/the-global-gender-gap-report-2017
[29] UN Women 2017

- For the first time, a National Development Plan (2013 – 2018) mainstreamed gender equality and women’s empowerment in all its areas.
- The National Gender Equality Policy (2013 – 2018) focused on advancing substantive equality.
- Increased public resources earmarked for gender equality: this reached $1,65 billion USD in 2015, representing a 157% increase, but is still only 0.5% of public spending.
- Political-Electoral Reform (2014): elevated gender parity to a constitutional level for candidacies to Federal and State Congress. In March 2015, this solidified when parity became a statutory obligation to register candidates.[30]
  [30] UN Women: Mexico, UN Women Americas and the Caribbean; http://lac.unwomen.org/en/donde-estamos/mexico

The National Commission to Prevent and Eradicate Violence against women (CONAVIM), set up in 2009, is charged with designing policies for the prevention and eradication of violence against women. The Specialised Prosecution Office for Violence Against Women and Human Trafficking (FEVIMTRA) contributes to equal justice for women and men, strengthening the rule of law, complying with the international treaties ratified by Mexico and addressing the gender perspective. To these ends, it focuses on the integration of criminal investigations in the fight against this type of crime and the integral attention of the victims. This institution participates in the construction of public policies aimed at preventing violence against women and collaborates in the search for missing women and girls.

UN Women also reports that, despite the progress made, gender inequality in Mexico continues to face a series of structural challenges; caused by an implementation gap between what is stated in the laws, plans, programmes and budgets on women’s rights, and practical implementation and compliance in daily life. A public spending reduction in 2015, affected government funding available for gender equality.
#### How the programme will help

All initiatives carrying out UK technical assistance have to comply with the Gender Equality Act 2014. All programmes need to ensure that gender issues and opportunities are addressed in design, prioritisation, delivery and monitoring to ensure compliance. Bidders are required to submit a preliminary gender equality assessment (including consultations with women or women’s groups) outlining how they propose to address gender issues in the programme design and delivery, and gender equality will be a requirement of every agreement signed for the delivery of the programme. A gender expert will be involved at appropriate stages to ensure the programme continues to maximise the opportunities to deliver gender equality and support women’s economic empowerment.

The proposed programme will look to improve the lives of women and girls in a number of ways. For example, the work proposed in this document aims to increase the participation of women in decision-making processes in all levels of government. It seeks to foster dialogue among key actors, promote cultural change within political parties, carry out professional training and mentorships for public officers, and to increase knowledge of women’s rights.

Challenges to Mexico’s Future

Mexico faces challenges both domestically and internationally across the socio-political and economic landscape. These limit Mexico’s ability to achieve its potential economic growth and to close the wealth gap.

Challenge 1, Security, corruption and rule of law:
Corruption in Mexico is often referred to as ‘endemic’, Mexico is ranked 135 out of 180 countries in the Corruption Perception Index according to Transparency International. Lack of accountability and weak legal and enforcement institutions are at the root of the problem. Security remains a challenge in Mexico: according to numbers provided by the Executive Secretariat of the National System of Public Security (SESNSP) and to the INEGI, the homicide rate increased in 2016, reaching levels not seen since 2012. [31]This will not be fixed without addressing impunity: according to the Global Impunity Index, Mexico is 58th of 59 countries with the highest levels of impunity (only the Philippines is ranked lower). Public dissatisfaction with corruption is high and there have been significant advances in Mexico’s anti-corruption legislation (including reclassifying it as a criminal rather than administrative offence). In July 2016, the Senate signed a new ‘National Anti-corruption System’ into law.
[31] ‘Y la sangría no para’, Alejandro Hope, 22 August 2016. http://www.eluniversal.com.mx/entrada-de-opinion/columna/alejandro-hope/nacion/2016/08/22/y-la-sangria-no-para

Challenge 2, Justice and human rights:
For more than a century, Mexico’s criminal justice system was based on the inquisitorial system but in June 2008, the Mexican constitution was amended to start a process to replace this with an adversarial system. The reform involves a profound change in the country's legal culture. The process of written trials where the accused had no access to or information about the investigation, accusation and prosecution – and which resulted in a 98% rate of impunity in Mexico[32]– has been replaced by an oral trial system, which it is hoped will provide more effective and legitimate justice, including stronger protection of human rights.
[32] End of mission statement by the United Nations Special Rapporteur on the situation of human rights defenders, Michel Forst on his visit to Mexico from 16 to 24 January 2017, January 2017 http://www.ohchr.org/EN/NewsEvents/Pages/DisplayNews.aspx?NewsID=21111&LangID=E

Challenge 3, Education:
In March 2017, the previous Government introduced an education reform aimed to establish an evaluation system to raise the quality of education delivery across the country and to professionalise the teaching profession through meritocratic recruitment. However, Mexico faces significant issues related to the implementation of its education reform and the government is currently reviewing Education policy with further changes possible.

Challenge 4, Constraints to economic growth and poverty reduction:
Mexico’s economic potential is greater than its predicted growth. The difference is due to continuing market failures such as lack of economic policy and regulation, lack of skills and knowledge and insufficient capacity. These limit Mexico’s ability to meet the Sustainable Development Goals (SDG), particularly more inclusive and sustainable economic growth, employment and a decent work environment, and to revitalize the global partnership for sustainable development through finance and capacity building.
### What role can the UK play in Mexico’s future development?
#### A shared vision for economic growth and poverty reduction
Designed to deliver against a vision for change in Mexico, the programme will work in partnership with the Mexican Government while also aligning with UK strategic objectives and the UN Sustainable Development Goals. Considering where the two country’s strategic objectives align we have also considered where the UK is best placed to provide expertise, building upon existing trading and diplomatic relationships and exploring the challenges and opportunities for UK investment in Mexico.
#### Programme fit with UK Strategic objectives
The Prosperity Fund will help achieve the three pillars of the UK National Security Strategy:

- Promote our prosperity: particularly in sectors such as Energy or Financial Services, with strong growth potential and a good fit with UK business strengths. It will further enhance our partnership on global prosperity issues: Mexico is an evangelist of free trade, strongly believing in its benefits – it has 14 agreements covering trade with 46 countries, more than the US and China combined.
- Protect our people: by tackling corruption, strengthening the rule of law and improving cyber security.
- Project the UK’s global influence: the UK brand has already been enhanced by our Prosperity work to date although this is not the primary objective of the programme.

The Mexico Prosperity programme also supports the 2015 UK Aid Strategy, which shifted how the UK intends to spend its 0.7% commitment to ODA to tackle great global challenges which directly threaten British interests.

In particular, it will help us achieve the following elements of that Strategy:
- Crisis resilience and response. The Energy element of the programme has a focus on encouraging the deployment of renewables and the adoption of energy efficiency policies to will help mitigate climate change and subsequent natural disasters.
- Global prosperity. The programme will promote the adaptation and implementation of legislation that shifts Mexico’s economic development up a gear. It will also mitigate possible consequent increases in inequality by working on urban development (via Future Cities). The entire programme is structured to ensure we drive and take advantage of secondary commercial benefits for international businesses including UK businesses, arising from this ODA activity.
- Global peace, security and governance. The Anti-Corruption and Rule of Law element of this programme will contribute to a reduction of impunity and corruption (both major brakes on Mexican growth) by improving the functioning of the Mexican justice and security sectors. This will have spill over beneficial effects on UK’s security by, for example, creating a more hostile environment for drug traffickers.
- Extreme poverty and the most vulnerable. Rural Mexicans face specific challenges regarding a lack of access to credit or basic infrastructure. Our Financial Services programme is structured around improving financial inclusion for the poorest.

The programme is also in line with the Department for International Development Economic Development Strategy; the strategy which recognises the importance of trade as an engine for poverty reduction and the importance of the following priority areas in propelling economic development:

Financial sectors, new technology and innovative financing mechanisms.
- Infrastructure, energy and urban development.
- Extractive industries.
- Economic inclusion.
- Stability, peace and security.
- Governance, politics and corruption
#### Programme fit with UN Sustainable Development Goals
The Mexico programme aims to support the achievement of the following UN SDGs:

Goal 1: End poverty in all its forms everywhere
Goal 5:	Achieve gender equality and empower all women and girls
Goal 7:	Ensure access to affordable, reliable, sustainable and modern energy for all
Goal 8:	Promote inclusive and sustainable economic growth, employment and decent work for all.
Goal 9:	Industry, innovation and infrastructure
Goal 10: Reduce inequality within and among countries
Goal 11: Make cities inclusive, safe, resilient and sustainable
Goal 17: Revitalize the global partnership for sustainable development, particularly:

Finance: Developed countries to implement fully their official development assistance commitments, including the commitment by many developed countries to achieve the target of 0.7 per cent of ODA/GNI to developing countries and 0.15 to 0.20 per cent of ODA/GNI to least developed countries ODA providers are encouraged to consider setting a target to provide at least 0.20 per cent of ODA/GNI to least developed countries

Capacity building: Enhance international support for implementing effective and targeted capacity-building in developing countries to support national plans to implement all the sustainable development goals, including through North-South, South-South and triangular cooperation.

A modest but growing trading relationship

According to INEGI’s figures, in 2016, the UK became the 7th most important export partner for Mexico, with $3,232 million USD traded between both countries (1% share) and the 17th most important import partner with $2,128 million USD traded (0.6% share).

According to the latest available data from the Observatory of Economic Complexity, in 2015, the main export was Machinery (which represents 34% of the total exports of Mexico to the UK) followed by Precious Metals (23%), Transportation (14%) and Instruments (6.4%). Imports were also led by Machinery (which represents 35% of the total imports of Mexico from the UK) followed by Chemical Products (6.5%), Transportation (9.9%) and Metals (9.7%).

Challenges and opportunities for UK business in Mexico

Britain currently has only a very modest stake in the Mexican economy. The UK accounts for less than 1% of total trade in goods, and 3% for services (this equates to £1.95bn). Thus, increased economic growth by itself would not result in large automatic secondary benefits for the UK, unless supported by targeted trade efforts and increased awareness in the UK of Mexico’s commercial opportunities. DIT is working to exploit this potential via High-Value Opportunity campaigns and any future UK-Mexico trade agreement. However, there is a need to supercharge those trade and diplomatic relations with the effective use of ODA funds to open new markets and build global standards into Mexico’s economy. Non-ODA funds will also be used to enable Department for International Trade (DIT) to exploit the opportunities opened by ODA funding due to an increase in economic growth and newly opened markets.

Why the UK? The additionality case

Designing the programme we recognised that many international donors are operating in Mexico, as are domestic actors. We have focused on those areas which, in addition to meeting our four main principles (primary benefit, secondary benefit, value for money, strategic fit), offer the clearest argument for British intervention, defined on the basis of three criteria:

UK area of expertise. As a developed market economy, the UK has strong expertise in building a strong, rules-based, business-friendly framework for private enterprise. There is also specific sector knowledge in areas such as energy or financial services, and UK cities are a wealth of experience in designing urban centres of the future to marry economic, environmental and equity imperatives.

Gap in the market. Although many donors operate in Mexico, very few focus on the market framework. Instead, EU countries have chosen to prioritise climate and resource-management issues. The U.S. (with a large programme) has focused mostly on security. Donors such as the World Bank (WB) and OECD have tended to fund mostly technical assistance and analysis, rather than more innovative approaches. We are directing this programme at niche areas where relatively small interventions can have a ‘leverage effect’ via changes in legislation or the creation of pilots.

HMG ability to make a difference. The Mexico programme builds on our previous Prosperity Fund programming, which, in addition to the Dual Year of UK and Mexico in 2015, has built a great deal of momentum behind our programme activity. We are building on this excellent reputation, particularly in regards to energy, where our work has helped Mexico become a global leader on climate advocacy and reform its energy sector incorporating best practice on energy regulation and auction processes. In this we can draw on synergies with other UK funds in Mexico, such as the International Climate Fund or the Newton Fund where UK companies are also well placed in these fields.

	Mexican challenges	Specific UK added value / USP
Energy	Without better regulation, Mexico’s energy sector will not attract quality investment and deliver full potential impact of reforms to the wider economy. / A new regulatory environment following de-nationalisation of the electricity, and oil and gas markets. / Mexico’s poor health and safety record in the energy sector is a barrier for international investors. / Skills gap: technical requirements of deep-water oil and gas extraction. / Policies to include clean and affordable energy in support of industrial productivity and economic growth.	World class regulatory bodies (OFGEM, OGA, HSE). / Experience of energy sector privatisation and market liberalisation. / Experience of exporting Health and Safety best practice. / World leader on deep-water oil and gas extraction. / Innovative financial solutions for the energy sector (PPPs, ESCOs, UK Export Finance). / 1st country to incorporate climate change objectives into national energy strategy.
Future Cities	Mexico faces huge challenges to meet the needs of a growing urban population, particularly on mobility. / Poor transport policies can increase pollution, generate health problems, facilitate gender violence and limit social mobility and economic growth. / Challenges in coordination between various planning agencies in urban environment – barrier to unlocking economic potential in cities. / Skills gaps: technical requirements (big infrastructure project management, construction, security planning). / Increasingly educated urban middle class keen to play a role in innovation to improve lives of population – in need of pairing with international entrepreneurship.	Experience of exporting sustainable city regeneration. / World leader in use of open government and open data innovation (TFL, Thompson Reuters, Arup, Syngenta, Digital Marketplace). / World leader in monitoring pollutants and producing evidenced based public policy on transport and pollution (Kings College, Imperial). / World leader in integrated transport systems and sustainable mobility solutions. / World leader on the use of human resources for the development of a digital economy (UK Digital Strategy, Tech City UK, The future of work: jobs and skills 2030). / World-class examples of big infrastructure projects (Wembley, Eurotunnel, Heathrow, London 2012, Cross Rail).
Financial Services	Large percentage of population (particularly in rural areas) lacks access to and an understanding of financial services (including bank accounts, savings, insurance, pensions). / Financial mechanisms are inefficient, restrictive and outdated, which prevents financial inclusion of individuals and business from growing sustainably and to their full potential. / Lack of financing mechanisms to allow capital growth, business security, and investment in projects required to allow Mexico to transition to a dynamic and low-carbon economy. / Lack of financial services regulatory framework.	World leading Financial Services Capital. / World leader on Financial Services Technology (Fintech) solutions. / World leader on Green and Social Finance. / Global centre of carbon trading. / World leader on insurance and reinsurance. / World leader on PPPs. / Leader on Financial Service reforms after the economic crisis.
Anti-Corruption & Rule of Law.	Lack of enforcement of laws by institutions. / Lack of capacity and technology/systems for law enforcement. / Ineffective institutions, lack of coordination, collusion with organised crime.	World leader on anti-bribery and anti-corruption legislation and implementation. / Experience of advising on police reforms (Northern Ireland, Scotland Yard). / UK Rule of Law systems seen to be leaders in international standards. / World leader on post-conflict policing and justice (Northern Ireland). / World leader on community policing. / Bilateral Memorandum of Understanding (MoU) signed on Anticorruption, Transparency and Open Government. / Experience of advising on anti-corruption and anti-money laundering reforms (MoJ, SFO, amongst others).

Rationale for four-sector programme approach
This case sets out the potential to increase economic growth and reduce poverty in Mexico based on an assessment of the domestic and international political and economic context. Having considered the analysis of poverty and gender inequality in Mexico, we identified a long-list of interventions across different policy areas that have the potential to deliver primary and secondary benefits. The selection of the long-list of policy areas was informed by a country diagnostic (summarised in the context section of this case) and extensive engagement with stakeholders in Mexico. This long-list of potential interventions has been considered in the context of the primary and secondary benefits they would deliver, the strategic fit with Mexico’s priorities and the UK’s priorities, set out earlier in this case, and where the UK could add most value based on areas where the UK holds unique expertise. Potential areas for intervention were assessed against the following Critical Success Criteria:

- Primary benefit
  - Poverty alleviation
  - Inequality reduction
  - Inclusive economic growth and greater productivity
  - Increase investment flow
  - Fostering a sustainable economy
- UK’s experience/transferability of advice
- Fit with Mexico’s priorities (addressing the challenges to Mexico’s future set out earlier in this business case)
- Secondary benefit (including influence): open up opportunities for business, especially those where the UK is well-positioned to benefit

These criteria were weighted based on importance and then graded on a scale of 0-5 (0 being ‘does not deliver’ and 5 being ‘fully delivers’). The scores below were determined with input from internal and external stakeholders through consultations and roundtables.
Criteria and weighting	Primary	Fit with Mexico’s priorities	UK’s experience/ / transferability of advice	Secondary	Total
	35%	25%	20%	20%
Agriculture	4	2	2	1	2.5
Anti-Corruption and Rule of Law	5	4	4	3	4.15
Education	4	3	3	4	3.55
Energy	5	4	5	5	4.75
Financial Services	4	4	5	4	4.2
Future Cities	5	4	4	4	4.35
Health	4	3	3	4	3.55
Mining	1	1	1	2	1.2
Telecoms	2	2	2	3	2.2
Trade	4	4	3	2	3.4
Water and Sanitation	4	3	3	1	2.95

As set out in the table, we have prioritised four sectors for the programme. In each case we will focus on areas where there is an ongoing domestic reform or investment programmes which we can support and influence with UK expertise. Each strand will help to address the four challenges for Mexico’s future outlined earlier in this case:
Energy is the highest value sector for the Mexican economy. It is therefore the greatest potential driver of the Mexican economy in terms of investment, job creation, value creation and a driver of education (addressing challenges 3 and 4 set out earlier in this case). It is also the sector where the greatest value opportunities for international business exist.

Future Cities faces the biggest challenges given Mexico’s demographics and growing urban population. These challenges therefore represent the greatest opportunity for growth in terms of driving innovation and investment and unlocking social mobility (addressing challenge 4 set out earlier in this case). Building on our current Prosperity Fund Programme, we have also demonstrated UK leadership in the sectors of mobility, digitalisation and infrastructure.

Financial Services is the sector with the greatest potential for impact across the economy because of the lack of financial mechanisms to allow investment. This is therefore a fundamental enabler of the theory of change: supporting the financial reforms and enabling investment (both domestic and international, public and private) will have a growth-enabling effect across the key sectors (addressing challenge 4 set out earlier in this case). It also has the potential to drive financial inclusion. The UK has a key advantage in this sector because of the City of London, our burgeoning Financial Technologies (Fintech) sector, and innovative financing models such as Green Finance and Public Private Partnerships (PPP).

Anti-Corruption and Rule of Law, is the single biggest brake on Mexico’s growth and repeatedly identified by British businesses as being the reason for them not to enter the Mexican market. This is another fundamental cross cutting element to our theory of change as, without improvements in the Anti-Corruption and Rule of Law, the impacts of Mexico’s economic reforms and opportunities for international business will be more limited.

### Programme overview and theory of change

The Theory of Change set out below has been designed through extensive engagement with beneficiaries and implementers across all sectors. The logical steps that lead from inputs to activities to outputs to outcomes to the high-level impacts are based upon the following assumptions.

Input assumptions:
- Engagement with private and public sectors to foster capacity building.
- Change of government does not affect the purposes of the programme.
- Continued improvements on the perception of competitiveness and reduced index of corruption.

Activity assumptions
- Change of government party does not affect poverty-reduction ambitions.
- Keep relevant governmental institutions with skilled human capital.
- Federal and Local government willingness to implement and develop.
- Other law enforcement institutions cooperate.

Output assumptions
- Continued improvements on the perception of new mechanisms.
- Enough international and domestic finance (increase in domestic saving).
- Federal and Local government willingness to implement.

Outcome assumptions
- Key population areas are accessible and responsive to change initiatives
- Investment able to be replicated: good governance, stability and coordination

The ultimate goal is poverty reduction in Mexico, however our expectations are for long-term sustainable improvement beyond the life of the Programme, results within the programme’s four years are anticipated to be modest.

Programme Level Theory of Change
What is the developmental problem?
Impact	Outcomes	Intermediate Outcome	Outputs
A relationship that promotes growth between UK and Mexico: / Higher rates of sustainable growth in Mexico / Greater investment flows / Greater trade flows	Improved conditions for growth in Mexico, through increased capacity and an improved environment for trade and economic growth	1. More efficient detection and investigation of serious and organised crime and corruption cases	1. Agreement of standards and processes for identifying and investigating serious crime and corruption. / 2. Scale up of a specialized training programme on identifying and investigating serious crime and corruption. / 3. Greater recognition of the roles, responsibilities and handover points between different actors involved in the investigation or serious crime and corruption.
		2. More productive and resilient men and women, businesses and government officials to support Mexico’s transition to a low carbon economy.	1. Larger pipeline of certified male and female specialists to meet industry demand and a local workforce that is resilient to economic shocks; / 2. Incorporation of market ready local male and female-owned Small and Medium-Size Enterprises (SME) in the supply chain of Multi-National Companies (MNC) in the energy sector; and / 3. Increased levels of technical proficiency amongst regulators and male and female officials that uphold adherence to international standards in the Energy Sector.
		3. More inclusive and competitive Financial Services sector, accessible to all sections of Mexican society and new international entrants.	1. More financially literate male and female consumers who feel greater trust in Financial Services institutions and have the ability to use formal financial services / 2. Supportive regulatory environment for the Fintech sector that works for both men and women. / 3. Increased number of (MSMEs) procuring Fintech solutions that provide financing alternatives; and allowing for more accessible, cashless transactions for men and women.
		4. Improved efficient urban development in Mexico’s cities that results in better, safer and more sustainable public services for citizens, particularly women and girls	1. Improved governance, decision-making and planning mechanisms for urban mobility services within Mexico’s cities; / 2. Adoption of strategies tested in successful pilots to deliver better urban mobility services, particularly for women and girls in Mexico’s cities.

## Strand 1: Energy

#### Key Facts
- Approximately 3.9 million households live in extreme energy poverty in Mexico[33]
  [33] “Privation of energy services in Mexican households: An alternative measure of energy poverty”, García Ochao and Graizbord, 2016, http://www.sciencedirect.com/science/article/pii/S2214629616300767
- The OECD estimates that from 2005 to 2009 energy subsidies accounted 1.5% of the average annual GDP; in 2008, 10% of the richest population received 9 times more energy subsidies than the resources received by the poorest 10%[34]
  [34] “Mexico: Better Policies for Inclusive Development”, OECD, 2012, http://www.oecd.org/publications/mexico-better-policies-for-inclusive-development-9789264201682-en.htm

With an expected 13% decrease in electricity prices, the energy reform could increase manufacturing output by 3.6% and GDP by 0.6%[35]
[35] “Made in Mexico: Energy Reform and Manufacturing Growth”, IMF, 2015,https://www.imf.org/external/pubs/ft/wp/2015/wp1545.pdf

Context
Energy is one of the highest value sector for the Mexican economy currently undergoing development. Current energy policy in Mexico aims to strengthen the sector, increase production and subsequently boost national economic growth.
##### Current state of the sector
Energy poverty, or fuel poverty, is an issue in Mexico: 8.9 million Households do not have access to at least one energy service, and approximately 3.9 million live in conditions of strong or extreme energy poverty (lack of 4 and 5 services respectively). The two main contributing factors to energy poverty in Mexico are geographical location and income. For example, with a quarterly per capita income of less than $7,000 MXN (around £282) the odds of living in extreme energy poverty are increased by 575%. Likewise, the odds of living in extreme poverty are reduced by 93.6% when a household is located in an urban area. Insufficient and inadequate pipeline infrastructure can often leave entire states cut off while the outdated and deteriorated transmission lines have high levels of energy loss in transmission and distribution shortages[36]. Improved energy services are a necessity for meeting nearly all the UN SDGs.
[36] “Estrategia Nacional de Energía 2012-2026”, Secretaria de Energía (SENER), 2012 https://www.gob.mx/sener/prensa/mexico-a-la-vanguardia-en-eficiencia-energetica

Energy poverty links closely to gender inequality. Affordable and reliable energy can enable the diversification and modernization of productive activities and thereby lead to increase in employment opportunities and access to education for women and girls.
#### Primary Purpose: economic development and poverty reduction in Mexico
##### Programme contribution to UN’s Sustainable Development Goals (SDGs)

In addition to supporting the crosscutting goal of No Poverty (SDG 1), the Energy strand will support Mexico in achieving the following UN’s Sustainable Development Goals (SDGs) by addressing some of the top constraints to growth outlined over the page:

Proposed interventions	SDG goal	Impact
Intervention 1: Targeted skills development and certification to international standards of male and female specialists to meet industry demand and create a local workforce that is resilient to economic shocks	5 - Achieve gender equality and empower all women and girls. / 8 – decent work and economic growth	The programme will support the skills development of the workforce with a key focus on promoting female empowerment to ensure that both men and women alike can take advantage of higher paid and better quality jobs in the energy sector. It will also prepare the local workforce with transferable skills across in related industries to mitigate the impact of economic shocks (e.g. Fall in oil price) and to support the transition to a low carbon economy.
Intervention 2: Capacity building for male and female-owned SMEs to support market-readiness and supply chain connectivity.	5 - Achieve gender equality and empower all women and girls. / 9 – industry, innovation and infrastructure	The programme will support the development of local SMEs to improve their market-readiness and facilitate connections with large MNCs and investors. As three in five SMEs[37] are run by women, this intervention will also have a positive impact on gender equality.
Intervention 3: Capacity building for energy regulators to promote best practice in the implementation and enforcement of regulation.	7- affordable and clean energy / 9 – industry, innovation and infrastructure	The programme will focus on improving the regulatory environment to support the continued development of the energy sector. Through sector development, the Mexican population will have access to cleaner and more affordable energy.
[37] “Nafin impulsará con más créditos el programa "Mujer Pyme” en 2017”, Nacional Financiera (NAFIN), 2017

##### Top constraints to growth and poverty reduction

CONSTRAINT 1: CAPACITY, TECHNOLOGY AND INFRASTRUCTURE

Mexico has limited institutional capacity and is lacking technological solutions and infrastructure to exploit its extensive oil and natural gas reserves. Several new agencies and regulators while existing institutions have taken on new responsibilities and processes. For example, Mexican Petroleum (PEMEX), is still the largest player in the oil and gas sector in Mexico, and does not have sufficient resources and capabilities to take advantage of its extensive oil and gas reserves. Empowering these institutions not only with the necessary legal power but also with adequate resources and capacity is essential to guarantee that the continued development of a transparent and productive sector. Estimates suggest that at least 2.5 million formal jobs may be created by 2025 from increased investment and production in the entire energy sector, however, the necessary skills and capacity must be in place to ensure that this job creation leads to growth.[38] As three in five SMEs are female owned in Mexico, this is also a significant area of opportunity to improve gender equality by empowering female business owners and supporting their incorporation into the formal labour market. Finally, the fall in oil price has had a significant effect on oil-dependent local communities that are still recovering from a high-level of unemployment and lower productivity. There is a clear need to prepare these communities against economic shocks through improved revenue management and diversification of skills and productive activities.
[38] “Reforma energética”, Secretaria de Gobernación (SEGOB), 2016, http://cdn.reformaenergetica.gob.mx/explicacion.pdf

CONSTRAINT 2: POLICY AND REGULATION

There will be a need to support the current administration with the development of technical regulation and policies to support their ambitions in the energy sector. One of these ambitions is to increase oil production in the energy sector and as such, greater energy output, combined with increased efficiency should have a direct effect on energy prices, particularly in electricity, natural gas and petrol. A reduction in energy costs will support economic growth as both businesses and consumers will have more income to spend on productive activities, thus increasing consumption.

CONSTRAINT 3: FINANCE

Mexico requires innovative financial mechanisms to support energy efficiency and renewable projects in a context where public finances have significant internal and external pressures. Innovative financial mechanisms are a key tool for SMEs to reduce energy costs and thus increase investment in productive activities.
##### Gap for Prosperity Fund Interventions

Despite strong growth predictions, Mexico’s energy sector is set to underperform against its potential. Based on analysis carried out by multidisciplinary teams at the British Embassy (in line with Her Majesty’s Treasury (HMT) Green Book guidance), engagement with Mexican government stakeholders and other donors, it was determined that the Energy Strand should focus on actions to combat two of the main constraints to growth: building capacity and supporting policy and regulatory development.

There are clear opportunities to support Mexico in the resolution of these constraints to have direct and indirect a positive effect on poverty reduction in the following areas:

- Local workforce and SME capacity. The UK is a recognised global centre of subsea excellence in terms of skills, expertise and technology. The development of a suitably skilled talent base in the wider energy sector could benefit from the UK’s long experience of supporting the education sector to respond strategically to industry’s requirements. The UK also has significant expertise to share around the certification of specialists, which is identified as a key shortfall in the current workforce. There is an area of opportunity in working with female-owned SME’s to have a greater impact on poverty reduction and gender equality.
- Policy and regulation. The UK has extensive experience in energy related regulation as well as some of the most prestigious universities and training programmes in the world. The UK can support Mexico in the continued development of strong regulations that will create the market conditions to support an open and transparent business environment in the energy sector and, thus, more competitive energy prices. Knowledge of the UK’s world-renowned Health and Safety standards will help design the tools to adequately prevent major accidents and reduce financial, reputational and social consequences for government, operators and the Mexican population. The UK recognises the importance of assessing social and environmental impact and is thus a priority in energy projects design. The UK can share experience on developing clear and fair regulation for social and environmental risk management procedures such as consultation, assessments, resolution of conflicts and particularly, impacts on marginalised communities and women.

##### Delivery of primary purpose

The Energy strand primarily aims to support Mexico’s efforts to provide decent work and economic growth (SDG 8) and affordable, clean energy (SDG 7). Evidence in the literature links the benefits of improving workforce skills in the energy sector and its impact on the labour productivity and overall economy[39]. As estimated by Banxico, until 2014, oil-related revenue typically accounted for between one-third and 40% of total government income[40]. Once production increase in the sector, the revenue received by the government from royalties paid by international companies operating in Mexico will increase. This revenue, which is held in the Mexican Petroleum Fund (Fondo Mexicano del Petroleo) and administered by Banxico assigns a percentage of these resources to a number of different funds that support development programmes such as investigation and scholarships. Given that the energy sector hires relatively high-skilled workers, the compensation per worker in energy-related industries is four times the average in Mexico. Therefore, improvement in workforce skills in the energy sector reflects an increase in Labour Productivity Output (USD/worker) which results in a boost in economic output.
[39] http://www3.weforum.org/docs/WEF_EN_EnergyEconomicGrowth_IndustryAgenda_2012.pdf
[40] https://www.iea.org/publications/freepublications/publication/MexicoEnergyOutlook.pdf
##### What the Energy Strand will do and how

Our Energy Strand will focus on improving capacity and capabilities within the workforce, industry and government institutions to support the continued development of the oil & gas, electricity, renewable and energy efficiency sectors. Detailed strand activities will be determined during the inception phase however; these will focus on delivering the outputs described below. Fragmentation is a key risk which we will expect our implementers to mitigate when designing the programme. The programme will have three large interventions:

  1. Targeted skills development, and certification to international standards of male and female specialists, to meet industry demand and create a local male and female workforce that is resilient to economic shocks;
  2. Capacity building for local male and female-owned SMEs to support market-readiness and supply chain connectivity; and
  3. Capacity building for energy regulators and male and female officials to promote best practice in the implementation and enforcement of regulation.

The Energy programme will also have an ‘Agile Programme Fund’: a Facility run by the implementer (in consultation with Embassy) to fund nimble targeted smaller-scale projects which either complement and support larger interventions, or allow us to pilot measures which can be scaled up in future years of the programme. This, in line with an active portfolio management approach, will mitigate uncertainty of exact future Federal Government policy during the early stages of implementation of Mexico’s National Development Plan. This approach will also prepare the ground for future interventions in the event of an extension of the Prosperity Fund into the next Spending Review.
#### Secondary benefits to international business

The opening up of the energy market represents an opportunity for international businesses but barriers to entry mean that in some cases they are unable, or unwilling to take advantage of them. Significant investment will be taking place over the coming years – for example, the Ministry of Energy expects investments of around $16 billion USD (£13 billion) by 2019 to expand the National System for Transportation and Storage of Natural Gas.

The Energy programme will open opportunities to international business by:
- Sharing UK regulatory expertise to guide regulation and policy development in the energy sector in the form of action plans, road maps and pilots paving the way to an attractive, open and transparent market for international businesses.
- Developing innovative finance solutions which could enable a significant scaling up of finance in Mexico to develop Energy projects, creating a large pipeline of projects to invest in while ensuring project viability and high technological performance.
- Supporting Mexico to introduce more transparent procurement practices which could make more opportunities available to the international market.

Strand 2: Future Cities

#### Key Facts
- 87% of Mexico’s Gross Value Added (GVA) is produced in cities with a population of over 100,000.[41]
  [41] World Bank (2016). Mexico Urbanization Review: Managing Spatial Growth for Productive and Liveable Cities in Mexico. Retrieved June 30, 2017 from https://openknowledge.worldbank.org/handle/10986/24930.
- 83% of Mexico’s population will live in cities by 2030.[42]
  [42] Diario Oficial de la Federación – Mexico’s Official Journal of the Federation (2014). National Urban Development Programme 2014-2018. Retrieved June 25, 2017 from http://www.dof.gob.mx/nota_detalle.php?codigo=5342867&fecha=30/04/2014
- Poor mobility causes a daily loss of 3.3 million man-hours: Mexicans in metropolitan areas have an average daily commute of 2.5 hours.[43]
  [43] UN Habitat (2015). Mexico National Urban Mobility Report. Retrieved June 25, 2017 from http://www.onuhabitat.org/Reporte%20Nacional%20de%20Movilidad%20Urbana%20en%20Mexico%202014-2015%20-%20Final.pdf
- The emissions generated by vehicles represent up to 60% of the total pollution by coarse suspended particles, and according to the World Health Organization (WHO), every year 14,700 people die in Mexico due to diseases associated with air pollution[44]
  [44] UN Habitat (2016). Pollution, cars and air quality. Retrieved June 25, 2017 from http://onuhabitat.org.mx/index.php/contaminacion-automoviles-y-calidad-del-aire
- Private cars generate 18% of CO2 emissions, the main gas that causes the greenhouse effect. This phenomenon costs up to 6% of Mexico’s GDP[45].
  [45] United Nations (2014). World Urbanization Prospects. Retrieved June 25, 2018 from https://esa.un.org/unpd/wup/publications/files/wup2014-highlights.pdf
- Interventions designed to improve mobility and increase digitalisation services in Mexico could result in £166m increase in real GDP from 2017-2026.

#### Context – how do Future Cities contribute to poverty reduction and economic growth?
The Future Cities sector represents the greatest opportunity for growth in Mexico in terms of unlocking social mobility and driving innovation and investment. Mexico’s demographic trajectory means 83% of the population is expected to live in cities by 2030. This demographic trajectory represents an opportunity to drive economic growth in the country and the potential to reduce poverty. 46However, urbanisation can also bring challenges – for example, increasing costs of public services, pollution and traffic congestion in the transport system. Realising the potential gains of urbanisation will depend on how well urban growth and its evolving challenges are planned and managed, and the extent to which the benefits accruing from urbanisation are equitably distributed. If poorly planned and inadequately managed, urbanisation could result in the proliferation of slums, poverty, more unequal, less productive and less habitable cities[46].
[46] UN Habitat (2016). Urbanization and Development: Emerging Futures, World Cities Report. Retrieved June 25, 2017 from http://wcr.unhabitat.org/wp-content/uploads/2017/02/WCR-2016-Full-Report.pdf

##### Current state of the sector

In Mexico, urbanisation is an essential component of economic growth, resulting from positive externalities such as lower costs of transportation, better logistics, more innovation and economies of scale. According to El Colegio de Mexico, a 1% increase in urbanisation rates would lead to a 4.5% increase in Mexico’s GDP whilst Standard and Poors estimate that every 1% GDP invested in urban infrastructure will lead to a 1.3% increase in economic growth. Sustainable urbanisation such as integrated transport systems would bring services closer to users, increasing levels of social inclusion, including gender equality.

Mexico’s existing cities face severe challenges which directly impact upon citizens – air pollution accounted for 3.1 million medical appointments in 2013-14[47]; in Mexico City 65% of women have been victims of some type of gender violence on public transportation or at mass transport stops, terminals or platforms[48]; and road transport emissions account for around 94% of overall transport emissions.
[47] Mexican Institute of Competitiveness (2013). The air pollution: a problem that harms the health and the economy. Retrieved June 25, 2018 from http://imco.org.mx/wp-content/uploads/2013/09/IMCO-Presentaci%C3%B3n-Corta-24Sep13.pdf
[48] World Bank (2014). Sexual harassment: the high cost of being a woman in a bus. Retrieved June 25, 2017 from http://www.bancomundial.org/es/news/feature/2014/09/08/gender-violence-public-transportation
#### Primary Purpose: economic development and poverty reduction in Mexico
##### Programme contribution to UN’s Sustainable Development Goals (SDGs)

The Future Cities strand will aim to support Mexico in achieving the UN’s Sustainable Development Goals (SDGs) by addressing a number of barriers outlined below. In particular:

Table 4
Proposed interventions	SDG goal	Impact
Intervention 1: Improved governance, decision-making and planning mechanisms for urban mobility services within Mexico’s cities	1 - End poverty in all its forms everywhere / 5 - Achieve gender equality and empower all women and girls / 9 - Industry, innovation and infrastructure / 11 - Make cities inclusive, safe, resilient and sustainable. / 13 - Take urgent action to combat climate change and its impacts.	The programme will look to / Contribute to the objective of eradicating extreme poverty by 2030 by increasing productivity, employment opportunities for men and women, and large-scale investment in transport services, therefore improving quality of life and decreasing the vulnerabilities of excluded population in urban areas. / Empower women by providing better and safe transport systems. / Share international best practices with the Mexican government with the aim of delivering more and better sustainable mobility mechanisms. / Contribute to the UN’s Goal 11 by providing access to safe, affordable, accessible and sustainable transport systems for all, with special attention to the needs of those in vulnerable situations, including women and children. / Support Mexico’s targets adopted through the New Urban Agenda and COP 21, including tackling health risks related to poor air quality in cities.
Intervention 2: Adoption of strategies tested in successful pilots to deliver better urban mobility services, particularly for women and girls in Mexico’s cities y.

##### Constraints to inclusive growth and poverty reduction
###### CONSTRAINT 1: Planning and technical capacity needs

Urban transport planning, management and operations is complex, requiring: 1) strong and cooperative institutional structures; and 2) wide range of skills and capacity to develop and implement holistic and multi-sectoral approaches, integrating aspects of economics, engineering, politics, communications, urban design and environment.[49] Challenges on planning and technical capacity needs at national, state and local governments prevents enforcement and compliance control. The traditional, generalist transport planning approach, which emphasizes the movement of cars by expanding infrastructure has been a key focus of cities in Mexico.
[49] World Bank (2013). Leaders in urban transport planning. Retrieved June 2018 from http://www.worldbank.org/content/dam/Worldbank/document/transport/LUTP_V10-print-reduced-size.pdf

##### CONSTRAINT 2: Coordination between governmental structures and levels
There is no existing organism at the national level responsible for coordinating sustainable urban mobility plans (UN-HABITAT, 2011). The short three year term of municipal administrations brings challenges to long term planning of mobility services. The autonomy of state authorities can be limited, as they depend financially on the federal government to make investments in urban mobility services. Strengthened coordination of the three branches of government (federal, state and municipal) would help achieve greater and better movement of people.
##### CONSTRAINT 3: Innovative funding and financing methods and instruments

Access to finance is a barrier for the Mexican Government in delivering its ambition for the development of cities in Mexico; there is an opportunity to improve the governance structures needed to address and monitor the financing and creation of projects. For example, with the implementation of federal and local fiscal policy actions oriented to a user-financed model that allows for the generation of the necessary resources for the financing of public and non-motorised transport; and introducing measures such as the establishment of environmental fees for automobiles directed to reducing externalities.

##### Negative externalities
Transport policies play a fundamental role in the development of a country’s economic activities. The indiscriminate use of the automobile generates a big number of negative impacts at the economic, environmental and social level throughout Mexico’s cities; therefore, a well-designed urban mobility plan is predominately important to improve economic and social development and quality of life of citizens.[50] It is estimated that the economic losses derived from the negative externalities from car use represent an average of 4% of GDP of the largest five metropolitan areas in the country, of which 42% of the country’s urban population is concentrated (Medina, 2012). According to the WHO, every year 14,700 people die in Mexico due to diseases associated with air pollution, which is a result of public policies that have not considered the entire mobility spectrum.
[50] Institute for Transportation and Development Policy (ITDP Mexico). Transforming Urban Mobility in Mexico. Retrieved March, 2018 from http://mexico.itdp.org/wp-content/uploads/Transforming-Urban-Mobility-in-Mexico.pdf

##### Gap for Prosperity Fund Interventions
Analysis was carried out by multidisciplinary teams at the British Embassy (in line with HMT Green Book guidance), to match UK capabilities with market barriers through engagement with Mexican government stakeholders and other donors. The analysis determined that the Future Cities programme should focus on the barriers to growth set out above in the following areas: mobility, digitalisation and infrastructure (with infrastructure and digitalisation being a key area of focus through smaller scale programme interventions).

There are clear opportunities to support Mexico in the resolution of the above constraints in the following areas:

    - Sustainable mobility services: Comprehensive mobility planning facilitates an optimized use of capital in relevant projects, and enhances the economic competitiveness of cities by improving logistics and access to jobs, basic services and education, amongst others. It is therefore crucial and urgent to develop and implement sustainable mobility policies in urban areas to achieve the following objectives:
    - Reduce the number of urban trips by conventionally fuelled transport through transport planning integration;
    - Promote a modal shift towards active modes and public transport, as well as a structural change in vehicle use;
    - Improve vehicle energy efficiency, in particular through the transition to electric vehicles.
##### Delivery of primary purpose

The primary objective of the Future Cities strand is to support Mexico’s efforts to strengthen sustainable cities supporting Goals 11 (sustainable cities and communities) and 9 (industry, innovation and infrastructure) of the UN SDGs.

##### What the programme will do and how

Our Future Cities programme will focus on improving capacity and capabilities particularly within government institutions, across different Mexican cities. Detailed programme activities will be determined during the inception phase of the programme. However, we expect these to focus on delivering the outputs described below. Fragmentation is a key risk which we will expect our implementers to mitigate when designing the programme. The programme will deliver two large interventions:

1. Improved governance, decision-making and planning mechanisms for urban mobility services within Mexico’s cities;
2. Adoption of strategies tested in successful pilots to deliver better urban mobility services, particularly for women and girls in Mexico’s cities.

The Future Cities programme will also have an ‘Agile Programme Fund’: a Facility run by the implementer (in consultation with Embassy) to fund nimble targeted smaller-scale projects which either complement and support larger interventions, or allow us to pilot measures which can be scaled up in future years of the programme. This, in line with an active portfolio management approach, will mitigate uncertainty of exact future Federal Government policy during the early stages of implementation of Mexico’s National Development Plan. This approach will also prepare the ground for future interventions in the event of an extension of the Prosperity Fund into the next Spending Review.
#### Secondary benefits to international business

The Mexican Future Cities market offers significant opportunities. For example, over the past five years, the transport sector has experienced an average growth of 13% and digitalization has experienced an average growth of 4%. The total size of the Future Cities market currently far exceeds £100m each year, through exports of vehicles from the UK to Mexico. The government’s transport and infrastructure plans represent an opportunity for international businesses, but barriers to entry mean that in some cases they are unable or unwilling to take advantage of these.

The Future Cities programme will open opportunities to international business by:
Improving sustainable transport planning;
- Developing new financial mechanisms;
- Improving capacity to deliver digital projects within public organisations

### Strand 3: Financial Services

#### Key Facts
Only 36.9% of adults 15+ in Mexico own a bank account.[51]
[51] “Global Financial Inclusion Index“, World Bank, 2018,
In Mexico, remittances account for 2.7% of GDP, equivalent to a market of up to £18bn[52].
[52] “Personal remittances, received (% of GDP)”, World Bank, 2015. https://data.worldbank.org/indicator/BX.TRF.PWKR.DT.GD.ZS?locations=MX
Financial Technology start-ups could capture 30% of Mexico’s banking market within ten years.[53]
[53] ”Las Fintech gestionarán 30% del Mercado bancario para el 2027”, Expansión, 2017. https://expansion.mx/tecnologia/2017/01/31/las-fintech-gestionaran-30-del-mercado-bancario-en-mexico-para-2027
Large amounts of investment will be required to finance Mexico’s transition to a low carbon economy, with $5bn a year needed for clean energy alone.[54]
[54] “Estudio sobre las inversiones necesarias para que México cumpla con sus metas de energía limpia”, PWC, 2015, https://www.pwc.com/mx/es/industrias/energia/archivo/20151018-gp-cespedes.pdf
Mexico is the UK’s second largest export market for Financial Services in Latin America[55].
[55] HMT Analysis
Through this programme’s contributions to unblocking barriers for financial inclusion and implementing innovative financing mechanisms, a £200 million increase in Mexican GDP could be achieved.[56]
[56] “Primary Benefit Methodology and Calculations”, British Embassy Mexico City Economic Unit, 2018
#### Context – how do Financial Services contribute to poverty reduction and economic growth?

The primary purpose of the strand is to increase the depth, coverage and efficiency of financial services in order to promote sustainable growth and development. Development of the financial services sector has been driven by the overarching goal of increasing the financial sector’s contribution to economic growth, including through increasing competition across the sector, promoting greater financial inclusion and strengthening development banks, including through the ‘Financial Reform’ which was passed in 2013. There is a significant appetite from both the public and private sector to modernise the financial sector and fully exploit its economic potential, particularly given the considerable degree of consolidation of Mexico’s financial markets, coupled with relatively underdeveloped capital markets in terms of size, liquidity and efficiency. There is a significant appetite from both the public and private sector to modernise the financial sector and fully exploit its economic potential. The Mexican government is working to develop a financial system where all of Mexican society can benefit; this strand of the programme will expand and open the financial sector in Mexico to drive its contribution to poverty reduction, productivity and inclusive social and economic development through driving financial inclusion, increasing access to finance and the development of innovative financial mechanisms.
##### Current state of the sector

While there is no single way of combating inequality to combat inequality in Mexico, improving the Financial Services sector has the potential to provide the greatest impact across the economy, because of the current lack of:
1. Financial Inclusion to drive social and economic growth and mobility for vulnerable Mexicans, 58% of whom work in the informal economy,[57]
  [57] “Es informal el 58 por ciento del empleo”, El Financiero, 2016
2. (ii) developed Financial Mechanisms to encourage inclusive and sustainable growth.
High levels of informality, lack of access to credit and geographical inequality have all been identified as factors keeping financial inclusion in Mexico below regional averages.
While some of Mexico’s problems are cultural, e.g. people not trusting banking institutions, primarily they are structural. Requirements to access financial services and products are beyond the reach of many, and there is a need to make it more attractive for actors to provide products, services, and credit to the underserved portion of the population.
According to the World Bank, increasing access to financial services has a direct effect on inequality and growth. Within less-developed financial markets, individuals’ economic opportunities are determined by wealth, social status and political influence, rather than by individual skills and initiative. This shapes capital allocation throughout the economy, increasing the long-term income gap between poor and rich households.[58] The consequence of this lack of access is that there is a significant amount of people in emerging economies who are under-served.[59]
[59] “The Role of the Financial Services Sector in Expanding Economic Opportunity”, Sutton, C. & Beth, J. , 2007.
Within its latest Global Findex Database[60] the World Bank shows that mobile phone ownership is widespread among the unbanked. In the case of Mexico, the World Bank estimates that around 66.6% of the unbanked own a mobile phone. This shows the potential for fintech for financial inclusion and poverty reduction purposes.
[60] The Global Findex Database”, World Bank, 2017, https://globalfindex.worldbank.org/
#### Primary Purpose: economic development and poverty reduction in Mexico
##### Programme contribution to UN’s Sustainable Development Goals
The Financial Services programme will support Mexico in achieving the UN’s SDGs by addressing the top constraints to growth identified below. In particular:
Table 51
Proposed intervention	SDG Goal	Impact
Intervention 1: / Increasing financial inclusion for female beneficiaries of Mexico’s largest social development programme	SDG 1: End poverty in all its forms everywhere. / SDG 5: Achieve gender equality and empower all women and girls. / SDG 10: Reduce inequality within and among countries.	The programme will contribute to the UN’s targets of eradicating extreme poverty, achieving gender equality and reducing inequality by 2030 through promoting efficiency in the financial services sector by supporting the digitisation of G2P payments and improving access to finance and financial education for the base of the pyramid.
Intervention 2: / Implementation of the new Financial Technology (Fintech) law in Mexico	SDG 1: End poverty in all its forms everywhere. / SDG 5: Achieve gender equality and empower all women and girls. / SDG 10: Reduce inequality within and among countries.	The programme will contribute to the UN’s targets of eradicating extreme poverty; achieving gender equality and reducing inequality by 2030 through increasing the level of access to and use of digital finance. Promoting competition and efficiency in the financial services sector and strengthening the financial technology ecosystem in Mexico; benefitting both, MSMEs and individual financial services users, with a focus on those at the base of the pyramid.
Intervention 3: Strategic support for MSMEs and male and female users within the Fintech sector

##### Top constraints to growth and poverty reduction
Evidence suggests that the particular market failures constraining the further development Mexico’s financial services sector and its ability to support sustainable and inclusive economic growth and poverty reduction are:
CONSTRAINT 1: LACK OF ACCESS TO FORMAL FINANCIAL SERVICES FOR MEN AND WOMEN AT THE BASE OF THE PYRAMID
This is a serious growth constraint. Financial exclusion of those at the base of the pyramid caused by imperfect credit markets exacerbates inequality and impedes growth. Low levels of financial inclusion drive Mexico’s high rate of inequality (Gini coefficient of 0.46,[61] the second highest in the OECD). Those with no bank account are less likely to be well educated, to work in the formal sector, and typically have an average monthly income of $256 USD – just 60% of that those with bank accounts earn. Imbalance of information distorts development of the market and prevents people securing capital to invest in productive projects. Restricted access to financial services prevents citizens from investing their savings, protecting themselves from uncertainty, and transferring risk (demand for insurance has rarely exceeded 2% of GDP, versus 2.8% in other Latin American countries[62]), and aggravates income shocks; resulting in poverty traps.
[61] “Topics: Inequality”, Organization for Economic Cooperation and Development, 2017, http://www.oecd.org/social/inequality.htm
[62] “Opportunities and Challenges in the Insurance Industry for Mexican and British Companies”, Mexican Chamber of Commerce in Great Britain, 2016.
CONSTRAINT 2: LACK OF TRUST AND UNDERSTANDING OF FINANCIAL MECHANISMS AND PRODUCTS (INCLUDING FINTECH SOLUTIONS) BY BUSINESSES AND MALE AND FEMALE USERS

Mexico accounts for 2.6% of the 2 billion unbanked adults worldwide (higher than Brazil, Vietnam and Ethiopia at 2.4%, 2.4% and 2.1% respectively[63]) and a large proportion of the unbanked sector live day to day in a cash-based society – unable to manage their money effectively, or to save or to insure themselves against future risk. Insurance penetration – measured by premiums as a share of GDP – is low at 2.2% placing the country 57th globally, way below the OECD average of 13%[64]). Strengthening financial education is essential for speeding up the adoption and continuous, productive use of financial services.
CONSTRAINT 3: RISK AVERSION IN MEN AND WOMEN LEADING TO USE OF PRODUCTS WITH REDUCED RISK (E.G. LOWER MATURITY INVESTMENT LOANS)

From the demand side, a key barrier for financial inclusion is risk aversion from potential users. This affects men and women differently depending on social and individual background (e.g. education level). For instance, women and men in rural areas have considerably less access to formal financial products in comparison with people living in urban or semi-urban areas given that most of the financial institutions’ infrastructure and branch network are concentrated in cities. This goes hand in hand with lack of effective information services and financial illiteracy; a great barrier to adopting new technologies required for increased access to financial services.
Case studies from the World Bank show that risk aversion has a disproportionate effect on women. As a client group, women tend to be more risk-averse and less eager to borrow from formal financial institutions. The latter because they usually hold financial responsibility for their families and fear losing the collateral often required for diversification of financial services usage. As a result, they expand their business slowly, over time and with less outside capital. Given this, women tend to prefer informal savings and credit cooperatives since they are also often under higher time constraints than men.[65]
[65] “Strengthening Access to Finance for Women-Owned SMEs in Developing Countries”, International Finance Corporation, 2011 https://www.ifc.org/wps/wcm/connect/a4774a004a3f66539f0f9f8969adcc27/G20_Women_Report.pdf?MOD=AJPEREs
CONSTRAINT 4: PUBLIC SECTOR FINANCE AND LACK OF INNOVATIVE FINANCING METHODS
A large informal economy coupled with falling oil prices (in a traditionally oil-based economy) and exchange rate depreciation have impacted Mexico’s economy, affecting government tax income and government spending. According to the World Bank, in the infrastructure sector alone, the country needs approximately US$230 billion of new investments.[66] This, combined with limited capacity, particularly at sub-national level, to implement innovative financing mechanisms (e.g. Green Finance and PPPs) and to further develop its capital market to close the gap in capital needs, inhibits investment and the ability to fund sustainable development.
[66] “Mexico: Capital Market Development”, World Bank, 2013. https://openknowledge.worldbank.org/handle/10986/16747?locale-attribute=es

CONSTRAINT 5: LACK OF ACCESS TO FINANCE FOR MSMES, IN PARTICULAR FEMALE OWNED MSMES
Lack of access to finance prevents MSMEs from forming and formalising, creates barriers to entry for new firms and impedes expansion plans for established business. MSMEs tend to have a high mortality rate; out of 200,000 companies that start to operate in Mexico each year, only about 35,000 still operate two years later.[67] As such, MSMEs lack the ability to finance growth. Undeveloped capital markets also play a part.
[67] “Impact evaluation of Small and Medium Enterprise Programs in Latin America”, Lopez Acevedo, Tan, et al, 2011
According to the International Finance Corporation (IFC), SMEs with full or partial female ownership represent 31 to 38 percent of formal SMEs in emerging markets. They make up an estimate of 32-39 percent of micro firms, 30-36 percent of small enterprises and 17-21 percent of medium-sized companies.
CONSTRAINT 6: REGULATORY UNCERTAINTY
Regulatory uncertainty remains an issue for particular sectors. For example, for the Fintech market, it stifles the introduction of innovative financial technologies that may otherwise be used to increase financial inclusion. While Mexico has recently introduced its principles based law to regulate financial technology, implementation and secondary legislation are crucial to address market failures, and ensure that the Law does not represent a barrier to entry for new, innovative players. Regulating crowd funding is of great importance to ensure that resources channelled through such platforms reach their destination appropriately.
CONSTRAINT 7: UNDERDEVELOPED, NON-COMPETITIVE FINANCIAL MARKETS
While the insurance industry now aligns with Solvency II regulatory standards, market concentration is a concern with the five-top players controlling 45% of the market [68]. Low market penetration is affected by limited public policies and financial education.
[68] “Se dispersa concentración de seguros en Mexico”, El Economista, 2011
CONSTRAINT 8: GENDER RELATED BARRIERS FOR WOMEN TO ACCESS FINANCIAL SERVICES
Women’s access to finance in also shaped by non-financial barriers. These may include specific conditions related to the Rule of Law that affect women’s and men’s businesses disproportionally (such as the quality of infrastructure and legal barriers); cultural barriers limiting women’s interest or familiarity with financial institutions; poor access to information, poor social networks and risk aversion.[69]
[69] “Strengthening Access to Finance for Women-Owned SMEs in Developing Countries”, International Finance Corporation, 2011 https://www.ifc.org/wps/wcm/connect/a4774a004a3f66539f0f9f8969adcc27/G20_Women_Report.pdf?MOD=AJPERES
Gap for Prosperity Fund Interventions
##### A gap analysis carried out by multidisciplinary teams at the British Embassy (in line with HMT Green Book guidance), engagement with Mexican government stakeholders and other donors determined that the areas where UK capabilities match the constraints to growth identified for the Financial Services strand are: financial inclusion and financial mechanisms, with a particular focus on Fintech. Though other donors are working in this area, Prosperity Fund activity will use UK niche areas of expertise, such as behavioural economics and regulatory sandboxes, to complement the ongoing efforts of other actors, including the Mexican government.
##### Delivery of primary purpose
##### The Financial Services strand primarily aims to support Mexico’s efforts to create higher levels of inclusive economic growth and poverty alleviation through increased financial inclusion, and innovative financial mechanisms. Well-developed financial mechanisms are complementary to inclusive economic growth, which would allow both citizens and firms to invest their savings, protect themselves against uncertainty and obtain credit to finance consumption or invest in productive activities.
An important area of focus for Mexico will be the potential to narrow the cost of sending and receiving remittances, which currently represent more than 3% of the Mexican GDP.[70] A reduction in the cost of remittance payments could have a positive impact on poverty alleviation. Studies have shown that an increase in remittances will lead to a decline in the share of people living in poverty (Adams, R. (2004), Adams, R. Et al. (2005)).
[70] http://www.banxico.org.mx/SieInternet/consultarDirectorioInternetAction.do?accion=consultarCuadro&idCuadro=CE81
We will also leverage financial services and policy dialogue to help under-served women. By addressing data gaps, disseminating research, information and best practices, we will also encourage possible ways of addressing and help close the gender gap in Mexico.[71] Providing access to capacity building support, we will help Mexico meet their national financial inclusion. Supporting female recipients of social benefit programmes (for instance PROSPERA) would have a positive impact in increasing financial inclusion and education across female beneficiaries.
[71] “Banking on Women: Extending women’s access to financial services”, The World Bank, 2017, http://www.worldbank.org/en/results/2013/04/01/banking-on-women-extending-womens-access-to-financial-services
##### What the programme will do and how
The Financial Services programme will create a more inclusive and competitive Financial Services sector, accessible to all segments of Mexican society and new market entrants. Detailed programme delivery will be designed through Phase with the supplier; however interventions will deliver the outputs described below. The programme will deliver three large interventions:

1. Increasing financial inclusion for female beneficiaries of Mexico’s largest social development programme.
2. Support the implementation of the new Fintech law in Mexico.
3. Provide strategic support for MSMEs and male and female Fintech users.

The Financial Services programme will also have an ‘Agile Programme Fund’: a Facility run by the implementer (in consultation with Embassy) to fund nimble targeted smaller-scale projects which either complement and support larger interventions, or allow us to pilot measures which can be scaled up in future years of the programme. This, in line with an active portfolio management approach, will mitigate uncertainty of exact future Federal Government policy during the early stages of implementation of Mexico’s National Development Plan. This approach will also prepare the ground for future interventions in the event of an extension of the Prosperity Fund into the next Spending Review.
Secondary benefits to international business
Financial Services is an important market for economic development due to the positive “spill-over” effects that a sound financial services sector can have across the wider economy. As a secondary objective, the programme aims to open market opportunities to international companies, including those from the UK. Secondary benefit is expected to be generated in two ways:
1. Removing or reducing constraints to businesses in Mexico
2. Specific areas of opportunity for businesses

Opportunities include:
- Financial inclusion is a cross cutting agenda that involves banking institutions, pension funds, insurance, Fintech and social programmes.
- Technological innovation in telecoms and innovative business models offer significant opportunities for investment in SMEs, microfinance and remittance management. The UK is a centre of excellence for Fintech.
- One of the biggest areas of opportunity that can be supported through intervention 3 (the Fintech accelerator) is the application of Peer to Peer (P2P), Peer to Business (P2B) and other payment solutions in reducing transaction costs and increasing accessibility.
- An accessible pension funds market of £21bn (only £700m have been invested globally), of which the UK currently has a 4.1% market share[72].
  [72] “Beyond their Borders, Evolution of foreign investment by pension funds”, PWC, 2015.
- Mexico's infrastructure needs require investment, part of which will need to come from the private sector through PPPs. UK PPP advisors could be expected to provide advice in these infrastructure projects. UK firms can also benefit by diversifying their investment into Mexico.
- According to the Climate Bonds Initiative, the potential value of the Mexican green bonds market in the next three years is £1.4bn. The UK value from financial intermediation to the Mexican green sector is estimated to account to up to £35m, cumulative undiscounted to 2021.[73]
  [73] “Estimating the economic value and investment opportunities for Mexican and British businesses in the clean energy and green finance sectors”, Carbon Trust, 2016

Mexico’s Equity market has huge potential to grow – expected to be above 4%. Private firm Central de Corretajes has launched a second technology-powered stock market (Institutional Stock Market - BIVA) earlier this year. Both present opportunities for UK expertise and capacity building.

### Strand 4: Anti-corruption and Rule of Law
Key Facts / The cost of corruption in Mexico is as high as 10% of GDP[74], in 2015; the corruption cost was $906 billion pesos in 2015, 5% of the year’s GDP.[75] / 4.9 million acts of corruption were registered in Mexico in 2015.[76] / 93.3% of victims of corruption did not file a complaint in 2015.[77] / According to Mexican Institute for Competitiveness (IMCO), corruption reduces investment by 5% and eliminates 480,000 jobs from small and medium-sized businesses per year.[78] / Mexico is the poorest performer in safety and corruption across OECD countries.[79] / Mexico has impunity levels of around 98%.[80] According to the Mexico Peace Index[81], the total economic impact of violence in 2015 was $2.12 trillion pesos, around 13% of the country’s GDP. This is the equivalent of $17,525 pesos per Mexican citizen, or nearly two months’ wages for an average Mexican worker.[82] / In 2015, business losses from crime and expenditure on preventative measures were calculated at $139 billion pesos.[83]
[74] “Corruption costs Mexico up to 10% of its GDP”, El Universal, 2015, http://archivo.eluniversal.com.mx/in-english/2015/corruption-cost-mexico-105997.html
[75] “El costo de la corrupción en México en 3 gráficas”, El Financiero, 2017 http://www.elfinanciero.com.mx/economia/el-costo-de-la-corrupcion-en-mexico-en-graficas.html
[76] “Presentación de Anatomía de la Corrupción , Segunda Edición”, MCCI, 2016, https://contralacorrupcion.mx/presentacion-de-anatomia-de-la-corrupcion-segunda-edicion/
[77] “Estadísticas A Propósito Del Día Internacional Contra La Corrupción (9 De Diciembre)” INEGI, 2016, http://www.inegi.org.mx/saladeprensa/aproposito/2016/corrupcion2016_0.pdf
[78] “Fighting Corruption in Mexico”, Foreign Affairs, 2016, https://www.foreignaffairs.com/articles/mexico/2016-06-22/fighting-corruption-mexico
[79] “OECD Economic Survey, Mexico”, OECD, 2017 https://www.oecd.org/eco/surveys/Mexico-2017-OECD-economic-survey-overview.pdf
[80] End of mission statement by the United Nations Special Rapporteur on the situation of human rights defenders, Michel Forst on his visit to Mexico from 16 to 24 January 2017, January 2017
[81] Mexico Peace Index 2017, Institute for Economics and Peace, 2017 http://visionofhumanity.org/app/uploads/2017/04/MPI17_English_Report_WEB_03.04-1.pdf
[82] “This is how much violence costs Mexico's economy”, World Economic Forum, 2016, https://www.weforum.org/agenda/2016/05/this-is-how-much-violence-costs-mexicos-economy/
[83] “Improving Mexico’s Economic Competitiveness Through Security Cooperation”, Center for American Progress, 2017 https://www.americanprogress.org/issues/security/reports/2017/05/02/431429/improving-mexicos-economic-competitiveness-security-cooperation/

#### Context – how does Anti-corruption and Rule of Law contribute to poverty reduction and economic growth?
A weak rule of law, in particular corruption, and poor access to justice and security, is one of the biggest brakes on Mexico’s growth. This element of the programme underpins the three other strands (Energy, Future Cities and Financial Services) by supporting a better environment in each of those sectors. Literature shows that a weak rule of law and high levels of corruption reduces potential investment and acts as a break on economic growth, for example, the World Economic Forum has stated that greater levels of violence lead to less productivity, a distortion of public resource allocation and exit of human capital. This in turn reduces incentives for new job creation and long-term investment, affecting long-term economic development.[84] As well as the general theory of an improved overall environment for business, the programme will be focused on improving the transparency, fairness and efficiency of Mexico’s justice and anti-corruption agencies.
[84] World Economic Forum. 2016. “This is how much violence costs in Mexico’s economy” https://www.weforum.org/agenda/2016/05/this-is-how-much-violence-costs-mexicos-economy/
Current state of the sector
Overall, the Mexican economy is growing, but corruption, insecurity and impunity are acting as a break on the country’s growth potential. The cost of crime is high (1.3% of the country's GDP, outstripping the 2013 growth rate of 1.1%)[85] – a fact that is viewed by Mexican businesses as the top obstacle to growth.[86] Crime is also the biggest concern for the wider population alongside insecurity, closely followed by corruption which is closely linked to both. [87] A weak rule of law, enables impunity, leading to criminals going unpunished and making justice provision inaccessible for many of the population, particularly to men and women at the 40% lower income range.
[85] The Mexican Employers Association, Coparmex
[86] The percentage of enterprises reporting crime as their top obstacle to growth rose by 5 percentage points over the 2006-2010 period.
[87] “Estadísticas A Propósito Del Día Internacional Contra La Corrupción (9 De Diciembre)” Inegi, 7 December 2016, http://www.inegi.org.mx/saladeprensa/aproposito/2016/corrupcion2016_0.pdf
Legislation has been introduced to combat many of the issues highlighted,[88] but its implementation will ultimately determine whether it is successful in improving the rule of law and tackles corruption or not. Capacity within Mexican institutions to support these reforms needs to be built and there is much the UK, and the international community, can do to support capacity and expertise building.
[88] The reform to the Criminal Justice System (from inquisitorial to adversarial) passed in 2008 and entered into force national-wide in June 2016; and the creation of the National Anti-corruption System by constitutional reform in 2015, the system started operation in July 2017.
#### Primary Purpose: economic development and poverty reduction in Mexico
##### Programme contribution to UN’s Sustainable Development Goals (SDGs)
Our programme, by addressing the top constraints to growth outlined below, will support Mexico in achieving the UN’s Sustainable Development Goals (SDGs) at the core of Mexican policies. The Anti-corruption and Rule of Law strand in particular will contribute to achieve some of these goals. In particular:
Table 6
Proposed intervention	SDG Goal	Impact
Intervention 1: Adoption of clearer, consistent, traceable processes and standards for identifying and investigating serious crime and corruption. / Intervention 2: Improved capacity and capability of male and female officials involved in identifying and investigating serious crime and corruption. / Intervention 3: Improved coordination of the actors detecting and investigating serious and organized crime and corruption.	1 - End poverty in all its forms everywhere.	This programme will contribute to increase the growth of the Mexican economy by creating a safer and fairer environment for business; this will have spill-over effects on job creation, business dynamics, and further reducing the poverty gap within the country.
	5 - Achieve gender equality and empower all women and girls.	The programme will contribute to tackling gender inequality, particularly in security, justice and transparency in Mexico and to guarantee women and girls rights.
	10 - Reduce inequality within and among countries.	This programme will contribute to improve the quality of public service as the best mean of building an equitable, sustainable, peaceful and democratic society.
	16 - Promote peaceful and inclusive societies for sustainable development, provide access to justice for all and build effective, accountable and inclusive institutions at all levels.	The programme will support Mexico by strengthening its criminal justice institutions at federal, state and local level. In addition, it will contribute to build effective, accountable and inclusive institutions in the country by reducing corruption levels.

##### Top constraints to growth and poverty reduction
##### CONSTRAINT 1: CORRUPTION IN PUBLIC AND PRIVATE INSTITUTIONS
Corruption and poverty go hand in hand, having a direct negative effect on Mexico’s inclusive economic growth. Corruption in Mexico delays, distorts and diverts economic growth:
Effects of corruption in society: it creates and sustains economic inequality by reducing the income of men and women in the lower 40% income range. According to research conducted by Transparencia Mexicana, approximately 14% of an average family’s income is used for “informal payments”[89]. Corruption affects men and women at the base of the income pyramid forcing them to allocate 33% of annual income to corruption-related costs.[90]
[89] “¿Qué tan corruptos somos los mexicanos?”, Eduardo Bohorquez and Rafael Garcia Aceves, Animal Politico, 2015 http://www.animalpolitico.com/blogueros-blog-invitado/2015/01/29/que-tan-corruptos-somos-los-mexicanos/
[90] “México: Anatomía de la corrupción”, Maria Amparo Casar, Mexican Institute for Anti-competivness (IMCO), 2015 http://imco.org.mx/wp-content/uploads/2015/05/2015_Libro_completo_Anatomia_corrupcion.pdf
Effects of corruption on companies: it primarily affects new MSMES and indirectly favours monopolies. On average, companies spend 15% of their income on bribes; this is more manageable for big firms with consolidated profits.[91] In 2010, the Wold Bank conducted a survey directed at owners and senior executives of 1,480 Mexican firms; 50% identified corruption as a major obstacle for doing business in Mexico.
[91] “Reducir al corrupción para reducir la desigualdad”, Viridiana Rios, Excelsior, 2016, http://www.excelsior.com.mx/opinion/viridiana-rios/2016/10/23/1123940
Establishment of new companies: Mexico’s main drivers of economic growth are entrepreneurs, and MSMEs who generate 52% of the GDP and 72% of the employment in Mexico. It is clear that MSMEs play an important role in the Mexican economy; however the rate of creation of new companies still has some way to go to support this. [92]
[92] Encuesta Nacional sobre Productividad y competitividad de las Micro, Pequeñas y Medianas Empresas, INEGI, 2015 http://www.inegi.org.mx/est/contenidos/Proyectos/encuestas/establecimientos/otras/enaproce/default_t.aspx ; MSMEs accounted for 99.8% of the firms in Mexico, INADEM 2015.

##### CONSTRAINT 2: UNEQUAL ACCESS TO JUSTICE DEPENDING ON SOCIAL BACKGROUND ETHNICITY AND GENDER
##### Access to security and justice is a basic principle for rule of law, which in turn is necessary when creating an environment conducive to business development.
In scoping interviews commissioned by the Prosperity Fund in 2017, Mexican stakeholders expressed frustration at the ineffectiveness of the criminal justice system in preventing, investigating and prosecuting offenders. This affects men and women at the lower income level disproportionately as they cannot access the resources required to create an effective defence strategy that will safeguard their interests.
According to Enrique Cardenas, an expert on the study of poverty, 55.3 million Mexicans cannot fulfil their potential and overcome their poverty situation due to corruption inhibiting access to security, justice and quality public services.[93]
[93] # Head of the Centre Espinosa Yglesias for Research (CEEY)
Gap for Prosperity Fund interventions
The UK’s leadership on Anti-corruption and Rule of Law is growing fast, gaining support from political leaders and the public. UK’s support on this issue during the Fund’s transition period has been welcomed. The new administration has expressed their interest in continue strengthening the UK-Mexico relationship. During the transition period the Prosperity Fund has supported small interventions on anti-corruption, open government and anti-money laundering. These interventions aimed to increase government and civil society’s capacity to expose corruption and sanction corrupt individuals.
There is demand for British expertise on these issues. The UK’s support on anti-corruption reform to date has been a key partner in shaping Mexico’s new laws and institutions. For instance, both governments signed a bilateral Memorandum of Understanding on Anti-corruption, Open Government and Transparency in 2016, to set clear parameters for joint working. The UK is in a unique position to support the Mexican Government to fulfil their legal requirements under the new anti-corruption legislation, including the National Anti-corruption System.
The UK’s reputation on more general rule of law issues is also respected. Initial exchanges on policing and justice have been well received, and have created appetite for more (models of community policing and anti-corruption units within police corporations included British best practice). Additionally, Mexico sees the UK as an established leader in fighting cyber-crime and enforcing cyber security, both in public policy design and operational performance, in particular through compliance with international standards and gaining public trust on cyber security.
Mexico is looking to diversify away from almost exclusive cooperation with the US on security and rule of law issues. Early Prosperity Fund projects have focused on a range of areas: strengthening law enforcement institutions to support implementation of the adversarial justice system, improving the capacity of public defenders); development of evaluation methodologies to improve the response of police officers as first responders and the piloting of a community policing model. In addition, the design of a police disciplinary regime to tackle corruption – all based predominantly on UK best practices.
The UK is currently the only donor with an anti-corruption strategy. The UK is the only donor currently working with all the seven representatives of the National Anti- corruption System and is the only donor that has considered short, medium and long-term issues, including capacity building, digital coordination platforms and other commitments from the Global Anti-Corruption Summit in London in 2016. The bilateral MoU has a wider scope than other donor countries as it not only includes integrity, but also anti-corruption, transparency and open government.
The UK is the sole donor with an interest in working with public defenders in need of training and capacity building regarding the transition to the new adversarial legal system. Although public defence is different in the UK and in Mexico, British best practice, values and methodologies have the potential to be transferable and impactful in Mexico.
##### Delivery of primary purpose
The Anti-corruption and Rule of Law strand primarily aims to support Mexico’s efforts to build a more peaceful society, supporting Goal 16 of the UN Sustainable Development Goals (promotes the provision of access to justice for all, and building effective, accountable institutions at all levels). As the World Bank’s Development Report of 2011[94] shows, weak security and justice institutions have negative impact to the development and economic growth of countries. Furthermore, corruption poses serious threats to the stability and security of societies, undermining institutions and jeopardising sustainable development.
[94] “Word Development Report 2011”, The World Bank, 2011. http://siteresources.worldbank.org/INTWDRS/Resources/WDR2011_Full_Text.pdf

As outlined in the Theory of Change for this strand, the Strand’s planned interventions will help Mexico to achieve a more efficient detection and investigation of serious crime and corruption.
##### What the programme will do and how
Our Anti-corruption and Rule of Law programme will focus on improving the capacities, capabilities and coordination of the officials and agencies involved in detecting and investigating serious crime and corruption. Detailed programme activities will be determined during the inception phase of the programme however these will focus on delivering the outputs described below. Fragmentation is a key risk which we will expect our implementers to mitigate when designing the programme. The programme will have three large interventions:
1. Increasing the accountability of public service by streamlining and standardising processes for detecting and investigating serious crime and corruption.
2. Increasing the quality of public service by building capacity in male and female officials working in the detection and investigation of serious crime and corruption to ensure access to justice and security for all.
3. Improving the coordination between security, justice and anti-corruption institutions in three states.

Overseas Security and Justice Assistance
The assistance proposed in the Anti-corruption and Rule of Law strand meets the definition of assistance under the Overseas Security and Justice Assistance (OSJA) Guidance. Detailed assessments will be carried out for all interventions taken forward to ensure that it supports our values and is consistent with our domestic and international human rights obligations.
In addition, given the difficult human rights situation in Mexico, all activities will be designed with increased compliance with human rights standards as the core principal and will steer away from more operational work with appropriate mitigating measures being implemented where required. Risks arising from working on anti-corruption and rule of law in Mexico will be less on the legal side but there are reputational risks we will mitigate with the implementing partner.
Secondary benefits to international businesses
Efforts to improve Mexico’s business environment are directly linked to increased UK security and influence in the world. Creating a better environment for international companies, can only be achieved through government-to-government cooperation. This will increase economic growth by attracting investment and contributing to poverty reduction and gender equality. This is area of intervention is crosscutting for our other three areas of work in the Prosperity Fund and is integral to wider inclusive economic development. According to the OECD the security sector in Mexico will grow 20% over the next five years. Control Risks estimates that UK companies spend £450 million a year on security-related costs when operating in Mexico.[95] Furthermore, a DIT scoping study confirmed that the actual value for the security sector itself is $17 billion USD. Through government-to-government cooperation, the programme will increase the UK's market share in Mexico from 0.8% to a desired 3.7% or higher, and consistently support UK industry in all efforts for achieving significant export wins
[95] Nick Panes, Senior Managing Director for Control Risks Mexico, notes taken during a meeting, October 2015.

Appraisal Case
### Introduction
The Mexico programme aims to tackle the growth constraints identified in the Strategic Case through a multiyear programme covering four priority sectors. The Strategic Case sets out the argument and evidence that underdeveloped energy and financial sectors, poor urban planning and a weak business environment are contributing to poverty by restricting inclusive growth, productivity and investment in Mexico.
The Strategic case therefore identified four strands for intervention:

  1. strengthening the Energy sector (highest value for the Mexican economy);
  2. supporting sustainable development of Future Cities (greatest opportunity for growth);
  3. embedding Financial Services as an enabler for growth (greatest potential for impact across the economy); and
  4. Improving the Anti-Corruption and Rule of Law (the biggest brake on growth).
The Appraisal Case explores how we will address the needs set out in the Strategic Case in a way that optimises Value for Money and where feasible delivery options for achieving the objectives are considered.
### Options for intervention
In line with an initial steer from the Prosperity Fund Ministerial Board and to match the ambition and impact potential in Mexico, our analysis has concluded that a programme budget of £60m over four years is optimal, in addition to access to global Prosperity Fund programme funds, including education, health, trade, anti-corruption and infrastructure (see Financial Case for further detail).
The programme has been subject to a comprehensive set of economic, financial, social and environmental assessments in line with HM Treasury’s Green Book. A full assessment of possible interventions[96] within each sector has been carried out to ensure that the programme specifically targets the opportunities and challenges in each sector, as well as where the UK can add value.
[96] Potential interventions in the strategic case were assessed on the ability to deliver the primary impact (economic development and poverty reduction in Mexico), secondary impact (creation of opportunities for international business, including the UK), level of UK experience to transfer knowledge to Mexico, Value for Money and alignment with the Mexican government’s priorities.
### Quantified Benefits (Cost-Benefit Analysis)
##### This analysis sets out the quantified benefits and costs of the programme based on the four strands identified in the Strategic case.
##### Primary and Secondary Benefits Result: Net Present Value summary table
##### Primary benefits have been discounted at a standard discount rate of 10%, as used by Department for International Development (DFID) and the World Bank when appraising the benefits of development projects to recipient countries. Secondary benefits and costs have been discounted at 3.5%, the standard discount rate recommended by the UK’s Green Book.
#### Primary Benefits
Strand	Calculation
Anti-Corruption and Rule of Law	Decrease in the cost of corruption and crime as a share (%) of national GDP.
Financial Services	Positive impact on GDP as a result of increasing Financial Inclusion and reducing the cost of sending remittances using Fintech.
Energy	Positive impact on GDP, as a result, of an increase in the skill level of workers in the Energy sector in Mexico, which will therefore increase the productivity of the workforce in the sector.
Future Cities	Reducing the overall costs of congestion to society and reduction in costs to the Mexican government when providing e-government or digital government.

Secondary Benefits
Strand	Calculation
Anti-Corruption and Rule of Law	Increase in the Exports (goods) from the UK to Mexico from of decreasing constraints that affect international businesses in Mexico.
Financial Services	Increase in Financial Services exports from the UK to Mexico.
Energy	Increase in the energy related Exports from the UK to Mexico.
Future Cities	Increase in digitalisation and mobility related Exports from the UK to Mexico.

Strand	Primary Benefit (£m)			Secondary Benefit (£m)
	High	Central	Low	High	Central	Low
Anti-Corruption and Rule of Law	809	219	24	234	153	72
Financial Services	421	221	80	52	28	4
Energy	320	215	129	376	254	139
Future Cities	684	231	53	35	27	20
Total	2,234	886	286	697	462	235

### Anti-Corruption and Rule of Law

The intended impact of the Anti-Corruption and Rule of Law strand’s interventions is to increase security and legal certainty for citizens and businesses through a more fair, open and competitive business environment. The three primary outcomes from the Anti-Corruption and Rule of Law strand are:
1. Adoption of clearer, consistent, traceable processes and standards for identifying and investigating serious crime and corruption cases
2. improved capacity and capabilities of male and female officials involved in identifying and investigating serious crime and corruption cases,
3. improved coordination of the actors identifying and investigating serious crime and corruption cases.
This means reducing the negative externalities associated with weak rule of law, such as direct economic losses for businesses, an increase in the cost of opening and operating a business in Mexico, lack of investment, and the associated loss of jobs.
This primary benefit estimation therefore considers the IMF GDP forecast for Mexico to obtain monetised benefits for the Anti-Corruption and Rule of Law strand. In order to accomplish that, the strand was divided into two components, perception on i) corruption and ii) crime; and we calculated the monetised benefits for each of the two strands. We then combined the results to obtain the total benefit for the Anti-Corruption and Rule of Law strand, as detailed in following pages under ‘Primary Benefits’.
The costs of the Anti-Corruption and Rule of Law strand will be £10m, profiled over four years as outlined in the financial case above, which gives a total discounted cost of £9.11m.
##### Corruption
##### For this appraisal, we modelled a reduction in the costs to society resulting from corruption over a 10 year period. Our methodology is based on the assumption that we can quantify the cost of corruption to society and that Prosperity Fund intervention will reduce the cost of corruption by a marginal amount over the time period.
Table 2
	2019	2020	2021	2022	2023	2024	2025	2026	2027	2028	Total
Intervention Impact	0.0%	0.0%	0.0%	0.0%	0.0%	0.0%	0.0%	0.0%	0.1%	0.1%
Cost of Corruption (%)	5.0%	5.0%	5.0%	5.0%	5.0%	5.0%	5.0%	5.0%	4.9%	4.9%
Cost of Corruption (£bn)	51	54	57	60	63	67	71	73	77	81	656
Cost Saving due to Intervention (£bn)	0.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	1.6	1.7	3.2
Discounted for Additionality (£bn)	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.00	0.39	0.41	0.8
Discounted for Risk (£bn)	0.000	0.000	0.000	0.000	0.000	0.000	0.000	0.000	0.196	0.206	0.403

Results
Based on the assumptions set out above, the primary benefits for the corruption strand are estimated to be £403 million over ten years, which is the additional primary benefit attributable to the Prosperity Fund, in comparison with the “business as usual” scenario. The GDP of the Mexican economy is therefore expected to be £403m larger compared to a scenario where no intervention is applied.
##### Security & Justice
For this appraisal, we modelled a reduction in the costs to society resulting from crime over a 10-year period. Our methodology is based on the assumption that were able to quantify the cost of crime to Mexican society and that programmatic intervention will reduce the cost of crime by a marginal amount over the time period.
Table 8
	2019	2020	2021	2022	2023	2024	2025	2026	2027	2028	Total
Intervention Impact	0.00%	0.00%	0.00%	0.01%	0.01%	0.01%	0.01%	0.01%	0.01%	0.01%
Cost of Crime (%)	1.92%	1.92%	1.92%	1.91%	1.91%	1.91%	1.91%	1.91%	1.91%	1.91%	0
Cost of Crime(£bn)	20	21	22	23	24	26	27	28	30	32	252
Cost Saving due to Intervention (£bn)	0.0	0.0	0.0	0.1	0.1	0.1	0.1	0.1	0.2	0.2	1.0
Discounted for Additionality (£bn)	0.00	0.00	0.00	0.03	0.03	0.03	0.04	0.04	0.04	0.04	0.2
Discounted for Risk (£bn)	0.00	0.00	0.00	0.01	0.02	0.02	0.02	0.02	0.02	0.02	0.124

#### Results
#### Based on the assumptions set out above, the primary benefits for the security and justice strand are estimated to be £124 million over ten years, which is the additional primary benefit attributable to the Prosperity Fund, in comparison with the “business as usual” scenario. The GDP of the Mexican economy is therefore expected to be £124m larger compared to a scenario where no intervention is applied.
#### Therefore, we expect the overall primary benefits for both strands of the Anti-Corruption and Rule of Law programme to be £527.1m over the 10-year period (2019-2028). After discounting for present value and accounting for programme costs, the Total Net Present Value (NPV) for Primary Benefits is £218.7m.
##### Sensitivity analysis
There are uncertainties surrounding the assumptions we have made in this analysis due to the scarcity of available data. In order to attempt to mitigate this, and to aid decision-making around how best to invest Prosperity Fund money, we have used conservative scenarios, based on assumptions that reflect our best judgment. This should in theory, result in accurate and plausible estimations, which would be equivalent to the most likely expected outcomes, given the Anti-Corruption and Rule of Law programme risks and information asymmetries. However, is also important to note that, even in the presence of wider uncertainties, we have strong buy-in and support from the Mexican government on the Anti-Corruption and Rule of Law agenda, and that this agenda has risen in importance for the current Government, increasing our option for interventions under this strand.
The table below includes the resulting net present values (discounted benefits minus discounted costs) of the additionality calculated from all the components of the Anti-Corruption and Rule of Law strand:
Chart 2: Anti-Corruption and Rule of Law - Primary and Secondary Benefits resulting from Prosperity Fund Interventions
Anti-Corruption and Rule of Law Primary Benefit (£m)	2019	2020	2021	2022	2023	2024	2025	2026	2027	2028	Total

Higher	-2	-2	24	25	25	24	23	241	231	221	809
Central	-2	-2	-3	9	10	10	9	9	91	88	219
Lower	-2	-2	-3	-1	2	2	2	2	2	21	24

Anti-Corruption and Rule of Law Secondary Benefit (£m)	2019	2020	2021	2022	2023	2024	2025	2026	2027	2028	Total

Higher	-2	-1	1	7	13	20	29	41	55	72	234
Central	-2	-1	-0	4	9	13	19	27	37	48	153
Lower	-2	-2	-2	2	4	7	10	14	18	24	72

### Financial Services
### The intended impact of the Financial Services strand’s interventions is to create a more inclusive and competitive sector, accessible to all sections of Mexican society and new market entrants. There are three main components: financial inclusion for individuals; targeted regulatory improvement to support the development and growth of the Fintech sector and a socially focused Fintech accelerator. Each intervention will ultimately target the unbanked, underserved populations:
- For the Mexican government’s social development programme the intervention will target the beneficiaries of who each have a debit card for receiving their conditional cash transfers. Although the programme currently has more than 6.9 million beneficiaries, 78% of them have no access to financial services meaning that they receive the aid in cash. This poses security risks for both beneficiaries and the Mexican government.
- The Fintech regulatory strand and accelerator are targeted to increase financial inclusion and increase access to finance for MSMEs, which will in turn help to create Fintech solutions to benefit the unbanked and underserved population in Mexico.
### When looking at Mexico’s Fintech Law (which has provisions for a Regulatory Sandbox and Open Financial Data Sharing Standards) it is important to remember that the UK’s own Regulatory Sandbox (part of Project Innovate) only came into use in 2016. In addition the Open Banking Standard in the UK only came into force in January (2018). As such, we have limited information on which to measure primary and secondary impact of these initiatives, both of which are the longest running of their kind in the world. However, evidence from the Open Data Institute (which led on developing the Open Banking Standard in the UK) has shown that disruption in the Financial Services sector through improved access to products, and the development of new ones, has allowed consumers to have improved means of accessing financial services.
### The primary benefit estimation therefore considers how the inclusion of this unbanked population will impact the Mexico’s GDP, in order to do this we based our calculations on figures obtained from the IMF GDP forecast for Mexico. The total costs of the Financial Services strand from 2016 to 2023, are expected to be £11m, profiled over seven years as outlined in the financial case below, which gives a total discounted cost of £10.02m.
#### Financial inclusion
To evaluate the impact of the Prosperity Fund on this intervention, we modelled the effect the increase of beneficiaries of the Mexican Conditional Cash Transfer programme (that receives their conditional cash transfers in a debit account) has on the GDP using the Moody’s analysis[97]. We also derived the impact that access to microcredit has on GDP, assuming 20% of the new debit cardholders for the Conditional Cash Transfer programme will ask for a micro loan (which are granted for beneficiaries). This was done using an elasticity derived by Sultan, Y. Et al. (2016)[98]
[97] https://usa.visa.com/dam/VCOM/download/visa-everywhere/global-impact/impact-of-electronic-payments-on-economic-growth.pdf
[98] https://mpra.ub.uni-muenchen.de/72123/1/MPRA_paper_72123.pdf

Table 9
Indicator	2019	2020	2021	2022	2023	2024	2025	2026	2027	2028
Number of Mexican Conditional Cash Transfer programme beneficiaries (millions)	25.06%	27.92%	34.89%	41.86%	48.83%	55.80%	62.77%	69.74%	76.71%	84%
% of Mexican Conditional Cash Transfer beneficiaries with a debit card	1.85	2.12	2.73	3.37	4.05	4.76	5.52	6.31	7.15	8.03
Mexican Conditional Cash Transfer programme beneficiaries with a debit card	46.96	49.50	127.39	134.31	141.60	149.29	157.40	165.95	174.96	184.46
GDP impact of Financial Inclusion (£m)	18.96	19.99	51.43	54.23	57.17	60.28	63.55	67.00	70.64	74.47
Impact of Micro-financing (£m)	0.00	0.00	105.45	111.17	117.21	123.58	130.29	137.36	144.82	152.69
Additionality Inclusion (£m)	7.38	7.59	7.82	8.05	8.29	8.53	8.79	9.05	9.31	9.59
Additionality	0.00	0.00	105.45	111.17	117.21	123.58	130.29	137.36	144.82	152.69
Discounted for Additionality 40%	0.00	0.00	42.18	44.47	46.88	49.43	52.12	54.95	57.93	61.08
Discounted for risk 75%	0.00	0.00	31.63	33.35	35.16	37.07	39.09	41.21	43.45	45.81

#### Financial technology
To evaluate the impact of the Prosperity Fund on the Fintech sector, we modelled the effect of reducing the cost of sending and receiving remittances on Mexico’s GDP. Using figures on remittances from the Mexican Central Bank[99] (BANXICO) and remittance prices from the World Bank[100] we were able to calculate the cost of sending money to Mexico (we used the total average cost of sending money from the US to Mexico, as remittances received from the US account for more than the 94% of the total amount received). We have projected the remittances using the average growth rate (5.15%) from the last five years (2013-2017) to predict its figures to 2028.
[99] http://www.banxico.org.mx/SieInternet/consultarDirectorioInternetAction.do?accion=consultarCuadro&idCuadro=CE81
[100] http://remittanceprices.worldbank.org/en/corridor/United-States/Mexico
Table 10
Indicator	2019	2020	2021	2022	2023	2024	2025	2026	2027	2028
Remittances / £m	25,043.45	26,332.29	27,687.47	29,112.39	30,610.64	32,186.00	33,842.43	35,584.11	37,415.43	39,340.99
Cost of sending Remittances / (£m) BAU scenario	1,229.52	1,292.80	1,359.33	1,429.29	1,502.84	1,580.19	1,661.51	1,747.02	1,836.93	1,931.46
Cost of sending Remittances / (£m) PF scenario	1,229.52	1,292.80	1,318.55	1,364.97	1,412.67	1,461.67	1,536.90	1,615.99	1,699.16	1,786.61
Additionality	0.00	0.00	40.78	64.32	90.17	118.51	124.61	131.03	137.77	144.86
Discounted for potential beneficiaries / 50%	0.00	0.00	20.39	32.16	45.09	59.26	62.31	65.51	68.88	72.43
Discounted for Additionality 30%	0.00	0.00	8.16	12.86	18.03	23.70	24.92	26.21	27.55	28.97
Discounted for Risk 75%	0.00	0.00	6.12	9.65	13.53	17.78	18.69	19.65	20.67	21.73

#### Results
#### Based on the assumptions set out above for both, Financial Inclusion and Fintech interventions, the primary benefits in a conservative scenario for the Financial Services strand are estimated to be £221 million over ten years, which is the additional primary benefit attributable to the Prosperity Fund in comparison with the “business as usual” scenario.
#### Sensitivity Analysis
#### In ideal circumstances, we would be able to estimate the impact of the Prosperity Fund immediately and with precision. However, in the absence of clear evidence, as was the case here and for any other economic appraisal, there are uncertainties surrounding the assumptions we have made in this analysis, due to the scarcity of available data. In order to mitigate this, and to aid decision-making around how to best invest Prosperity Fund money, we have used the most conservative scenarios, based on assumptions that reflect our best judgment. These should, in theory, result in the most accurate and plausible estimate possible, which would be equivalent to the most likely expected outcome. The Financial Services strand does not represent a considerable risk given the importance attached to the sector in Mexico (increasing the likelihood of achieving primary benefits) and the UK’s acknowledged competitive advantage (also increasing the likelihood of achieving secondary benefits). The table below includes the resulting net present values of the additionality calculated from all the components of the Financial Services strand:

#### Chart 3: Financial Services - Primary and Secondary Benefits resulting from Prosperity Fund Interventions

Financial Services Primary Benefit (£m)	2019	2020	2021	2022	2023	2024	2025	2026	2027	2028	Total

Higher	-2	-2	51	54	56	58	55	53	51	48	421
Central	-2	-2	25	28	30	31	30	28	27	26	221
Lower	-2	-2	7	10	12	12	12	11	11	10	80

Financial Services Secondary Benefit (£m)	2019	2020	2021	2022	2023	2024	2025	2026	2027	2028	Total
Higher	-2	-2	-1	3	5	7	9	10	12	14	52
Central	-2	-2	-2	1	3	4	5	6	7	8	28
Lower	-2	-2	-3	-0	1	1	2	2	3	3	4

### Energy
The Mexico energy programme aims to achieve the following outcomes:

- Larger pipeline of certified male and female specialists to meet industry demand and a local workforce that is resilient to economic shocks;
- Incorporation of market ready local male and female-owned SMEs in the supply chain of MNCs in the energy sector; and
- Increased levels of technical proficiency amongst regulators and male and female officials that uphold adherence to international standards in the Energy Sector.
The costs of the Energy strand are £28m, profiled over four years as outlined in the financial case above, which gives a total discounted cost of £25.5m.
The approach for establishing the primary benefit of the energy programme can be summarised as:

More productive and resilient men and women, businesses and government officials to support Mexico’s transition to a low carbon economy

For our appraisal, we modelled an increase in the proportion of high-skilled workers[101] in the energy sector in Mexico, leading to an increase in labour productivity and increase in the overall GDP generated by the sector.
[101] Managers, professionals, and technicians (Skill Levels 3 and 4), as defined by ILO at http://www.ilo.org/ilostat-files/Documents/description_OCU_EN.pdf

Primary Benefits Calculations
Table 3
	2019	2020	2021	2022	2023	2024	2025	2026	2027	2028	Total
Total, discounted increase in GDP due to Increased Productivity (GBP m)	0	0	28	37	45	53	62	71	80	90	468
Increased GDP due to Increased Productivity (GBP m)	0	0	144	183	225	267	311	356	403	452	2,342
Increased Productivity Level (USD/worker)	22,557	23,348	25,777	27,040	28,345	29,691	31,082	32,519	34,004	35,538
Increased % of High Skilled Workers	18.9	18.99	19.73	19.96	20.18	20.40	20.62	20.84	21.06	21.27
Number of Extra High Skilled Workers in Target Group	0	0	821	1,047	1,281	1,524	1,775	2,034	2,302	2,578	13,361

#### Results

This results in a primary benefit of £468.56 m over the ten year period (2019-2028). After discounting for present value and accounting for programme costs, the Total NPV for Primary Benefits is £214.88m.
#### Sensitivity Analysis

There are uncertainties surrounding the assumptions we have made in this analysis due to the scarcity of available data. To mitigate this, and to aid decision-making on how best to focus Prosperity Fund in Mexico, we have used conservative scenarios, based on assumptions that reflect our best judgment. These should in theory, result in plausible estimates, which would be equivalent to the most likely expected outcome. Therefore, a sensitivity analysis has been applied test the factors above in their best case and worst case scenarios.

Chart 4: Energy - Primary and Secondary Benefits resulting from Prosperity Fund Interventions

Energy Primary Benefit (£m)	2019	2020	2021	2022	2023	2024	2025	2026	2027	2028	Total

Higher	-6	-7	23	33	40	43	46	48	49	50	320
Central	-6	-7	13	22	28	30	32	33	34	35	215
Lower	-6	-7	6	13	18	19	20	21	22	22	129
Energy Secondary Benefit (£m)	2019	2020	2021	2022	2023	2024	2025	2026	2027	2028	Total

Higher	-6	-3	2	15	26	37	50	65	84	105	376
Central	-6	-3	-1	9	19	26	35	45	58	73	254
Lower	-6	-5	-4	4	11	15	20	26	33	42	139

The results of the Sensitivity Analysis show that, although there is some variability in the results of the model depending on the inputs used, the programme is expected to give strong, positive Net Present Value for primary and secondary benefits under all scenarios.
### Future Cities

For this strand, we take into consideration three components: Mobility, Infrastructure and Digitalisation.

- For Mobility, we consider the impact of increasing the efficiency of public transport systems to encourage people off the road, as well as encouraging the use of electro-mobility.
- For infrastructure and digitalisation, as stated in the strategic case the implementer in consultation with the Embassy will run an Agile Programming Fund ” to fund nimble targeted smaller-scale projects which either complement and support larger interventions, or allow us to pilot measures which can be scaled up in future years of the programme. This will help us mitigate the high degree of uncertainty of exact future Federal Government policy after the elections of July 2018 in line with an active portfolio management approach; and prepare the ground for future interventions in the event of an extension of the Prosperity Fund into the next Spending Review. Due to the small-scale nature of the interventions, we will not quantify the benefits of this sub strand at this stage.

The costs of the Future Cities strand is £11m, profiled over four years as outlined in the financial case which gives a total discounted cost of £9.88m.
#### Mobility

Our methodology for this strand of the appraisal is based upon a marginal decrease in the cost of congestion to 3 selected Mexican cities.

Table 12
Indicator	2019	2020	2021	2022	2023	2024	2025	2026	2027	2028
Hours Spent in Traffic	42.0	42.0	41.8	41.7	42.0	41.5	41.5	41.5	41.5	41.5
Total Hours Saved	0.00	0.13	0.25	0.00	0.42	0.42	0.42	0.42	0.42	0.42
Value of Hours Saved (£m)	0.00	78	166	0	307	323	341	360	379	400
Discounted for Additionality (£m)	0.00	19.60	41.40	0.00	76.70	80.86	85.26	89.89	94.77	99.91
Discounted for Risk (£m)	0.00	14.70	31.05	0.00	57.52	60.65	63.94	67.41	71.08	74.94

#### Results
#### Based on the methodology set out above, the primary benefits for the mobility strand are £395 million over ten years.
##### Digitalisation
##### Our methodology for this strand of the appraisal is based upon a decrease in the costs of providing public services to citizens of 10 Mexican cities.

Table 4
Indicator	2019	2020	2021	2022	2023	2024	2025	2026	2027	2028
Number of People Accessing Services Online	10.1	11.1	12.7	13.9	15.1	16.3	17.6	19.0	20.3	21.8
Number of Online Public Service Transactions	120.8	133.0	152.9	166.7	181.0	195.9	211.4	227.4	244.1	261.4
Additionality - Extra Transactions Online	0.0	0.0	7.3	7.9	8.6	9.3	10.1	10.8	11.6	12.4
Additionality - Costs Avoided through Online Transactions (£m)	0.0	0.0	50.6	55.2	59.9	64.8	70.0	75.3	80.8	86.5
Discounted for Additionality (£m)	0.00	0.00	12.65	13.79	14.98	16.21	17.49	18.82	20.20	21.63
Discounted for Risk (£m)	0.00	0.00	9.49	10.34	11.23	12.16	13.12	14.11	15.15	16.22

Based on the methodology set out above, the primary benefits for the digitalization strand are estimated to be £76 million over ten years.
Overall Primary Benefits
The overall primary benefits for all strands of the Future Cities programme are therefore expected to be £487m over the ten year period (2019-2028). After discounting for present value and accounting for programme costs, the Total NPV for Primary Benefits is £231.26m.

Sensitivity
There are uncertainties surrounding the assumptions we have made in this analysis due to the scarcity of available data. In order to attempt to mitigate this, and to aid decision-making around how best to invest Prosperity Fund money, we have used the most realistic and conservative scenarios, based on assumptions that reflect our best judgment. These should in theory, result in the most accurate and plausible estimate possible, which would be equivalent to the most likely expected outcome. Therefore, a sensitivity analysis has been applied around the displacement factor used to calculate primary benefit (introducing a variance of 10% either side of the central 80% estimate) and around the additional UK exports business within the Future Cities space (introducing a variance of 0.10% either side of the central estimates for each sub-strand).

Chart 5: Future Cities - Primary and Secondary Benefits resulting from Prosperity Fund Interventions
Future Cities Primary Benefit (£m)	2019	2020	2021	2022	2023	2024	2025	2026	2027	2028	Total

Higher	31	4	11	101	98	95	91	88	84	81	684
Central	-2	10	20	6	43	41	40	38	37	35	231
Lower	-2	-2	-0	5	2	11	11	10	10	9	53
Future Cities Secondary Benefit (£m)	2019	2020	2021	2022	2023	2024	2025	2026	2027	2028	Total

Higher	-2	-1	-1	2	4	5	6	7	8	9	35
Central	-2	-1	-1	1	3	4	5	5	6	7	27
Lower	-2	-2	-2	1	2	3	4	4	5	6	20

## Commercial Case
Route to Market
This Commercial Case presents evidence on the commercial viability for the Prosperity Fund Mexico, Years 3-5 Programme, and the procurement strategy that was used to engage with the market. It also provides details about the potential organisations that bid to deliver the programmes, the contract and pricing considerations and implications, delivery, risk and timescales for implementation.
Contract Structure Requirements
The contracts procured using the Cross- Whitehall Prosperity Fund Framework Agreement (the ‘Framework Agreement’), clearly outlined the following outputs:
Contract / Framework Lot	Outcomes to be Achieved
Energy / B2	Larger pipeline of certified male and female specialists to meet industry demand and a local workforce that is resilient to economic shocks; / Incorporation of market ready local male and female-owned SMEs in the supply chain of MNCs in the energy sector; / Increased levels of technical proficiency amongst regulators and male and female officials that uphold adherence to international standards in the energy sector
Financial Services / A2	More financially literate male and female consumers who feel greater trust in financial services institutions and have the ability to use formal financial services. / A supportive regulatory environment for the Fintech sector that works for both men and women. / An increased number of “MSME”s procuring Fintech solutions that provide financing alternatives; and allowing for more accessible cashless transactions for men and women.
Future Cities / B3	Improved governance, decision-making and planning mechanisms for urban mobility services for all that are safer, inclusive, resilient and sustainable within Mexico’s cities; / Implementation of strategies tested in successful Pilots to deliver safer, inclusive, resilient and sustainable urban mobility services, particularly for women and girls in Mexico’s cities.
Anti-Corruption and Rule of Law / A1	Adoption of clearer, consistent, traceable processes and standards for detecting and investigating serious crime and corruption; / Scale up of a specialized training programme on detection and investigation of serious crime and corruption; / Improved coordination of the stakeholders detecting and investigating serious crime and corruption.

### B. Market testing and assessment of delivery options
The Foreign and Commonwealth Office (FCO) has a strict procurement policy based on the core principles of open competition, Value for Money (based on 'Whole Life Cost') (VfM) and ethical practices. All acquisitions of the Prosperity Fund programme will comply with the FCO's procurement policy. The programme will be delivered through four managed service contracts that were procured via the Prosperity Fund Framework Agreement.
Our commercial strategy includes the procurement of the inception and delivery phases of the programme. Due to Presidential elections in July 2018, it was not feasible to procure the design phase separately as the risk of requirements changing post-election was very high (late 2018). Therefore our programme procured all three phases at the same time.
To assess whether the market had the capability, capacity and interest to deliver the services required, the Embassy has engaged with over 100 potential implementing partners over 2016, 2017 and 2018, in 7 different market engagement events and 1 Expression of Interest per contract.
Market engagement began in August 2016 with the Mexican Government, civil society organisations, the private sector and academia. One early engagement event was held in August 2017, which provided helpful information about how the programme could be delivered in the local context; this event also helped to determine the chosen procurement process. A second round of Market Engagement events took place on 27th February and 1st March 2018, to test and refine the requirements set out in each of the Service of Requirements (SoRs). These events had four main objectives:

  1. Obtain intelligence from the market (including innovative ways to achieve outcomes) which was used to improve the SoRs;
  2. Raise awareness for the procurement process to ensure healthy competition between potential suppliers;
  3. Facilitate the building of strong supply chains which can deliver the desired activities and achieve maximum impact; and
  4. Lay the groundwork for an open, fair and transparent procurement process to mitigate the risk of future legal challenges to our programme.
Initial market engagement indicated that there was sufficient private sector interest in delivering the services required to achieve the outcomes and outputs set out in the Strategic Case. This interest was both at a global (Framework Agreement) level and at local supply chain level. Engagement also identified that these organisations were used to working together in Mexico as consortia or as prime contractors/sub-contractors.
Four more market engagement events post Invitation to Tender (ITT) were undertaken once the FCO Framework Agreement was awarded (Energy, Financial Services, Future Cities and Anti-Corruption and Rule of Law). These were advertised through the Bravo e-sourcing commercial platform for Lot specific Framework Suppliers, 3 weeks after the programmes were published.
The Expression of Interest (EoI) for the four strands was sent through Bravo during May-June 2018, in order to understand how many suppliers were potentially going to bid:
Lot A1 – Business Environment	EOI June 2018	Lot A2 – Finance Trade	EOI June 2018
Total Framework	20	Total Framework	15
Likely to bid	6	Likely to bid	4
Actual Bidders	5	Actual Bidders	3
Lot B2 Future Cities	EOI June 2018	Lot B3 Energy	EOI June 2018
Total Framework	22	Total Framework	23
Likely to bid	5	Likely to bid	8
Actual Bidders	3	Actual Bidders	6

Suppliers were selected based on evaluation of technical and commercial offerings and all were invited to tender for the Prosperity Fund requirements for years 2018-2023.
Recommended implementation partners
Implementing Partner	Brief Description	Priority Sectors	Form of Procurement	Programme
DAI	International development company working since 1970, in more than 150 countries—delivering results across the spectrum of international development contexts, from stable societies and high-growth economies to challenging political and military environments.	Digital Acceleration, Economic Growth, Environment and Energy, Fragile States, Global Health, Governance and Business Sustainability	Framework	Energy – PF MEX 18 015 / Financial Services – PF MEX 18 016
PA	An innovation and transformation consultancy, focused on building a positive human future in a technology-driven world. Use of strategies, technologies and innovation. Diverse teams of experts combine innovative thinking and breakthrough technologies to progress further with over 2,600 specialists. Operate globally from offices across the Americas, Europe, the Nordics and the Gulf.	Consumer, defence and security, energy and utilities, financial services, government, healthcare, life sciences, manufacturing, and transport, travel and logistics	Framework	Anti-Corruption and Rule of Law – PF MEX 18 018
PWC	Multinational professional services network, ranks as the second largest professional services firm in the world present in 158 countries and over 250 k staff, 26% of which are based in North America.	Consumer markets, Engineering, Energy, Financial Services, Public Services, Technology, Transportation & logistics.	Framework	Future Cities – PF MEX 18 017

C. Contracting route
The Framework Agreement provides Prosperity Fund programmes with access to a number of pre-qualified suppliers that have the experience and capacity to implement Prosperity Fund programmes in target countries and sectors and assist in the delivery of the primary and secondary benefits of the Fund. HMG ensures Value for Money by ensuring the three main implementing partners were part of a call off competition for each contract, across the relevant Framework Agreement lot.
There were three engagement events held in London to validate the design of the commercial strategy and of the Framework including the lot structure. Over 300 suppliers expressed an interest in supplying services with over 200 bids received, indicating capability and market interest globally in delivering PF programmes.
The four Mexico contracts were procured via the Framework Agreement, which had awarded a total of 39 suppliers across 11 Lots and available from March 2018. The Framework Agreement was designed specifically for the Prosperity Fund and is also available to Other Government Departments. These contracts were competed via a call for further competition from lots:

- A1 Business Environment: 20
- A2 Finance Trade: 15
- B2 Future Cities: 22
- B3 Energy: 23
D. Ensuring implementing partner performance
The Framework Agreement sets out key contractual terms the suppliers will be required to adhere to when delivering at local level. Contracts awarded via the Framework Agreement will be managed robustly by Contract Managers locally in Mexico with support from FCO’s Central Procurement Group. Provider’s performance will be monitored against agreed Key Performance Indicators (KPIs).
The ITTs and the market engagements events indicated that delivery of the individual strands included sub-contractor arrangements in favour of forming consortia, although no preference or steer to this end was stated in the SoRs for as single bidders, partnerships or consortia. Where applicable, bidders were required to provide full details of consortia and sub-contract elements of the programme. This assisted effectively in evaluating potential to deliver impact and to manage risk accordingly. In the instance of either supplier sub-contracts or consortia, a single contract was issued to the prime supplier per strand, who will be responsible for successful programme delivery against milestone achievement. The prime supplier will be the main interface with Embassy teams.
The bidders set out their design of the programme and interventions to deliver the outputs and outcomes required for each contract, and focus on the delivery. The tenders also set out the standards that the supplier will need to deliver. It did not specify how suppliers should deliver the services. KPIs and Performance measures will be managed by the British Embassy in Mexico City. There is clear definition of outputs and KPIs, also to mention that Service Levels will be agreed along with the Annual Work Plan, between the FCO and the final Delivery Partner. There is a platform in place in order to measure and input indicators, which is standardised in line with all PF programmes. Our expectation is that by the end of Inception Phase in 2019, the Service Level Agreements and the KPIs are set and agreed in between the parties in order to continue to Implementation Phase. This will ensure alignment with the new Mexico Government and Prosperity Fund objectives.
#### Payment by Results and Key Performance Indicators
#### A system of KPIs and respective Service Level Agreements (SLAs) are set out in the Invitation to Tender documents for the four strands, and will be further developed after contract signature.

Furthermore, Service Credits will be applied to all strands where the suppliers fail to achieve SLAs in relation to KPIs.

For Energy and ACROL, Payment By Results (PBR) will create a value based – efficient relationship and is a Global trend towards increased flexibility. From a Procurement point of view, the PBR is value based remuneration.

Milestone payments will also be used to incentivise:
- Performance
- Fairness
- Innovation
- Outcome orientation

PBR maximises transparency and accountability, by having agreed results and openness between FCO and the Delivery Partner. Clear targets empower the accountability for results and a strong focus on performance.

Pricing Mechanisms

The approach to the commercial model will be an hybrid of monthly fixed T&M elements and milestone payments, where the detailed requirements provide for a level of risk sharing and incentivising suppliers.
The initial inception phase will be set as a fixed price with a detailed set of requirements and quality measures provided within the ITT, ensuring VfM for HMG and incentivising the supplier to deliver to time and quality.

Other models, including payment by results if applicable, will be further negotiated in line with the outputs of the inception phase and to ensure risk share and VfM.

Payments will be in line with HMG standards and via electronic invoice procedures. Where appropriate, when and if the payment model evolves, payments will in all cases reflect the following characteristics:

- Practical
- Measurable deliverables
- Incentives for the supplier to perform
- Appropriate risk transfer
- Flexibility
- Affordability
- Transparent and auditable

Bidders will also be required to: a) demonstrate the processes they will apply to benchmark their prices to ensure they continue to offer value for money; and b) identify how they will offer economies of scale where, for example, multiple programmes are implemented by one party in Mexico.

Payments will be awarded at defined points (milestones) in the set up process such as receipt of final governance structure, workflows or project/resource plans for each intervention. Milestones will be linked to withheld /delayed payments in case of failure to meet them.

After each financial year review, any annual rate increases for the original rate card will have to be analysed and approved by the Authority and pass through a formal Variation Procedure in the Contract. This will, if necessary, also adjust the work plan for the next year for the services to cover a certain amount of activities and expenditure.

Timescales
The programme is designed to include two phases. Below we can see the overall activities related to each phase of the programme:
Procurement Process	Milestone
Summer-Autumn 2018	ITT and evaluations
February - 2019	Contract Signature
Inception Phase	Milestone
February – July 2019 (ACROL, FS & FC)	Inception Report Delivery
February – October 2019 Energy	Inception Report Delivery
August – 2019 (ACROL, FS & FC)	Approval of Annual work plan and mobilisation period.
November – 2019 Energy	Approval of Annual work plan and mobilisation period.
Implementation Phase	Milestone
August 2019- December 2019	Implementation of Annual Work Plan
December 2019 – March 2023	Last Quarter of Annual work plan – evaluations and changes. / Next Fiscal Year Annual Work Plan Agreement

FINANCIAL CASE
As outlined in the Strategic and Appraisal cases, there is a clear rationale to scale up Prosperity Fund programme activity in Mexico to £60m, in line with ministerial approval, using the Framework Agreement to procure four contracts. This funding is available through current resource allocation.
### Expected costs and key cost drivers of the programme
The budget available is up to £60 million to March 2023 from the Cross Whitehall Prosperity Fund from which £1.3 million will be used for the FY 18/19 Transition Programme and first stage of the Inception Phase.
The budget available is up to £60m to March 2023 from the Cross Whitehall Prosperity Fund from which £920,000 will be used for the FY 18/19 Transition Programme.
A key cost driver will relate to programme delivery when using trusted third-party suppliers. The overall implementation of the programme will account for 96% of the £60m allocation (£57,800,000). Our forecast includes programme delivery costs which correspond to the costs related to financial audits, quality/KPIs audits, impact on gender audits and stakeholder engagement (both at federal and state levels).
The expected cost drivers of the programme will also include administrative costs – including staffing costs (14 Full Time Equivalents (FTE)) and related travel, meetings and conference calls, Learning and Development and management and operation overheads. It is expected that HMA Mexico as SRO for the programme (or Embassy staff delegated to act in her stead) will be asked to carry out representation and negotiation activities for the fund. The costs arising from these activities will be covered by the programme allocation. This will also be applicable if and when there is a need for Embassy technical experts to accompany missions and other relevant programme activities, given their insight on policy and commercial developments. Further detail of the staffing costs can be found below in the Management Case.
Some assets or equipment may be purchased through the programme if required by the supplier. Where implementers consider it necessary to use funding to buy equipment they shall inform the Programme Team at the earliest opportunity. Written approval must be received from the Programme team prior to such use of the funding. This will be stipulated in all contracts.
Based on the rationale below, the following table shows the available £60m Prosperity Fund budget disaggregated by component and by year. However, work plans and associated budgets will need to retain a degree of flexibility to cover any changes to the pace and scope of policy reforms over the medium term.
Table 14
Strand	Type of service to be purchased [1]	Value (£M)
Energy		FY 17/18	FY 18/19	FY 19/20	FY 20/21	FY 21/22	FY 22/23	Total
	Skills Development	0.09	0.03	1	2.6	1.8	1.8	7.32
	Supply Chain Development	0.09	0.03	1.1	2.6	1.8	2.2	7.82
	Institutional Capacity Building	0.09	0.03	0.9	1.5	1.26	1.3	5.08
	Agile Programming Fund	0.09	0.03	0.7	1.28	1.22	1.1	4.42
Future Cities	Intervention 1 (Mobility): Planning & Governance	0.09	0.03	0.94	1.46	0.5	0.4	3.42
	Intervention 2 (Mobility): Pilots	0.09	0.03	0.45	1.71	1.56	0.47	4.31
	Agile Programming Fund	0.09	0.03	0.97	0.85	0.16	0.15	2.25
Financial Services	Financial Inclusion	0.09	0.02	0.8	0.9	1	0.9	3.71
	Fintech Law	0.09	0.02	0.5	0.56	0.6	0.54	2.31
	Accelerator	0.09	0.02	0.6	0.74	0.8	0.74	2.99
	Agile Programming Fund	-	-	0.4	0.25	0.29	0.25	1.19
Anticorruption & Rule of Law	Policy support	0.08	0.04	0.82	0.2	0.2	0.5	1.84
	Capacity building	0.08	0.04	0.3	0.8	0.75	2	3.97
	Coordination Mechanisms	0.08	0.04	0.71	0.25	0.85	1	2.93
Other	Transition programme	0.36	0.17	-	-	-	-	0.53
	Underspend from contracts	-	-	0.12	0.13	0.12	-	0.37
Overall	Admin & programme delivery costs	0.45	0.45	0.52	0.52	0.52	0.52	2.98
	Financial & gender audit	-	-	0.22	0.22	0.22	0.22	0.88
	Platform charges	0.28	0.28	0.28	0.28	0.28	0.28	1.68
TOTAL		£2.2	£1.3	£11.3	£16.9	£13.9	£14.4	60

Following approval of the Full Business Case, the final budget breakdown will be defined and agreed during the Inception phase for the contracts.
### Monitoring and reporting
Programme spend and forecasts will be monitored by the Programme team using FCO Financial systems. Budgets will be entered onto the FCO's systems using Hyperion, the FCO's online forecasting tool at the start of each financial year. The Embassy team will use the FCO’s financial dashboard, Oracle Business Intelligence Enterprise Edition (OBIEE) and Hyperion systems to monitor and report spend to date and forecasts.
### Payment by Results and Key Performance Indicators
As set out in the Commercial Case, a system of Key Performance Indicators (KPIs) and respective Service Level Agreements (SLAs), linked to Payment by Results (PBR), will be set out in contracts.
### Accountability
Funding will be delegated to the FCO from the Cross-government Prosperity Fund which receives its Funding from HMT. The FCO is the department responsible for spend compliance. The funds will be approved by HMT and FCO in accordance with delegated authority transmitted from Cabinet Office/HMT through FCO PUS. The Senior Responsible Officer (SRO) for the Mexico programme is Her Majesty’s Ambassador to Mexico.
We will not plan any expenditure in areas other than those approved by Ministers. Should additional resources become available; the programme will be scaled up through expanding our work to additional states as identified in our geographical strategy (see Annex F). All additional funding will be required to comply with audit and accounting requirements.
### Financial Risk and Fraud
Financial risk and fraud is assessed as low throughout the programme, given the Embassy staffing that will be in place to monitor and react to any inconsistencies in spend. Financial and fraud risk will be monitored via the programme governance structures throughout the life of the programme, including: risks of expenditure not being properly accounted for, poor value for money and funds being diverted from their anticipated purposes. No funds will be channelled directly through in-country government mechanisms.
#### Mitigating and monitoring fraud risk
Fraud risk will be monitored and mitigated and the Prosperity Fund Portfolio level and in country through the Mexico programme governance structures.
The agreed contract management structure offers the British Embassy in Mexico a large degree of oversight and influence over the suppliers. The programme team will work with suppliers through the lifetime of the programme to ensure that all financial requirements are met. Delivery partners are required by contract to follow rigorous management, monitoring and reporting.
Programme Managers will feed into the Programme Management Committee on a monthly basis and raise any possible fraud risks. In addition to FCO-wide systems to ensure audit compliance to prevent fraud, the Programme Strategy Board will take a report on programme processes annually and an audit trail will be maintained to show all financial decisions taken at programme and project level.
#### Risks to the programme spending as planned

Risks to programme spending are included in the programme risk register in the Management Case.
### HMT Approval

HMT approval was received for the release of the Programme at OBC stage. Further HMT approval was secured for the Energy programme given that the contract value is over £15m. All Prosperity Fund programmes which are deemed to be novel and/ or high risk programmes will be reviewed.

## Management Case
### Governance and management structures
The FCO is the appointed lead department and will hold the budget for the Mexico Prosperity Fund Programme l the SRO for the Mexico programme will be Her Majesty’s Ambassador to Mexico who will have overall responsibility for the delivery of the programme’s objectives. The SRO for the Mexico programme will report to the FCO Director who sits on the Cross-Whitehall Portfolio Board, creating a reporting line into the overall portfolio. The FCO Americas Directorate will delegate authority for the allocated funds to Post, both in terms of management of public money and ensuring compliance with the International Development Act. The Senior Budget Holder for the Mexico programme will be Her Majesty’s Ambassador to Mexico who will be accountable through their annual appraisals for their fiduciary responsibilities including spending money in the public interest and ensuring value for money.
Post will liaise with Other Government Departments (OGDs) to ensure that the programme remains aligned with HMG policy priorities, however OGDs are not responsible for the delivery of the Fund. We will continue to consult HMT, DIT, CO, BEIS, DfT, MoJ, DfID, amongst others.
### Strategic programme management
The programme in Mexico will be governed at three levels (with the Ambassador as SRO holding overall responsibility for financial and reputational oversight, reporting into the Portfolio structure via the Director on the Cross-Whitehall Board):
#### Strategy Board
 This will be chaired by the Ambassador, and consist of HMG representatives (London and Mexico including Embassy, and Americas Directorate), senior levels of the Mexican government, British and international businesses in Mexico, civil society and other donors. In addition, senior representatives of the four delivery partners will be asked to attend the group once a year to report on progress of their strand of the programme. The group will meet regularly with two objectives:

- Ensure proper strategic oversight of programmes
- Maximise the impact of programmes on the Mexican economy/society.

Members of the Strategy Board will play an advisory role. Responsibility for decision-making for the programme remains with the SRO who may take into account the views of the Strategy Board but ultimately will take the final decision.

Management Committee

This will be chaired by the Prosperity Counsellor, and consist of Embassy Section Heads, procurement and economic representatives, and London portfolio representation. Policy Coordinators of Virtual Teams and Programme Managers will also attend as observers.

As well as reporting to the Strategy Board, the Management Committee will report directly to the SRO on a monthly basis.
#### Virtual teams
Virtual teams bring together representatives from the Programme, Policy and DIT teams in the Embassy around a specific policy area. The teams are ‘virtual’ as individuals do not sit within the same section of the Embassy or share a line-management chain. They are often not physically co-located as they sit with their section team, although they may be co-located where circumstances allow.
The virtual teams will be the primary structure for ensuring effective governance of the various strands of the programme. The diagram below sets out how the structure fits together and can incorporate additional strands from whatever centrally led sector programmes become approved in Mexico.
### Management structure of the Mexico Programme

Steering Board
Management Committee
SRO Mexico (HMA)
SRO Portfolio (PUS)
Central Programme Management Office
Energy Virtual Team
Future Cities Virtual Team
Financial Services Virtual Team
Business Environment
Virtual Team
Global Programmes Virtual Teams
Policy and Political officers (analysis)
Programme strand officers (interventions)
DIT officers (commercial follow-up)
In London, the Mexico Prosperity Fund will be governed by:

- Annual updates to the Prosperity Fund Ministerial Board
- Six-monthly discussion with FCO Minister responsible for the programme
- Her Majesty’s Ambassador (HMA) to Mexico as SRO for the Mexico Prosperity Fund programme, reporting into the Portfolio SRO (Permanent under Secretary) and his delegated representatives.
- Advice from PFDU, JFU, EDD and other central FCO units responsible for oversight of the Fund
- Monitoring, Reporting, Evaluation and Learning which will be designed through the Monitoring, Reporting, Evaluation, Learning (MREL) contract in London as set out below.
The programme team consists of a central programme management team and a programme and policy sub-team for each of the strands of the business case. Staffing structures for programme, Prosperity funded staff, are set out in the figure below with further detail on roles and responsibilities in the focus box.

Programme team (2017/18 – 2021/22)

Central Programme Management Team
0.3 x D7 Prosperity Counsellor
1 x D6 Head of Prosperity Fund
1 x C4 Head of Procurement / Regional Implementation Manager
1 x B3 Communications Officer
1x C4 Economist
Energy

1xC4 Programme and Policy Manager

1x B3 Programme and Policy Officer

0.5x Programme Delivery Support Officer
Future Cities

1xC4 Programme and Policy Manager

1x B3 Programme and Policy Officer

0.5x Programme Delivery Support Officer
Financial Services

1xC4 Programme and Policy Manager

1x B3 Programme and Policy Officer

0.5x Programme Delivery Support Officer

ACROL

1xC4 Programme and Policy Manager

1x B3 Programme & Policy Officer

0.5x Programme Delivery Support Officer
The primary focus of all of the above staff is to secure the primary programme objective (poverty reduction). All staff will also have a role in ensuring both secondary (indirect UK commercial benefits) and tertiary (public diplomacy) benefits of the programme are realised. This will include representational work – leading on Government to Government engagement to support delivery partner’s work, ensuring UK presence and branding of programme activities and liaising with UK companies and DIT teams regarding potential commercial opportunities.

Monitoring, Reporting, Evaluation & Learning
The MREL for this programme will be consistent with the Fund approach to MREL (provided that the Fund-level approach is up and running in time for the start of this programme), as detailed by PFMO below:

##### Results framework
We will work with the Fund contractors to develop critical indicators for Fund and programme level reporting, identifying specific indicators for regular reporting and management indicators. The programme MREL will be consistent with the programme theory of change and the log-frame analysis that flows from this. We will report expenditure monthly and impacts (results) quarterly in line with Fund reporting rhythms.

##### Reporting frequency and costs
Consistent with our Fund requirements we will instruct the implementer for the programme to develop a quarterly results reporting system and will work with the Fund Monitoring and Reporting contractor to ensure consistency with Fund processes and systems – particularly around data quality and consistency. Programme data capture and baselining will be the responsibility of the programme and its implementers.

##### Evaluation and Learning
 We will work with the Fund Evaluation and Learning contractor to develop the strategic questions that will be required for both the fund evaluation and programme evaluation. The overarching evaluation methodology will be decided by the fund level evaluators and we will work to deliver the required coordination between the various contractors at programme level. These questions may include fund level questions if appropriate. We further note that it will not be possible to evaluate all programmes and as part of the coordination with the evaluation contractors we will assess this and decide on a way forward with the PFDU.

##### Monitoring and Reporting
Responsibility for data capture, base-lining and reporting sits with the programme managers and their implementers. Indicators will need to be agreed with the fund level monitoring and reporting contractor, the evaluators and the programme implementers. The monitoring and reporting contractor will identify the data requirement in terms of format and quality. We will work with our stakeholders to ensure that reporting is done in a timely and useful manner. Results will be reported up to the Management Committee and Strategy Board, and to portfolio governance structures in London.

##### Adaptive & Flexible Programming
The programme structure will support adaptive and flexible programming. The ToRs and the Call off Contract Terms and Conditions ensure that the programme can be adapted to changing demands, as advised through the Programme Management Committee and the Strategy Board.
Changes in context and priorities will be managed through ensuring flexibility between strands to allow for re-distribution of resources based on the deliverables that yield the highest impact on policy developments and commercial opportunities. The programme will continue to have a strategic engagement plan with the Mexican government (at federal and state level) and the private sector throughout, including through high-level talks such as the UK-Mexico High-Level Economic Talks.
#### Stakeholder management, communications and branding
External communications will be an important part of ensuring the success of the Mexico Prosperity Fund programme. The key focus of the programme is policy reform which will need strong buy-in from the Mexican Government and other stakeholders. A close association between the programme and HMG will therefore be vital.
In order to maximise awareness and understanding of the programme, and to help ensure that beneficiaries and partners understand that this is a British government initiative, even though delivery may be outsourced, we will explore branding and identity options (guided by HMG principles and PFDU Communications Guidance) as part of the contracting process. Communications will be co-led by the Programme Management team, which has a dedicated programme communications officer, and implementing partners.
### Risks
The key risks for this programme are outlined in the risk analysis below, within which the likelihood of the risk occurring, the impact and mitigation strategies has been assessed collaboratively across the Embassy. A full Infrastructure and Projects Authority (IPA) Risk Potential Assessment for the programme has been carried out and submitted. The Mexico programme is assessed as ‘low’. The key risks in the programme are:

- Misalignment between the priorities of the government and the programme.
- Tendency of most commercial partners and implementers to be based in and focus primarily on the capital city. Many of Mexico’s poorest and most developing areas are beyond Mexico City.
- Difficulty in measuring Primary Purpose and Secondary Benefits for each programme
- Exchange rate fluctuations continue. As experienced in 2011 – 2017, managing programmes worth up to £28m, exchange rate fluctuations presents a risk between the Mexican peso and Pound sterling. Historically the peso has depreciated against the pound. Volatility is expected to continue over coming years.
- Failure to implement the programme with a gender focused strategy
- Funds are diverted and used inappropriately
- Mexico programme efforts are duplicated with other donors or other HMG programmes
- UK is seen to be too focused on securing commercial secondary benefits for the UK through the use of ODA funds
- A human rights abuse is indirectly linked to our programme
- Mexican government may be deterred from looking to the UK for its expertise.
- Mexico not considered a priority market for UK companies.
### ODA Compliance
As stated throughout the business case, the Mexico programme, with funding from the Prosperity Fund will be fully ODA compliant. The Prosperity Fund programme for Mexico has been designed to be consistent with the legal requirements under the Development Assistance Committee (DAC) and the International Development Act 2002 as well as with our obligations under human rights legislation.
All activities under the Mexico programme will have economic development and welfare as the main objective and will contribute to a reduction in poverty in Mexico. The fund will not be used to finance military aid (including the supply of military equipment and services), enforcement of peacekeeping, civil police work[102], and assistance to refugees, nuclear energy or anti-terrorism. These requirements will be applied to all contracted-out partners. No funding will be tied.
[102] Under OECD guidance, expenditure on police training is reportable as ODA, unless the training relates to paramilitary functions such as counter-insurgency work or intelligence gathering on terrorism. OECD. “Is it ODA” http://www.oecd.org/dac/stats/34086975.pdf