PROSPERITY FUND

ASEAN Economic Reform programme (renamed from South East Asia Economic Reform Programme)
Business Case
As at 31 October 2018

Executive Summary

1. This business case investigates the opportunities to promote inclusive economic growth in SE Asia and for increasing global prosperity, including for the UK, through the use of £19m of Prosperity Fund Official Development Assistance (ODA). The funding will deliver a four year programme of economic reform covering business environment and financial and business services. This programme helps to progress the UN’s Sustainable Development Goals (SDGs) and is expected to deliver £351m of primary (poverty reduction) benefits and £352m of secondary (opportunities for international and UK business) benefits over 10 years.
2. South East Asia has a population of more than 600 million people. It is equivalent to the world’s 7th largest economy and is expected to be the 4th largest by 2030. SE Asia has experienced a decade of high economic growth however, there are still 87m people below national poverty lines, 38m people who fall below the World Bank’s $1.90 a day poverty measure[1]. Economic inequality is growing.
  [1] Statistic excludes Burma for which there is no data
3. Challenges on poverty reduction remain, stemming from uneven and unequal economic growth and the fragility of some recent advances (e.g. on healthcare). Making the transition from a middle income to high income country is challenging and requires a different approach to moving an economy from low income to middle.
4. SE Asia is increasingly important to the UK in both international diplomacy and trade. ASEAN is the third largest non-EU export market for the UK – after the US and China – worth £14.2bn in 2016. SE Asia delivers four times more inward investment into the UK than China does. But the UK is still relatively underrepresented in terms of our trade relationship with SE Asia compared with other European partners.
5. This programme will operate in the six largest South East Asian countries (the ‘PF6’: Burma, Indonesia, Malaysia, the Philippines, Thailand and Vietnam), covering 95% of SE Asia’s total population and those in poverty (both metrics) and 86% of SE Asia’s GDP.
6. This Economic Reform programme covers two themes: business environment and financial and business services. These are central to inclusive economic growth and support further sector-specific Prosperity Fund work.

- Business Environment: Improving the business environment can deliver a significant boost to economic growth, with each regulatory reform associated, on average, with a 0.15% increase in growth.[2]
  [2] Haidar, J. I., 2012, “The impact of business regulatory reforms on economic growth”, Journal of the Japanese and International Economies, 26: 285 – 307
- Financial and Business Services: Economic growth would be more stable and inclusive if the region’s capital markets were developed further. Growth from financial development can be inclusive only by meeting the financing needs of households and firms, including the underprivileged[3].
  [3] Asian Development Outlook 2015: Financing Asia’s Future Growth. Asian Development Bank, page 71
The Prosperity Fund Economic Reform programme has been designed to address these issues, looking at where the UK can add the most value.
# Acronyms
ACMF	–	ASEAN Capital Markets Forum
ADB	–	Asian Development Bank
AEC	–	ASEAN Economic Community
ASEAN	–	The Association of South East Asian Nations was established in 1967 with the purpose of
fostering cooperation between ten member countries namely Burma, Brunei Darussalam,
Cambodia, Indonesia, Laos, Malaysia, the Philippines, Singapore, Thailand, and Vietnam.
ASEAN-5 –	Indonesia, Malaysia, the Philippines, Thailand, Vietnam
BEIS	–	Department for Business, Energy & Industrial Strategy
BER	–	Business environment reform
BHC	–	British High Commission
BRDO	–	Better Regulation Delivery Office
CEDAW –	Convention on the Elimination of All Forms of Discrimination against Women
DFID	–	Department for International Development
DIT	–	Department for International Trade
EDD	–	Economic Diplomacy Directorate
ER	–	Economic Reform
ESE	–	East and Southeast Asia
EU	–	European Union
FCO	–	Foreign and Commonwealth Office
FDI	–	Foreign Direct Investment
FinTech –	Financial Services Technology
FSD	–	Financial services development
FTA	–	Free Trade Agreement
FTE	–	Full Time Equivalent
GDP	–	Gross Domestic Product
GII	–	Global Innovation Index
GINI	–	income inequality index measuring the extent to which the distribution of income (or, in
some cases, consumption expenditure) among individuals or households within an economy deviates from a perfectly equal distribution
GIZ	–	Gesellschaft für Internationale Zusammenarbeit
GSO	–	General Statistics Office
GVC	–	Global value chains
HMG	–	Her Majesty’s Government
IDA	–	International Development Act
IEA	–	International Energy Agency
IMF	–	International Monetary Fund
IP	–	Intellectual Property
IPA	–	Infrastructure and Projects Authority
IPO	–	Intellectual Property Office
JFU	–	Joint Funds Unit
JICA	–	Japanese International Cooperation Agency
KPIs	–	Key Performance Indicators
MoU	–	Memorandum of Understanding
MREL	–	Monitoring, Reporting, Evaluation and Learning
NCDs	–	Non-Communicable Diseases
NPV	–	Net Present Value
NSPAW –	National Strategic Plan for the Advancement of Women
ODA	–	Official Development Assistance
ODA-8	–	Prosperity Fund-6 countries plus Cambodia and Laos
ODI	–	Overseas Development Institute
OECD	–	The Organisation for Economic Cooperation and Development
OGD	–	Other Government Department
OJEU	–	Official Journal of the European Union
PF6	–	‘Prosperity Fund 6’ comprise of countries including Burma, Indonesia, Malaysia, the
Philippines, Thailand, Vietnam
PFDU	–	Prosperity Fund Delivery Unit (FCO)
PPP	–	Public Private Partnership
REA	–	Rapid evidence assessment
SDG	–	Sustainable Development Goals
SE Asia	–	South East Asia, comprising the ten nations of ASEAN listed above
SMAA	–	Standard Model Administration Arrangement
SRO	–	Senior Responsible Officer
TPP	–	Transpacific Partnership Agreement
UKCCU	–	UK Climate Change Unit
UN	–	United Nations
UNDP	–	United Nations Development Programme
UNESCAP –	United Nations Economic and Social Commission for Asia and the Pacific
VFM	–	Value for money
WB	–	World Bank
WEO	–	World Economic Outlook

Contents

Strategic Case
This business case investigates the opportunities to promote inclusive economic growth in SE Asia and for increasing global prosperity, including for the UK. This Prosperity Fund programme would deploy £19m of Official Development Assistance (ODA) to pursue these objectives.
## South East Asia and country selection rationale
South East Asia has a population of more than 600 million people and is equivalent to the world’s 7th largest economy. It is the fourth-largest exporting region in the world, trailing only the EU, North America, and China/Hong Kong, and accounts for 7% of global exports. It is a major hub for manufacturing and well positioned in global trade flows. Developing Asia has experienced a decade of high economic growth that has lifted 1bn people out of poverty (1990-2012)[4] and allowed the region to meet the first of the Millennium Development Goals: halving between 1990 and 2015 the proportion of people whose income is less than $1 a day. However, there are still 87m people below national poverty lines in SE Asia and 37.9m people who fall below the World Bank’s $1.90 poverty measure,[5] of which 2/3rd are women[6]. While still comparatively strong globally (2.4% projected global growth 2016[7]), growth in Southeast Asia has moderated in recent years[8], productivity is levelling out and the gains of the last decade face increasing threat from the uncertain global economy, on which the SE Asia economy is highly dependent. Additionally, just as SE Asia is dependent on global growth, global growth is increasingly dependent on Developing Asia giving all players in the global economy an incentive to foster Asian growth.[9] SE Asia is increasingly important to the UK too in both international diplomacy and trade. In addition to our diplomatic co-operation on global challenges such as climate change and illicit trafficking, the UK continues to develop its defence and security partnerships with countries across the region in areas such as counter-terrorism, maritime security, and cyber security. ASEAN is the third largest non-EU export market for the UK – after the US and China – worth £14.2bn in 2016. UK exports to SE Asia compared favourably to our exports to other major players in 2016: China £16.7bn, India £6.6bn and Brazil £3.8bn.[10] SE Asia delivers four times more inward investment into the UK than China does but the UK is still relatively underrepresented in terms of our trade relationship with SE Asia compared with other European partners.
[4] Asian Development Outlook 2016: Asia’s Potential Growth. Asian Development Bank, page xvii
[5] Statistic excludes Burma for which there is no data
[6] UN Women, 2013
[7] Global economic prospects: A fragile recovery (World Bank Group, 2017)
[8] Average 4.6% in the region in 2015 compared to 9.4% average 2005-2007. Average 4.6% in the region in 2015 compared to 9.4% average 2005-2007. Economic and Social Survey of Asia and the Pacific 2016: Nurturing productivity for inclusive growth and sustainable development. UNESCAP, page 96
[9] Asian Development Outlook 2016: Asia’s Potential Growth. Asian Development Bank, page xvii
[10] United Kingdom Balance of Payments - The Pink Book: 2018
### Geography and History of Southeast Asia
1. Southeast Asia is a geo-political construct describing countries to the east of the Indian subcontinent and south of China. Its easterly border is generally taken to be the Philippine Sea and to the south it borders Papua New Guinea and Australia. The term originated in the Second World War and there is no universally agreed list for which countries it includes.
2. More recently, Southeast Asia has been characterised by high economic growth, particularly in Singapore and the “ASEAN 5”: Indonesia, Malaysia, the Philippines, Thailand and Vietnam, and by closer regional integration. Burma, Cambodia and Laos have typically grown more slowly and have remained poorer, in part due to political instability.
3. Alongside country-specific and multi-country analysis, the strategic case will look across ASEAN (The Association of Southeast Asian Nations). ASEAN was established in 1967 with the purpose of fostering cooperation between the 5 countries of South East Asia in the economic, social, cultural, technical, educational and other fields, and in the promotion of regional peace and stability through respect for justice and the rule of law.
Programme country selection
1. The programme is designed to operate regionally within SE Asia. The regional approach has been selected because:
  1. It echoes how the region self-organises through ASEAN. This provides proven delivery pathways and clear signals about direction of travel in economic reform and governments’ prioritises
  2. It provides opportunities for lesson learning from peers among countries in the region.
  3. A regional approach will drive regional harmonisation which will improve the conditions for intra-region and international trade, improving economic growth.
  4. The marginal cost of including a country is low because the programme is able to utilise regional programme delivery partners
2. While the regional approach offers opportunities to leverage regional cooperation among countries and for economies of scale, there is a risk of fragmentation. We therefore sought to reduce the countries covered to the minimum number for which the benefits of a regional approach could still be realised. Of the 10 SE Asian countries[11], only 8 are eligible for ODA so Singapore and Brunei were automatically excluded.
  [11] Burma, Brunei, Cambodia, Indonesia, Laos, Malaysia, the Philippines, Singapore, Thailand, Vietnam
3. Burma, Indonesia, Malaysia, the Philippines, Thailand and Vietnam are good fits for the programme. We have termed these the ‘PF6’ for the purposes of this programme. All except Burma are middle-income, populous and economically fast growing which will provide the right conditions for the Prosperity Fund to promote inclusive economic growth through economic reform to a high number of people. Burma has a high total number of people in poverty and high predicted economic growth, giving it strong primary benefit potential and a good chance of benefitting from economic reform in the near term as its economy grows.
4. Laos and Cambodia are not such good fits for the programme. Laos and Cambodia have less developed and diverse economies than their neighbours, so are less suited to this type of programme which focusses on economic reform: the business environment, financial, business services. Despite focusing on only 6 of the 10 SE Asian countries, it will still be possible to realise the benefits of the regional approach. As the table below indicates, the PF6 countries make up 94.5% of the population of South East Asia, 90.5% of its landmass, 86% of its GDP and 95.7% of its population below national poverty lines and 96% below the World Bank $1.90 poverty measure.

Country	Population (m)	GDP (US$ bn)	People living below World Bank $1.90 measure		Population below the national poverty line		Land mass (km2)
			Percentage	Number (m)	Percentage	Number (m)
Brunei	0.4	13	-	-	-	-	5 770
Burma	54	60	NA	NA	25.6[12]	13.8	678 500
Cambodia	16	18	2.2	0.3	17.7	2.1	181 035
Indonesia	258	862	8.3	21	11.3	28.9	1 904 556
Laos	7	12	6.7	1.1	23.2	1.6	236 800
Malaysia	30	296	0.3	0.1	0.6	0.18	329 750
Philippines	101	292	13.1	12.6	25.2	25.4	300 000
Singapore	6	293	-	-	-	-	693
Thailand	68	395	-	-	10.5	7.4	514 000
Vietnam	92	194	3.1	2.8	13.5	7.7	329 560
PF6 as a % of total SE Asia figure	95.4%	86%	96.3% of those below $1.90 a day[13]		95.7% of those below national poverty line		90.5%
[12] ADB Basic 2017 Statistics: Economic Research and Regional Cooperation Department, April 2017
[13] Statistic excludes Burma for which there is no data

1. We will also use “South East Asia” analysis as a proxy for the PF6 countries where there is existing analysis of the region which cannot easily be disaggregated into individual countries.
2. Analysis of these 6 countries – the PF6 – will look at their unique features and also their similarities to identify common barriers to growth that can be tackled with a multi-country approach and recognising where country-specific issues need addressing where, There may also be benefits to working initially with 1 or 2 countries on a theme where they have particular interests or expertise. The aim will be to avoid a fragmented programme and deliver co-ordinated interventions
3. The PF6 countries on which we are focused have a strong drive for regional integration under the ASEAN Economic Community (AEC). The Prosperity Fund may have a role to play pursuing this objective which aligns with the aims of the Prosperity Fund, goes with the grain of how ASEAN organises itself, maximises the multiplier effect and helps promote regional harmonisation. Where ASEAN-level programming is identified as the most effective way to promote inclusive economic growth, funding may be extended to Laos and Cambodia to participate in the programmes, furthering regional integration. This might be the case, for example, if the ASEAN organisation itself is developing regional standards on low carbon issues. Work with the ASEAN secretariat[14] will include Brunei and Singapore as ASEAN members, but no programming will take place in either country and no funding will be extended to them.
## Economic, poverty and socio-political context in the PF6 countries
### Economic Context
#### Economic trends and current situation across the PF6 countries
##### Major trends in the PF6
1. Macroeconomic stability has provided a platform for growth The PF6 countries proved to be remarkably resilient in the aftermath of the 2008 global financial crisis. Generally economic growth has been less volatile than in other regions and GDP has outperformed average global growth.
2. GDP per capita growth has dramatically outpaced the rest of the world since the late 1970s. Income growth has remained strong since 2000, with average annual real gains of more than 5 percent.
3. As the PF6 countries have developed more sophisticated manufacturing capabilities, their exports have diversified. The PF6 countries also sit at the crossroads of many global flows. By 2025, more than half of the world’s consuming class will live within a five-hour flight of Burma.[15]
  [15] Ibid, point 5
4. SE Asia’s rapid reduction of people in poverty has led to one of the world’s fastest growing consumer markets. 67 million households in SE Asia are already part of the “consuming class,” with incomes exceeding the level at which they can begin to make significant discretionary purchases.[16] That number could almost double by 2025, making the PF6 a pivotal consumer market of the future.
  [16] Ibid, introduction
##### Current economic situation
Real GDP growth in the PF6 economies is expected to remain robust. Average annual growth is estimated to be extremely robust by global standards for the rest of the decade, at 5.1% between 2017-21[17]. Patterns of growth vary between countries in the PF6. Burma’s growth is expected to be the highest in Emerging Asia in the coming years. The Philippines and Vietnam will continue to set the pace in the PF6, while Indonesia, Malaysia and Thailand can expect fairly stable or improving growth.
[17] OECD Economic Outlook for Southeast Asia, China and India (2017)
Figure 1: Growth rates for PF6 countries (Nominal GDP Growth, constant prices)[18]
[18] ASEAN figures are estimated using weighted average share of GDP (PPP$) to world total, as in the IMF WEO Database of April 2016 Source: ASEAN Secretariat and IMF World Economic Outlook 2016

%GDP growth
Years
Sources of economic growth
Labour-force expansion and productivity improvements have generally driven GDP growth. SE Asia has the third-largest labour force in the world, behind China and India; its youthful population is producing a demographic dividend. Perhaps most importantly, almost 60% of total growth since 1990 from PF6 countries has come from productivity gains, as sectors such as manufacturing, retail, telecommunications, and transportation grow more efficient.[19] Female participation in the labour force is an on-going issue in SE Asia. Women in Asia are on average 70% less likely than men to be in the workforce, with great disparities amongst countries[20], and women labour force participation has not evolved much in the last 25 years[21]. This is clearly a missed opportunity, as there is evidence that high level of female participation in the labour force leads to greater economic prosperity. Recent studies show that closing the gender gap could generate a 30% increase in the per capita income of an average Asian economy in one generation[22].
[19] Priority Areas for Growth with Inclusion in ASEAN, (World Economic Forum, 2016)
[20] 2014 Gender Gap Index (global ranking): Philippines (7), Thailand (71), Vietnam (65), Indonesia (88), Malaysia (106), Burma (no available data)
[21] Female labor force participation (1997-2017), World Bank Data, Retrieved September 2017
[22] Women in the workforce: an unmet potential in Asia and the Pacific, Asian Development Bank, 2015
Table 1: Female labour force participation (%) World Bank Data 2017
	2012	2013	2014	2015	2016	2017
Burma	50	50	50	50	50	50
Indonesia	38	38	38	38	38	38
Malaysia	36	38	38	38	..	..
Philippines	39	39	39	39	39	39
Thailand	46	45	45	45	45	45
Vietnam	48	48	48	48	48	48

Table 2: WEF Gender Gap Index (Score and Ranking, 2016)
	Overall Index		Economic Participation and Opportunity		Educational Attainment		Health and Survival		Political Empowerment
Country	score	rank	score	rank	score	rank	score	rank	score	rank
Philippines	0,786	7	0,780	21	1,000	1	0,980	1	0,386	17
Vietnam	0,700	65	0,736	33	0,978	93	0,950	138	0,138	84
Thailand	0,699	71	0,770	22	0,990	74	0,980	1	0,057	131
Indonesia	0,682	88	0,598	107	0,987	87	0,976	58	0,168	72
Malaysia	0,666	106	0,658	80	0,985	89	0,969	109	0,051	134

NB: Figures not produced for Burma
1. Private consumption and fixed investment are the 2 main demand-side drivers of growth in the PF6 countries. Services and to some extent, industry, are the main supply-side drivers.
2. International trade in goods — along with other types of cross-border flows — plays a significant role in regional growth. The implementation of the AEC is allowing the freer movement of goods, services, skilled labour, and capital, boosting interregional trade. While tariffs on goods are now close to zero in many sectors, progress on liberalisation of services and investment has been slower, and non-tariff barriers remain a stumbling block to freer trade.[23]
  [23] Vinayak, HV et al, Understanding ASEAN: Seven things you need to know (McKinsey, 2015), Point 6
3. Slowing trade is a big risk for PF6 economies but increases the need for economic reform to find new sources of growth. The US withdrawal from the TPP is likely to have an impact. More broadly, as global export growth continue to falter these economies will not be able to rely on export led growth to improve GDP in the future and will need to find new sources of growth by increasing productivity and developing new trade.
Table 3: Major SE Asia trading partners, 2015 (top 10)[24]
[24] ASEAN External Trade Statistics (ASEAN Secretariat, Nov 2016)
Trade partner country/region	Value (US$ million)			% Share to total ASEAN trade
	Exports	Imports	Total trade	Exports	Imports	Total trade
ASEAN	305 693	238 059	543 751	25.9	21.9	24.0
China (People's Republic of)	134 249	211 515	345 764	11.4	19.4	15.2
Japan	113 694	124 350	238 044	9.6	11.4	10.5
EU 28	127 584	100 056	227 640	10.8	9.2	10.0
United States	129 171	83172	212 343	10.9	7.6	9.4
Korea, Republic of	45 809	76 676	122 484	3.9	7.0	5.4
Taiwan	33 077	61 261	94 338	2.8	5.6	4.2
Hong Kong	77 303	14 113	91 416	6.5	1.3	4.0
India	39 101	19 453	58 554	3.3	1.8	2.6
Germany[25]	26 756	28 755	55 512	2.3	2.6	2.4
Total top 10 trade partner countries	1 032 436	957 411	1 989 847	87.3	88.0	87.6
Others	149 595	130 868	280 463	12.7	12.0	12.4
UK[26]	12 045	12 744	24 789	1.0	1.2	1.1
Total	1 182 031	1 088 279	2 270 310	100.0	100.0	100.0
[25] Germany data is also included in the EU28 figures
[26] UK data taken from ONS Pink Book. Data only includes: Indonesia, Malaysia, Philippines, Singapore and Thailand. UK will also be included in ‘EU28’.

#### The role of the Association of South East Asian Nations (ASEAN) in the PF6 countries
#### The ASEAN Economic Community
1. As part of ASEAN’s economic integration, the ASEAN agreed to a joint approach to economic integration – The AEC Blueprint 2025.[27] This provides strategic direction for the AEC from 2016 to 2025. Its objective is to establish a common market that extends the principles of free trade to the movement of mobile factors of production, such as labour and capital.
  [27] ASEAN Economic Community Blueprint 2025 (ASEAN Secretariat, 2015)
2. This approach presents a clear and structured framework for UK economic cooperation to assist in delivering the AEC blueprint. Progress has been strong to date on lowering trade tariffs. Progress on non-trade barriers has been slower however, with a dearth of collective political will, no enforcement mechanisms and domestic interests trumping regional priorities the primary causes.[28] Overall progress of integration can, inevitably, be relatively slow. Therefore it is also vital that ASEAN countries – such as the 6 supported by our proposed programme – pursue implementation of supportive domestic policies that, if not enacted, can delay regional integration. Such supportive policies facilitate deeper co-operation and improve long-term commitments to regional integration.
  [28] B. Tanjangco, ASEAN Integration: A Work in Progress (April 2017)
### Poverty context
#### Poverty levels in SEA, geographical spread, trends in recent years.[29]
[29] Poverty and Equity database (World Bank Databank, 2017), latest available data
1. Poverty reduction in SE Asia has been making good progress albeit the persistent problem in addressing absolute poverty. Efforts are marred by rising inequality greatly affecting rural areas and ethnic minorities in the PF6 countries. Indonesia and the Philippines, having the biggest populations in PF6 countries, have the highest percentage of people living below the national poverty line. On the other hand, Malaysia has a relatively lower poverty level (0.6%) in comparison to the rest of the region but has the highest GINI index (46.3%), showing the degree of inequality of family income distribution in the country. It is apparent that addressing poverty in the region is driven by wide-ranging issues including varying income levels, energy access, gender, education, and health and mortality issues. Inequality and lack of inclusive growth remain as pressure points to help tackle poverty and keep progress on track in SE Asia.
2. On all metrics, in the last decade SE Asia has made great strides in reducing extreme poverty among its 600 million people – 9% of the world’s population. However there are still 87 million people below national poverty lines in SE Asia and 37.9 million people who fall below the World Bank’s $1.90 a day poverty measure,[30] revealing substantial development challenges. Structural problems loom, with a predicted skills shortfall and some countries reaching the end of their demographic dividend of young workers in the near future. Some metrics are moving in the wrong direction: deepening income inequality and environmental degradation are holding back poverty reduction and putting sustainable growth at risk.
  [30] Statistic excludes Burma for which there is no data
3. The factors that drove several decades of poverty reduction will not necessarily continue to contribute in the same way in future years. In most of SE Asia, agriculture accounts for proportionally less of the economy year on year and urbanisation will reduce agricultural growth’s influence on poverty. As the middle-income countries in the region move up the value chain, the role of unskilled workers in the economy is likely to change too. Structural changes in the economies of SE Asia are also driving further inequality and reducing the link between GDP growth and poverty reduction. Rising inequality is hampering poverty reduction and needs to be addressed. If Asia’s economic growth had been achieved without the rise in inequality, an additional 240 million people would have been lifted out of poverty. The 3 main drivers of rising inequality in SE Asia are technological change, globalisation and market-orientated reform. Outlook: Despite some positive trends, poverty reduction is slowing.

Table 4: Population, poverty and inequality[31]
[31] Poverty and Equity database (World Bank Databank, 2017), latest available data at time of writing
Country	Population (m)	People living below World Bank $1.90 measure		Population below the national poverty line		GINI index[32]
		Percentage	Number (m)	Percentage	Number (m)
Burma	54	NA	NA	25.6[33]	13.8	NA
Indonesia	258	8.3	21	11.3	28.9	39.5
Malaysia	30	0.3	0.1	0.6	0.18	46.3
Philippines	101	13.1	12.6	25.2	25.4	43.0
Thailand	68	-	-	10.5	7.4	37.9
Vietnam	92	3.1	2.8	13.5	7.7	37.6
[32] “The GINI income inequality index measures the extent to which the distribution of income (or, in some cases, consumption expenditure) among individuals or households within an economy deviates from a perfectly equal distribution.” World Bank Databank
[33] ADB Basic 2017 Statistics (Economic Research and Regional Cooperation Department, April 2017)

1. Effective national and regional economic reforms in SE Asia could lead to around 200 million more people in SE Asia joining the middle class by 2030 (ADB and UN figures). However, alongside general economic slowdown, “progress on poverty reduction is slowing, inequalities are rising and prospects of decent employment are weakening.”[34] The current economic model in the region is not sufficiently inclusive to cement or extend poverty reduction gains. The creation of decent jobs is low and the benefits of growth are increasingly flowing to the wealthier members of society. In line with global trends, youth unemployment is high in South-East Asia (13% for both[35]). Overall, young people in the labour force are 5.4 times more likely to be unemployed than their adult counterparts. Women are more likely than men to be in vulnerable jobs: 60.1% for women and 52.8% for men.[36] Economic growth is also coming at the price of environmental degradation that is unsustainable and will, if left unchecked, increase the risk of people falling back into poverty.
  [34] Economic and Social Survey of Asia and the Pacific 2016: Nurturing productivity for inclusive growth and sustainable development. UNESCAP, Preface
  [35] Global Employment Trends for Youth 2015: Youth employment crisis easing but far from over. International Labour Organization
  [36] Economic and Social Survey of Asia and the Pacific 2016: Nurturing productivity for inclusive growth and sustainable development. UNESCAP, p36
2. The region has a high proportion of people in the transitional class – those who have moved out of poverty, but are not yet established in the middle class. The group is very vulnerable to falling back into poverty during a persistent decline in economic growth and employment prospects or due to shocks such as disease in the family, loss of the main breadwinner or natural disasters.

### Socio-political context
1. There is a considerable range of political systems across the region, and in a number of countries the current form of government is in transition or has changed significantly over the past few decades. Our assessment is that any future changes of government in the region will be moderated in terms of their international outlook and engagement by each country’s economic reliance on global trade.
2. Indonesia is a large democracy and a member of the G20. Though ethnically diverse, it has the largest Muslim population in the world. President Jokowi’s election in 2014 on a reformist, anti-corruption ticket represented a departure from Indonesia’s traditional dynastic politics. Indonesia’s parliament takes time to deliver reform. Legislation often takes many years to be drafted and passed. This makes it harder for the government to push forward its reform agenda. Lack of coordination and decision making between/within ministries also acts as a brake.
3. Vietnam is a one-party communist state with political power residing in the existing 18-member Politburo. There are human rights concerns, including over freedom of expression. Economically, however, Vietnam is changing significantly towards a more liberalised model.  In particular, Vietnam’s pursuit of ambitious international trade agreements means that it is now appears set on a path of progressive economic liberalisation. The Party has a vested interest in promoting their economic reforms if judged necessary to maintaining Vietnam’s high-growth trajectory.
4. The Philippines is a presidential, representative, and democratic republic. Democracy was restored in 1986 after two decades of autocratic rule. Duterte elected to power in 2016 is both head of state and the head of government. The new administration’s commitment to continue sound macroeconomic policies has boosted investor confidence. There are human rights concerns, in particular over the way that the “war on drugs” is conducted.
5. Malaysia and Thailand are both monarchies, though significantly different. Malaysia is a federal, representative, democratic and constitutional monarchy, since independence in 1957. There was a historical change in Government in Malaysia in May 2018. The new government has shown particular interest in tackling anti-corruption. Progress has been made by introducing requirements for ministers to declare assets, making pledge to improve Malaysia's ranking on Transparency International's Corruption Perception Index and setting up a framework on integrity of civil servants.
6. In Thailand, following a coup in 2014, the military government has introduced a new constitution passed by referendum in August 2016. The new constitution provides for a continuing oversight role for the military through establishment of an unelected senate with the power to nominate a prime minister, who may be a non-political figure if there is no majority candidate. Elections were held in March 2019, but a new government has yet to be formed.
7. Burma successfully navigated is first peaceful, democratic handover of power in April 2016. However the military retains a central role. It still holds 25% of seats in Parliament, and controls the powerful, Defence, Home Affairs and Border Ministries. Daw Aung San Suu Kyi’s civilian government faces a number of challenges as it seeks to transition the country towards a more democratic system of governance, from a centrally controlled economy to a market-based economy, and ending more than five decades of civil war. . International attention on Burma has been dominated by the violence in Northern Rakhine state in August 2017, which resulted in over 700,000 Rohingya fleeing across the border into Bangladesh. The UN Fact Finding Mission on human rights violations and abuses in Burma recommended in August 2018 that senior Burmese military figures should be investigated and potentially prosecuted for crimes against humanity, including genocide.
### Gender equality
1. An increase in female labour force participation results in faster economic growth.[37] According to the World Bank’s 2012 World Development Report: Gender Equality and Development, closing the gender gaps matters for development and policymaking. Greater gender equality can enhance economic productivity, improve development outcomes for the next generation, and make institutions and policies more representative.[38] Over the last decade there are more girls in education, less maternal mortality, more women earning, and more in politics and public bodies[39]. There is acceptance generally in the region that women can earn and control their money, and gain an education. Numbers of women moving to post secondary education training has increased in all the PF6 countries.[40] School life expectancy for girls has risen from 10.2 years in 2000, to 12.2 years for 2012.[41]
  [37] Organization for Economic Cooperation and Development (OECD), Gender Equality In Education, Employment And Entrepreneurship: Final Report To The Mcm 2012. http://www.oecd.org/employment/50423364.pdf p17. See also, Klasen, S. and Lamanna, F. (2009), “The impact of gender inequality in education and employment on economic growth: New evidence for a panel of countries,” Feminist Economics, 15: 3, pp. 91-132 (as retrieved from UN Women, Progress Of The World’s Women 2015-2016: Transforming Economies, Realizing Rights Chapter 4, p. 199).
  [38] Ibid, 312
  [39] ADB
  [40] “Women in SE Asia”, Barbara Watson Andaya. Asia Society Centre for Global Education
  [41] UNESCO Institute for Statistics
2. Most states in SE Asia have committed to gender equality. Most of SE Asia has signed the Convention on the Elimination of All Forms of Discrimination against Women (CEDAW) except Laos and Vietnam. The Philippine Plan for Gender-Responsive Development (PPGD) 1995–2025 outlines policies that enable women to benefit from national development. An Indonesian presidential decree in 2000 obliges all government bodies to mainstream gender in their policies, programmes and budgets. Malaysia’s development plan commits to increasing women representation to 30% in decision making roles/boardroom in government; women representation in Parliament and state legislatives; and in the top 100 corporations; and increasing female participation in the workforce to 55%. Vietnam has clear objectives on gender equality in its National Strategy on Gender Equality 2016-2020 and it’s National Socio-Economic Development Plan 2016-2020, aiming to ensure substantive equality between men and women in all political, economic, cultural and social domains. Burma formed the National Committee for the Advancement of Women, and assigned the Ministry of Social Welfare, Relief and Resettlement responsible for implementing and monitoring the country’s Strategic Plan for the Advancement of Women (NSPAW) – a 10-year plan aiming at advancing women’s status in 12 areas and reaching substantive gender equality in Burma until 2022. Thailand passed a Gender Equality Act in 2015 with a jail term of up to 6 months for anyone committing gender discrimination.
3. Significant disparities on gender remain throughout the region, including with rights to land, gender based violence, and sexual discrimination. Women are significantly more likely to suffer the impact of forced prostitution and forced labour. 18% of parliamentary seats in SE Asia were held by women in 2015.[42] But those reaching highest offices are often by dint of familial connections, and some women politicians and officials continue to be marginalised. In Asia Pacific, women’s wages remain between 70-90% of men’s.[43] The gender parity (ratio of female labour force participation compared to men) has remained fairly static over the past decades at around 0.72.[44] Women form the bulk of unpaid contributing family workers.
  [42] ADB
  [43] Ibid
  [44] Ibid
4. The UNDP 2017 Gender Inequality Index of 188 countries ranks as follows: Malaysia 62nd, Vietnam 67th Thailand 93rd, and Philippines 97th. Indonesia 104th and Burma 106th.
### Constraints to economic development in SE Asia
Challenging business environment
##### Regulatory Reform and Enforcement
1. A poor business environment hampers investment, increases transaction costs and creates a drag on economic growth. With women’s rights often restricted because of gender equality, poor business environment and corruption create additional obstacles to their inclusion in economic activities[45]. Improving the business environment can deliver a significant boost to economic growth and reduce gender inequalities in business. A study based on World Bank Doing Business data finds robust evidence of a positive impact of regulatory reforms on economic growth, with each regulatory reform associated, on average, with a 0.182% increase in growth[46].
  [45] Transparency International, 2008
  [46] Haidar, J. I., 2012, “The impact of business regulatory reforms on economic growth”, Journal of the Japanese and International Economies, 26: 285 – 307
2. The business environment picture across the PF6 countries is varied. Malaysia’s Ease of Doing Business rating is relatively high at 24 out of 190. Conversely, Burma is in the bottom 10% at 171 out of 190.[47] Good progress is being made in some areas but on others is slow due to the difficulty of agreeing a common approach or the lack of capability. Particular issues persist in: bureaucratic and ineffective governance and regulatory frameworks, lack of transparency, inadequate enforcement and underdeveloped financial markets. ASEAN’s Economic Community blueprint provides a ready-made platform to address the problems and all 6 PF6 countries have signed up to implementing the blueprint, giving it good political buy-in. Implementing this plan is predicted to boost regional GDP by 7% by 2025, creating 14 million new jobs.[48] Regulatory reform and harmonisation is expected to benefit SMEs more than large companies (which have the capacity to handle complex regulatory structures) so will encourage more inclusive growth.
  [47] World Bank’s Ease of Doing Business Ranking 2018. PF6’s Ease of doing business rankings: Malaysia (24), Thailand (26), Vietnam (68), Indonesia (72), Philippines (113), Burma (171)
  [48] ASEAN Community 2015: Managing Integration for better jobs and shared prosperity, xii. ADB 2104
##### Inefficient allocation of finance and lack of access to financial services
The Asian Development Bank sets out three changes to allow the financial sector to contribute to regional prosperity:[49]
[49] Asian Development Outlook 2015: Financing Asia’s Future Growth. Asian Development Bank, xvi-xix
1. Develop the financial sector to benefit from the economic growth dividend it delivers
2. Expand and broaden financial access to achieve more inclusive growth
3. Safeguard the region's financial stability to secure long term prosperity
1. Financial markets are relatively well developed and regulated in comparison to other developing economies, with the exception of Burma. But there is an over-reliance on expensive bank finance and economic growth would be boosted by further development of the region’s capital markets. The World Bank has identified below (global emerging market) average levels of private sector investment as one of the key factors preventing SE Asian countries reaching their full growth potential. Economic growth would be boosted and made more stable and inclusive by further development of the region’s capital markets. Inclusive economic growth includes financial inclusion: ready access for households and firms to reasonably priced financial services. For example, boosting developing Asia’s average ratio to GDP of liquid liabilities—currency plus checking and interest-bearing accounts in financial institutions—from 65% to 75% adds almost 0.4 percentage points to average annual GDP growth per capita. Also, on average, an increase of 10 percentage points in developing Asia’s average ratio of private credit to GDP (an alternative measure of financial depth) is associated with higher growth in GDP per capita by 0.3 percentage points per year.[50]
  [50] Asian Development Outlook 2015: Financing Asia’s Future Growth. Asian Development Bank, page 53
2. Emerging markets in the region are under-insured (non-life insurance), a particular problem given SE Asia’s high incidence of natural disasters and exposure to the effects of climate change. Growth from financial development can be inclusive only by meeting the financing needs of households and firms, even the underprivileged[51]. Significant segments of the population have limited access to the formal financial sector. For example only 21% of adults in Burma have access to a bank account. Governments are keen to promote greater participation in the financial sector, especially by women and in rural areas and by promoting Islamic Finance where there are significant Muslim populations. There are also opportunities to support existing reforms to increase digital access to finance (e.g. e-payments) and greater use of FinTech in several SE Asian economies. This would improve the ease of doing business, which is important for the country’s development and to attract foreign trade and investment.
  [51] Asian Development Outlook 2015: Financing Asia’s Future Growth. Asian Development Bank, page 71
##### Variable openness to trade
The World Bank (2015)[52] estimates that about 70% of global trade is now associated with global value chains (GVC), and that developing countries with high GVC participation have a median per capita growth rate almost five times higher than those with low participation. The AEC explicitly aims at ‘enhancing participation in the global value chain’, as well as aiming to increase intra-regional trade. The prize to be gained from increased trade is substantial. The PF6’s progress to date has been mixed. Protectionism/nationalism has been a growing constraint to economic growth in Indonesia and also remains a concern in the Philippines. In Burma, where many sectors are opening up after decades of state-enforced isolation, protectionist sentiment is stymieing growth and innovation, as well as deterring foreign trade and investment. Combined with weak infrastructure and a poor business environment, protectionism reduces these countries’ export competitiveness and ability to attract foreign investment. As an example of the economic benefits of openness, Vietnam is expected to see a 7-8% cumulative boost to its GDP by 2025 as a result of the recently signed EU FTA[53] and 13.6% increase over the same time frame from the TPP[54].
[52] The World Bank Briefs: Global Value Chains, July 2015
[53] Vietnam Ministry of Trade
[54] ‘Harvard Prof: Vietnam Could See 13.6% GDP Growth by 2025’, The Saigoneer, 10 April 2014
Social Infrastructure constraints
SE Asia’s growth to 2025 will come from 142 cities with populations between 200,000 and 5 million.[55] Yet Southeast Asian cities are often inefficient, congested and polluted; unable to meet the enormous demand for essential services. Unsustainable urbanisation stems from a lack of strategic planning and increases vulnerability to frequent climate and weather shocks. Improving the quantity and quality of physical infrastructure will be a vital requirement for ensuring SE Asia’s pace of urbanisation is sustainable and the benefits of inclusive growth are achieved. Similarly, lack of capacity and capability in health provision continue to threaten and undermine growth potential in the region. Disadvantaged populations such as the poor, people living in rural or remote areas, are the hardest hit. Increasing urbanisation will also put pressure on education systems demanding higher spending on enhanced education[56].
[55] Understanding ASEAN: Seven things you need to know, by Vinayak HV, Fraser Thompson, and Oliver Tonby, May 2014. McKinsey, point 4
[56] Trends Shaping Education 2014 Spotlight 3: Urban Life: The Rise of the Megacity. OECD. 2014
Unsustainable energy provision and increased environmental risks, including from climate change
The International Energy Agency (IEA) forecasts that SE Asian energy demand will increase by 80% by 2040. Regional electricity demand will triple. This carries with it the imminent concern on increased carbon emissions as a result of main energy challenges including energy access, lack of renewable energy and insufficient energy efficiency[57]. Mitigating and adapting to climate change is an economic imperative if poverty reduction wins are to be protected.
[57] Enhancing regional cooperation for sustainable energy in Asia and the Pacific, Note by the secretariat. UNESCAP. 5 April 2017
## The UK as a development partner for ASEAN
### UK and SE Asia trade relationship
ASEAN is the third largest non-EU export market for the UK – after the US and China – worth £14.2bn in 2016. UK exports to SE Asia compared favourably to our exports to other major players in 2016: China £16.7bn, India £6.6bn and Brazil £3.8bn.[58] But the UK is still relatively underrepresented in terms of our trade relationships compared with other European partners. The UK also exports proportionally more business services to ASEAN than the rest of the world, but less financial, insurance and tech services. Trading opportunities are improving with the populous and rapidly growing but more challenging emerging markets: Indonesia, the Philippines, Vietnam, and Burma. In these markets the business environment and the lack of maturity in the financial sector are key obstacles to increasing trade.
[58] Pink Book 2016
Table 5: UK Goods, Services and Total Exports to ASEAN-6 in 2016 and 2017
Source: ONS Pink Book 2015
	Goods			Services			Total Exports
	2014 (£m)	2015 (£m)	% change	2014 (£m)	2015 (£m)	% change	2014 (£m)	2015 (£m)	% change	As % of total UK exports
ASEAN-10	7670	8056	5.0	5549	6215	12.0	13219	14271	8.0	2.8
Indonesia	499	480	-3.8	330	443	34.2	829	923	11.3	0.2
Malaysia	1477	1409	-4.6	906	798	-11.9	2383	2207	-7.4	0.4
Philippines	301	416	38.2	188	212	12.8	489	628	28.4	0.1
Thailand	1463	1289	-11.9	607	604	-0.5	2070	1893	-8.6	0.4
Vietnam	334	397	18.9	238	130	-45.4	572	527	-7.9	0.1

### Existing Aid landscape and the UK as a development partner
#### Aid Landscape
While there is still significant engagement from Western aid donors, their focus is increasingly shifting away from Asia towards sub-Saharan Africa and the Middle East. The Asian Development Bank (ADB), the Japanese International Cooperation Agency (JICA), the World Bank and Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ, a German development agency) are all active in the region, among others. Along with the rest of Asia, donor activity in SE Asia tends to focus on two areas that reflect donor objectives in the region. The first is promoting inclusive economic growth, including on gender equality, protecting human and environmental rights and advancing democracy. The second is preparing for and responding to the frequent, devastating natural disasters. A greater focus on bringing these two objectives together could yield dividends for creating sustainable economic growth. Those who are most vulnerable to environmental disaster tend also to be the most economically fragile and therefore least resilient, creating a cycle of poverty and widening inequality.[59]
[59] Evolution of the Donorship Landscape & Emergence of New Aid Actors in Asia: Key Trends Analysis to 2020, Inter-agency Regional Analysts Network, December 2016
#### The UK as a development partner
Previous Prosperity Fund projects and FCO engagement in the region has proven that there is considerable demand in SE Asia to learn from UK experience and expertise on certain issues, giving us scope to leverage that and differentiate our engagement and impact in what is often a crowded field in terms of donor support. We have already seen this with the high demand in SE Asia for:
- support from Infrastructure UK on PPPs and infrastructure planning;
- learning about UK experience with regulatory reform, an area on which we are seen as a global thought leader,
- drawing on UK public and private sector expertise on financial services,
- support from UK’s Intellectual Property Office on IPR issues where the UK has been ranked second in the Global Innovation Index (GII) for 2015 and has an outstanding tradition in producing the very best in science and research.
- working with UK in the area of Islamic Finance. Malaysia is currently seeking to internationalise its Islamic finance sector, with the help of UK expertise.
- learning from the UK bribery act.
DFID runs country programmes in two of the P6 countries, Burma and Indonesia. In Burma there is a substantive programme to reduce poverty and support the economic development of the country; this includes programmes to support the peace process, humanitarian assistance, on healthcare and education and on inclusive economic development. In Indonesia the UK Climate Change Unit (UKCCU), funded and staffed by DFID, works to support the country to address the governance and market failures impeding the sustainable management of forests and land use.
### Potential for secondary benefits
A consultation with DIT colleagues in the PF6 revealed commonalities in the issues business cite when operating the region:
- Cumbersome, opaque business processes that are slow to complete and open to corruption
- Restrictive controls on foreign ownership of businesses
- Inadequate or expensive infrastructure, notably in energy, transport and communications.
- Slow, unpredictable and opaque government procurement processes
- Difficulty enforcing contracts, including with government organisations.
- Inadequate IP protection and high customs rates that favours domestic manufacturers and increase smuggling.
## The programme
## Business Environment and Growth
There is a substantial body of evidence that links poor business environments and lack of financial sector development as key constraints to growth. The figure below summarises the direct and indirect benefits of business environment reform and financial and business services provision.
Figure 2: The link between Economic Reform and Poverty Reduction

Business environment is a broad enabler to economic growth across the whole economy. A number of studies provide evidence linking BER with economic growth. The realisation of these benefits also rests however on the provision of additional factors, such as energy, infrastructure, access to finance, etc. The delivery of these additional factors can in turn be improved by a better enabling environment through a better business environment, creating a virtuous circle.
Transmission mechanisms from BE reform to growth
Reforms to the business environment are undertaken so that businesses are able to change their behaviours in ways that lead to increased levels of investment and innovation and the creation of more and better jobs. BER impacts on firms by reducing red tape and procedures, thereby reducing costs, improving efficiency and productivity, and by making it more attractive to register into the formal sector, increasing competition. The mechanisms in which this feeds through to growth are by:
- Reducing business costs, risks and uncertainty – incentivising businesses and allowing them to increase profits which can be used to increase employment and invest in growth.
- Increasing competitive pressures – stimulating the efficiency and innovating incentives of the market.

Isolated reforms are found not to be as successful as a programme of linked reforms and other measures to support business activity[60].
[60] See for example DFID (2015)
## Business Environment Reform and Poverty Reduction
1. The critical role the BER plays in poverty reduction can be seen in 2 ways. First, at the aggregate level, economic growth is closely associated with reductions in poverty. An econometric analysis found that FDI inflows into the ASEAN region had a poverty reducing marginal impact of 0.32 i.e. each dollar of investment reduced poverty by 32 cents.[61] 40% of the poverty-reducing effect was indirect by increasing economic growth, and the other 60% had a direct impact on poverty through labour training and direct employment of the poor.
  [61] Jalilian and Weiss, 2001
2. Second, the contribution can be seen in the way a good business environment enhances the lives of people directly, in their many capacities:
- As employees – Poor people getting a job—whether through self-employment or from salaried income —is a path out of poverty. The private sector accounts for more than 90% of jobs in developing countries. Better job opportunities also increase incentives for people to invest in their education and skills, thus complementing efforts to improve human development. Firms that are more productive can also pay better wages and invest more in training.
- As entrepreneurs - Hundreds of millions of poor people in developing countries make their living as micro-entrepreneurs—as farmers, as street vendors, as homeworkers, and in a range of other occupations. They often operate in the informal economy, which accounts for more than half of economic activity in many developing countries. Firms in the informal economy face many of the same constraints as other firms, including insecure property rights, corruption, policy unpredictability, and limited access to finance and public services. Relieving these constraints increases incomes for entrepreneurs and allows them to expand their activities. A business environment also increases incentives to become part of the formal economy.
- As consumers - A good business environment expands the variety and reduces the costs of goods and services, including those consumed by poor people, such as food. Lowering barriers to market entry by 10% has been estimated to reduce the average price mark-up by nearly 6%.
- As users of infrastructure, property, and finance - Improving infrastructure, property rights, and finance can deliver broad benefits across the community. Building rural roads helps firms get their goods to market. Providing more secure rights to land encourages farmers and other firms to invest and can ease their access to finance. Improving the functioning of finance markets helps firms take advantage of promising investment opportunities, and also helps poor people weather family emergencies, educate their children, and improve their homes.
- As recipients of tax-funded services or transfers - Firms and their activities are the principal sources of tax revenue for governments, and growing economies generate more taxes. A good business environment can thus expand the resources governments have available to fund public services (including health and education) and transfers to disadvantaged members of society.
### Costs
Government policies and behaviours influence the costs of doing business and hence the range of investment opportunities that might be profitable. Weaknesses in government performance in these roles can greatly increase the costs for firms and make many potential opportunities unprofitable. The costs of contract enforcement difficulties, inadequate infrastructure, crime, corruption, and regulation can amount to over 25% of sales—or more than 3 times what firms typically pay in taxes. Both the level and the composition of these costs vary widely across countries.
### Risks
As investment decisions are forward looking, firms’ judgments about the future are critical. Many risks for firms, including uncertain responses by customers and competitors, are a normal part of investment, and firms should bear them. However, governments have an important role to play in maintaining a stable and secure environment, including by protecting property rights.
### Barriers to competition
1. Barriers to competition that benefit some firms deny opportunities to and can raise costs for other firms and for consumers. They can also dull the incentives for protected firms to innovate and increase their productivity. High costs and risks can act as barriers to entry. Governments also influence barriers more directly through their regulation of market entry and exit and their response to anticompetitive behaviour by firms.
2. A 2016 assessment of best practice in BE reform for gender impact concluded that there ‘is insufficient evidence on which reforms have the greatest impact for women’.[62] Much depends on the sectoral impact of the reforms and the degree to which women feature in those sectors. The project should monitor both the disaggregated data on impacts on employment and business activity as well as monitoring any changes in gender social roles and power relations so as to better understand the impact of reform on women.[63]
  [62] Hetherington, D. (2016)
  [63] Bayaz and Hedley (2016)
## Financial sector development and growth
Growth theory identifies 2 main channels through which financial sector development might affect long-run growth:
1. Through its impact on capital accumulation (including human as well as physical capital)
2. Through its impact on the rate of technological progress
The financial sector plays a key intermediation role in allowing:
- The mobilisation of savings for investment
- Facilitating and encouraging inflows of foreign capital (including FDI, portfolio investment and bonds and remittances); and
- Optimises the allocation of capital between competing uses, ensuring that capital is put to the most productive use.
## Financial sector development and poverty reduction
1. DFID’s Economic Development Strategy confirms that both business environment and financial sector development can contribute substantially to reducing poverty.
2. Expanding the supply of financial services to the poor will increase income growth for the poor and therefore have a direct impact on poverty reduction. This happens through various mechanisms:
- Provision of savings facilities – Which can enable the poor to accumulate funds securely in order to finance relatively large, anticipated future expenditure or investment. Research measuring the impacts of savings access is explained by Burgess and Pande (2005), where there was a 2.22 percentage point reduction in rural poverty per 1 percentage point increase in the share of savings held by rural banks.
- Allowing the poor to cope with risk – Reduce vulnerability of the poor to shocks in the absence of savings or insurance by allowing borrowing and consumption smoothing when there are unanticipated fluctuations in income.
- Increasing the opportunities to invest in higher return assets – Enabling poor people to invest in potentially higher risk but higher return assets (such as education) or productivity enhancing technologies, with overall long-term income enhancing impacts.
- Facilitating remittances and domestic transfers - Where Financial Sector development leads to low costs, more secure and rapid transfers, and easier access to transferred funds it benefits the poor through enabling remittances from abroad and domestic transfers that are an important source of income for the poor and can reduce vulnerability by diversifying sources of income.
- Non-monetary benefits - Financial constraints may impede the creation of firms and depress labour demand, which would push some workers into self-employment. Bianchi 2012, found that the differences in utility between self-employed and employees increase with increased financial development. Utility refers to job creation and a better matching between individual motivation and occupation, and can be equated to growth in this context.
## The link between business environment and financial sector development
In addition, institutional characteristics – such as legal systems, degree of corruption and wider business environment quality – are found to individually have a positive effect on economic growth but tend to be highly correlated with each other. This makes it difficult to identify the magnitude of their independent effects. More broadly, a number of recent studies show that regulatory changes that strengthen creditor rights, contract enforcement and accounting practices boost financial intermediary development with positive repercussions on economic growth (e.g Levine, Loayza & Beck, 2000). Regulation can also provide stability to the financial system and reduce risk, which then has a positive effect on growth and poverty. These factors add weight to the need for a varied programme of reform that tackles financial service development, development and enforcement of adequate regulatory and business environment frameworks. A recent rapid evidence assessment (REA) paper by DfID[64] reviewed evidence from 89 assessments of business environment reform programmes and concluded that a key success factors for BER programmes that effectively reduce poverty in developing economies are to:
[64] Business Environment Reform and Poverty: Rapid Evidence Assessment, DFID, October 2015.
“Complement reforms with support interventions: attention should be given to issues such as access to finance and information, as well as to labour productivity.
Formulate country and culture-specific reforms: there is a clear need for country and culture-specific approaches to BER in which donors take a long-term view, seeking to build consensus among stakeholders in order to ensure that reforms are viewed as legitimate.”
### Targeted interventions to reform the business environment and develop financial services
#### Business Environment Reform
Pillar 1: Strengthening Business Environment
Intellectual Property (IP) Enforcement
Intellectual property (IP) protection in the PF6 is currently inadequate. Issues include the prevalence of counterfeit goods; sub-standard food, drink and pharmaceuticals; and inadequate border controls. Domestic and foreign companies can be reluctant to invest in research and development of new products if they are uncertain of their ability to protect their IP and make a return on their investment. This reduces innovation and investment, hampering economic growth. Counterfeit products are also risks to public safety, as recent deaths due to counterfeit medicines and alcohol have highlighted.[65] The PF6 need to enhance their participation in the global market by developing internationally respected IP systems. The ASEAN action plan aims to establish and build an inclusive ASEAN IP ecosystem through further co-operation and engagement with stakeholders in the region. For the PF6 to be a part of a wider competitive global market the region must step up IP awareness and utilisation. National policies on IP need to be aligned with regional policies to realise these goals.
[65] “Growing threat from counterfeit medicines” Bulletin of the World Health Organization, Volume 88, Number 4, April 2010, 241-320 “Indonesian bootleg alcohol kills 24 in central Java”, BBC News 8 February 2016
Strengthening regulatory frameworks and processes
“There is nothing more important to the progress of our economies and societies than good regulation.”[66] Several studies have proved a strong correlation between good regulation and economic growth. This is achieved by programmes of reform that “...stimulate companies to change their behaviour, to enhance investment and to encourage innovation. The economic policymakers should reduce business costs and risk and increase competitive pressure by improving administration and fiscal policies, access to finance, legislation and labour administration, access to information on the market etc.”[67] A study for the UK’s Department for International Development (DfID) has also confirmed that an improved business environment contributes to poverty reduction through increasing investment and economic growth.[68] This programme will focus on simplifying the regulatory process for businesses which the OECD identified as priority for ASEAN.[69] This is an area the UK has strong expertise in through successive regulatory simplification programmes.
[66] OECD Regulatory Policy outlook 2015, 28th October 2015, page 3
[67] “Business regulations and economic growth: What can be explained?” Boudhiaf Messaouda, Zribi El Ghak Teheni. International Strategic Management Review, Volume 2, Issue 2, December 2014, Pages 69-78
[68] White, S and Fortune, P (2015), Business Environment Reform and Poverty: Rapid Evidence Assessment, London, Coffey International Development
[69] Dayan, Z and W Bolislis (2017), “Business registration pillars: Good regulatory practice for ASEAN” OECD Regulatory Policy Working Papers. No 9. OECD Publishing, Paris
Competition Policy
Lack of competition in markets reduces incentives for innovation and drives up costs for the consumer. Pro-market reforms can provide benefits across the whole economy. “For example, in Australia, a cross-sector set of reforms was estimated to boost GDP by 2.5% on ongoing basis. The value of pro-competitive regulatory reforms in particular sectors can be dramatic. This is because restrictive regulations can seriously distort markets from their competitive outcome. For example, reform in the Irish taxi sector in the year 2001 increased the supply of taxi licenses by more than 300%. Pro-market reforms to Argentinean ports increased cargo handling by 50% between 1990 and 1995.”[70]
[70] Draft: Quantifying Consumer Benefits Of Pro-Market Regulatory Reform, Sean Ennis, OECD, December 2016
Pillar 2: Advancing business and government transparency and compliance
Serious weaknesses persist in the area of public procurement in the PF6. These include fragmented procurement procedures; the lack of professional procurement expertise; the absence of open, competitive tendering, especially for foreign suppliers; and the lack of transparency.[71] These result in poorer value for money for tax payers and prevent companies competing for opportunities based solely on the merit of their bids. It also facilitates corruption. Corruption remains a significant problem in the PF6[72] with the Corruption Perception Index 2016 highlighting significant shortcomings and little improvement in the average score over time.[73] Financial crime is also a wide-spread problem. Issues such as money laundering make economies less stable and confer unfair advantages on groups that can access and utilise finance from illegal sources. Insufficient corporate governance and business integrity makes partnering with local organisations more challenging and opaque and again confers advantages on those able to work outside a rules based system. The PF6 still face difficulties in enforcing details of competition and consumer protection policies, especially with the speed of adopting these policies. The quality and adequacy of national competition policies and consumer protection vary among the PF6 countries depending on the level of economic development and according to differences in the structure of the economy, institutions, sectors, concentration and production. The speed of adoption of these policies differs among ASEAN countries, but is relatively slow overall.
[71] “Public procurement in Southeast Asia: challenge and reform” David S. Jones. Journal Of Public Procurement, Volume 7, Issue 1, 3-33 2007, UNPCDC
[72] “Geckos, crocodiles and paper tigers – anti-corruption enforcement in South East Asia”, Maurice Burke, Global Investigations Review, 22 September 2015
[73] 2016 rankings out of 176 countries: Burma 136, Indonesia 90, Malaysia 55, Philippines 101, Thailand 101, Vietnam 113. Corruption Perception Index 2016, Transparency International
#### Financial and business sector development
Pillar 3: Broadening and deepening financial markets
1. Only 27% of the population of SE Asia have a bank account.[74] This massively impacts on a population’s ability to borrow and save money, reducing financial stability and the ability to invest in the future. Creating a more inclusive financial system will allow people to become more financially stable. This can be achieved for example through innovations in Fintech and the provision of Islam-compliant financial services.
  [74] “Fintech: Opening the door to the unbanked and underbanked in Southeast Asia”, Jan Reinmueller, KPMG, 5 April 2016
2. There is also an overreliance on bank finance in the region which tends to be more expensive than other forms of finance such as bonds. This is an inefficient allocation of finance that increases the cost of doing business. In the PF6, domestic financial markets would get a boost from regional financial integration. “Financial integration fosters domestic financial development by reducing transaction costs and the costs of capital and creating business opportunities. Further financial integration to develop domestic financial markets would strengthen economies and make them more resilient and sustainable, fostering economic activities.”[75] ASEAN central bank governors launched a summary report in 2013, The Road to ASEAN Financial Integration, to guide further financial integration. This provides a good foundation for programme development.
  [75] Economic Outlook for Southeast Asia, China and India 2017: Addressing Energy Challenges, page 101, OECD
#### Secondary benefits in the target areas
Work to improve the business environment and financial and business services will deliver benefits to international and UK companies looking to export to or operate in SE Asia. Benefits will accrue to a wide range of sectors – for example greater intellectual property enforcement helps companies enforce their rights whether in pharmaceuticals, automotive engineering or fashion design. A better regulatory environment can simplify licensing to reduce set up times and the opportunities for corruption, benefitting businesses in many sectors. This programme is a lynchpin, supporting sector specific PF programmes by removing barriers that affect the whole economy. Sectors that will see a direct benefit from the programme are clustered in financial and business services, for example FinTech, Islamic Finance and Accountancy services providers.
### Economic Reform: the Sustainable Development Goals (SDGs) and gender equality
#### The Sustainable Development Goals (SDGs)
As a broad enabler, this programme indirectly supports many of the SDGs by improving the environment in which the sectors work – for example in healthcare (SDG 3) and education (SDG 4). The programme will directly promote the following SDGs:
  1. No poverty
  1. Gender Equality
  1. Decent Work and Economic Growth
  2. Industry, Innovation and Infrastructure
  3. Reduced inequality
  1. Peace, Justice and Strong Institutions
#### Gender equality and compliance with the International Development (Gender Equality) Act 2014
1. This programme has been designed to comply with the requirements of the International Development Act; in particular, the International Development (Gender Equality) Act 2014 to ‘have regard to the desirability of providing development assistance that is likely to contribute to reducing poverty in a way which is likely to contribute to reducing inequality between persons of different gender.’ We have done this in 3 ways: by investigating the link between gender equality and economic reform; by considering the impact of the programme on gender equality throughout the design phase; and by placing stringent requirements on delivery partners to carry the incorporation of gender considerations forward into delivery. This approach ensures the contents of the programme align with evidence on the issues women face in the business environment and financial services. This goes beyond the principle of doing no harm into actively pursuing interventions that address the issues women face. The potential prize is substantial: A recent study estimates that achieving equality in economic opportunities for women and men could spur $28 trillion in world GDP growth by 2025 – about the equivalent of the size of the Chinese and U.S. economies combined.[76]
  [76] “Why gender equality in doing business makes good economic sense”, Cecile Fruman, 17th November 2016
2. Link between gender equality and economic reform: The financial exclusion of women in developing countries is markedly worse than that faced by men: just 50% of women are banked in comparison to 54% of all adults.[77] This impacts on women’s ability to borrow money to start a business for example and entrenches existing, male-dominated economic hegemony. There is robust evidence for a link between gender equality in financial inclusion and equality in labour force participation. However, these potential benefits are not automatic and poor programme design can mean failure to fully realize these benefits.
  [77] FinScope data
3. The issues women face in economic reform and how this informs programme design: In developing our programme, we have carefully considered how the different elements of the programme can improve the lives of women and girls through increasing their engagement with the business environment and access to financial & business services. We have conducted a careful review of the evidence available on gender impacts of economic reform to better understand how our programme can contribute to improved gender equality. Research for APEC looking at supporting women’s economic role in SE Asia mirrors our own findings on the reforms needed for wider inclusive growth on which this programme is based. The factors that affect the ability of women to start and grow their businesses included:
- Business management and operational challenges
- Financial barriers, including access to capital
- Business networking and participation in business associations
- Government support, including challenges in business licensing
- Corruption and demand for informal payments
- Social support systems[78]
  [78] Access to trade and growth of women’s SMEs in APEC developing economies: Evaluating the business environment in Indonesia, August 2013.

1. This correlation is understandable given the increasing role of women in the SME sector in the region. The number of women-owned SMEs is growing at a rate of almost 10% annually.[79] We can therefore reasonably expect that where our planned activity will impact SMEs it will contribute to improving women’s economic empowerment and gender equality.
  [79] Access to Trade and Growth of Women’s SMEs in APEC Developing Economies: Evaluating Business Environments in Malaysia – Philippines – Thailand, February 2013. Asia Pacific Economic Cooperation
2. To ensure women reap the benefits of improved energy access and reduced barriers to business, we will:
- Incorporate women’s voices throughout the design, delivery and evaluation phases of the programme
- Ensure female participation in consultations and other engagement activities, including individual participation and through community groups and women’s business associations
- Require collection and analysis of gender disaggregated data (including quantitative data) where possible in project monitoring, reporting, evaluation and learning (MREL)
- Include women in training programmes
- Consider the likelihood of delivering positive impacts for women as one of the criteria when honing interventions over time
- Consider the impact on gender norms at household, community or wider societal levels that could result from an improved business environment and financial & business services. We will carefully assess the potential for any unintended negative consequences (e.g. changes in status, power and influence between girls/women and boys/men, which could lead to domestic violence; increased drudgery for women.
## Impact description – the headline results the programme will target
### How a PF programme could drive change: the Theory of Change
The central aim of the ASEAN Economic Reform Programme is inclusive economic growth and poverty reduction in SE Asia. Specifically, this programme’s Theory of Change targets 4 outcomes:
1. Business environment integrity improved
2. Ease of doing business improved
3. Efficiency of finance allocation improved
4. Inclusivity of financial system improved
These in turn feed into 2 intermediate outcomes in the Prosperity Fund’s theory of change:
(3) Trade, Financial and Economic Reform: Strengthen policy and regulatory environment to promote efficient and integrated markets
(5) Ease of Doing Business: Demonstrated Government commitment to improve institutional and business culture
The programme is also expected to deliver secondary benefits to the UK in the form of increased trade with SE Asia and increased influence with host governments.
Figure 3: Theory of Change

# Appraisal Case
The Appraisal Case builds on the Strategic Case presented above by assessing the main options for delivering effective interventions; and outlining the available evidence of the expected impact of the programme
## 1. Assessing Programme Options
### Overview
The Strategic Case set out the case for the countries in the programme (the PF6) and the key barriers the programme should seek to address. The final benefits and costs are likely to be influenced by the programme and delivery mechanisms chosen and the associated level of risk and ability for HMG to control outputs. As a first step, we identify the preferred programme option through qualitative analysis.
### Programme Options Appraisal

The strategic case identified the economic reform barriers that align with the AEC blueprint and are key constraints and opportunities for growth in the SE Asia region. There are various different levels of intervention required to tackle these constraints, which depend on the nature of the issue being addressed:
- Barriers which are country specific and require tackling at a national-level;
- Barriers which are prevalent across the majority of PF6 countries but require a national-level approach to tackle;
- Barriers which are prevalent across the PF6 countries and require a regional-level approach through the ASEAN grouping to ensure they are consistently tackled;
- Barriers which are country specific and need to be pursued at national-level to bring them in line with regional standards.
1. Not all PF6 countries are willing to tackle all the identified barriers they have at the current time due to capacity issues, broader interest and national priorities. Posts have worked extensively with governments to identify where the proposed programme could target areas identified as important, while also seeking to work with the grain in support of key barriers where host governments are most interested in making progress.
2. For the initial sift of viable programme options a qualitative assessment will be undertaken based on an assessment of the potential primary and secondary impact. The long list of programme options considered are:

Table 6: Programme Options
Option	Primary Benefits		Secondary Benefits		Primary Benefits Rating	Secondary Benefits Rating
	Advantages	Disadvantages	Advantages	Disadvantages
Do nothing	Resources can be channelled into other PF priority areas. / No risk of programme delivery overshadowing wider prosperity objectives.	Other PF programmes such as infrastructure, future cities, health are less effective as enabling environment for business not improved. This programme is a lynchpin for other programming in the region, fundamental to the realisation of benefits in the other programmes by removing the barriers that affect all businesses operating in the region. / Diplomacy alone cannot drive the necessary changes. Govts are willing, but often lack capacity, skills or knowledge to carry out activity. Diplomatic efforts alone are insufficient.	None.	No additional benefits to international and UK businesses. / Substantially less involvement of the UK in comparison to previous years leads to limited UK influence in the region and no additional UK benefits from anticipated economic growth in the region. / Perception that the UK is not interested in SE Asia, a key economic power and ally.	Low	Low
P1 - Single barrier – national level	Highly focused nature allows single barrier to be comprehensively addressed	Limited primary impact of programme. No single barrier is the silver bullet to improve economic growth in the PF6. / Barriers interlinked and effective reform can only be tackled by pursuing a range of barriers at the same time / Any changes to govt buy-in for reform will have significant negative impacts on benefits of programme i.e. difficult to spread risk	Potential for international and UK business to benefit from reforms in the area of the targeted barrier	Secondary benefits limited to one narrow sector, reducing potential for secondary impacts, particularly as interlinked reforms (either other national or regional) will not have been tackled and may still have a significant impact on the ability of businesses to take advantage of the change in the single barrier. Scale of opportunity much lower than in later options	Low	Low
P2 - Multiple barriers –national level	More holistic approach than single barrier approach leads to mutually reinforcing outcomes and greater overall impact / Regional AEC agenda already influences national agendas, allowing harmonisation to occur without ASEAN engagement where ASEAN policy is already established. / Spreads risk that one barrier, and subsequent benefits, might stall	No engagement with ASEAN – a significant reforming influence in SE Asia – inhibits our ability to influence policy at a regional level. / Reduces likely consistency of reforms if not matched with AEC priorities	Significant reforms in targeted national level barriers could open up opportunities by significantly levelling the playing field for international and UK companies in those areas and therefore facilitating extra trade opportunities. / Allows wider possibilities for benefits than focusing on one barrier and allows complementary reforms that work together to allow firms a more level playing field in country.	No UK support to ASEAN would damage relationships within ASEAN and in-country, hampering our ability to pursue secondary benefits and forge alliances / Reduces ability for international and UK firms to reap benefits through regional reforms and ability to benefit from consistent application of reforms	Medium	Medium
P3 - Multiple barriers - ASEAN	Programme influences policy development at the regional level, creating spill over into all ten ASEAN countries / Less resource intensive to deliver as no country-specific content to be managed	Does not address country-level implementation of ASEAN policy – increases risk the ASEAN policy moves further away from in-country reality, creating potential credibility issues and hampering harmonisation / Concentrates risk in one institution - ASEAN. / Interventions trend towards lowest common denominator, meaning they may be too generic to address each countries' circumstances, increasing risk they are not accepted in-country or that they fail to achieve outcome.	Firms can benefit through understanding and taking advantage of consistent standard of economic reforms across multiple countries.	No in-country resource to monitor delivery, capitalise on political dividends or pursue secondary benefits. / Businesses may have more difficulty understanding opportunities in specific markets as reforms are driven by regional considerations	Medium	Medium
P4 - Multiple Barriers – national level & ASEAN	The most significant barriers are addressed, regardless of whether in-country or ASEAN interventions are needed, maximising the impact of the programme. / Strong local involvement maximises political dividend. / No trade off between shaping regional agenda and pursing secondary opportunities	More resource intensive to oversee which can create greater risk of fragmentation of the programme, reducing programming synergies	Firms can benefit from consistent economic reforms across multiple countries. / Additional benefits from complementary reforms undertaken at national level	Resource intensity of covering barriers at national and ASEAN level would also present issues for taking full advantage of the potential secondary benefits. Multiple reforms may increase the complexity of pursuing and communicating potential value/opportunities for secondary benefit / Focus on a range of barriers could lead to fragmentation of the programme and more complicated approach needed to track and take advantage of opportunities for firms	High	High

### Preferred programme option
1. The conclusion from the assessment above is that tackling the barriers identified in the strategic case requires a programme that tackles these barriers at both the ASEAN and national-level (Programming option 4). This will be vital to the realisation of the overarching AEC Blueprint that pushes for further regional harmonisation to support economic growth.
2. Although this is likely to be a more resource intensive approach to programming, it ensures that the programme can be sufficiently comprehensive to meet the aspirations of the Prosperity Fund, while also allowing the more targeted approach which tackles the barriers in a way which is most likely to yield outcomes that are in line with the AEC agenda.
## 2. Quantifying a Base Case
1. The programme design takes into account where UK and SE Asian countries’ interests overlap, UK expertise that can be provided to the region, and the key priorities for governments and ASEAN to ensure strong buy-in. The Strategic Case also identified the key outputs and outcomes across these five project strands – based on the Theory of Change – and provides the evidence base which demonstrates the contribution these project strands will have on growth and poverty reduction.
2. Improving the business environment and developing the financial and business services sector are both areas that have a cross-cutting and economy-wide impact which are often difficult to model. That said, there is a reasonable body of evidence that looks at the theoretical and indirect impact of these areas on growth and poverty. Therefore the overall Theory of Change for this programme is based on medium evidence and is subject to a range of assumptions outlined in later sections.
3. The appraisal case will estimate the specific benefits of the key project strands in the programme, based on key expected objectives.
Table 7: Summary of proposed objectives of the programme
Pillar	Project Strand	Objectives supported
Business Environment	ER1 – Business environment	Progress in implementing ASEAN IP 2016-2020 action plan, especially on enforcement including online trade mark infringement and engaging regional online intermediary platforms on their IP policy; and IP Helpdesk resource to help international, including UK and SE Asian firms navigate and utilise IP frameworks / policies. / Improved in-country IP policy frameworks and their implementation in SE Asia, helping to enhance the business environment and protect international and UK commercial interests. / Improve regulatory efficiency, transparency, predictability and harmonisation in ASEAN, strengthening the business environment for domestic and foreign firms. / Strengthened regulation and reductions in unnecessary red tape. / Level the playing field in ASEAN by strengthening competition policy frameworks and their enforcement, and bringing arbitration/dispute settlement procedures into line with international best practice.

	ER2 – Advancing business & government transparency and integrity	Improved transparency, prevent corruption in government contracts and promote a competitive business environment in SE Asia. / Promotion of business integrity and strong corporate governance through advocacy and improved compliance with business and government.
Financial and business services	ER3 - Broadening and deepening financial markets	Capital market development in ASEAN, diversifying sources of funding for business and governments. / Support and inform SE Asian governments as they develop the regulatory environment for FinTech, encouraging industry development – one way of improving provision of financial services to SE Asia’s 300 million unbanked citizens. / Embedding international best practice in professional and business services markets through improvements in accountancy standards to help support expansion and wider coverage of financial markets. / Embed international commercial arbitration best practices in selected governments to support further international investment.

This analysis was developed by economists in post and completed using a private sector economic consultant. In addition, the analysis and outcomes were quality assured by a second, independent private sector consultant. Based on economic modelling and estimation (detailed below) we estimate the possible benefits of the programme as a whole to be:
Table 8: Overall Benefits of SE Asia Economic Reform Programme over 10 years
	10 Year Primary NPV (£m)	10 Year Secondary NPV (£m)
Central estimate (conservative)	351	352

Further below this section also includes an assessment of the upper and lower estimates for primary and secondary benefits, based on sensitivity analysis.
### Quantifying Costs

The programme budget allocated to the SE Asia bid at concept stage was £19m. We have designed a programme across the 3 priority project strands worth £17.5m, with approximately £1.3m (6.8%) allocated to implementation costs including FCO staff and travel and subsistence. For the purpose of the Cost-Benefit Analysis (CBA), the total administrative cost has been identified based an assessment of the staffing requirements, and the corresponding estimated costs of this staffing.
Table 9: PF Economic Reform Programme – Cost Profile in £ thousand
Pillar and Strand		17/18	18/19	19/20	20/21	21/22	Prog Total
ER1 – Strengthening Business Environment	A1: Improving Country IP Systems and Development		1144	1738	1852	411	5145
	A2: Supporting Regional IP Cooperation and Harmonisation
	B1: Deregulation Processes
	B2: Supporting Regional Regulatory Harmonisation
	C: Developing Competition Agencies
ER2 – Advancing Business & Government transparency and Compliance	A: Transparency & Compliance		1766	1766	1770		5302
	B: Construction Transparency
	C: Corporate Social Responsibility
	D: Anti-Corruption
ER3 - Broadening and deepening financial markets	A: Development & Integration of ASEAN Capital Markets		814	1738	2073	2454	7079
	B: Bond Market Development (including Islamic Finance)
	C: FinTech Regulatory Development
	D: Developing Accounting Standards
	E: Financial Crime/Anti-Money Laundering
Funding by year (Programme)			3724	5242	5695	2865	17526
Transitional Funding		151	28				179
Funding by year (Admin)		79	231	328	329	328	1295
Total Funding by year (Prog & Admin)		230	3983	5570	6024	3193	19000
Total Funding by year (%)		1%	21%	29%	32%	17%	100%

This gives the following cost profile for the programme:
Table 10: Summary cost profile in £ millions
FY	2017/18	2018/19	2019/20	2020/21	2021/22	Total
Cost (£m)	0.23	3.98	5.57	6.0	3.19	19.00

Table 11: Summary of central results narratives for project strand
Project strand	Inputs	Outputs	Outcome	Impact	Proxy measure of direct impact	Proxy measure of indirect impact
ER1 / Strengthening Business Environment	Helpdesk resources, IP policy and online tools / IP reform / Develop and disseminate professional accreditations / Research, inc diagnostics, route maps / Participating in G-G and regional dialogues; / Capacity building and knowledge sharing / Contributions to legislation development / Public advocacy and outreach	Faster implementation of regulation harmonisation plans in AEC2025 Blueprint / Improved IP policy frameworks and implementation through Improved regulatory efficiency, transparency, predictability and harmonisation in ASEAN. / Strengthening the business environment for domestic and foreign firms. / Strengthened regulation and reductions in unnecessary red tape / A level playing field in ASEAN by strengthening competition policy frameworks and their enforcement, and bringing arbitration/dispute settlement procedures into line with international best practice. / Stronger business environment for domestic and foreign firms including: / Greater competition, ease/cost of doing business	Improved business activity / Protect international and UK commercial interests therefore increase trade and / FDI.	GDP growth SEA and rest of world including UK	0.182% increase GDP growth rate per reform	Value of increased UK exports to the region as a result of increased SEA GDP
ER2 / Advancing business and govt transparency and integrity	Develop and disseminate professional accreditations / Capacity building and knowledge sharing / Participating in G-G and regional dialogues / Contribute to legislation writing / Public advocacy and outreach	Increased capacity of procurement agencies / Increased adherence to international agreements (UNCITRAL, WTO, TPP, FTAs); / Private sector and civil society participation with practical tools (Integrity Pacts, COST) to mitigate integrity risks in procurement. / Improved transparency, prevent corruption in government contracts Greater competition, reduced cost of doing business	Improved business activity / Protect international and UK commercial interests therefore increase trade and / FDI.	GDP growth SEA and rest of world including UK	0.182% increase GDP growth rate per reform	Value of increased UK exports to the region as a result of increased SEA GDP
ER3 / Broadening and deepening financial markets	Capital market development in ASEAN, diversifying sources of funding for business and government. Fintech regulatory development, commercial arbitration best practices	Increased capital and Fintech market growth, access to fin services for poor	Capital market growth	GDP growth SEA and rest of world including UK	0.1% impact on corporate bond market.	Value of increased UK exports to the region as a result of increased SEA GDP

#### Quantified Primary Benefits
Estimate of base-level benefits are based on:
An assessment of the benefits from successful reforms in the project strands identified for the programme:
#### Estimating the benefits of strands ER1 to ER3
1. In order to estimate the benefits of strands ER1 to ER3, we need to estimate the impact of these reforms on future GDP, the impact of the programme on reform success and the impact of the PF programme as part of a multi-donor effort in the countries.
2. Macroeconomic impact of business environment reform (ER1-2). While difficult to attribute the impacts for a given reform in a complex business enabling environment, a series of studies have analysed the relationship between the business environment as a whole and macroeconomic performance. All authors agree that reform to the business enabling environment helps boost economic growth. Estimates of the value of that relationship are limited. However, an important study by Haidar (2012)[80] goes further, to estimate the size of this impact. Considering data from the World Bank’s Doing Business surveys for 172 countries over 5 years, he finds that, on average, each business regulatory reform is associated with a 0.182 percentage point increase in economic growth. This finding is widely cited in the literature, by the World Bank and the Doing Business surveys themselves.[81] Another study, by Djankov et al (2006)[82] conducts a similar analysis of the relationship between the burden of business regulations and economic growth. They find that a shift from the worst to the best quartile of business regulations is associated with a 2.3 percentage point increase in economic growth. A third study, focused on low-income economies, found that business regulatory reforms led to a 0.4 percentage point increase in growth the following year[83]. Both the widespread referencing of Haidar and the consistency with the Djankov study suggest that the Haidar results are sufficiently credible as an estimate of the impact of successful reforms to be used in this analysis.
  [80] Haidar J. I. (2012) The impact of business regulatory reforms on economic growth. Journal of the Japanese and International Economies Volume 26, Issue 3, September 2012, Pages 285-307 https://scholar.harvard.edu/files/haidar/files/jjie_0.pdf
  [81] See, for example, World Bank (2017) Reforming the Business Environment in 2015/16 http://www.doingbusiness.org/~/media/WBG/DoingBusiness/Documents/Annual-Reports/English/DB17-Chapters/DB17-Reforming-the-Business-Environment-in-2015-2016.pdf and J. Anderson and A. Gonzalez (2013) Does Doing Business matter for foreign direct investment? World Bank. http://www.doingbusiness.org/~/media/WBG/DoingBusiness/Documents/Annual-Reports/English/DB13-Chapters/DB13-CS-Doing-Business-matter-for-FDI.pdf
  [82] Reported in DFID (2015)
  [83] Eifert (2009) reported in World Bank (2013)About Doing Business: measuring for impact
3. Because the macro level indicator of GDP growth is captured in this approach, there is no need to add in separate estimates of the impact on, for example, FDI or domestic business activity as this is captured in the macro analysis. Indeed any additional domestic benefits factored in at this stage would effectively represent double counting which is inconsistent with the approach of a conservative estimate of benefits.
4. GDP is forecasted for the 6 countries over the 10 year benefit horizon of the project. Existing forecasts for real GDP growth (GDP at purchasing power parity, current dollars) are used to 2022[84] and these figures are increased annually by the latest available GDP growth forecast for each country[85]. The resultant GDP forecast is used throughout the CBA.
  [84] International Monetary Fund, World Economic Outlook Database, April 2017 accessed 15/08/2017
  [85] IMF (2017) Regional Economic Outlook: Asia and Pacific, May 2017: Preparing for Choppy Seas.
5. The impact of the programme – how many successful reforms? The analysis is very sensitive to both the overall number of successful reforms and the location of those reforms. This is because the Haidar 0.173% increase in GDP is significantly affected by the starting size of GDP. However the 0.173% impact identified in the Haidar study is an average of 172 countries, so it should capture the GDP levels and corresponding impact on growth at the both the low and high end. If an additional reform is assumed successful in Indonesia (the largest economy in the sample), rather than Burma (the smallest economy in the sample), the benefits differ by a factor of 10 because of the relative size of the economies. Overestimating the level of influence is common in up front appraisals. Because of this, we consider carefully the expected level of reform success by considering the historical reform success in the countries and assuming a limited contribution to success from this programme (both in terms of the likelihood of this programme being part of a successful reform, and the attribution to the UK from the broader government and multi-donor effort).
6. The project targets a total of 16 reforms across the 6 countries over the 4 years. This is the equivalent of an average of 0.67 successful reforms, per country, per year. We estimate this target number of reforms by analysing the proposed interventions under each pillar and identifying where we anticipate a reform may occur in each country. For example, a proposed intervention that targets reform of IP in Vietnam under pillar ER1 counts as one reform. Proposed interventions to target reforms were based on a range of information including assessments of post experience in delivering reforms through previous PF projects, knowledge of buy-in to particular reforms by host governments
7. Benefits are assumed to be achieved in 2021 (given the time taken to achieve the reform success). Table 12 outlines the assumptions made about the reform effort from this programme in strands ER 1 to 3.
Table 12: Reform effort of the PF programme
	ER1 Regulation & Intellectual property	ER2 Transparency	ER3 Financial Services	Total reforms over programme (ER1-3)
Indonesia	1	2	0	3
Malaysia	0	1	0	1
Burma	1	1	1	3
Philippines	2	1	0	3
Thailand	1	1	1	3
Vietnam	2	1	0	3
TOTAL	7	7	2	16

Note: this excludes reforms that are calculated at a regional level through the main programming in the financial services strand

1. Is 0.67 reforms per country, per year reasonable? Statistically, the average number of successful reforms in each country gives an appropriate benchmark from which to estimate the potential success factor in this project. The Haidar (2012) dataset included observations of all relevant reforms (which impact the Doing Business indicators) in 172 countries over 5 years. The average number of successful reforms across the full sample was 6.51, or 1.3 successful reforms per country per year. For our 6 countries, over 4 years, this suggests the total successful reform effort of the country might be 31 reforms. This suggests the 16 reforms targeted by this project would equate to this project being involved with 50% of the total successful reform effort of the 6 countries, which may initially sound high.
2. Are these 6 countries more reforming than this average?  The 2018 World Bank Doing Business review lists 2 successful reforms in the latest period (2016-17) for Burma and the Philippines, 3 for Malaysia, 5 for Vietnam and 7 for Indonesia and 8 for Thailand which is among the top 10 reformers in the world.   This gives a regional total of 27 successful reforms per year (4.5 per country per year on average). At this average a forward estimate over a 4 year period would be 108 successful reforms. The data also suggest that during the latest period (2016-17), PF6 countries account for 10.2% of total number of reforms globally and they are faster reformers than the global average (4.5 reforms in SE Asia vs 1.39 reforms globally), achieving more than triple the average number of successful reforms.  This gives us confidence that the number of reforms being targeted (16 over four years) is reasonable but not overly ambitious share of the regional reform effort.
Table 13: Expected reforms
Country	Total no. of reforms in 2016-17	Average reforms over 4 year period	2015-16	2014-15	2013-14
Burma	2	1.67	2	2	1
Indonesia	7	4.33	7	3	3
Malaysia	3	1.00	2	1	0
Philippines	2	1.00	2	1	0
Thailand	8	1.33	3	0	1
Vietnam	5	3.33	3	5	2
PF6 total	27	12.67	19	12	7
Global	264	248	283	231	230
% PF6 reform	10.2%	5.1%	6.7%	5.2%	3.0%
No of countries globally	190	190	190	189	189
Global average reform per country	1.39	1.31	1.49	1.22	1.22
Regional average reform	4.5	2.11	3.17	2.00	1.17

Note: WB undertakes the Ease of Business report on a June to June yearly cycle
1. Of the total successful reform identified as targets for the programme (16), what share of these should be assumed to be attributable to the PF programme? There is no way of knowing the full reform agenda of each country, so we need to make an assumption about a reasonable success rate for the programme. We have made a conservative assumption that of the 16 reforms targeted, the programme interventions will only be successful in 25% of the cases. Detailed evaluation evidence is not available for similar previous programmes so we have had to base this figure on experience in post relating to the proposed intervention, buy-in from governments through ongoing conversations about these reforms and the number of reforms that have followed from previous, smaller prosperity fund related project (although these are not directly comparable). Given the reform mindedness of the region this is a conservative estimate. This probability has been applied to the reform effort of the programme in the cost benefit analysis. It should also be noted that this assessment does not take into account other outputs of the programme beyond achieving reform, for example work on developing and disseminating professional qualifications.
2. How much can we attribute to UK efforts? This programme is one agent of change amongst many in ASEAN. Governments lead the business enabling environment reform programmes, working with regional neighbours. Commitment is strong across the region, with Indonesia one of the top 10 Business Enabling Environment reformers in 2015/16[86]. The APEC Ease of Doing Business (EoDB) initiative agreed between leaders in 2009 to make doing business easier, cheaper and faster, builds on its earlier successes through the Action Plan (2016-2018) targeting a further 10% improvement in key aspects of the BEE by 2018[87]. Other donors are also active in the sub-sector, with major programmes of reform supporting the BEE from the World Bank, DFID and others. Given that this programme will be part of a multi-donor portfolio of support to the business environment reform in ASEAN, and that the reform programme will be spearheaded by the Governments of the countries, we need to discount the likely benefits of the programme by an additionality factor to account for the UK’s contribution. Advice from the World Bank, in the context of their role in co-ordinating donor efforts in the sector, suggests that the PF project might expect to achieve additionality on the donor effort[88] for interventions that remove a significant barrier for investment attraction, entry, expansion and retention. To add an extra level on conservativeness, the CBA applies only 1% to the total benefit stream to estimate the part of the benefits attributable to the UK, which World Bank advice aligns with interventions that amplify additional investment attraction, entry, expansion and retention.
  [86] World Bank (2017) Reforming the Business Environment in 2015/16 http://www.doingbusiness.org/~/media/WBG/DoingBusiness/Documents/Annual-Reports/English/DB17- Chapters/DB17-Reforming-the-Business-Environment-in-2015-2016.pdf
  [87] World Bank (2017) Reforming the business environment in 2015/16.
  [88] Based on World Bank attribution figures based on Investment Contribution Framework. This information is classed Confidential
#### Estimating the benefits of strand ER3
1. To estimate the likely benefits of strand ER3, on broadening and deepening financial markets, we need to estimate the growth of these markets without the programme (the baseline/counterfactual) and subtract that from the additional growth expected as a result of the programme.
2. Impact on capital market growth: The main focus of this component of the programme is on the expansion of the capital market and wider reforms to support this. For the ASEAN-5 countries (Indonesia, Thailand, Malaysia, Philippines and Vietnam) this was valued at approximately $255bn (£204bn) in 2017, up from $229bn (£152bn) four years ago[89]. Based on internal calculations using trend growth rates, the market growth under the baseline is assumed to be an average of 3% per year which is the regional average growth rate over the last 4 years. The growing trend is expected to continue and accelerate given ASEAN’s efforts to grow and integrate its bond markets[90].
  [89] Asia Development Bank, Outstanding Corporate Bonds (as of March 2017)
  [90] Deutsche Bank, What’s behind recent trends in Asian corporate bond markets? (2014)
3. It is assumed that the interventions made over the 3 years of the programme will result in an increase in the corporate bond market through a collection of activities including reform[91], better standards and frameworks. Recent literature finds a significant positive relationship between economic growth and bond market development[92], including that $1 of corporate debt issued across East Asia creates growth in GDP per capita of 1.038%[93]. As there are limitations to this research (e.g. Thailand is the only ASEAN country sampled) and given the diverse stages of regional development and varying input factors we conservatively assume a 1:1 capital-output ratio i.e. a $1 increase in corporate will lead to an increase in GDP per capital of 1%. We were unable to find any quantified data on the impact of programme reforms to the growth rate of bond market. We therefore have to make an assumption. We assume the programme will result in an additional 0.1% growth rate of the bond market. We deem this assumption to be a conservative and plausible estimate from a £6.6 million investment in this strand. A 0.1% increase would take the existing 3% growth rate up only slightly to 3.003%, which is only a slight increase. Given the uncertainty of this figure we also test this assumption as part of our sensitivity analysis and find even more conservative growth rates still result in a positive NPV. This additional growth in the bond market is assumed to be achieved from in 2021-2023, once the programme has had time to take effect. Applying this additional growth of 0.1% to the baseline growth of the bond market of 3% gives the estimated value of the intervention. The benefits of the additional compounded growth are also estimated. Similarly to ER 1 to 2, the UK attribution to these benefits is then calculated using the same factor.
  [91] Financial Times (2016), India’s ‘mini bang’ to boost corporate bond market
  [92] Kapingura & Makhetha-Kosi (2014), The causal relationship between the bond market development and the economic growth in Africa: a case study of South Africa
  [93] Said (2012), East Asian bond markets and economic growth
4. As an additional benefit, we have also included benefits that are derived from this strand that would also have a business environment enabling reform, and have used the methodology outlined for ER1-2 specifically on reforms on accounting and arbitration standards. Our proposed interventions in these areas will focus on Burma and Thailand, as these have been identified as the 2 countries where these issues are particularly important and where our interventions should focus. This is again conservative and we would anticipate a significant possibility of reforms in the other countries, but for the sake of the analysis we focus on these two countries. Therefore, the total business environment reform effort of the programme under ER3 is assumed to be 1 reform in each of those countries (see Table 14). As for ER 1 to 2, the benefit is assumed to be achieved in 2021. The likelihood of the reform targeted being successful is taken from the analysis for ER 1 to 2 as 25%. Again, the attribution to the UK of the resultant benefit is taken as being 1%.
#### Summary of primary benefits
The primary benefits stream from the proposed programme is summarised in Table 8 All of the analysis has estimated the benefits as an additional amount of GDP for the region. This is important as it is this additional GDP which is used to derive an estimate of the secondary benefits.
Table 14: Summary of primary benefit estimates for ER 1 to 3 (not discounted), £ billions
	2018	2019	2020	2021	2022	2023	2024	2025	2026	2027	Total
ER1	0.00	0.00	0.00	0.03	0.03	0.04	0.04	0.04	0.04	0.05	0.27
ER2	0.00	0.00	0.00	0.04	0.05	0.05	0.05	0.05	0.06	0.06	0.36
ER3	0.00	0.00	0.00	0.01	0.01	0.01	0.01	0.01	0.01	0.02	0.09
Total	0.00	0.00	0.00	0.08	0.09	0.10	0.10	0.11	0.11	0.12	0.72

NB: Due to the relatively small size each strand and the interdependent nature of economic reforms, detailed comparison for the sake of prioritisation is not advised. The overarching NPV calculation is preferred.
#### Quantifying Secondary Benefits
1. There are 2 main routes through which the project is expected to generate secondary benefits. First, the additional GDP growth in the ASEAN countries will increase demand for international, including UK exports to the region, thereby increasing global growth. The second route is through greater international, including UK investment in the region. For this latter case, we conclude that there are too many assumptions required to estimate the likely additional impact of this. Thus, this CBA proxies the value to the UK of the additional demand for UK exports as a conservative estimate of the full secondary benefits from the programme.
2. Calculating the additional growth in imports in ASEAN countries as a result of this project. In each case under the primary benefit calculation, ER 1 to 3, the impact on the ASEAN economy is analysed using the expected additional GDP for the region. Some of that additional GDP (in total, not the 1% attributed to the UK) will be spent in the form of increased imports. By calculating the propensity to import in each country (or the elasticity of imports with respect to growth), these levels of expected growth in GDP can be converted to additional import value for the region as a result of this project. Propensity to import (Table 15) is calculated by dividing the growth in imports for each country in the sample between 2010 and 2016 by the growth in GDP over the same period. The countries are varied, with an increase in imports of 0.65% for every 1% increase in GDP in Malaysia, to an increase of 1.5% in Burma.
Table 15: Elasticity/propensity to import (7 year average, 2016-2022) – UNCTAD data
Country	Propensity to import
Burma	1.5
Indonesia	0.8
Malaysia	0.65
Philippines	1.2
Thailand	1.2
Vietnam	1.8

Calculating the UK market share of the ASEAN imports: Using current values of the UK’s market share in imports to the 6 countries gives an estimate of the degree to which the UK will benefit from the increased import demand in the countries. Applying these elasticities to the additional GDP estimates, then applying the estimated UK market share for each of the countries based on estimated GDP and import growth between 2016 and 2022 by the IMF (see table below), gives an estimate of the potential additional UK exports to these markets that are expected to result from the programme.
Table 16: Current UK Export Market Share to PF6 countries (UNCTAD 5 year average 2012-2016)
Country	Current UK Market Share

Burma	0.10%
Indonesia	0.50%
Malaysia	1.10%
Philippines	0.50%
Thailand	1.20%
Vietnam	0.65%

#### Summary of secondary benefits
1. The conservative estimate of secondary benefits using the proxy of an increase in UK exports to the six countries is presented in . This is a base estimate and does not capture the full impact of this programme. Other sources of benefit which have not been monetised might include: increased exports routed through Singapore, the returns on increased investment in the region, lower prices for consumers of exports from ASEAN countries, and greater employment in the export sectors
2. Table 17: Summary of secondary benefits to the UK, £bn (not discounted)
	2018	2019	2020	2021	2022	2023	2024	2025	2026	2027	Total
ER1	0.00	0.00	0.00	0.02	0.02	0.02	0.03	0.03	0.03	0.03	0.18
ER2	0.00	0.00	0.00	0.02	0.03	0.03	0.03	0.03	0.03	0.03	0.21
ER3	0.00	0.00	0.00	0.01	0.01	0.01	0.01	0.01	0.01	0.01	0.09
Total	0.00	0.00	0.00	0.05	0.06	0.06	0.07	0.07	0.07	0.08	0.47

NB: Due to the relatively small size each strand and the interdependent nature of economic reforms, detailed comparison for the sake of prioritisation is not advised. The overarching NPV calculation is preferred.
### Conducting a cost-benefit analysis
The programme costs and monetised primary and secondary benefits have been discounted following the PF Appraisal Case Guidance. Costs are discounted at 3.5%, primary benefits at 10% (DFID practice) and secondary benefits discounted at 3.5% (Green Book principle). Table 18 presents the present values of costs and primary benefits, Table 19 the present values of costs and secondary benefits. The programme’s estimated net present value of primary benefits is £351 million and NPV of secondary benefits of £352 million are indicative of the strong returns to be made in this investment.
Table 18: The NPV of primary benefits (m)
Year	17/18	18/19	19/20	20/21	21/22	22/23	23/24	24/25	25/26	26/27	Total
PV of cost (£m)	0.97	4.41	5.12	6.61	0.00	0.00	0.00	0.00	0.00	0.00	17.12
PV of primary benefits (£m)	0.00	0.00	0.00	56.59	56.65	55.47	53.07	50.78	48.59	46.51	367.66
Primary NPV (£m)	-0.97	-4.41	-5.12	49.98	56.65	55.47	53.07	50.78	48.59	46.51	350.54

Table 19: The NPV of secondary benefits (m)
Year	2018	2019	2020	2021	2022	2023	2024	2025	2026	2027	Total
PV of cost (£m)	0.97	4.41	5.12	6.61	0.00	0.00	0.00	0.00	0.00	0.00	17.12
PV of secondary benefits (£m)	0.00	0.00	0.00	47.77	50.74	52.78	53.42	54.08	54.77	55.46	369.03
Secondary NPV (£m)	-0.97	-4.41	-5.12	41.15	50.74	52.78	53.42	54.08	54.77	55.46	351.91

Table 20: Estimates of Primary Benefits
Pillar	Project Strand	Do nothing counterfactual	Intervention variable and result	Impact	NPV Primary Benefit over 10 years (£m)
Business Environment	ER1 – Strengthening regulatory frameworks and processes	Growth rate of region in line with international estimates.	Increase in SE Asia GDP resulting from BE reform	Inclusive economic growth and poverty reduction / Increased trade and investment	350.54
	ER2 – Advancing business & government transparency and integrity	Growth rate of region in line with international estimates.	Increase in SE Asia GDP resulting from BE reform
Financial and Business Services Development	ER3 - Broadening and deepening financial markets	Growth rate of bond market and subsequent growth rates in line with average over last 4 years	Increase in size of SE Asia corporate bond market (proxy for size of capital market)
Overall Primary Benefit (NPV)

NB: Due to the relatively small size of each strand and the interdependent nature of economic reforms, detailed comparison for the sake of prioritisation is not advised. The overarching NPV calculation is preferred.

Table 21: Estimates of Secondary Benefits
Pillar	Project Strand	Intervention and Result	NPV / Secondary Benefit over 10 years (£m)*
Business Environment	ER1 – Strengthening regulatory frameworks and processes	Improvements in the Intellectual property regime indirectly benefit the UK and the rest of the world through increasing the wealth of potential consumers through growth effects and improvements in income per capita and minimising lost revenue for firms from IP theft. / Increasing overall GDP (derived from primary benefit) leads to a larger market for goods and services, plus additional capacity for SE Asian investors to invest overseas. / Improvements in the strength of regulatory frameworks indirectly benefit the rest of the world through increasing the wealth of potential consumers through growth effects and improvements in income per capita and increasing business certainty for businesses. / Increasing overall GDP (derived from primary benefit) leads to a larger market for goods and services, plus additional capacity for SE Asian investors to invest elsewhere.	351.91
	ER2 – Advancing business & government transparency and integrity	Improvements in transparency and business integrity indirectly benefit the rest of the world through increasing the wealth of potential consumers through growth effects and improvements in income per capita and improving the ability of businesses to operate in SE Asia. / Increasing overall GDP (derived from primary benefit) leads to a larger market for goods and services, plus additional capacity for SE Asian investors to invest elsewhere.
Financial and Business Services Development	ER3 -- Broadening and deepening financial markets	Broadening and deepening financial markets allows wider market entry by foreign firm and leads to opportunities for international and UK firms to increase business in the region / Increasing overall GDP (derived from primary benefit) leads to a larger market for international and UK goods and services, plus additional capacity for SE Asian investors to invest elsewhere.
Overall Secondary Benefit (NPV)

Note: Not all benefits are derived during the programming period (2017-2021) due to conservative assumption that the impact of policy reform will feed through slowly. Due to the relatively small size each strand and the interdependent nature of economic reforms, detailed comparison for the sake of prioritisation is not advised. The overarching NPV calculation is preferred.
### Unmonetised Impacts
The economic appraisal makes quantified assessments of the potential benefits of the programme through impact on growth and the value of increased exports. There, by its nature the analysis will ignore wider, potentially substantial benefits that cannot be monetised. The indicative results framework (gives a detailed breakdown of potential impacts by strand. At an overall level we anticipate additional benefits to also include greater financial stability through deeper financial markets, reduced corruption (all primary benefits) and additional secondary benefits to include: positive impacts on UK bilateral relationships in the region, positive impact on UK-ASEAN relationship, promotion of rules-based system, and raising of standards.
### Sensitivity analysis
Sensitivity analysis was conducted on the economic appraisal. Given the heavy reliance of both the primary and secondary benefit estimation on the size of the impact of reform, this variable was revised to test sensitivity. Using the central estimates of the impact of reform on GDP, these figures were adjusted 30% up and down to give the range of NPV values under the sensitivity analysis. Table 22 presents the new assumed impacts of reform giving a range of primary benefit from £0.22 billion to £0.51 billion suggesting little risk that the costs outweigh the benefits. Table 22: The assumed range of impacts of reform
	Sensitivity analysis
Assumptions	Low	High	Base
Additionality factor UK	0.009	0.011	0.010
Impact of reform on GDP growth rate	0.121	0.225	0.173
Additional growth in bond market	0.0007	0.0013	0.0010
Total growth of bond market	0.027	0.033	0.030

£m	Primary NPV	Secondary NPV
High Case	508.64	558.57
Central	350.54	351.91
Low Case	214.50	292.86

The calculation of benefits and costs of the programme indicate a significant return is likely and that the programme represents value for money. Even taking the lower estimates of primary (£215m) and secondary benefits (£293m) outlined in the sensitivity analysis above, the programme would still deliver a significant return.
### Risk Analysis
In addition to the size of the impact on GDP growth, other aspects of the model are sensitive to risk. In particular, the likelihood of success in the reform programme and the share of benefits attributable to the UK are the major indicators subject to risk. The likelihood of success is currently estimated at 25%. Although the project is ambitious in the level of reforms it will achieve, it is common for reforms to be slow to achieve or set off track. Based on an estimate that if the rate of reforms of the region fell back to the global average (rather than the higher SE Asia average), then 40% of the programme benefits would be at risk. Therefore we apply a 40% risk figure. The attribution to the UK is also a significant source of risk. Although the FCO teams are well networked in the six countries and technical support will be a core component of the project, it is possible that the UK’s additionality might be less. Depending on the performance of other donors, the UK might also have additional influence in the region. This risk is estimated at a further 10%. Giving a total risk factor of 50% on the results. Assuming a +-25% variance, we assume a low risk likelihood of failure of 25% and a high risk likelihood of 75% gives a range of NPV for the programme’s primary benefits of £88m to £263m. With the same assumptions, the secondary benefit NPV risk analysis yields a range from £88m million to £264m.
Table 23: Risk adjusted sensitivity analysis
	Assumptions	Risk adjusted central estimate of primary NPV (£m)	Risk adjusted central estimate of secondary NPV (£m)
High risk	UK additionality factor: -10% (base 0.05) / Conversion of number of reforms to successful reforms: -40% (base 0.25)	87.63	87.98
Central		175.27	175.95
Low risk	UK additionality factor: +10% (base 0.05) / Conversion of number of reforms to successful reforms: +40% (base 0.25)	262.90	263.93

## 3. Shortlisting Key Delivery Options
1. Thus far the appraisal case has identified the preferred approach to programming and quantified a base-case of likely benefits and costs. The next stage is to identify a shortlist of key delivery options for delivering the programme. Potential Delivery Models
2. In addition to the do nothing option, there are three delivery models that could be applicable to this programme:[94]
  [94] Other models are not considered feasible for this programme and have been discounted already. These include: direct management and implementation by existing FCO teams (e.g. Prosperity teams) and XWH partners – insufficient capacity or expertise in programme management in FCO policy teams; and direct partnerships with local non-profit groups – limited regional replicability and regional reach, increasing programme management resources.
#### Option D1 - Do Nothing
1. Assumes that SE Asia will continue its existing economic reform path and will maintain its modest level of progress on reforms outlined in the ASEAN Economic Community 2025 blueprint and in broader complementary domestic reforms.
2. Under this option, the pace of poverty reduction and the incidence of domestic and regional economic reform that lead towards a more benign business environment would be different from the options set out below. We judge that the outcomes outlined in the appraisal case would not occur during the time period.
#### Option D2 - Fully contracted out to commercial delivery partner
The proposed programme would be contracted out to an external private implementer through a competitive tendering process using the Prosperity Fund procurement framework. The successful implementer(s) would be tasked with delivering the outcomes outlined in the business case through a contract with the FCO and would be able to either deliver though its own network and with subcontractors, where appropriate. Existing FCO prosperity resource in SE Asia would maintain engagement with stakeholders and ensure strong contract management but would have limited direct involvement in the delivery of the programme. The implementer would take the lead on engagement with relevant government agencies
#### Option D3 - Appoint a multilateral organisation
The proposed programme would be delivered through a MoU, or similar, with a multilateral organisation. The multilateral organisation would be tasked with delivering the outcomes outlined in the business case. FCO prosperity resource in SE Asia would maintain engagement with stakeholders and ensure strong contract management. It would have some direct involvement in the delivery of the programme but would require the implementer to take the primary lead on engagement with relevant government agencies.
#### Option D4 - Combined delivery model with additional HMG partnership
1. The proposed programme would combine some of the previous 2 delivery models to match reform priority with the delivery partner that had the most relevant expertise and ability to work with relevant agencies.
2. The majority of the project strands would either be procured through a private contractor or through the appointment of a multilateral organisation. A limited number of selected streams of work would be carried out directly by HMG where the relevant UK agency has a strong international delivery model and proven track record for delivery and relationship with the country. These areas would be limited to only a small number of areas where the criteria outlines above be more effectively satisfied through a direct government-to-government relations. This would ensure that overstretch of HMG partners and requirements for substantial supporting resource from the FCO SE Asia network would be kept to a minimum. More widely though, compared to option D2 and to some extent D3, this option would require closer management of the programme by the FCO SE Asia network - in terms of setting the direction, leveraging relationships in governments, and making some operational decisions. This would require the FCO SE Asia network to collaborate closely with the lead implementers who would be responsible for the resourcing and oversight of the main activities and delivery of the programme results.
3. This model also enables the UK to be more visible to host governments, which will provide benefits in terms of ensuring engagement with key government stakeholders (which are not always inclined to work directly with third parties such as commercial or multilateral organisations which are acting on behalf of HMG), and in ensuring the corresponding diplomatic and secondary benefits of the programme can be incorporated more readily as the programmes are delivered.
### Critical success factors for delivery options

The critical success factors for assessing these delivery options against the base case of benefits and costs are:
Table 24: Critical success factors for delivery options
Critical Success Factor	Overview	Assessments made against delivery options
Value for Money	Ability to deliver results required through a quality and fast-paced service at the best value	Efficiency (cost): The delivery partner needs to be capable of delivering efficiency over the long term. This should be considered on a whole lifecycle basis.
Ability to address the challenge	The supplier has the right mix of convening power, a strong track record and robust governance practices to meet the challenge of the programme.	Experience and track record of driving reform and key decision makers through technical assistance and capacity building programmes: / The delivery partner will need to have proven credentials in driving sustainable, effective reform with client governments based on relationships of trust and respect. / The deliver partner must have (or be connected to) a strong network of local delivery agents. / Convening power and ability to influence key decision makers, including local presence: The delivery partner will need to have the brand and local convening power to have credibility with key decision makers such as ministers and senior civil servants in the countries in scope. / Robust governance, good practice management of conflicts of interest, and actual and perceived independence. / The delivery partner will need to be able to navigate relationship complexity / To preserve credibility and trust with clients, it will need to be, and be seen to be, offering independent and objective advice. / Ability to coordinate with other actors: The delivery partner must be able to plug into wider developmental agendas both in-country and also at a global level so as to secure co-investment from other donors and avoid duplicative efforts
Capability and Capacity	The supplier has the good mix of expertise, in-country capability and access to strong regional knowledge, relationships and networks to meet the requirements of the programme.	In-house technical competency and ability to draw upon industry and HMG expertise: The delivery partner will need real technical expertise, in-house, to deliver rapid response technical analyses to requests, as well as to direct and execute research and strategically commission and quality assure technical assistance programmes to governments. / Ability to scale-up in response to demand: The delivery partner will need to be able to respond quickly to peaks and troughs in demand. It must be able to both maintain a core staff and also access an effective procurement channel of experts and other supporting delivery partners. / Ability to operationalise quickly: The delivery partner will need to be in a position to launch no later than Winter 2017
Control over risk and delivery	The ability of HMG to steer the direction and delivery of the programme to ensure it is targeting the key priorities and can adapt to grasp new priorities that emerge. Likely visibility of the UK to be seen as the key delivery partner in the programme is also a factor.	Governance: sufficient level of transparency, oversight and control from HMG. Responsive to FCO requests / Given the reporting requirements of the Prosperity Fund the delivery partner will need to track and evaluate its benefits and to ensure its continued alignment with HMG objectives. This will mean retaining FCO control over the countries and scope. / Visible UK branding is also important.

## 4. Identifying the Final Proposed Option

A detailed assessment of each delivery option against the critical success factor is outlined below:
Table 25: Critical success factor of delivery options
	Critical Success Factor				Total Score (unweighted / weighted out of X)
Low = 1 / Medium = 2 / High = 3	Value for Money	Ability to address the challenge	Capability and Capacity	Control over risk and delivery
Option D1 - Do nothing	Low (1) / Zero monetary cost so resources could be allocated elsewhere	Low (1) / Continued limited outside support will constrain the region in being able to address the challenge.	Low (1) / Ability to support direction and development of economic reforms would be limited to more standard diplomacy efforts with no ability to use funding in influence	Low (1) / Loss of strong relationships built up through previous PF programmes and ability to work collaboratively with countries on areas of mutual interest	4
Option D2 - Fully contracted out to commercial delivery partner	Medium (2) / Potentially good understanding of secondary benefit criteria / Procurement can be time consuming / Profit motive complicates programme direction and limits HMG room to amend/manoeuvre.	Low (1) / Strong understanding of how private sector will engage with reforms and their needs for reform / Less host-government support for working with the private sector on sensitive issues – e.g. Corporate Governance and business integrity. Therefore likely to be unable to address all the barriers identified, particularly those relating to regional barriers	High (3) / Network capacity across country offices / Strong expertise in some sectors – e.g. services liberalisation, fintech / Brings in delivery expertise that may not exist in HMG	Low (1) / Limited UK Government engagement with host government with outsourced model / Risk of underutilisation of local sub contractors with intimate knowledge of countries	7
Option D3 - Appoint a Multilateral organisation	High (3) / Mandate of organisations focuses on primary benefit delivery / Expertise in monitoring and evaluating key programmes / Potentially harder to enshrine secondary benefit requirements / Setup can be resource intensive	Medium (2) / Generally strong host government trust and engagement. / More latitude to work on politically sensitive or contentious issues compared with private sector. Able to address the majority of regional and national barriers identified but capability to deliver financial services strand likely to be more limited than expertise that is available from the UK private sector expertise, particularly as this is a sector where UK is a global leader. / No risk sharing with partner organisations for direct government-to-government delivery.	High (3) / Strong expertise in some areas – e.g. public procurement transparency / Brings in delivery expertise that may not exist in HMG / Less clear separation between delivery and oversight	Medium (2) / Able to directly leverage UK Govt expertise and influence policy development directly / Flexibility to control and amend programme as no contract renegotiation required / Limited UK Government engagement with host government with outsourced elements of model / Potentially harder to direct programme, particularly if joint funding a multilateral organisation led programme.	10
Option D4 - Combined delivery model with additional HMG partnership	High (3) / Choice of delivery organisations can be varied to focus on the route which would best deliver outcomes. Incorporates strengths of each delivery model listed above. / Allows ability to provide direct partnership with key HMG agencies that already wish to operate in the areas proposed. / Procurement likely to be time consuming / Further direct work by HMG can put a stretch on resources if not managed well.	High (3) / Flexible delivery model allows programme to match best delivery method with a tailored approach across countries that maximises impact and specifically addresses the national and regional barriers identified	High (3) / Best fit for delivering a multi strand, multi country approach and utilising most capacity and capability	Medium (2) / Ability for HMG to have greater involvement in direction of project strand where direct partnership is required / Allows ability to bring in wider expertise and capacity while also maintaining greater control of risks and priorities. / Complexity created through multiple delivery model	11

### Comparison of options
1. The do nothing scenario scores low against the 4 criteria. It would not deliver on the primary and secondary objectives of the programme as we assess that without the programme the constraints identified would not be tackled due to lack of impetus and resources in the region, along with the complexity of implementation across the region. Option 1 has therefore been rejected.
2. Value for money – From an efficiency perspective, option D3 (Multilateral) is likely to be able to deliver the most efficient programme over the long term given they are well established in the region and have extensive experience, relationships and networks, as well as certainty of operation over a longer period of time. However, in terms of effectiveness and efficiency linked to UK priorities, they are likely to be weaker and may be less suited to delivery of secondary benefits, for example through the professional and business services development strand. Option D4 (combined delivery model) is likely to incur some additional costs through HMG staff (or at least a greater call on staff time, including those not funded by the PF), but it holds greater potential for HMG to steer the direction of project strands and deliver the most effective programme.
3. Ability to address the challenge – option D2 is more limited in its ability to address the challenges as it scores less well on its ability to convene and influence key decision makers on its own across the proposed project strands. However, option D2 offers a better ability to coordinate with other actors, as it is able to bring in sub-contractors and local agents with specialist knowledge to complement its own; however it is uncertain whether this would be consistent across all the project strands given the range of relationships that would need to be forge. Option D3 (multilateral) may be more limited / less likely to coordinate with other actors as multilaterals are likely to have greater internal resource that is already in-country. That said, this means it is more likely to already have the convening power and ability to influence key decision makers and more robust governance and would be more likely to be seen to be offering independent and objective advice (this is particularly important across some project strands which are more sensitive and government is unlikely to favour working with a commercial partner). Option D4 provides a mixed model which would enable the best aspects of both options D2 and D3 to be identified under the most suitable project strands and therefore scores most highly.
4. Capability and capacity – the availability and quality of partners able to deliver the primary purpose of the programme under the three options is likely to be high. Economic development and poverty alleviation capacity will be required as the main requirement for any contractual arrangement, be it an MoU or contract. Multilateral organisations will likely have the widest experience delivering these types of programmes in-house and would have a wide reach in the region. Option D2 (commercial) would be able to respond to demand more quickly by using a network model but the level of in-house technical competency may be more limited, with a need to bring in external partners with expertise of the region needed. Options D1-D3 would likely be able to be operational quickly. Option D4 allows the targeting of the most beneficial aspects in terms of capability and capacity from options D2 and D3 towards different project strands, this outweighs the potential drawback of taking longer to operationalise due to a wider number of agreements needed to be made.
5. Control over risk and delivery – Option D4 is deemed to allow a great level of oversight and control by allowing a more targeted approach to delivery and allowing some delivery by HMG agencies in a small number of areas. Option D2 will allow some variation in delivery but this can be limited by the flexibility of the contract and its ability to anticipate changing circumstances in the region. Option D3 has limitations on control depending on the MoU signed and the ability of HMG to ensure a more bespoke programme that delivered UK objectives.
6. This assessment of delivery options above indicates that option D4 (Mixed Delivery Model) is the option that would maximise the potential impact of the programme as appraised in the economic case, and should therefore be selected.
# Commercial Case
## Programme delivery – a multi-channel approach
1. This programme will involve provision of advisory, delivery and management services to provide policy support, capacity building and technical assistance to improve the business environment in the PF6 and facilitate the provision of financial services. This will be delivered through a combination of three delivery pathways.
2. The table below shows how this model fits the components and the budget for each section:
Table 26: Programme pillars and associated budget by delivery pathway (exc. Admin)
Pillars	Delivery Pathway	Budget £k[95]
ER1 Strengthening business environment	Procured	1222
	Internally delivered	749
	Regulatory Delivery (BEIS)	800
	OECD	2374
ER2 Advancing business and government transparency and compliance	UNDP Lead Implementer	5302
ER3 Broadening and deepening financial markets	Procured	6879
	Internally delivered	200
[95] Excludes £220k transitional funding

1. The key constraint to using a commercial supplier was whether the private sector would be able to build host government buy-in. Governments in the region generally have a high regard for UK Government impartiality and expertise and are open to our advice on regulatory, business and financial matters. Multilateral organisations are also respected and trusted to be impartial. Private sector companies can find establishing trust more challenging, particularly in areas where the private sector would be in a position to propose solutions that benefit business at the expense of the country they are operating in. Without buy-in from host governments, interventions are very unlikely to be successfully delivered or have lasting impact so this criterion was considered as a pass or fail.
2. As Table 26 sets out, the programme will be delivered through a combination of 2 contracts procured through the framework, 3 MoUs with multilateral organisations or other UK Government departments and 2 small internally delivered components. We have divided these approaches into three pathways:
  1. Pathway One – Procured: Roughly half the programme will be delivered through a commercial contract through the PF Framework.
  2. Pathway Two – Multilateral/OGD: Agreements will be made with UNDP, OECD and Regulatory Delivery in the form of MoUs or equivalent.
  3. Pathway Three – In-house: In-house delivery, using HMG staff appointed in the region.
The remainder of the budget will be used to fund UK Government staff (in individual posts and a Singapore hub) to ensure effective oversight and delivery of the programme and to maintain the strategic direction
## Ensuring Value for Money, including due diligence
### Value for Money
The Programme Team at the Singapore British High Commission will apply best practice programme management principles and the National Audit Office criteria for VFM throughout the planning and implementation processes.
Table 27: Value for Money measures
Area	Measure	Detail	Demonstrated if
Economy	Programme and operational costs	Programme implementation costs: procurement (using the Most Economically Advantageous Tender approach), contracting, programme and contract management, staff costs, implementation, following up on monitoring and evaluation results, etc.	Operational costs remain as forecasted and any increases are properly justified and approved
Efficiency	Disbursement Ratio	Disbursement of funds divided by total undisbursed funds by the beginning of the fiscal year	99%-101% compliance ratio
	Implementation progress	Implementation progress measures outputs and outcomes in terms of high-value direct procurement – supported by robust contracting terms and KPIs	Over 80% compliance measured against initial agreements
Effectiveness	Log framework	All programmes have been designed following the Prosperity Fund Theory of Change, specifically applied for the SE Asia Economic Reform programme. The logic framework will be used to measure progress against relevant indicators. When needed programmes will be re tuned to adjust them to the conditions of the environment	Measured against baselines, milestones and indicators.

#### How is value added to the programme and how will we measure and improve this?
The Appraisal case set out the case for a mixed delivery model. Value for money was one of the criteria used to evaluate the options. This section sets out how each of the three pathways delivers value for money.
##### Pathway One:
  1. Economy:
- Rates for suppliers on the Framework have been benchmarked against other programme frameworks,
- As prices have already been tested within the Framework competition. Proposals will be awarded on the basis of most economically advantageous tender ("MEAT").
- The programme has not been prescriptive in how requirements are to be delivered but is clear on the requirements and measures of success.
  1. Efficiency: The selected supplier has demonstrated the proposal appropriately resources their team in terms of seniority, experience and numbers to deliver the desired outputs.
  2. Effectiveness: elements of the proposals that would improve the overall impact of local technical capacity or introducing better management practices into the sector as a whole.
##### Pathway Two:
1. Economy: UNDP, OECD and Regulatory Delivery’s budgets were benchmarked against their previous work for the PF in year 1 and the old PF
2. Efficiency: Approximately 10% of the budget for UNDP’s and 5.3% of the budget for OECD’s components will go to general management support. This compares favourably with other delivery methods and there is no risk of stranded assets on completion of the programme.
3. Effectiveness: UNDP and OECD have enduring presences in the region and have already established relationships with host governments RD has a proven track-record of delivery through previous years of the Prosperity Fund.
##### Pathway Three:
1. Economy: Where HMG has the necessary expertise to deliver the work, economy can be achieved by leveraging non-PF expertise and resources within HMG to deliver the programme, particularly from the Intellectual Property Office and the Economics Network.
2. Efficiency: Programme design minimises staffing for internal delivery, staff from the central hub will be flexibly deployed to handle surges in workload.
3. Effectiveness: The Intellectual Property Office has longevity and consistency of engagement across the PF6, allowing for effective engagement during delivery and enduring impact
Due diligence
For pathway one, due diligence of potential suppliers has already been completed as part of the Framework Award process. Bidders have provided significant detail on their sub-contractor and consortium members within their bid as relevant and provided assurance that they are fit in terms of financial standing and ethical and legal requirements to provide and deliver services to HMG. For pathway two, we have consulted the FCO’s Policy Programme Transformation Unit and DfID’s Commercial Relationship team who oversee HMG’s relationship with UNDP and OECD to confirm the multilaterals meet HMG’s due diligence requirements. For pathway three, we will ensure staff working on the programmes receive fraud training where needed and are aware of whistle blowing policies etc.
## Securing implementers

### Market engagement

1. There were 3 engagement events held in London to validate the design of the commercial strategy and of the Framework including the lotting structure. Over 300 suppliers expressed an interest in supplying services with over 200 bids received, indicating capability and market interest globally in delivering PF programmes.
2. A supplier call was conducted in November 2017 to socialise design and allow potential suppliers to ask clarifying questions. This also helped construct SoRs
3. To ensure that the field of potential bidders for tendered contracts was as wide as possible a further supplier engagement event was held in March 2018. The Statement of Requirements, agreements with non-FCO HMG and multilaterals, internal work plans
- The scope of activity to be undertaken was defined in detailed Statement of Requirements (SORs – pathway one), agreements (E.g. MoUs – pathway two) and work plans with activity based budgets (pathway three). Final work plans were developed and the documents were drafted to ensure delivery of the programme outputs as described in this business case and to allow for effective supplier management. On the 25th of May 2018 the Invitation to Tender (ITT) PF18 002 for the South East Asia region programme – Economic reform was published and set out clear deliverables Improved IP policy frameworks and their implementation in SE Asia, helping to enhance the business environment and protect UK commercial interests
- Improved business environment integrity
- Improve regulatory efficiency, transparency, predictability and harmonisation in ASEAN
- Strengthening the business environment for domestic and foreign firms
- Strengthened regulation and reductions in unnecessary red tape
- A level playing field in ASEAN by strengthening competition policy frameworks and their enforcement
- Improve transparency, prevent corruption in government contracts and promote a competitive business environment in SE Asia
- Promoting business integrity and strong corporate governance through advocacy and improved compliance with business and government
- Support capital market development in ASEAN, diversifying sources of funding for business and governments and creating new opportunities for international and UK financial firms.
- capital markets in ASEAN play a greater role in financing infrastructure development in the region
- Increase in financial inclusion
- Embed international commercial arbitration best practices in selected governments to support further international investment and enforceable contracts
1. The ITT also made clear that there was scope for the implementers to input their own ideas as to how best to deliver the required outputs and outcomes, thus benefitting from their expertise and innovative outlook.
2. The SoRs included an explicit section on Gender Act Compliance requirements.
3. The SoRs for the two procured components required suppliers to do the following:
Phase 1 – an inception period: scope out, prepare the ground for and delineate the final package of activities and deliverables. This included refining the interventions already identified by offering innovative, practicable and timely activities based on an up-to-date assessment of the region’s needs in intellectual property and financial services, and corresponding UK expertise. Key outputs will include:
- A finalised Programme Delivery Strategy
- A detailed, costed annual outputs-based work plan for the first 12 months after the Inception Phase, including an agreed list of early activities/outputs to be delivered,
- Outline output based work plans for subsequent years,;
- Monitoring and Evaluation Plan
- Consultancy team structure to deliver the programme
Phase 2 – the Operational phase of the programme: This will implement the inception plan mutually agreed at the end of Phase 1 to deliver the programme objectives. Activities will enable the key objectives of the programme: policy support, capacity building and technical assistance to facilitate intellectual property improvements and financial services.
### Delivery partners’ key responsibilities
The delivery teams will take responsibility for ensuring the aims and objectives of the programme are achieved as set out in the detailed documentation- SoRs. The Lead implementers will manage the delivery of activities, identification and disbursement of funds to any subcontractors (following verified invoices to the FCO) and ensure compliance with FCO’s and the PFMO’s financial and management requirements, including MREL requirements. Key activities include:
  1. Assure the proposed programme activities for suitability against the Theory of Change and assess their likelihood to achieve Programme outcomes
  2. Co-ordinate and manage subsequent interventions to provide policy support, capacity building and technical assistance to facilitate improving the business environment and the provision of financial and business services, through the following types of activity
  3. Deliver programme activities
  4. Monitoring and reporting on the programme component’s performance against a milestone-based implementation schedule
  5. Continuously demonstrating how the programme identifies and mainstreams diversity, equality and inclusion throughout design and delivery
  6. Ensure compliance with the International Development Act.
The documentation will be designed so that an adaptive and flexible approach can be used that delivers credible VFM and appropriately apportions operational risk.
### Pathway One: Procurement
1. Two components were procured in one ITT published at the end of May 2018 using the PF Framework. The ITT covered one area of ER1, namely Improving Country IP Systems and Development, and most of ER3: Broadening and Deepening Financial Markets. The two contracts were procured together and from one Framework supplier. The contracts were procured via the Cross-Whitehall Prosperity Fund Agreement, awarded by the FCO to a total of 27 suppliers across 11 Lots. The Framework has been designed specifically for the Prosperity Fund Programme and is available to Other Government Departments to access. This contract was competed via a call for further competition from suppliers that have been selected based on evaluation of technical and commercial offerings and all will be invited to tender for this requirement.
2. 5 suppliers bid under the programme. All bids were compliant and good with some showing a very strong understanding of what the programme is looking to deliver. The Lead Delivery Partners all formed a consortium to access specific the breadth of expertise and beneficiaries (e.g. host Governments) targeted by the programme. A lead implementer model was selected for the following reasons:
1. Consistency with preferred PF approach
2. Greater programme coherence in delivery. Allows FCO resources to focus on strategic programme management and making links with DIT colleagues pursuing secondary benefits.
3. Components areas are sufficiently connected thematically to believe a single implementer, potentially working with sub-contractors or in a consortium, could have the necessary expertise, relationships and capacity to deliver them all.
#### Evaluation, Moderation, Interviews and Contract Announcement
1. Following the close of the deadline for the ITT returns, we ran an evaluation process to assess and make a decision on the 5 bids received. Contract proposals were evaluated individually over a period of 4 weeks by members of an evaluation panel. This consisted of the regional hub team in Singapore, managers from all 6PF posts and 2 experts, one on IP and one on Gender Inclusion. The panel included the Head of Economic and Trade (South East Asia), Head of Prosperity Programmes (South East Asia), a FCO Commercial representative.
2. Once the individual evaluations had taken place, the entire evaluation panel met for a bid moderation session in Singapore. The panel reviewed respective views of the members and experts of the panel at length in order to reach where possible a consensus on the score for each section of each bid.
3. In early September 2018, all 5 bidders were invited to bring their delivery team and work strand leads to an interview at the British High Commission. A number of bidders had team members join the interview via video conference call as well. The
4. The bidder with the highest score was the Price Waterhouse Coopers (PWC) who are offering the Most Economically Advantageous Tender. To ensure VFM and the right balance of quality vs price and that priorities in terms of service capability and capacity is addressed, there was a defended quality threshold for bidders to meet in order for commercials to be evaluated.
### Pathway Two: Multilateral Development Organisation and non-FCO HMG delivery
The FCO negotiated legally non-binding arrangements in the forms of Memoranda of Understanding (MOU). UNDP (May 2018) covering Pillar ER 2OECD (June 2018) covering Developing Competition Agencies under pillar ER 1 Regulatory Delivery in BEIS ( July 2018) covering the inception phase on supporting Deregulation Processes and Supporting Regional Regulatory Harmonisation in ASEAN (Pillar ER1)

The UNDP provided an overall umbrella for organisations like CoST, and will be delivering their own regional and in country activity. This reduced the transactional costs for the FCO’s regional office as multilaterals often would provide the overall management.

1. Work plans and detailed budgets were discussed and agreed with the core delivery teams of all three multilaterals and annexed to the MOUs. All three organisations ran short inception phases to scope out the work proposed and to firm up the proposed deliverables and interventions in each of the 6PF countries. Whilst some Comms activity has already taken place, the UNDP and OECD are started to implement their proposed work plans in country in September 2018 and Regulatory Delivery is expected to begin implementation in early January 2019.
2. Where any additional expertise was needed from the commercial sector, we required multilaterals and their suppliers to adhere to the UK’s procurement rules (or equivalents). Where were used, we jointly agree the selection criteria to be taken into account in the selection process. This was set out in the programme documentation.
### Pathway Three: Internal Delivery
1. On the Supporting Regional IP Cooperation and Harmonisation strand , the IPO attaché based in Singapore has produced a detailed work plan and budget and recruited Economic Reform Delivery Support (IP) 1 C4L to help deliver the work. The project is designed to build Intellectual Property capacity and networks in ASEAN through technical assistance, capacity building and knowledge sharing.
2. On the Development & Integration of ASEAN Capital Markets strand, plans to develop an ASEAN Capital Markets Forum are underway. Priority areas to be determined but could include: Green finance; companies; creating asset class; a forum on green finance; green equity; Facilitating infrastructure finance and development of intermediaries; Intermediating capital for CLMV Cambodia, Laos, Burma and Vietnam ; Research on secondary markets (liquidity, implications of Basle, developing more uniform capital market unions); Managing Implementers during delivery
### Contract forms and duration
1. The Foreign and Commonwealth Office (FCO) is the Contracting Authority. For pathway one, contracts were awarded on the basis of the Framework Agreement Terms and Conditions of Contract. For pathway two: the FCO signed non-binding MoUs (or equivalent) with UNDP, OECD and Regulatory Delivery. We sought FCO legal guidance on the correct form for the MoUs and they were based on existing templates already agreed between HMG and the relevant organisation (or internal templates for RD).
2. The Prosperity Fund will close on 31 March 2023 and commercial contracts will have that end date, with scope to extend by contract amendment for an additional fifty percent of value or an additional time to retain flexibility.
### Contract Management
1. The SE Asia Economic Reform Steering Group will focus on strategic oversight and will ensure the programme delivers on stated goals and aligns with HMG objectives at both global and country level.
2. The Head of Prosperity Fund SE Asia will be the contract manager for the programme, working closely with the Head of the Economics and Trade Network in Singapore and Programme Managers at the individual Posts. A contract management plan will be developed and agreed and will provide the basis for robust and clear contract management activities, principles and review points. Programme Managers will be responsible for:
- rigorous day to day operational management
- relationship management
- monitoring progress against Key Performance Indicators and Payment by Results
- managing contract variations;
- maintaining contract documentation;
- risk and benefit management;
- contract reviews including cost review;
- financial oversight;
- escalation, issue resolution and conflict management;
- mobilisation and exit management

Ensuring GEA compliance and technical QA for gender, poverty and inclusion.
1. Programme Managers are supported by expertise on financial legal and commercial management when required.
2. For pathway three, a full time member of staff at C4L/SEO grade is supporting front-line delivery working to the IPO’s attaché in the region and the Head Economics and Trade.
### Performance and reporting: Payment by Results and Key Performance Indicators
Detailed reporting and monitoring requirements has been included in agreements with Delivery partners’ and agreed with PFMO central Monitoring, Reporting, Evaluation and Learning (MREL) and with FCO’s Prosperity Fund Department. The Fund Manager submits monthly accounting reports to FCO and PFMO to enable the HMG team to make key decisions regarding the direction of the programme. The PFMO Evaluation Manager will submit quarterly operational reports on the performance of the programme.
### Terms and Conditions
1. The Framework Terms and Conditions reflect the Government Model Contract Terms for Services and have been developed to reflect the specifics of the Prosperity Fund, ODA and IDA requirements.
2. Call-off terms provided for a roll down to a more detailed level to be adapted in line with the requirements and the environment in which the services will be delivered.
3. Additional clauses in Service Levels and Credits, Performance Management, Business Continuity and Exit arrangements were included and as relevant to the requirement.
# Financial Case
## Programme Budget
### What sources of funding will the programme use?
The programme is seeking £19m Prosperity Fund ODA funding over four years for this programme. This includes all implementing activities, such as administrative costs.
The main cost across the programme is advisory services to deliver the technical assistance and capacity building activities. We expect to manage these costs in 3 ways: Selection of lead implementer will include assessment of VFM including costs of programme delivery; implementing partners will run competitive tenders to ensure VFM, benchmarking costings and reducing costs where possible; contracts will be based on milestone payments contingent on delivery of outputs. Fee levels will be managed through the procurement process.
Of the expected total budget of £19m:
- £17.5m for implementers to deliver programme activity, connectivity, trust and resilience, and enabling activity.
- £1.3m for essential staffing for programme management.
- £0.2m has been used to fund transitional activity ahead of main programme delivery (FY 17/18, 18/19 only)
First year expenditure is low to allow for the PF assurance process and the time taken to appoint implementers.
Table 28: Programme costs (£000s)
		17/18	18/19	19/20	20/21	21/22	Sub Total	Total by delivery strand	Pillar Total (Prog)
ER1 – Strengthening Business Environment	A1: Improving Country IP Systems and Development		180	220	411	411	1222	1222	5145
	A2: Supporting Regional IP Cooperation and Harmonisation		170	225	354		749	749
	B1: Deregulation Processes		122	254	253		629	800
	B2: Supporting Regional Regulatory Harmonisation		17	77	77		171
	C: Developing Competition Agencies		655	962	757		2374	2374
ER2 – Advancing Business & Government transparency and compliance	A: Transparency & Compliance		960	960	961		2881	5302	5302
	B: Construction Transparency		103	103	105		311
	C: Corporate Social Responsibility		120	120	120		360
	D: Anti-Corruption		583	583	584		1750
ER3 - Broadening and deepening financial markets	A: Development & Integration of ASEAN Capital Markets		30	70	100		200	200	7079
	B: Bond Market Development (including Islamic Finance)		196	384	418	518	1516	6879
	C: FinTech Regulatory Development		196	641	566	710	2113
	D: Developing Accounting Standards		196	541	602	897	2236
	E: Financial Crime/Anti-Money Laundering	0	196	102	387	329	1014
Funding by year (Programme)		0	3724	5242	5695	2865	17526	17526	17526
Transitional Funding		151	28					179	179
Funding by year (Admin)		79	231	328	329	328	1295	1295	1295
Total Funding by year (Prog & Admin)		230	3983	5570	6024	3193	19000	19000	19000

Cost assumptions for the programme are based on previous experience of delivering PF projects in SE Asia under the old PF and from estimates from delivery partners who are already signed up to the programme – e.g. UNDP, IPO.
Table 29: Indicative management staffing costs
Title	Grade and number	Cost per annum (£000s)
Head of Prosperity Programmes	0.25 D6UK	46
Prosperity Fund Portfolio Officer	0.25 B3L	22
Economic Reform Programme Manager	0.5 C4L	59
Programme Managers	0.5 C4L x6	164
Total Management (4 years)		292 / (1,168)

In addition to the management staffing costs, a C4L was employed to deliver the internal elements of the programme. The costs of that role have been included in the programme costs..
### How will it be funded: capital/programme/admin?
Funding will be ‘programme’ spending (RDEL).
### Profile of expected costs
1. The programme team will provide a total budget of £19m up to March 2022. The allocation of the budget between activities and the profile will be confirmed during the inception phase once the detailed discussions with the lead implementer on costing the interventions are completed.
2. The allocation of funds between different components and scope of individual activities to maximise impact through adapting to learning and any changing circumstances will be reviewed as required by the Steering Board.
## Financial Management
### Disbursement of programme funds
1. As agreed with the Prosperity Fund Management Office, funds will be allocated by SRO letter on a per annum basis.
2. There will be no ongoing liabilities to the Prosperity Fund beyond the lifetime of the Programme.
### How will expenditure be monitored, reported and accounted for?
Robust due diligence processes have been put in place before any expenditure takes place, as detailed in the Commercial case. Financial reporting will be carried out monthly. In accordance with the contractual provisions, funds to the commercially procured contractors will be disbursed in arrears monthly on receipt of a valid invoice supported by a breakdown of activity that has been delivered. In accordance with the Procurement Framework’s standard contractual provisions, each invoice will be supported by a breakdown of the costs being claimed against each budget line in the contract. The implementing partners(s) will submit annual audited accounts for each of the financial years covered by the project.
## Financial and Fraud risk assessment
1. The main financial risk is that programmes take time to reach implementation and that procurement delays and delivery delays result in drawdown being postponed. We have sought to mitigate this risk by being realistic on year 1 spend, building in sufficient time to complete the procurement processes. We will further manage the risk by effective contracting and working closely with implementers to spot and address any external delivery roadblocks.
2. Any programme of this size and geographical reach needs to consider the potential fiduciary and fraud risk in the operating environment. For this programme these risks will be mitigated in the following ways:
1. Funds will be disbursed either through the lead implementer or directly by HMG. Both routes will follow the procedures described above to verify payments before funds are disbursed.
2. A thorough due diligence will be carried out on all recipients of funding throughout the delivery chain, before any payments are made.
3. It is not expected that funds will be transferred through partner government systems or directly to small community based organisations which are likely to present a higher fiduciary risk.
4. Payments will be made in a phased way, starting with modest contributions against planned milestones until the effectiveness of the intervention has been proven and scale up is agreed (where appropriate). Funds will be disbursed in arrears as standard practice.
We also considered currency risk, with the potential for volatility surrounding Brexit negotiations and beyond. We will mitigate this by agreeing that implementers bear currency risk, but ultimately this may result in lower levels of service and consequent effect on outputs and impacts.
## The potential for scaling up or down
1. Our initial assessment is that this programme could be scaled-up by up to 50% in existing components before it would have a significant impact on staffing levels. Further analysis would be needed to judge the impact on staffing of adding new components. The primary option to scale down the programme is in the number of countries covered the by each component. Options to scale up the funding include further outreach and advocacy work, raising awareness of the changes the programme has brought about, increasing the number of government officials, civil society organisations and businesses that adopt the new policies or products and increasing the programme’s impact.
2. Finally, the programme will have the opportunity to complement other donor initiatives. Coordination with other donors present in each country will be essential and could result in significant leverage.
# Management Case
## Governance
### Fund Level Governance Structure
1. The Governance structure puts in place the appropriate oversight and support to ensure the programme delivers the results outlined in the Appraisal Case and agreed by the Portfolio Board (PB). The budget for the Economic Reform Programme is held by the FCO. The FCO (via either the Permanent Under-Secretary or the Director General Economic and Consular) has delegated responsibility for the allocated funds to BHC Singapore, both in terms of management of public money and ensuring compliance with the International Development Act.
2. The senior responsible officer (SRO) at Post with operational responsibility for the South East Asia Prosperity Fund Programme is the High Commissioner in Singapore, as regional lead for the Prosperity Fund. The Head of Economics and Trade (D6, Singapore) ensures policy coherence and has day-to-day oversight of the programme. Head Economics and Trade is assisted by a 0.5 C4L (Singapore) to help with the initial procurement and set-up phase of the programme and ongoing co-ordination across the region. The Head of Prosperity Fund SE Asia (D6 UK, Singapore), leading the Programme Office, ensures the programme’s adherence to the programme management processes and manages finance.
#### Steering Board
1. A Steering Board has been formed during implementation and has met twice. It will continue to meet every 4 months during the lifetime of the programme to review progress, help shape strategic priorities and support delivery. The Board is chaired by the SRO and will be made up of senior representatives from FCO, DIT, JFU, PFDU and PF6 Heads of Mission.
2. The Board will provide overall policy direction for the programme, oversee the activities of the Working Group, sign off financial forecasts and allocations and approve annual progress reviews before submission to PFDU The Steering Board will be responsible for prioritising future activity, based on the performance of the components against the results framework.
#### Working Group
The Working Group reviews and helps inform progress with the various pathways in the programme. It will meet every month during the lifetime of the programme to discuss progress, co-ordinate work between delivery partners and provide day-to-day oversight. It is chaired by the Head of Trade and Economics. Membership includes programme leads from each post including the regional programme manager, lead contractors and sub-contractors depending on the agenda,

Figure 4: Governance Structure

## HMG resources needed to manage the programme
### Proposed structure
The programme supports 4 FTE posts for programme management and 1 for delivery of internal components. This covers 0.25 D6 UK, 3.5 C4L and 0.25 B3L for programme management and 1.0 C4L for internal delivery. 0.5C4Ls are put in place in each of the PF6 posts and a Regional Economic Reform Programme Manager 0.5 C4L is based in Singapore. Policy input in each Post will be available from the Economics Attaché network and DIT teams (all non PF). Leading on the engagement with the delivery partners, finance, governance and liaison with London would be the Delivery Manager – the D6 UK Head of Prosperity Fund SE Asia, a shared PF resource funded 25% by this programme and a B3L Prosperity Fund Portfolio Officer (also a shared resource, 25% funded). Together these posts form the PF6 Programme Office which is fully PF funded. The proportion of the PF6 Programme Office charged to this programme was based on the programmes eventually approved for the region. Note: There is currently no FCO Economic Officer slot in Burma. This may impact on Post’s ability to engage with the detailed content of the programme and to input fully into MREL. The Economic Delivery Support (IP) is a PF Programme funded role for IP and is not charged to the admin budget.

Key features:
- A central oversight and co-ordinating function will support and guide programme managers at post.
- The responsibility of assessing the programme’s continued suitability to meet the programme aims will fall to the policy lead.
- The responsibility for programme management – e.g. assessing the programme against delivery milestones will be held by the delivery lead and team.
- Programme Officers at post will monitor and assist implementers in country and liaise with DIT on secondary benefits.
- A delivery support officer facilitating Government-to-Government delivery of the Intellectual Property Enforcement components.
- The programme will draw on existing (non PF) Communications, Economic and commercial support from SE Asia FCO and DIT colleagues working regionally and on a country by country basis.
## Monitoring, evaluating, reporting and learning (MREL)
Departmental leads and the PFMO are also involved in the monitoring and evaluation process to ensure compliance with the aims and objectives of the programme as set out in this business case.
### Results framework
The MREL for this programme will be consistent with the Fund approach to MREL. We will work with the Fund contractors to develop critical indicators for Fund and programme level reporting, identifying indicators that can be aggregated for regular reporting and management indicators to allow programme managers to assess progress and impacts. The programme MREL will be consistent with, and regularly test, the programme theory of change and the logframe that flows from it. We will report expenditure monthly and impacts (results) quarterly in line with Fund reporting rhythms.
### Reporting frequency and costs
Consistent with our Fund requirements, we will instruct the implementer for the programme to develop a quarterly results reporting system and will work with the Fund Monitoring and Reporting contractor to ensure consistency with Fund processes and systems – particularly around data quality and consistency. Programme data capture and baselining will be the responsibility of the programme and its implementers but, as instructed, we will charge the costs of this to the central MREL budget. This element of the programme is capped at 1% of programme allocation.
### Monitoring and Reporting
Responsibility for data capture, baselining and reporting sits with the programme managers and the implementers. Indicators will need to be agreed with the fund level monitoring and reporting contractor, the evaluators and the programme implementers. The monitoring and reporting contractor will identify the data requirement in terms of format and quality. We will work with our stakeholders to ensure that reporting is done in a timely and useful manner.
### Evaluation and Learning
The overarching evaluation methodology will be decided by the fund level evaluators and we will work to deliver the required coordination between the various contractors at programme level.
## Risk Management
The risk register will be regularly reviewed and updated as part of ongoing scanning for emerging risks and a proactive approach towards risk mitigation. The table below summarises the risks in each category.
Table 30: Risk Management
Description	L	I	RAYG	Mitigation	L	I	RAYG
Context – risks include political developments, the economic situation, social unrest and conflict, and other environmental factors.	P	MD		Programming will focus on laying the foundations for long term economic growth, reducing the impact of short term economic changes. / Continued FCO Post engagement with relevant officials and ministers. / Monitoring government announcements to look for early signs of policy change most especially in countries like Burma and the Philippines where the political context is complex and can change rapidly / Focusing on interventions that are not contentious. / Flexible and adaptive programming to accommodate changing host or UK priorities.	U	MN
Delivery – risks include those associated with the partner and its supply chain, to beneficiaries as well as the performance of the programme.	U	MJ		Effective and open communication between delivery partners and FCO programme managers. / Agreement on robust environmental and social protection policies with delivery partners and monitoring of compliance. / Continuous engagement and flexible design to enable programme adaption. / Ensure delivery partner is bought into aims of programme, as well as the activity to be undertaken.	U	MD
Safeguarding – an important aspect of delivery risk is to “avoid doing harm”. Risks include those potentially impacting on social exclusion eg poor gender and inclusivity practice, child protection, slave labour (e.g. for large infrastructure development and construction) and trafficking.	U	MN		Ensure programmes focus on inclusive economic growth and monitor programme’s impact. / Careful financial control with delivery partners and their subcontractors. / Strong liaison with political officers at post. / Retention of flexibility to respond to any new information on the drivers of inequality in SE Asia.	R	I
Operational – these relate to the capacity and capability of the government departments involved in delivery to manage the programme.	P	MJ		Effective and open communication between delivery partners and FCO programme managers. / Strengthen existing experienced team; / Structuring of programme in few, large components; Building buy-in from senior staff. / Establishing robust change management processes.	U	MN
Fiduciary – these relate to the funds not being used for the intended purposes and / or not being properly accounted for.	P	S		Rigorous financial control, ensuring all subcontractors are aware of their obligations and prohibitions. / Finances managed according to the processes set out by PFMO and staff trained for fraud awareness. / Blocks on dispersal if concerns are raised	U	MD
Strategic – any risk that negatively affects the alignment between the Fund programme plus risks that affect international architecture, negotiations and finance and high level visits.	U	MD		Ensuring adequate guidance and training is in place to support the design and delivery of programmes with clear primary purpose. / Testing ODA/IDA compliance as an explicit part of the annual review process, alongside ongoing challenge from the Board.	R	I

## Programme Adaptation and Flexibility
It is recognised that programme implementation cannot be standardised across all PF6 countries given their very different contexts and needs. Whilst the five components are implemented in each of the countries, the specific content and balance between the components have been informed by the priorities of individual host governments and the level of harmonisation already reached by the country with the AEC blueprint. An operational learning approach will be adopted to enable the programme to adjust.
## Communications and stakeholder management
1. External communications will be a significant part of ensuring the programme is successful. Proactive and joined up external communications will be required to put across the key message: that sharing world class British expertise will not only help the region’s economic development but also help to create commercial opportunities for business (including UK companies) there. We will be guided by principles of strong HMG visibility and ownership even though some delivery may be outsourced. We will incorporate the PFMO Communications Guidance (when issued) as appropriate. We will use the OASIS[96] tool to ensure our communications are effective, efficient and evaluated.
  [96] A Guide to Campaign Planning https://gcs.civilservice.gov.uk/wp-content/uploads/2015/09/OASIS-Campaigns-Guide-.pdf
2. Objectives:
To demonstrate that ODA spend in the PF6 countries in South East Asia can deliver economic development for the region and opportunities for UK PLC;
- To ensure companies are aware and able to take advantage of opportunities and access resulting from programme activities;
- To influence national decision-makers to ensure that the programme is implemented and delivered effectively and efficiently;
- To raise the profile and reputation of the UK in the region, using the Programme to build a stronger and wider network with stakeholders in government, NGOs and business communities;
- To seek to ensure awareness and support for this Prosperity Fund programme among UK public, press and Parliament;
Audience Insight:
Our audience includes:
- PF6 national governments, in particular decision makers in business environment and finance and business services;
- PF6 businesses, project developers and investors involved in the provision of finance and business services, likely to engage in public procurement and those who rely on IP (e.g. conducting RD&D);
- PF6 public, NGOs, local and regional press;
- UK business and investors (including trade organisations such as the CBI, City of London and other sector-specific bodies);
Strategy/Idea:
A key focus of the programme is policy reform and capacity building at an official and business level: this will need strong buy-in from governments across the region and good linkages to the relevant business sectors. A
We also need to ensure that the potential positive spill-over commercial impacts and reputational benefits are realised. External communications is needed to ensure that the private sector/business community can inform the focus of programming, is aware of the programme and well positioned to take advantage of commercial opportunities that the programme helps bring to market.
1. Once the market assessment has given a clear trajectory of travel, we will also aim to showcase and market the programme at a suitable regional event.
2. The ASEAN organisation should be engaged in highlighting the cross-regional aspects of the Programme and encouraging its relevant members to work with the Programme especially where this fits with ASEAN’s regional aspirations.
3. Scoring/evaluation:
We will monitor outputs and outcomes throughout the campaign and evaluate during the programme (using timely feedback to improve implementation) and when complete.
# Resources

Key Indicators for Asia and the Pacific 2016, 47th Edition. Asian Development Bank
https://www.adb.org/publications/key-indicators-asia-and-pacific-2016
Economic and Social Survey of Asia and the Pacific 2016: Nurturing productivity for inclusive growth and sustainable development. UNESCAPhttps://www.unescap.org/sites/default/files/EconomicandSocialSurveyofAsiaandthePacific2016_0.pdf
United Kingdom Balance of Payments - The Pink Book time series dataset, July 2016
https://www.ons.gov.uk/economy/nationalaccounts/balanceofpayments/datasets/pinkbook
Asian Development Outlook 2016: Asia’s Potential Growth. Asian Development Bank http://www.adb.org/publications/asian-development-outlook-2016-asia-potential-growth
Asian Development Outlook 2015: Financing Asia’s Future Growth. Asian Development Bank
http://www.adb.org/publications/asian-development-outlook-2015-financing-asias-future-growth
Global Economic Prospects: A Fragile Recovery, June 2017. World Bank
World Bank Global Economic ProspectsWorld Bank Poverty and Equity databasehttp://povertydata.worldbank.org/poverty/country/
Basic 2017 Statistics: Economic Research and Regional Cooperation Department, April 2017. Asian Development Bankhttps://www.adb.org/publications/basic-statistics-2017
Understanding ASEAN: Seven things you need to know, by Vinayak HV, Fraser Thompson, and Oliver Tonby, May 2014. McKinsey
http://www.mckinsey.com/industries/public-sector/our-insights/understanding-asean-seven-things-you-need-to-know
Economic Outlook for Southeast Asia, China and India, 2017. OECDhttp://www.oecd.org/dev/economic-outlook-for-southeast-asia-china-and-india-23101113.htm
World Economic Outlook Database, April 2016. International Monetary Fund
https://www.imf.org/external/pubs/ft/weo/2016/01/weodata/index.aspx
Asian Development Outlook 2017: Transcending the middle-income challenge. Asian Development Bank
https://www.adb.org/publications/asian-development-outlook-2017-middle-income-challenge
Priority Areas for Growth with Inclusion in ASEAN, 2016. World Economic Forum
http://widgets.weforum.org/cards/economic-growth-and-social-inclusion-in-asean/structural-change-in-asean/
Asia Pacific Economic Outlook: Preparing for choppy seas, April 2017. International Monetary Fund
https://www.imf.org/en/Publications/REO/APAC/Issues/2017/04/28/areo0517
The Report: Burma 2017. Oxford Business Group
http://www.oxfordbusinessgroup.com/myanmar-2017
Malaysian Economic Planning Unit, 2016.
http://www.epu.gov.my/en
The Observatory of Economic Complexity, 2015
http://atlas.media.mit.edu/en/
Global Trade Atlas, 2017
https://www.ihs.com/products/maritime-global-trade-atlas.html
NESDB Economic Report: Thai Economic Performance in Q1 and Outlook for 2017, May 15, 2017. Macroeconomic Strategy and Planning Office
NESDB Economic report
Thailand Economy Profile. CIMB ASEAN Research Institute.
http://www.cariasean.org/asean-2/economy-profiles/thailand-economy-profile/
Thailand Ministry of Commerce. World Trade Organization 2015
http://stat.wto.org/CountryProfile/WSDBCountryPFView.aspx?Language=E&Country=TH
UN Comtrade data
https://comtrade.un.org/labs/BIS-trade-in-goods/?reporter=826&partner=764&year=2016&flow=2
General Statistics Office of Vietnam http://www.gso.gov.vn/Default_en.aspx?tabid=491
Custom Department of Vietnam
https://www.customs.gov.vn/Lists/EnglishStatistics/Default.aspx
Vietnam 2035: Toward Prosperity, Creativity, Equity, and Democracy, February 2016. World Bank and Government of Vietnam
http://www.worldbank.org/en/news/infographic/2016/02/23/vietnam-2035-toward-prosperity-creativity-equity-and-democracy
Beatrice Tanjangco, ASEAN Integration: A Work in Progress, April 10, 2017. Brink News
http://www.brinknews.com/asia/asean-integration-a-work-in-progress/
ASEAN Economic Community Blueprint, 2025. ASEAN Secretariat, 2015.
http://www.asean.org/wp-content/uploads/images/2015/November/aec-page/AEC-Blueprint-2025-FINAL.pdf
Routledge Handbook of Southeast Asian Economics, Edited by Ian Coxhead, University of Wisconsin-Madison, Chapter 14: The Drivers of Poverty Reduction Peter Warr, Australian National University Canberra, Australia, December 2014
http://www.aae.wisc.edu/hoseae/chapters/14-Warr.pdf
Inequality in Asia and the Pacific: Trends, drivers and policy implications; ed Ravi Kanbur, Changyong Rhee and Juzhong Zhuang; Preface. A co-publication of the Asian Development Bank and Routledge, 2014
https://www.adb.org/sites/default/files/publication/41630/inequality-asia-and-pacific.pdf
2016 SDG Index and Dashboard Reports: A global report. BertelsmannStiftung and Sustainable Development Solutions Network July 2016.
http://www.sdgindex.org/download/
Projecting Progress: The SDGs in Asia and the Pacific. May 2016. ODI
https://www.odi.org/publications/10421-projecting-progress-sdgs-asia-pacific
Ending poverty and boosting shared prosperity in a time of transition, a systematic country diagnostic. World Bank Group. November 2014, p 23-24
http://documents.worldbank.org/curated/en/871761468109465157/pdf/930500CSD0P150070Box385388B00OUO090.pdf
Badan Pusat Statistik Indonesia
https://www.bps.go.id/
Achieving Universal Electricity Access in Indonesia, ADB, 2016 https://www.adb.org/sites/default/files/publication/182314/achieving-electricity-access-ino.pdf
Malaysia Millennium Development Goals Report 2015, UN Malaysia. January 2016
http://un.org.my/upload/undp_mdg_report_2015.pdf
2015 Poverty in the Philippines, Philippine Statistics Authority https://psa.gov.ph/sites/default/files/2015_povstat_FINAL.pdf
Press Release: Farmers, Fishermen and Children consistently posted the highest poverty incidence among basic sectors, Philippine Statistics Authority, 30th June 2017
https://psa.gov.ph/poverty-press-releases
Philippine Development Plan 2017-2022, Investor Relations Office, Government of the Philippines http://www.iro.ph/article_doc/fc55bc53_PDP-2017-2022-Prepublication-2.pdf
National Economic and Social Development Board, Thailand ‘Table 1.3 Number of poor people when measuring consumption expenditure Classified by region and area, 1988 – 2015’
http://social.nesdb.go.th/SocialStat/StatReport_Final.aspx?reportid=670&template=2R1C&yeartype=M&subcatid=59
‘Thailand Third Most Unequal Country in the World’, Bangkok Post, 9th November 2016
http://www.bangkokpost.com/learning/advanced/1147468/thailand-third-most-unequal-country-in-world
Global Employment Trends for Youth 2015: Youth employment crisis easing but far from over. International Labour Organization.
http://www.ilo.org/global/about-the-ilo/newsroom/news/WCMS_412014/lang--en/index.htm
Organization for Economic Cooperation and Development (OECD), Gender Equality In Education, Employment And Entrepreneurship: Final Report To The MCM 2012.
http://www.oecd.org/employment/50423364.pdf
Klasen, S. and Lamanna, F. (2009), “The impact of gender inequality in education and employment on economic growth: New evidence for a panel of countries,” Feminist Economics, 15: 3 (as retrieved from UN Women, Progress Of The World’s Women 2015-2016: Transforming Economies, Realizing Rights Chapter 4).
http://progress.unwomen.org/en/2015/pdf/UNW_progressreport.pdf
Gender Equality and Women’s Empowerment Operational Plan, 2013–2020: Moving the Agenda Forward in Asia and the Pacific. April 2013.
https://www.adb.org/sites/default/files/institutional-document/33881/files/gender-operational-plan.pdf
“Women in SE Asia”, Barbara Watson Andaya. Asia Society Centre for Global Education http://asiasociety.org/education/women-southeast-asia
UNESCO Institute for Statistics
http://data.uis.unesco.org/index.aspx?queryid=147
Haidar, J. I., 2012, “The impact of business regulatory reforms on economic growth”, Journal of the Japanese and International Economies, 26: 285 – 307
http://www.sciencedirect.com/science/article/pii/S0889158312000226
World Bank Ease of Doing Business Rankings
http://www.doingbusiness.org/rankings
ASEAN Community 2015: Managing Integration for better jobs and shared prosperity, xii. ADB 2104
https://www.adb.org/sites/default/files/publication/42818/asean-community-2015-managing-integration.pdf
The World Bank Briefs: Global Value Chains, July 2015
http://www.worldbank.org/en/topic/trade/brief/global-value-chains
Vietnam Ministry of Trade
http://www.moit.gov.vn/
 ‘Harvard Prof: Vietnam Could See 13.6% GDP Growth by 2025’, The Saigoneer, 10 April 2014
 https://saigoneer.com/saigon-development/1786-harvard-prof-vietnam-could-see-13-6-gdp-growth-by-2025
‘Facts and Data about ASEAN Infrastructure’, ADB 3 May 2012
https://www.adb.org/features/fast-facts-asean-infrastructure-fund
Special Issue: ASEAN Integration and its Health Implications, Global Health Action. 27th January 2015
www.ncbi.nlm.nih.gov/pmc/articles/PMC4309835
Trends Shaping Education 2014 Spotlight 3: Urban Life: The Rise of the Megacity. OECD. 2014
https://www.oecd.org/edu/ceri/Spotlight%20No3%20Urban.pdf
Abe, Masato and Margit Molnar (2014), Myanmar Business Survey 2014: Survey Results, OECD and UNESCAP, page 5
http://www.unescap.org/sites/default/files/MBS_Survey_Results.pdf
Better Growth, Better Climate, Chapter 4: Energy, New Climate Economy
http://newclimateeconomy.report/2014/energy/
Enhancing regional cooperation for sustainable energy in Asia and the Pacific, Note by the secretariat. UNESCAP. 5 April 2017
https://www.unescap.org/commission/73/document/E73_7E.pdf
Regional Cooperation For Sustainable Energy In Asia And The Pacific, UNESCAP, 2017 page v http://www.un-expo.org/wp-content/uploads/bsk-pdf-manager/2017/06/Regional-Cooperation-for-Sustainable-Energy-in-Asia-Pacific.pdf
Challenges for Renewable Energy in Asia and the Pacific, Anthony Maxwell, ADB presentation
http://www.mofa.go.jp/mofaj/files/000027960.pdf
ESCAP, “Asia Pacific: Response to Climate Change”, 10 December 2015.
www.unescap.org/op-ed/asia-pacific-response-climate-change
Statistical bulletin: Foreign direct investment involving UK companies: 2015. Office of National Statistics, UK https://www.ons.gov.uk/economy/nationalaccounts/balanceofpayments/bulletins/foreigndirectinvestmentinvolvingukcompanies/2015
Evolution of the Donorship Landscape & Emergence of New Aid Actors in Asia: Key Trends Analysis to 2020, Inter-agency Regional Analysts Network, December 2016
http://www.iris-france.org/wp-content/uploads/2017/01/Donorship-Landscape-Evolution-in-Asia_Report_2016-12_PUBLIC-1.pdf
“Growing threat from counterfeit medicines” Bulletin of the World Health Organization, Volume 88, Number 4, April 2010, 241-320
http://www.who.int/bulletin/volumes/88/4/10-020410/en/
“Indonesian bootleg alcohol kills 24 in central Java”, BBC News 8 February 2016
http://www.bbc.co.uk/news/world-asia-35519438
OECD Regulatory Policy outlook 2015, 28th October 2015, page 3
http://www.oecd.org/publications/oecd-regulatory-policy-outlook-2015-9789264238770-en.htm
“Business regulations and economic growth: What can be explained?” Boudhiaf Messaouda, Zribi El Ghak Teheni. International Strategic Management Review, Volume 2, Issue 2, December 2014, Pages 69-78
http://www.sciencedirect.com/science/article/pii/S2306774814000039
White, S and Fortune, P (2015), Business Environment Reform and Poverty: Rapid Evidence Assessment, London, Coffey International Development
https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/471215/business-environment-reform.pdf
Dayan, Z and W Bolislis (2017), “Business registration pillars: Good regulatory practice for ASEAN” OECD Regulatory Policy Working Papers. No 9. OECD Publishing, Paris
Draft: Quantifying Consumer Benefits of Pro-Market Regulatory Reform, Sean Ennis, OECD, December 2016
 “Public procurement in Southeast Asia: challenge and reform” David S. Jones. Journal Of Public Procurement, Volume 7, Issue 1, 3-33 2007, UNPCDC
http://unpcdc.org/media/6112/public%20procurement%20in%20southeast%20asia%20-%20challenge%20and%20reform.pdf
“Geckos, crocodiles and paper tigers – anti-corruption enforcement in South East Asia”, Maurice Burke, Global Investigations Review, 22 September 2015
http://globalinvestigationsreview.com/insight/the-asia-pacific-investigations-review-2016/1024350/anti-corruption
2016 rankings out of 176 countries: Burma 136, Indonesia 90, Malaysia 55, Philippines 101, Thailand 101, Vietnam 113. Corruption Perception Index 2016, Transparency International
https://www.transparency.org/news/feature/corruption_perceptions_index_2016
ADB Economics Working Paper Series: Developing the Service as Engine of Growth for Asia: An Overview. Marcus Noland, Donghyun Park, and Gemma B. Estrad, No 320, November 2012
https://www.adb.org/sites/default/files/publication/30080/economics-wp320.pdf
“Fintech: Opening the door to the unbanked and underbanked in Southeast Asia”, Jan Reinmueller, KPMG, 5 April 2016
https://home.kpmg.com/xx/en/home/insights/2016/04/fintech-opening-the-door-to-the-unbanked-and-underbanked-in-southeast-asia.html
Economic Outlook for Southeast Asia, China and India 2017: Addressing Energy Challenges, page 101, OECD
http://www.oecd.org/dev/economic-outlook-for-southeast-asia-china-and-india-23101113.htm
“Why gender equality in doing business makes good economic sense”, Cecile Fruman, 17th November 2016
http://blogs.worldbank.org/psd/why-gender-equality-doing-business-makes-good-economic-sense
FinScope data
http://www.finmark.org.za/sites/finscope
Access to trade and growth of women’s SMEs in APEC developing economies: Evaluating the business environment in Indonesia, August 2013.
https://asiafoundation.org/resources/pdfs/EvaluatingtheBusinessEnvironmentinIndonesia.pdf
Access to Trade and Growth of Women’s SMEs in APEC Developing Economies: Evaluating Business Environments in Malaysia – Philippines – Thailand, February 2013. Asia Pacific Economic Cooperation
https://wlsme.org/sites/default/files/resource/files/2013_PPWE_Access-Trade-Growth-Women-SMEs.pdf
Anderson, J. and Gonzalez, A. (2013) Does Doing Business matter for foreign direct investment? Doing Business
http://www.doingbusiness.org/~/media/WBG/DoingBusiness/Documents/Annual-Reports/English/DB13-Chapters/DB13-CS-Doing-Business-matter-for-FDI.pdf
Bayaz, G. and Hedley, E. (2016) Business Environment Reform Facility How to Measure Value for Money in DFID Business Environment and Investment Climate Reform Initiatives Delivered by the IFC: An Evidence and Learning Note.
http://businessenvironmentreform.co.uk/wp-content/uploads/2017/05/BERF-VfM-Evidence-and-Learning-Note.pdf
Booth, D. (2016) Politically smart support to economic development: DFID experiences. ODI, London
Davis P. (2011) The Political Economy of Business Environment Reform: An Introduction for Practitioners DCED
http://www.enterprise-development.org/wp-content/uploads/Political_Economy_An_Introduction_for_Practitioners.pdf
DFID (2015) Business Environment Reform and Poverty Rapid Evidence Assessment, https://assets.publishing.service.gov.uk/media/57a0897b40f0b649740000d4/61565-REA-BEE-Q1publish.pdf
Hetherington, D. (2016) Business Environment Reform Facility Gender and Business Environment Reform: What is “Best Practice”? http://www.businessenvironmentreform.co.uk/wp-content/uploads/2016/07/DFID-Bangladesh-Gender-and-BER.pdf
IMF (2017) Regional Economic Outlook: Asia and Pacific, May 2017: Preparing for Choppy Seas.
Klapper L. and Love I. (2010) The Impact of Business Environment Reforms on New Firm Registration https://blogs.worldbank.org/files/allaboutfinance/DB%20Reforms.pdf
World Bank (2013) About Doing Business: measuring for impact http://www.doingbusiness.org/~/media/WBG/DoingBusiness/Documents/Annual-Reports/English/DB13-Chapters/About-Doing-Business.pdf
World Bank (2017) Reforming the Business Environment in 2015/16. Doing business http://www.doingbusiness.org/~/media/WBG/DoingBusiness/Documents/Annual-Reports/English/DB17-Chapters/DB17-Reforming-the-Business-Environment-in-2015-2016.pdf
World Bank (2017) Summaries of Doing Business Reforms in 2015/16
http://www.doingbusiness.org/~/media/WBG/DoingBusiness/Documents/Annual-Reports/English/DB17-Chapters/DB17-Reform-Summaries.pdf
East Asian Bond Markets and Economic Growth Rasidah Mohd Said Graduate School of Business, Universiti Kebangsaan Malaysia http://www.ipedr.com/vol57/014-ICBMG2012-B00030.pdf