#
# Project underperformance approach – process note for Grant Recipients
Summary

Performance against contracted targets will be monitored closely at Programme level in the 2014/2020 operating period. Failure to achieve milestones agreed in the Operational Programme will result in a range of possible sanctions including non-payment of performance reserve sums, interruption or suspension of the Programme and, ultimately, de-commitment.

In order for Programme level targets to be achieved, the delivery of individual project level targets is critical.

1. Underperformance against project targets will initially be managed through day to day contract and performance management activity. This may result in project change requests.
2. Where a project is underperforming and where all normal contract and performance management actions have been undertaken but have not led to the improvements required, the Managing Authority (MA) will consider the application of a financial penalty. This is in line with Funding Agreement paragraphs 12.8 a to f (Reduction in grant for underperformance) and Schedule 4 Underperformance Methodology. This course of action would be considered the last resort.
3. A revised approach has been agreed (November 2016) and this will apply to all projects entering into legal commits after this date. Projects that have entered into a legal commitment before this date are signed up to using a different approach ( see FA Schedule 4). Where this is the case, projects are able to ask for the new methodology to apply, if that is preferable, through a Project Change Request. As with all such requests there is no guarantee that this will be approved.

B:	ERDF Managing Authority approach to performance review
1. Growth Delivery Team (GDT) contract managers will work with Grant Recipients as part of the day to day contract and performance management of every ERDF project. In the majority of cases any slippage in the achievement of contracted outputs will be dealt with through normal contract management, including, project change requests.
2. Where a Grant Recipient reports outputs which cumulatively are 85% or less of their forecast target profiles in two successive claim periods, this will act as a trigger for the Change Request process to be implemented.
3. Accurate forecasting of finances and outputs is crucial, however, in exceptional circumstances the change process will allow Grant Recipients to accurately reforecast outputs into a realistic and reasonable profile based on their delivery experience. There is no guarantee that any request will be granted.
In cases where variations are not agreed, where projects continue to slip or experience difficulties again, the GDT contract manager will consider implementing the formal underperformance process. This consists of three stages.
Stage 1: Identification and notification of projects at risk of ESIF being reduced or clawed back

1. Using evidence generated by claims, monitoring and audit visits etc, the GDT contract manager will identify projects which are behind profile and, therefore at risk of having ESIF reduced or clawed back.
2. Where the variance from original profile is such that the project has cumulatively achieved less than 85% of its contracted target (especially in cases where a change request has previously been processed) the GDT contract manager will consider the facts as presented when making its decision on how to proceed. This could include, for example;
1. whether there are any mitigating or extenuating circumstances to be considered;
2. any provisional proposals or action already made to rectify under performance;
3. any other issues that have come to light through normal contract management activities.

1. Where it is determined that a project is underperforming the GDT contract manager will write to inform the Grant Recipient that there is a risk of ESIF being reduced or withdrawn should improvements not be made to a specified level and by a given date ( normally the end of the next quarter or claim period).
2. Where improvements are made and performance becomes satisfactory no further action need be taken. Normal contract and performance management activity will continue. The GDT contract manager will confirm this in writing.

Stage 2: Development and implementation of an appropriate Recovery Plan

1. Projects failing to show the required level of improvement within the agreed timescale will be provided with formal notification of a potential reduction or claw back of ESIF and be required to develop a formal Recovery Plan.
2. This Plan will clearly identify how the project will improve its performance within an agreed timescale (normally between 3 – 6 months) and how this will be reviewed and measured.
3. In considering the Recovery Plan, the GDT contract manager in discussion with GDT managers and / or Head of Team will consider the project specific issues presented. These will normally include:
1. whether amended delivery profiles (both end and period totals) are appropriate;
2. if the Recovery Plan addresses all of the issues previously identified in a realistic and complete manner;
3. if the actions proposed are likely to bring about the improvements required and
4. if the timescales proposed are acceptable and achievable.

Performance against the Plan will be closely monitored by the GDT contract manager and will result in either the operation’s performance improving, or a recommendation to the Head of Team for ERDF to be reduced or clawed back in full or in part. This will be confirmed in writing by the GDT Head of Team or nominated senior manager.

Stage 3: Initiation of action to reduce or withdraw ESIF awarded

1. Where a project fails to deliver on an agreed Recovery Plan, the GDT Head will make a final decision on whether the ESIF awarded should be de-committed i.e. reduced or withdrawn.
2. Levels of penalty and de-commitment will be considered on a case by case basis and will be commensurate with the level of underperformance as determined by the GDT contract manager and Head of Team. The penalty figure will be proportionate having regard to mitigating circumstances and be entirely at the GDT’s discretion.

Where a penalty is to be applied the methodology below will be applied as a starting point. This is as detailed in Schedule 4 of the Funding Agreement.

N.B. In the case of technical assistance projects output 1 should be “ER/T/R/01 number of TA project supported applications that are approved” and output 2 “ER/T/O/01 number of projects supported to submit an application”. A further two outputs may be chosen for outputs 3 and 4.

Where a project does not include a performance framework output then the GDT will apply a more proportionate distribution of the weightings in the underperformance calculation. Similarly, where the project will deliver less than 4 types of output the GDT will revise the distribution of the weightings proportionately.

1. Where underperformance is identified as part of project closure, assessment will be in line with the process outlined above, recognising that there will be limited scope for Recovery due to the proximity to the project’s end date.
2. The methodology shown allows GDTs to identify up to 4 outputs to be included in the underperformance penalty calculation. Where contracted, one of these (output one) will be a Performance Reserve related target. Selection is entirely at the GDT’s discretion, however, the outputs selected would normally :
  1. Include any that relate to the Programme level performance reserve;
  2. Present a good range of those contracted ensuring that different output types are covered e.g. business support and jobs etc;
  3. Acknowledge any over achieved outputs;
  4. Link back to the appropriate Priority Axis / Category of Region / Call / ESIF Area priorities.

1. Decisions to reduce or claw back ESIF will not be taken lightly and will be based on consideration of the facts of the case. Even at this stage a range of outcomes may be considered. These may include a final variation to the project, a decision to close the project early, a reduced level of ERDF available commensurate with revised achievement expectations or an offset / demand note for claw back of some or all of the ERDF paid to date or due.
2. The GDT Head of Team will formally write to confirm details.

ERDF UNDERPERFORMANCE REVIEW PROCESS