# PROSPERITY FUND BETTER HEALTH PROGRAMME
# FULL BUSINESS CASE

# Contents
Executive Summary…………………………………………………………………………..		2
Strategic Case…………………………………………………………………………………		4
Economic Case………………………………………………………………………………..		12
Commercial Case……………………………………………………………………………..		23
Management Case……………………………………………………………………………		31
Financial Case…………………………………………………………………………………		43
Appendix A: Log Frame………………………………………………………………………		47
Appendix B: indicative Country Outcomes…………………………………………………		49

Executive Summary

This proposed FCO-led Prosperity Fund Better Health Programme (BHP) will invest £79.3m over the next three years into improving health, and thereby contributing to inclusive economic growth and poverty reduction, in eight partner countries (Brazil, Mexico, South Africa, Malaysia, Myanmar, Philippines, Thailand and Vietnam).

The programme is funded by Official Development Assistance (ODA) money from the Prosperity Fund (PF). The Purpose of the PF is to support inclusive economic growth as part of both the 2015 Strategic Defence Review and the 2015 Aid Strategy. Inclusive economic growth is in turn expected to produce new opportunities for international business, including for businesses from the UK. In delivering its primary purpose, the BHP is naturally expected to create opportunities for UK’s world-leading health care sector. This supports the 2017 Industrial Strategy and DIT’s Healthcare UK initiative.

The BHP’s overarching objectives have been shaped in collaboration with our partner countries. Specifically, the BHP will:

Address the growing burden of non-communicable diseases (NCDs) such as heart disease, diabetes and cancer.

Strengthen local health system structures, processes, governance, regulation, and capabilities to drive improvements in quality of care. The objective here is to reduce sub-optimal levels of care, which contribute to infection, injury or premature death.

The FCO believes that by achieving these objectives, there will be inherent health benefits to partner country populations. Furthermore, we expect several positive results for inclusive economic growth:

Healthier citizens will be better able to participate in the workforce and will be more productive, resulting in higher incomes.

More equal access to health services for women and poorer people in our partner countries will enable these groups to participate more and benefit from growth in their respective economies.

A reduction in NCD conditions and improved provider quality will lead to a reduction in the care burden, of which women currently tend to bear the greater share of responsibility in the home. Again, this will increase their economic potential.

The programme’s expected impact will be:

- Progress against the UN’s Sustainable Development Goals (primarily SDG 3 Good Health and Well Being, and SDG 5 Gender Equality);
- Reduced morbidity and extended life expectancy, with associated economic benefits e.g. increased labour productivity for men and women;

An increase in UK exports as a result of new opportunities for international businesses.

The BHP is FCO-led in cooperation with the Department of Health and Social Care (DHSC), Department for International Trade (DIT) and Department for International Development (DfID). The BHP will be using the NHS as a “Strategic Partner” for the programme. The Strategic Partner will be responsible for ensuring that the FCO can act as an intelligent customer. The Strategic Partner will not be delivering the programme.

The BHP Delivery phase began in July 2019 with an Inception period due to last until October 2019. Full Implementation will start in November 2019 and run until September 2022 when the programme will begin a phased wind down.

# Strategic Case
The Strategic Case demonstrates that the spending proposal provides business synergy and strategic fit and is predicated upon a robust and evidence based case for change. This includes the rationale of why intervention is required, as well as a clear definition of outcomes and the potential scope for what is to be achieved.

Objective and outcomes

The core objective of this programme is as follows:
To partner eight middle income countries over a three-year period to increase the number of healthy years lived, resulting in increased local prosperity and quality of life, reduced poverty and gender inequality, and mutually beneficial trade.
Scoping work by the FCO and a range of experts identified the specific health sector needs in the partner countries, and the programme’s Steering Committee settled on two priority thematic areas for the programme:

Improved prevention and treatment of NCDs, leading to healthier lifestyles that reduce the risk of related disability, premature morbidity and mortality;

Improved patient safety and quality of care that reduce the risk of illness, injury and premature morbidity and mortality.

The high level programme outcomes and impact will be:
Primary: The outcomes will be the improved prevention and treatment of NCDs and improved quality and safety of care, contributing to the impact of reduced ill health and premature death due to non-communicable (chronic) diseases and reduced morbidity and early mortality due to adverse events in care (quality of care). The resulting increase in healthy life years among the worst affected segments of society (including women, excluded groups and the poor) will facilitate more inclusive economic growth and increase domestic purchasing power.

Secondary: The outcome will be new opportunities for international businesses including UK health sector businesses, which are strong performers in this sector. The impact will be increased and sustained economic opportunities and mutually beneficial trade for both the UK and our partner countries.
The programme log frame that links the outputs, outcomes and impacts of the programme, and shows the indicators and assumptions used to make these causal linkages, is set out at Appendix A.

Big Picture – Why are we proposing this programme?

The programme aligns with existing UK government strategies that work towards the overarching goal of reducing barriers to economic growth and supporting the SDGs. The UK is fully committed to the UN Sustainable Development Goals (SDGs) as a means of promoting enhanced peace and prosperity and sustainability of resources. The BHP provides the UK with an opportunity to support those goals, directly supporting:

- SDG 3 Good Health and Well Being
- SDG 5 Gender Equality

and also feeding into:
- SDG 1: No Poverty
- SDG 8: Decent Work and Economic Growth

The programme could make a significant difference to population health and hence productivity by increasing the quality of care and case management. Poor global health generates costs that hinder economic progress, both directly (increasing the burden of prevention and treatment, and crowding out other public and private investments) and indirectly (lost productivity and/or working years due to illness/death). The two issues the BHP has focused on are two of the biggest that face communities around the world, including in our eight partner countries: i) the rapid rise in non-communicable diseases (NCDs) and ii) the drive to strengthen and improve health care systems. NCDs account for 74% of premature fatalities in Lower and Middle Income Countries (LIC/MICs) and are forecast to cost 4% of GDP by 2025. The returns, through resulting improvements in productivity, from reductions in preventable NCD deaths are expected to be three times greater than the costs of prevention and treatment. Adverse events due to medical care, represent a major source of morbidity and mortality globally, with approximately two-thirds of all adverse events, and the resulting healthy life years lost, occurring in LIC/MICs.

Gender Equality and Inclusion: Promoting gender equality and economic empowerment of women and excluded groups in societies is a key component of inclusive economic growth. Investment in girls’ and women’s health increases their rights, capabilities and opportunities for participation and retention in the labour market. Women are disproportionately affected by NCDs, which are the leading cause of death for women worldwide, leading to 65% of all female deaths. Twice as many women as men suffer from malnutrition. Tackling gender discrimination and empowering women as decision-makers to drive healthy consumption and lifestyle choices for themselves and their families are important for helping to prevent NCDs. Globally, gender norms and societal barriers (such as caregiving role of women and their restricted ability to travel to seek healthcare in some middle-income countries) can result in reduced access to appropriate care and NCD treatment for women in comparison to men. As principal care-givers, girls are often taken out of education to support the household when a family member is sick, with intergenerational effects. Women in their child-bearing years are also particularly affected by poor patient safety. The maternal mortality ratio (maternal deaths per 100,000 live births) for middle-income countries is 170 compared to 57 for high-income countries. Investment in better health care systems increases children’s and mothers’ life expectancies, labour productivity, and income and asset accumulation. Good practice in health policy development and implementation can assist and accelerate greater inclusion for better health for all.

The UK also has a strong scientific imperative to engage more deeply with partner countries in tackling non-communicable diseases. NCDs are one of the world’s largest, and growing, medical problems. While the UK has considerable expertise in tackling these, we will also benefit substantially from shared thinking and collaboration on this with our partners.

The UK’s Export Strategy of supporting and connecting businesses to grow on the world stage. There is a heightened economic incentive for the UK help to support the expansion of prosperity within our partner countries, and to strengthen our trading relationship with them. UK health sector businesses and the NHS have a strong global offer. This programme should help them, and international businesses, to do more work in our partner countries. The clear association of PF support with the UK, as well as the likely involvement of UK expertise in programme design and delivery, will add weight to the UK’s bilateral relationships and help create the right environment for positive discussions on future Free Trade Agreements of mutual benefit to both the UK and the partner countries. DIT will look to capitalise on the programme’s commercial benefits through follow-on trade missions and the work of Healthcare UK (backed by DHSC/DIT/NHS England). The programme will complement Healthcare UK in its South East Asian priority markets for services, including clinical services, digital health and education and training.

The Partner countries are a good strategic fit with the programme. We have selected partners who are Lower or Middle Income (LMI) countries that are working towards, or aspiring to, universal health coverage. They are stable, have the potential to benefit from UK expertise, and have indicated a strong willingness to collaborate with the UK. All of these countries also have growing health sector markets, with Brazil and South Africa members of the BRICS. UK diplomatic missions (Posts) are active in all of the partner countries and have actively participated in programme design and related government-to-government engagement. This effort will be reinforced by Healthcare UK and its efforts to strengthen and support the UK’s commercial offer and through DIT trade missions. There are MOUs in place between the UK and Mexico, South Africa and Brazil on health that will integrate and provide a key supporting framework for Prosperity Fund health programming. Several HMG programmes have already helped lay the foundations for a successful PF programme, including:

- successful early PF year 1 projects in the partner countries e.g. Brazil
- related Newton Fund projects e.g. in South Africa, Mexico
- relationships established through the UK’s global Science and Innovation Network

Further information on the choice of partner countries can be found in the Economic Case.
BHP Fit with HMG Policy. As stated above, the BHP feeds into the UK’s commitment to the Sustainable Development Goals. It also aligns with the UK Aid Strategy by reducing poverty and serving our national interest, and the National Security Strategy and Strategic Security and Defence Review (2015) in terms of increasing UK prosperity abroad and boosting UK exports. The National Security Council has highlighted that the UK should seek to use ODA to “unlock private and public sector investment….” It is also IDA and GEA-compliant and aligned. The programme has been designed in close consultation with Whitehall government departments with overlapping health interest and strategic priorities: the Department of Health and Social Care (DHSC), the Department for International Development (DfID) and the Department for International Trade (DIT).

The programme will complement the UK’s global efforts to tackle Anti-Microbial Resistance (AMR). A Life Sciences component could also support AMR policy by facilitating collaboration on the development of new antibiotics, as well as support implementation of the UK’s Industrial Strategy, which identified the UK Life Sciences sector as critical to the UK economy and UK health.

The programme will complement DIT’s work in fostering collaboration and relationships with potential trading partners in overseas healthcare markets. DIT will look to seize the programme’s commercial benefits using non-ODA funds through follow-on trade missions and the work of the joint DHSC/DIT/NHS England-backed Healthcare UK. The programme will complement Healthcare UK in its South East Asian priority markets for services, including clinical services, digital health and education and training. Brazil and Mexico are DIT priority markets for Life Sciences. It will additionally help to unlock and broaden horizons towards future markets. The programme also complements the international agendas of UK government health organisations, including (but not limited to) Public Health England, Health Education England and NHS Improvement.

Gender Equality Act (GEA) Compliance and impact. This programme will ensure compliance and due regard to gender equality by integrating a gender and inclusion-sensitive approach that considers the differential impacts of proposed interventions on women and men and due diligence for doing no harm. Ensuring due regard to impact on gender equality, in line with the International Development (Gender Equality) Act (2014), will be integrated into the Terms of Reference for the programme’s design and procurement of delivery partners with the requisite gender expertise. It will be a key feature of social impact assessment and measurement, including disaggregation of impact on men and women.

Gender equality outcomes have been considered in the programme’s initial diagnostic work, Theory of Change and log frame (see Appendix A). G&I analysis will be required to inform the design of proposed interventions that improve women’s access to safe, affordable health services and better health and empowerment outcomes. Assessment of Gender impact has been included in the Terms of Reference for the Phase 1 design work and is covered in the Statement of Requirements for programme delivery. Suppliers are required to provide a gender and inclusion (G&I) action plan and Community Engagement plan, as part of their delivery work plans, to ensure that proposed interventions and approaches are responsive to the needs and views of poor and excluded women and men and actively promote opportunities for empowerment. For example, the community healthcare staff working with lower socioeconomic groups are predominantly women and the programme will directly educate, train and create opportunity for women in the health labour force.

Gender and inclusion issues will be integrated into the programme’s results framework, with data disaggregated by sex, socio-economic group, age and disability where feasible. GEA compliance, impact and alignment with the Prosperity Fund’s Gender and Inclusion Policy will be monitored as part of risk identification, evaluation, monitoring and management.

Poverty Impact. The programme will also integrate a poverty-sensitive approach, ensuring poverty reduction considerations and impact in design, implementation and evaluation. It will seek to address both absolute and relative poverty by promoting more equitable health outcomes. The programme includes efforts to increase levels of access to good quality, affordable primary care – still a key challenge facing the poorest segments of the population in middle-income countries, despite progress towards universalisation.

The interventions of this programme will contribute to poverty reduction, both by directly improving health outcomes and through improved prosperity. Measures to ensure poverty reduction is mainstreamed across the programme are set out in the log frame and poverty reduction outcomes are reflected in the Theory of Change. Poverty outputs and outcomes will feature in the Statement of Requirements for programme delivery and potential suppliers will need to demonstrate relevant expertise and how poverty reduction will be ensured. Inclusion issues will be factored into the results framework and KPI data will be disaggregated by sex, socio-economic group and age and disability to determine and measure impact. Poverty reduction impact will be monitored as part of risk identification, monitoring and management.

Environmental Impact. The programme is expected to deliver important environmental side benefits. These may include the reduced travel and hence CO2 emissions that result from the increased access to and reliance upon better, local services and corresponding lower demand on secondary and tertiary level care. Other potential benefits arising from the programme include changes in diet (leading to reduced meat consumption).

The programme complements Whitehall funds tackling other global health priorities. These include: the Newton Fund (not health specific), health elements of the Global Challenges Research Fund, and the Ross Fund, which tackles infectious diseases of epidemic potential. The Ross Fund includes DHSC’s Fleming Fund (limited to AMR/surveillance in low-income countries) and Global Health Research Programme, which commissions and funds outstanding applied global health research through the National Institute for Health Research (NIHR) and which is targeted at the health of the poorest and most vulnerable in LMICs. Other significant sources, including the Conflict, Security and Stability Fund (CSSF) and the Department for International Development (DfID), have different areas of focus (security in the CSSF case) or target countries (low and lower middle income in DfID’s case). Although Myanmar and – for a transitional period – South Africa remain countries in which DfID work, the focus of their work (reproductive health and communicable diseases) is different to the proposed focus of this programme.

Although distinct from other programmes, the BHP could still also strengthen the potential marketability of Newton Fund research outcomes e.g. by addressing clinical trial regulation in host countries to better align with international standards. The Global Challenges Research Fund and Ross Fund would be complemented by this programme e.g. by work to improve capacity and capability for disease surveillance.

The programme will complement wider donor activity dedicated to global health priorities, as well as potentially act as an enabler for larger scale programmes and health systems development. The activity of multilaterals, including the World Health Organisation (WHO) and the World Bank – both active on the thematic and geographical areas proposed – has been taken into account. The WHO has also set Member States the aim to reduce premature mortality from non-communicable diseases by 25% by 2025. Despite this, most bilateral donor activity remains focused on communicable diseases and reproductive health. The programme, therefore, fills a ‘gap’ in development assistance which will build on the WHO’s efforts (and limited resources) to address the growing NCD burden.

Fit with other PF Programmes

There are significant synergies between the BHP and other PF programmes (see table below), amplifying the overall impact of the PF. Local PF governance mechanisms operating at UK diplomatic missions will have a vital role to play in this process.

Programme	Link
Anti-corruption (covering most/all PF countries)	This programme will help create complementary environments and approaches that the proposed programme will benefit from (e.g. procurement).
Business environment (Mexico, Brazil, South Africa, SE Asia)	Business Environment will help improve competitiveness and regulatory environments, important for new and affordable medicines and medical devices – including from the UK
Trade (Brazil and others)	This will work with Brazil’s local patents and intellectual property office to reduce the time needed to approve new patents, including those for new medications, facilitating the entry of innovative pharmaceuticals
Future Cities (Brazil, South Africa, SE Asia)	The programme will help reduce congestion and pollution, easing access to vital services and improving respiratory health. Better-managed urban expansion means better access to health services and improved public transport and traffic management reduces pollution.
Digital (South Africa, Brazil)	The programme will improve internet access, creating an improved platform for digital health services among marginalised populations. The digital programme’s pillar on trust and resilience will increase confidence in digital services and health could be a focus for digitalisation pilots.
Skills (Mexico, Malaysia, Philippines, South Africa)	This programme may reinforce efforts to raise standards of medical education and professional development.
China (Health)	There is a shared focus on strengthened primary care, quality and standards of hospital care as well as potential cross-over in the area of life sciences regulation and policy

### Better Health is good for business
The programme is primarily designed to improve health and economic development outcomes. In doing so, it will create new opportunities by virtue of growing those very health sectors and economies.

Health is a significant area of opportunity. The world’s largest industry, it consumes an average of 10.5% of GDP globally. The Carlyle Group estimates the global market is worth almost £8trn annually and health spending is expected to grow at 6% a year for the next decade as emerging markets become richer and populations start to age. There are particular opportunities for the UK in the programme countries. They are projected to grow annually from 2024-28 at the following rates: 1.9% (Brazil), 1.3% (Mexico), 2.6% (South Africa) and 4.6% (South East Asia). In 2015, the value of UK global health exports was £32.6bn. This figure is currently estimated to increase to £40bn by 2020 due to increasing global commitments to healthcare investment, which will provide opportunities in the development of public health systems; health infrastructure; clinical services; education; training and digital health; and pharmaceuticals and medical products.

Scoping work carried out for this programme suggested that the health sub-sectors with the greatest potential to drive secondary (commercial) spillovers are:

- Clinical education and training
- Digitally-enabled primary care using telemedicine
- Health systems quality improvement

Given the strong correlation with partner country needs, these have all been selected as core thematic areas for the programme. In addition to creating direct opportunities in these health sub-sectors, supporting local health systems could also create a more favourable environment for exports of evidence-based, innovative pharmaceuticals and medical products. When combined, these sectors contribute substantially to UK exports. This is analysed further in the Economic Case.

The UK has an internationally distinctive reputation in health care organisation and delivery. The NHS was the world’s first ‘free at the point of use’ health system and, as a family of organisations, is recognised and renowned around the world for quality, efficiency and fairness, at scale. This is particularly so in low and middle-income countries. This provides a comparative advantage and unique platform for UK health organisations that are part of the broader NHS ecosystem of the Royal Colleges and professional associations; national health agencies; universities and research institutions; regulators and agencies; and the organisations that supply and partner with the NHS. We can build on and benefit from this high ‘brand recognition’. The significant comparative advantage of the UK’s health institutions has been noted by the All Party Parliamentary Group on Global Health (APPG). The UK has a globally respected national health service from which partner countries want to learn as they build their own public health offer. Although not an aim of the programme, this could create partnerships that help reinforce domestic capacity.

UK companies have strengths in all of the thematic areas relevant to the programme, including health consultancy; digital services and IT innovation; health research; health education; quality of care; efficiency; public finance; pharmaceuticals and medical devices. The UK is, for example, the G20’s most internet-based economy and the expertise and experience available from this technical advantage is significant. Furthermore, the UK is projected to benefit from the strength of its services sector. There are a number of consultancies that combine sector know-how and generalist consulting expertise. The UK also has a strong reputation for setting and monitoring implementation of standards. UK standards are more performance-oriented and therefore more adaptable and applicable to MICs.

Scoping for this programme involved interviews with a wide number of UK organisations to assess their capabilities, the obstacles they face entering middle-income markets, and their desire to enter those markets. Scoping demonstrated that the UK has the required capabilities to assist and the desire to export to these markets. Among the key barriers identified to exporting were:

- Regulatory certainty or clarity
- Depth of local relationships
- Lack of consistency in health care delivery
- Health system fragmentation and the lack of integrated systems
- Lack of local capability and capacity

This programme has been explicitly designed to address these barriers and builds on sub-sectors where the UK has competitive advantage, thereby maximising export opportunities. The implementation of this enabling programme should result in a pipeline of contracts that UK organisations are well positioned to win. The UK already has a strong foothold in most of the markets covered by the programme e.g. in South Africa it holds a 7% share of the market for goods and 15% of the market for services.

In summary, there are a wide range of factors and considerations that provide the strategic rationale for undertaking this programme.
Economic Case
This Economic Case considers how the programme services will be delivered and the procurement approach.

Options Methodology

The assessment of the potential partner countries was overseen by a cross-Whitehall Steering Committee, and involved consultation across the UK government. This included BEIS, organisations affiliated with the NHS (Public Health England, Health Education England, NHS Improvement, Royal Colleges), and the UK private and civil society sectors active in the health field. Outside the UK, the design process involved consultations with multilaterals (including WHO, World Bank, IFC) and local stakeholder governmental and non-governmental organisations. Independent consultants carried out detailed scoping of opportunities for the options assessment, and market engagement took place to test and refine the Steering Committee’s preferred options for programme structure and delivery.

The value for money appraisal was developed by FCO economists in conjunction with health economist consultants.

The Steering Committee used the following process to determine and agree potential options:

1. Prioritisation of countries
2. Determining their development needs and constraints
3. Determining business constraints
4. Assessing the UK health sector’s comparative advantage in those countries being considered
5. Establishing the thematic areas (“pillars”) where the UK could most add value.

The following sets out more detail for processes A and E:

Prioritisation of Countries (A)

To identify the programme’s priority countries, PF economists identified a long list of 19 countries. The list prioritised middle-income countries based on poverty levels and the size of market opportunity. Countries likely to feature a health component as part of another PF programmes were excluded. Those remaining were then assessed against the following criteria:
- interest from in-country stakeholders (indicating in-country policy alignment);
- health sector and market growth potential (GDP, health expenditure);
- ease of doing business;
- the health financing landscape;
- the existence of barriers to growth that the Prosperity Fund could address.

The list was then considered within the context of the UK’s distinctive capabilities in health relative to its competitors (based on research and interviews with a wide-range of health-related organisations in the UK). This provided a shortlist of four key countries / regions: South East Asia, Mexico, South Africa and Brazil.

Establishing the key intervention areas - the “pillars” (E)

Key intervention areas were narrowed down by the following process:

- Priority local development needs were identified, via i) literature review and ii) interviews with stakeholders;
- Needs were matched to UK capabilities (also based on literature review and interviews);
- Assessment of the degree of added value alongside local or donor-funded initiatives and alignment with national policies
- Assessment of the potential impact on inclusive growth, poverty reduction and gender equality
- Assessment of the potential opportunities for UK business

The Steering Committee then voted to establish the final intervention areas and these are:

- NCD Strategy
- Digital Health
- Health Education and Training
- Provider Performance Improvement and Quality of Care
- Life Sciences R&D Partnership Initiatives

These areas are referred to as the “pillars” of the programme. NCD Strategy and Provider Performance are the focus while Digital Health and Education will act as cross cutting supports. Life Sciences also supports both NCD strategy and Digital health.

In addition to the matching exercise, the FCO’s network of overseas Posts within the proposed partner countries undertook government-to-government engagement at national and sub-national levels to test the degree of alignment between the programme’s pillars and local needs.

From February to June 2018, the FCO asked the NHS to undertake additional extensive scoping in each of the eight partner countries. This scoping reinforced partner government buy-in and determined an agreed set of priority interventions. From this, country log frames were created which formed the basis of the Statement of Requirements used in the programme tendering process.

Programme design and structure

This section groups the barriers to development and commercial benefit under the five pillars of the programme, along with possible activities that would address them.

Pillar 1 – Strategies to counter Non-Communicable Diseases

The barriers to a more effective response to the NCD challenge include insufficient horizontal co-ordination across government on policy and the inconsistent application of NCD best practice across healthcare providers. There was also some lack of understanding of the prevailing risk factors and their interaction and lack of gender sensitive approaches on NCDs. For its part, business seeks clear strategic and policy direction in response to the NCD challenge and access to better data.

Subject to confirmation during the detailed design stage, activities in this pillar therefore could best focus on
- Supporting holistic solutions to NCD challenges within countries, based on coherent and evidence-based strategy and policy
- Improved understanding of risk factors (excess alcohol, poor diet, smoking, lack of exercise and their link with gender, age, poverty, disability, ethnicity, location and any other characteristics relevant to the local context)
- Effective and integrated public health campaigns
- Empowerment, training and better preventive action by female and male health workers at primary care levels

Implementation of this pillar and others will have clear benefit for lower socio-economic groups and women. Those on lower incomes are most affected by NCDs due to poor diet and a higher prevalence of smoking. NCDs are the leading cause of death for women worldwide, leading to 65% of all female deaths. Women also account for over half of the deaths due to NCDs each year. Twice as many women as men suffer from malnutrition and two-thirds of illiterate adults are women. Moreover, the community healthcare staff working with lower socioeconomic groups are predominantly women and the programme will directly educate, train and create opportunity for women in the health labour force.

Pillar 2 – Digital Health initiatives

Growing penetration into partner countries by affordable smartphones is presenting opportunities to transform health delivery in under-served areas - as small scale initiatives in South Africa and Mexico are already demonstrating. The main barriers to effective digital health are under-developed governance and regulatory frameworks (including on privacy), lack of access to patient data, insufficient data collection and analysis, capacity and capability at national and regional levels to assess and capitalise on opportunities, as well as patchy or localised impact and financing models. Business seeks a clearer regulatory environment and supportive operating framework, as well as access to better data.
Activities include:
- Provision of technical advice on establishing effective governance and regulatory frameworks, including robust mechanisms to enable use of patient data, while also protecting that data
- Assessment and prioritisation of potential digital services according to impact on beneficiary populations, taking into account women, poor and excluded groups differential access
- Setting up mechanisms to learn from the data
- Advice to government and IP owners on financing models
### Pillar 3 - Education and Training

Common barriers related to education and training include a relative lack of leadership and managerial skills in healthcare facilities (undermining efficiency and quality of operations), under-developed evidence-based and data-based decision-making to meet the needs of different service users; lack of gender and inclusion sensitive guidelines, and lack of clinical decision-making capacity at primary care levels. Business seeks clear standards governing the institutions operating in the sector, and policy commitment from government.

Activities under this pillar include:
- Strengthening of accredited management and leadership training, including ongoing professional education to enable healthcare professionals to adapt e.g. to epidemiological shifts
- Empowering and upskilling male and female primary care workers through training programmes, whether community healthcare workers, nurses or doctors
- Short courses and training for data analysts in healthcare settings
### Pillar 4 – Provider Performance Improvement
Some of the partner countries have relatively under-developed systems for monitoring and learning from provider performance, taking into account service-user feedback.
Activities under this pillar could include:
- Evaluating existing mechanisms of monitoring quality of care
- Technical advice to governments on how to establish quality monitoring mechanisms at the national level (as, for example, with the UK’s Care Quality Commission)
- Technical advice on data collection and management
### Pillar 5 – Life Sciences initiatives
Though a number of the countries have Life Sciences sectors, there is often a long lead-time on new pharmaceuticals products. When combined with an opaque or confusing regulatory environment, this can deter innovation. Domestic sectors would benefit from research partnerships in order to share data from drugs trials and to reduce the time and resources needed to bring new products to market. Business seeks a clear commitment to facilitate the approval of new medicines and medical devices.
Broadening beyond the R&D Partnerships suggested by the initial scoping, the activities that respond to these challenges could include:
- Improved and efficient regulatory systems
- Increasing research capacity through joint collaboration on new IP
- Establishing incubators for research and development of priority medicines
- Strengthening Health Technology Assessment

The Theory of Change (see Appendix A) shows the logic for how the programme will create impact through the interventions. The activity forming the basis of this distribution was revisited during Phase 1 based on further testing with partner countries. The activities forming the basis of the Statement of Requirements serve as the foundation for calculating the potential benefits of the programme. The links between interventions and impacts are explored further in the section entitled “Assessing costs and benefits”.
## Sustainability

The interventions have been selected based on strong alignment with partner country policies and national priorities e.g. stakeholders in Mexico City have confirmed their interest in learning from the UK about systems for improving quality of care. Once local prosperity barriers have been overcome, the primary benefits should be sustained without further significant HMG involvement e.g. the ‘training of trainers’ schemes that allow for continued expansion without further HMG funding. Changes of government are likely within the lifetime of the programme and the programme will be insured against such change by i) focusing on themes that are not considered partisan and ii) by mapping and consulting a wide range of stakeholders. The programme will allow some interventions to be designed after procurement to enable further programme development with incoming governments in several of the partner countries. The appointment of a Strategic Partner to oversee government-to-government dialogue in relation to the programme and its benefits will also strengthen sustainability.

On secondary benefits, DIT has committed – with the support of non-ODA programme resources secured by the programme team – to follow up on the opportunities created. This includes two ring-fenced staff dedicated to working with the private and public sector in the UK to respond to and generate leads. UK health sector businesses and organisations have expressed interest in the opportunities that the programme will create in growing markets right from the start. The following section looks at what those are worth both to the partner country and the UK.

Assessing costs and benefits

Assessing the primary benefits of the Better Health Programme is challenging as the programme has a major focus on interventions related to healthcare system strengthening. Since such interventions often influence health outcomes through long and complex causal chains, they are not readily amenable to “standard” economic appraisal. As such, although primary benefit estimates are presented here, the impact of the interventions on health outcomes is uncertain and strong assumptions have been made in terms of the attribution of health outcomes to the programme’s interventions. In recognition of these limitations, a review of the literature on the general benefits of health system strengthening is included in the business case as further rationale for the programme’s proposed interventions.

The programme is estimated to generate £69m primary benefits and secondary benefits of £55-66m, against programme costs of £51.7m (all discounted). The primary benefit-cost ratio is estimated to be 1.3:1 and the secondary benefit-cost ratio from 1.1:1 to 1.3:1.

However, these estimates only represent a subset of the benefits expected from this programme. The primary benefit estimates reflect the intrinsic value of improved health to individuals, but not the wider economic benefits, for example higher productivity, increased labour force participation, greater participation in education and so on. The secondary benefits estimates include the commercial benefits that could arise from the programme, but do not include the indirect economic benefits of a healthier population to the global economy e.g. greater demand for imports, the benefits of a more productive workforce for foreign investors etc.

The following table summarises the different potential benefits of the programme (referenced in the strategic case) and which of these have and have not been included in the estimates of programme benefits.

Benefit	Included in benefits estimates?	Explanation
Primary – Intrinsic value of improved health to the individual	✓	Healthcare system strengthening should lead to improved health outcomes (longer and better quality lives) for partner country populations, which is of value in its own right. There are various measures for estimating the impact of interventions on health outcomes such as Disability Adjusted Life Years (DALYs) and Quality Adjusted Life Years (QALYs) and techniques for estimating the value that individuals place on these.
Primary and secondary- Increased economic output	x	There are a number of channels through which healthcare system strengthening can lead to increased economic output, benefiting both the partner country and increasing the opportunities for international firms, including the UK’s: / Improved health outcomes should lead to improvements in workers’ productivity, increasing economic output and trade. Increased life longevity also increases individual incentives to save, providing more funds for capital accumulation, increasing long run output and growth. This resulting economic growth benefits citizens whilst increasing the size of markets for international business. / For example, two-thirds of premature deaths in adults are associated with childhood conditions and behaviours. NCD interventions focusing on healthy lifestyle education in schools could improve education outcomes; mitigate NCD prevalence and premature deaths. Currie and Vogl (2012) argue that the long-run consequences of early-life health shocks (e.g. on school completion, IQ, and wages) depend on the availability and effectiveness of mitigation strategies. / The number of individuals with caring responsibilities for others should also decrease with an improved healthcare system. Whilst this increases individual freedom and earning potential, it should also reduce the costs of health related absenteeism. / Health investment creates employment both directly in the health sector and indirectly in the industries supporting the sector. This benefits those employed with higher purchasing power whilst generating multiplier effects on the initial investment.
Secondary – Export opportunities arising from NCD Strategy and Education and Training interventions	✓	The programme’s intervention areas should result in opportunities for international providers of health services, including organisations in the UK, For example, improving provider quality may involve training and education of healthcare workers. UK health organisations have a significant comparative advantage due to the reputation the NHS has for quality, efficiency and fairness. UK health companies also have expertise across the thematic areas relevant to the Better Health programme.
Secondary - More regulatory certainty and increase in local capability	x	The programme aims to increase horizontal co-ordination across the healthcare system, by helping to develop standardised regulatory frameworks and by strengthening the training of new leaders to increase the efficiency of management. An improvement in the management of partner-country healthcare systems can make it easier for international health organisations and companies to supply those systems, increasing the likelihood of foreign direct investment in the sector, whilst also increasing the opportunities available for international firms, including the UK’s.
Secondary – Increase in soft power	x	Research, based on a large US aid programme, has shown that foreign aid in the health sector that is targeted, sustained, effective, and visible can significantly improve public perception of the donor country. Although the Better Health programme is of a smaller scale, there is scope for it to improve opinion of the UK in partner countries, particularly among key stakeholders.

This table does not include the other non-economic benefits of the programme described in the strategic case, such as the environmental benefit of improved digital health options that can reduce the need for travel, thereby reducing emissions, nor the poverty and gender impacts described in the strategic case that help the programme to deliver inclusive growth.

Quantitative analysis
1. The primary benefits of the programme have been estimated in terms of the intrinsic value of improved health to citizens. Improving population health can help address poverty reduction in that health issues often disproportionately affect lower income groups. In the analysis, improved population health has been estimated in terms of the Disability Adjusted Life Years (DALYs) that have been avoided because of the programme’s interventions in the programme countries. DALYs are a measure of life years lost due to disease or injury; they account for impact on quality of life as well as longevity.
2. To be able to compare benefits with costs, it is necessary to value avoided DALYs in monetary terms. Various techniques have been used to estimate the value of a DALY e.g. surveying patients/citizens’ “willingness to pay” for additional life years. In the analysis, a proxy of 1.5 per capita incomes has been used to value DALYs, drawing upon the health economics literature. However, given the uncertainty around such proxies, this has been tested in sensitivity analysis along with other key assumptions.

1. As discussed, wider economic benefits can also be expected from improved population health - through channels such as improved productivity and cognitive functioning and improved participation in the workforce and education.
2. At the time of analysis (2018), the interventions from the Phase 1 work were available only for a limited number of the target countries. These interventions were concentrated within the NCD and Education and Training pillars. As such, the programme benefits have been estimated “as if” the programme budget were solely allocated to the NCD and Education & Training pillars in all countries.
3. For the NCD analysis, an estimate has been made of the benefits of improving national NCD strategies in terms of the reduced prevalence of overweight status in the population. This has drawn upon the evaluated impact of a NCD intervention programme within China. A difficulty within the analysis is estimating the likely subsequent “reach” of the new policy (i.e. what fraction of the overweight population it will reach and by when) and also how much of the benefits can be attributed to the Better Health Programme’s interventions, given the complex pathways by which intervention inputs are connected to health outcomes.
4. For the Education and Training analysis, an estimate has been made of the benefits of improving primary healthcare workers’ skills in terms of the reduced risk of medical errors. Once again, drawing upon an evaluation study, reach and attribution are key uncertainties in the analysis and are tested through sensitivity analysis.
5. In both analyses, estimated benefits have been adjusted for an estimated likelihood of success for delivering positive health impacts in each programme country. These success factors have been informed by judgments of delivery risk made by the Strategic Partner.
6. The estimated primary benefit-cost ratio is 1.3:1, i.e. for each £ invested in the programme, there is an expected return of £1.3 in terms of improved population health outcomes (Table 1). This reflects the valuation of a DALY at 1.5x per capita income, a proxy for citizens’ willingness to pay for an additional life year. If this proxy is increased to 2x per capita incomes (2x is also referenced in the health appraisal literature), the programme’s primary benefit-cost ratio increases to 1.8:1.
7. The secondary benefits of the programme have been assessed in terms of the export opportunities that could arise from the proposed NCD Strategy and Education and Training interventions. These include UK institutions providing clinical guidelines, training, and education on NCDs, or primary healthcare training and data analytics to healthcare workers.
8. The estimated secondary benefit-cost ratio is 1.1:1 i.e. for each £1 invested in the programme there is an expected return of £1.1 in terms of UK healthcare education and training exports (Table 1). This ratio could rise as the programme interventions are finalised, including those in the other pillars. For example, cursory analysis of the potential benefits to UK pharmaceutical companies of reforming clinical trial regulations in Brazil (as an example) could improve the ratio to 1.3:1. The strategic partnership provided by the programme will also lead to significant additional export benefits that have not been included in the model. We will keep this benefit-cost ratio under review because our understanding of the programme’s economic impact will improve as the programme matures.
9. Table 1 summarises the costs and benefits of the programme. It should be underlined that these likely underestimate the potential benefits of this programme, given some benefits have not been estimated.
Table 1 - Summary of BHP Benefits (Quantitative Appraisal)
Total for 2018/19 – 2027/28
Total Programme Cost	£79.2m
Total Programme Cost (Allocated)	£58.0m
Present Value Costs (Allocated)	£51.7m

Total Primary Benefits	£158m
Present Value Primary Benefits	£69m
Primary Benefit-Cost Ratio	1.3 : 1

Total Secondary Benefits	£88m
Present Value Secondary Benefits	£55m
Secondary Benefit-Cost Ratio	1.1 : 1

Total programme costs relates to the total cost of the BHP, including design and management costs. “Allocated costs” refer to the costs that were assigned to interventions at the time of the analysis (approximately 75% of total costs) plus a pro-rata portion of the total management costs. The benefits estimated are based only upon interventions associate with these allocated costs.
Primary benefits are discounted to the start of 2018/19 using a 10% discount rate as these benefits accrue to the programme countries. Secondary benefits and Prosperity Fund costs are discounted to the start of 2018/19 using a 3.5% discount rate as these costs/benefits accrue to the UK.
Benefit-Cost Ratios = PV Benefits / PV Costs (Allocated)

1. Sensitivity analysis was conducted for both the primary and secondary benefits.
2. For the primary benefits, there is moderate tolerance to a worsening of the key assumptions before the programme’s benefits fall below its costs. In particular, there is little resilience at the start year for realising the benefits (currently assumed to be 2024/25). However, this is partly due to a fixed appraisal period of 10 years i.e. in reality, additional benefits would be realised beyond the assumed appraisal period if the programme were to be delayed.
3. There is some tolerance for the worsening of the assumed NCD population reach, reduction in overweight prevalence, number of doctors trained per year and reduction in medical errors and attribution factors, which would each need to halve (univariate) before the programme breaks-even on primary benefits.
4. For the secondary benefits, there is only limited tolerance to a worsening of key assumptions given the benefit-cost ratio is 1.1:1.

Literature Review
1. Given the limitations of the quantitative analysis, a literature review of the value and impact of health system strengthening interventions has been undertaken to demonstrate the importance of investing in them.
2. The findings relate to the impact of interventions in governance; in engagement of communities and leaders; translating research into policy and practice; human resources on health outcomes and the health system; and the barriers that weak health systems pose to scaling up interventions.

There is evidence that governance interventions that aim to create or promote the accountability of health services providers to their communities can have positive impacts on both health outcomes and the health system. The Leadership Development Programme, introduced in three districts in Aswan, Egypt, in 2002 to improve health services by increasing managers’ ability to create high performing teams and to improve their leadership skills, provides an interesting case study. In the districts in which the programme was introduced, teams focussed on tackling service delivery challenges where they saw a reduction in maternal mortality from 85 per 100,000 live births to 35 per 100,000 in Aswan.

Providing thought leadership, through dissemination of rigorous evaluations and other research studies, has also been shown to impact policy and practice that, in turn, can affect health outcomes. A study by Kings College London reviews a number of well-disseminated, rigorous research studies that have been impactful. For example, DFID-funded research, evaluating a pilot programme to improve access to quality reproductive health and family planning services, led to significant changes in the structure and delivery of the programme. This ensured improved access to quality reproductive health and family planning services for more than 750 million Chinese men and women when the government rolled out the programme nationally.

It is widely acknowledged that human resources are a fundamental component of a strong health system. In particular, there should be adequate numbers of well-trained health workers available in health facilities. A number of systematic reviews conclude that training health workers can have positive impacts on health outcomes such as new-born and maternal mortality. In addition, there is evidence to suggest that investing in health worker training can have additional impacts beyond those in health outcomes, such as increasing vaccination coverage and improving children’s nutrition. Another study found that community health-worker programmes, which help to bring health services closer to the community, have been shown to increase both the uptake of care for malaria, pneumonia, diarrhoea and the prevalence of healthy behaviours such as breastfeeding and use of long-lasting contraceptives.

Finally, there are numerous examples in the literature in which weak health systems are cited as a barrier to successfully implementing and scaling-up health interventions. Evidence suggests that one issue is that while there is a wealth of evidence of the efficacy and effectiveness of certain health interventions, less attention is paid to questions of how to deliver them and how to scale-up interventions. One study found that a key barrier to scale up is the limited capacity in terms of human resources, leadership and management and health systems capacity in low and middle-income countries.

# Commercial Case
This section considers how the services required of the programme will be delivered and therefore the procurement approach.

Overview: How the Programme is Being Delivered
The delivery model is as follows:

Phase 1: a Strategic Development phase* / Ran for 4 months from March – July 2018. This Phase clarified the intervention areas the BHP would be focusing on and secured partner government buy-in. / A Strategic Partner delivered this phase.
Phase 2: the programme delivery phase / Runs for 3.5 years from July 2019. This phase is split into inception (4 months of work planning by the Deliver Partner) followed by Implementation (actual delivery). / Four separate Suppliers have been selected to deliver the programme in Brazil, Mexico, South Africa and South East Asia for the duration of Phase 2.
Phase 2: / Strategic Partner engaged to support the FCO and help it operate as an intelligent customer. / The Strategic Partner MOU covers FY19/20 and there is the option to extend it to FY20/21 and beyond as needed.
*Transition period / Although not part of the delivery model, it is worth noting that this period, which followed Phase 1 and preceded Phase 2 covered the tendering process and contract completion period.

## Service requirements
1. The approach to delivering the programme was informed by the views of the programme’s Steering Committee, by Phase 1 design work and by market testing.
2. Phase 1 deployed a range of health experts from UK government health organisations in each proposed programme country, with the key purpose of building upon the initial scoping and government-to-government engagement to develop an agreed set of interventions for each geography.
3. For Phase 2, Delivery of the roles of the Strategic Partner and Delivery Partners are as follows:
Strategic Partner (SP):
- Primary health systems adviser and, where possible, interlocutor for the programme with decision-makers in partner countries, working with / through Better Health Programme leads in UK diplomatic missions as facilitators in country
- Looks across the activities in other countries in the programme to spot synergies and lessons
- Shares knowledge with partner governments on sector challenges both related to the programme and wider health needs
- Analyses and quality assures reporting from the across the programme
- Provides advice to the programme on changes required to maximise impact
- Provides advice on social inclusion and gender equality in health programmes, as well as methods of measuring impact by gender/socio-economic group
- Keeps abreast of UK and international best practice to ensure that a range of practice is being applied
- Provides health sector draw-down facility, furnishing the programme with technical expertise in support of implementation as required

The SP may also contribute to, or provide some of, the following programme management services in order to support the Authority, where these are not adequately captured by the PF-wide MREL contract, Delivery Partners or central London-based Better Health Programme Team:

- Ensure progress towards benefits is appropriately tracked
- Ensures risks and issues are being managed
- Reviews proposed communications from the programme and its Delivery Partners

Delivery Partners (DP):
- Deliver interventions with intended primary and secondary impacts, including on gender and poverty reduction
- Spot synergies within country environments
- Build effective relations with stakeholders such that buy-in and ownership is achieved
- Regular reporting to the Authority that informs cross-programme learning and management
## Delivery Criteria and Options
The key decisions the FCO had to take about contracting a Delivery Partner were:
(A) what type of Delivery Partner/s we would use - whether we would use in-house delivery, multilateral delivery or the private sector;
(B) whether we would use one Delivery Partner for the entire programme, or use a consortium or separate Delivery Partners by country / region;
(C) whether to procure from the existing PF Framework or go through a more extensive procurement process
For decisions A and C, the choice of an established private sector company on the PF Framework was considered the most logical choice.
On decision (A): The delivery criteria included, price, existing health expertise or health expertise resource capacity, in-country expertise, the risks of a UK-centric approach verses an international mind-set etc. The organisations that have the sort of global expertise that can be accessed within a reasonable period are major private sector companies with prior experience delivering in the health sector. Such companies are on the PF Framework list.
On decision (C): PF Framework companies have been pre-vetted and the procurement process is tried and tested. Therefore selecting Suppliers off the PF Framework is much quicker than doing a bespoke procurement process. Given the time constraints on all PF programmes (delivery to be completed by 2022), the Framework companies offered the best option.
For the final decision (B), the Foreign Office, in consultation with the NHS, DHSC, DIT and DFID took the decision to ask Suppliers on the PF Framework to separately bid for contracts in South Africa, Mexico, Brazil and South East Asia. This was to ensure that we would receive strong bids specifically tailored to each country or region. The PF Framework Suppliers were encouraged to bid for more than one country or region.
1. Although the majority of the programme’s interventions were defined in the ITT Statement of Requirements and were to form the basis of supplier tenders, the final set of activities and outputs will be determined during the inception phase at the outset of Phase 2 with the input of partner countries and the supplier. This will provide flexibility for programme development countries experiencing potential changes of government to respond to evolving requirements.
2. The key decisions the FCO had to take about contracting the Strategic Partner were quite straightforward: we primarily needed an organization that had sufficient breadth and depth of health expertise to cover the programme health intervention areas. We also needed an organization that had extensive experience in project / programme management with experienced personnel who could deal with senior stakeholders across the programme. An NHS consortium led by Health Education England possessed the requisite experience, expertise and resources to be the Strategic Partner for Phase 1 and for Phase 2. The FCO accordingly chose the NHS because their range of skills and expertise could not be matched by any private sector organization.
## Market engagement
The preparation of this business case has involved wide market engagement that has helped gauge the capability, capacity and interest of the market to deliver the programme. Contracting and risk transfer
## Overall Approach to Value for Money and Managing Performance
In terms of overall efficiency, effectiveness, economy and equity, the delivery model and approach to commissioning the work is expected to achieve high value for money:
VfM factor	High/Medium/Low assessment	Rationale
Efficiency	High	As a result of scoping and specifying interventions; as a result of using a competitive process (PF Framework) to allocate 85-90% of the programme funding; due to the strong degree of HMG control
Effectiveness	Medium/High	As a result of appointing health experts with strong knowledge of both primary and secondary benefit agendas to act in a strategic capacity in phase 1 and 2, as well as attached to the central/Post teams; from annual reviews and the use of adaptive programming
Economy	Medium/High	As a result of running a competitive process to allocate most of the funding; due to the use of maximum day rates; due to dividing the programme into service and geographic components to generate maximum competition; due to no limits being placed on the number of potential delivery partners
Equity	High	As a result of specifying interventions that address gender and income inequality, with accountability for them; due to an inclusive and participatory approach to programme design and delivery

1. The following sections elaborate on how VfM and effective performance will be achieved.
2. Quarterly and annual reviews will be conducted as part of overall programme governance set out in the management case. These will take account of and be aligned with the contracted Monitoring & Reporting service and Evaluation & Learning service.
### Type of contract
The FCO will be the contracting authority for all contracts. The contract type to be used for each service is set out below, together with the budget. The commercial agreements, will utilise the terms and conditions of the PF Framework unless an administrative agent is procured to support the Strategic Partner, Supplementary terms and conditions will be included as appropriate and agreed with the FCO commercial team. These may be required to cater for dynamic programming options and the need to potentially scale both up and down.
Service	Type of contract	Budget	Contract length
Phase 1 Strategic Partner	MOU	£900k (for FY 17/18 + 18/19)	4 months (started March 2018)
Phase 2 Strategic Partner	MOU	£886,062 (FY 19/20) / £3.0m over total Delivery Phase	42 months (assumes transitional phase from August 2018 and full role from July 2019)
Phase 2 Delivery Partners	Commercial contract(s)	£69.22m	38 months (assumes start date of July 2019)

## Procurement Methods
The planned procurement route and rationale for each service are set out below:
Service	Procurement route	Rationale
Phase 1 Strategic Partner	Single Source	Role best suited to HMG health experts
Phase 2 Strategic Partner	Single source, including support to central functions (primarily QA, but also advice on MREL, risk management and comms)	Experience of Phase 1 suggests role best suited to HMG health agencies, aligned with multilaterals, IFIs and key donors. Requirement jointly developed and evaluated with FCO
Phase 2 Delivery Partners	PF Framework	Rapid procurement option using eligible pre-qualified suppliers

Expertise
This is a complex procurement and the central programme team has sought and will continue to seek advice as required from the following to ensure a defensible, legal and value for money approach is taken:
- Commercial – FCO CPG and Joint Funds Unit (JFU)
- Legal – FCO Legal
- Financial – FCO Finance and JFU
- Communications – FCO Communications and JFU
- Economic – FCO Economics Unit; FCO PF Department Economist
- Gender – FCO PF Department Social Development Adviser
- MREL – FCO PF Department MREL Adviser
- Health – NHS, DFID, DHSC and DIT experts (pending a dedicated Programme Health Adviser)
1. Further information on the roles and responsibilities of staff involved in the programme are available from the management case.
2. Procurement took place over 1 November 2018 – 13 December 2018 with the contracts awarded to Delivery Partners on 1 July 2019.
Additional Market Engagement
As noted above, additional market engagement was held prior to ITT through online webinars. Market engagement confirmed wide interest from both framework suppliers and potential partners in the programme and enabled potential partnerships to form.
Statement of Requirements
The scope of work to be undertaken in each of the four programme lots was defined in a consolidated Statement of Requirements (SORs) supported by country and programme level logframes developed during Phase 1 of the programme. These provided a clear breakdown of the required programme outputs, as developed in partnership with in-country stakeholders, and indicative activities. Suppliers were invited to build upon and add value to the indicative activities and to propose quantitative and qualitative indicators. Service level KPIs were also set out in this document.
Delivery Partners – Key Responsibilities
The lead Delivery Partners will:
  1. Ensure proposed programme activities contribute to the Theory of Change and programme outcomes
  2. Deliver those programme activities and related outputs
  3. Ensure read across and coordination of programme activities
  4. Monitor and report on programme performance against a milestone and output-based implementation schedule aligned with the detailed, costed Work Plan, defined during the Inception Phase
  5. Advance Gender Equality and Social Inclusion through delivery and the impact of programme activities and outputs, ensuring GEA and IDA compliance.

Procurement Process
Four lots (Brazil, Mexico, South Africa, and South East Asia (comprising five countries)) were procured in one ITT published on 1 November using the PF Framework. The PF Framework Agreement - designed specifically for the Prosperity Fund Programme - awarded 20 suppliers the right to bid against these lots. The four Better Health contracts were competed via a call off competition.
#### Evaluation and Moderation
1. Following the close of the deadline for the ITT returns, the FCO Commercial team ran an evaluation process to assess and reach conclusions regarding the 12 bids received with support from the programme team and an external contractor Grant Thornton. Proposals were evaluated individually and independently over a period of 4-5 weeks by evaluation panels (one per LOT), comprising a minimum of four panellists.
2. All panel members attended in person and the panels involved between 15 hours and in excess of 60 hours of input depending on the number of bids and size of moderation panels involved. The scoring for the evaluation was weighted 70% Technical to 30% Commercial, reflective of the Framework evaluation weightings.
Contract Award
All winning suppliers (and bidding partners) had to demonstrate their ability in the following key areas:
- To work collaboratively with governments to ensure delivery of target outcomes
- A track record of working on related projects at scale
- A track record of delivering results and VFM
- The capability needed to deliver results in this programme

All four bids in total fell within our total budget. The total cost of the four contracts is £69.22m (this includes local tax).
## Contract Management
1. Key programme governance structures are defined in the Management Case. The Strategic Programme Board and monthly Programme Committees will be the key bodies providing overall strategic oversight and operational decisions. These will be supplemented and supported at the national or regional level by in-country Steering Committees or Delivery Boards.
2. The Contract Manager will be based in London in the Central Programme Team, but will work closely with both the Health Programme Advisers at Posts and the Strategic Partner to ensure contractual obligations are fulfilled. The Contract Manager’s work will be framed by a contract management plan that will provide the basis for robust and clear contract management activities, principles and review points. Country-based Programme Advisers will be responsible for:
- relationship management including working with stakeholders to support the supplier’s progress;
- monitoring progress against Key Performance Indicators and Payment by Results mechanisms such as milestone payments, and reporting on these (see below for further information on Key Performance Indicators and Payment Mechanisms);
- ensuring GEA compliance and technical QA for gender, poverty and inclusion.
The Strategic Partner will support them as and when required.
Performance and reporting
Detailed reporting and monitoring requirements will be agreed with the central Monitoring, Reporting, Evaluation and Learning (MREL) teams, both in the Joint Funds Unit and the Prosperity Fund Department. Monthly financial reports will enable the FCO to make key decisions regarding the direction of the programme.

Management Case
The Management Case demonstrates that the “preferred option” is capable of being delivered successfully, in accordance with recognised best practice.

Programme Governance
1. The programme is owned by the FCO, and the Senior Responsible Owner (SRO) will be the FCO Director of Economic Diplomacy.
2. The SRO will report via the Joint Funds Unit (JFU) to the PF Portfolio Board and National Security Council (NSC) ministerial oversight in accordance with standard FCO and PF reporting arrangements. The cross-Whitehall Steering Committee that guided the development of the concept note and business case has ceased and been superseded by a Programme Management Committee and Strategic Programme Board, both of which are already meeting on monthly and quarterly schedules.
3. The overall governance structure is set out in the diagram below.

The key roles of the above governance levels are as follows.
Governance level	Roles
NSC Sub-Committee	Held quarterly, this Ministerial Board provides overall strategic direction for the PF and CSSF Funds and approves the Programmes’ Concept Notes.
Minister for the PF	FCO approval of PF programmes
PF Portfolio Board	Chaired by Director NSS (Cabinet Office) and held monthly. Cross Whitehall and sets the programme’s strategic direction by approving Concept Notes, manages overall performance of the Prosperity Fund, agrees programme prioritisation and funding allocations and manages the portfolio’s risk exposure. FCO Head of Prosperity Fund Department attends.
PUS	Lead FCO accounting officer, supported by ExCo.
Joint Funds Unit (JFU)	Cross-Whitehall management of the portfolio, including governance, reporting and change control.
Prosperity Fund Delivery Unit (PFDU)	Supports FCO programme delivery and reporting.
Programme SRO	Accountable for programme delivery; high level direction of programme and responsible for key decisions
Strategic Programme Board (SPB) (Now called the Quarterly Strategic Board, or QSB)	Drives programme forward strategically and supports SRO
Expert Panel	Provides independent expert advice to the SPB and SRO
Strategic Partner	Reporting directly into SPB on country specific and programme wide issues and decisions flowing from supply and from strategic engagement
Programme Lead	Heads the Operational Committee and is a link to SPB. Day to day oversight of programme delivery; drives coherence within the sector across the Fund
Programme Management Committee (PMC)	Responsible for programme delivery and operational decisions; reports to SPB
Country Steering Committees	Drives programme forward locally and takes local decisions; reports to Operational committee, but can elevate issues direct to SPB; help to spot synergies with wider HMG and PF work

The SPB will include the following members:

  1. SRO (chair)
  2. Senior representatives from Posts
  3. Senior representatives from DHSC, DIT and FCO; DFID consulted
  4. Senior representatives from Strategic Partner
  5. Senior representatives from delivery partners (to be invited as required to report)
  6. Programme lead – day to day programme leadership and oversight

The Programme Management Committee will include the following members:

  1. The programme lead (chair)
  2. Working level representatives from Posts
  3. Core programme team
  4. Strategic Partner (advisory role)

Title	Description	Chair	Attendees
Quarterly Strategic Board	Meetings to focus on overall strategic direction of the Programme, review progress, benefits realisation (impacts – MREL) and continuous improvement.	SRO	Strategic Partner (NHS and HEE) / Post senior managers / DIT / JFU representatives / PFD representatives / Programme Team (Secretariat)
Monthly Programme Management Committee	Meetings to cover delivery of the programme and operational decisions, support individual in-country steering meetings and provide coherence between them; supplier performance monitoring against work plan, including KPIs/ SLA, management of contract and performance, savings and VFM. The PMC will also sign-off all invoice payments.	Programme Lead	Strategic Partner (NHS and HEE) / DIT / JFU representatives / PFD representatives / Programme Team / Post Health advisers
Monthly in-country Steering Committee	A mix of steering and technical meetings focused on coordination / technical aspects of delivery, local decisions, ensure effective local delivery and remains on-track, activities relevant and stakeholders engaged. Potential for Supplier presentations to inform progress, issues and next steps. Meetings to be staggered with monthly PMC meetings to allow each to pick up and respond to issues.	TBC during set-up but likely to be: / Senior representatives from Posts (e.g. Head of Prosperity)	Post Health advisers / Government rrepresentatives (advisory role) / Wider stakeholders as appropriate (advisory role)

The main governance meetings (overview)
## Programme Staffing
1. Programme interventions will be primarily delivered by the private sector, as will programme administration. HMG’s role in the programme will be predominately focused on:
  1. Government-to-government engagement
  2. Supplier management
  3. Ensuring outputs lead to short term outcomes (for example, gender and inclusion impact of training or improved access to services), as well as longer-term planned outcomes and impacts, both primary and secondary
  4. Maintaining alignment of programme outputs to wider (UK and international) policy.

1. HMG’s core programme resource will be led by a central programme team in London, supported by a South East Asia regional team in Singapore that provides leadership in that region, and resource in individual posts.
2. The team structure is set out below. Note that not all roles are full-time.
## Note that some advisory functions may be provided on a contracted basis. Linkages with the PF MREL (Monitoring, Reporting, Evaluation and Learning) contracts are to be determined.
The central programme team will manage the programme in accordance with HMG best practice, following MSP and PRINCE2 principles. In addition to the roles and functions of the central programme team and programme functions at Posts set out above, the programme will need to draw on expertise in the fields of health, social development and inclusive growth. The programme has appointed (from April 2019) two UK-based health advisers via the Strategic Partner platform, providing health technical expertise to the programme in the UK and a source of expertise and advice on health systems and development to posts and partner countries.
Implementation Plan
The key milestones over the coming months are set out below. A broad implementation plan for the duration of the programme will be developed at the end of this phase, once detail is known about the specific interventions. Where feasible, programme rollout will make use of piloted activity wherever possible so that lessons may be applied to similar activity within and in other countries of the programme.
June 2018
Review initial outputs of Strategic Development Phase and submit Outline Business Case (OBC)
Submit to FCO IIOC 2
July-August 2018
  1. FCO ExCo
- IPA/CO/HMT approval of OBC
- FCO Ministerial Approval
Sept-October 2018
- Preparation for procurement of the main delivery phase begins
- Statement of Requirements and ITT pack developed and tested
November 2018
ITT issued
December 2018 – January 2019
Bids evaluated
February 2019
- IIOC and Management Board Approval
- Strategic Partner MOU agreed
- Preferred suppliers notified
July 2019
- 3 Contracts signed
- Commencement of programme delivery
Late August 2019
Final Contract signed
The programme will allow for flexible or dynamic programming where lessons learned or changes in economic, political and social context during implementation suggest interventions should be scaled up or down within a country.
## Monitoring, Reporting, Evaluation and Learning
1. The monitoring, reporting, evaluation and learning (MREL) for this programme will be consistent with the PF approach to MREL, but the complexities of measuring health outcomes require MREL provisions to be set out in detail as part of overall assurance that benefits and impact will be fully tracked and measured. The MREL requirements of programmes that seek to strengthen health systems must take into account interrelationships and dependencies that exist between different core interventions, people, organisation, resources and policy that make up a health system.
  Figure 1 Illustration of monitoring – BHP interventions within health systems strengthening
2. The evidence on how to measure strengthened health system performance to achieve sustainable health improvements at scale is relatively limited. This is even more challenging concerning the link between improved health outcomes, health systems and Non Communicable Diseases
3. The 5 pillars identified by the BHP to be the fit between partner country priority, potential for impact and UK capability are intended to
1. reduce the risk of premature NCD related mortality and morbidity
2. improve patient safety and quality of care, which reduces illness, injury and premature mortality.
In the longer-term increases in life expectancy, reduced morbidity and prosperity are the ultimate impact.
1. Specifically BHP projects are designed to tackle NCDs, enhance telemedicine and other digital services, build workforce capacity in primary care, management and leadership, data and performance management for improved provider quality and improve the availability of medicines. Projects at country level may include one or more of these interventions; however, it can be seen that these pillars do not represent a total package of health systems strengthening in their own right.
2. Calculating attribution of one isolated package of interventions for example, health workforce capacity building towards impact is not possible to do in an accurate way, although limited research points to developing methods. The intervention is part of a broader system of other health sector strengthening initiatives which taken together amount to impact. Contribution methodology, which is a rigorous quali-quantitative approach that is used in impact evaluations to test the validity of claims, is required as the BHP will be complementing existing national programmes and initiatives to achieve impact.
3. MREL will be designed to capture not only the effectiveness of the BHP interventions but also system-wide changes occurring in other parts of the health system. This is necessary to understand whether strategies and interventions are having any effect on health system strengthening. In practice this means
1. including context and system-wide monitoring (contextual monitoring will include at least one outcome monitoring indicator and associated means of verification to track system-wide changes).
2. monitoring outcomes to explore causal links and contributions towards other health system functions
3. monitoring for unintended consequences, these approaches will be explored with the MR contractor.
Measuring value for money
1. As benefits of the programme are expected to be longer term (5 to 10+ years, post programme) to ensure VFM during the lifetime of implementation, robust project monitoring systems will be used as an on/off track markers along the way, to monitor that the trajectory towards outcomes and impacts is on course.
2. To ensure efficiency is maximised it will be necessary to monitor the unit cost of activities and analyse these costs against the outputs achieved.
3. Benchmarking activities and costs is good practice in ensuring value for money. As far as possible project managers will compare the costs of different activities to achieve similar outputs, looking across a range of similar projects
4. As these interventions sit within an overall health systems approach value for money can also be demonstrated by documenting and capturing the additional positive impacts resulting from the BHP with other related health systems strengthening initiatives in country, for example activities and outputs could likely be scaled up using host government (or private sector funds), and in contrast BHP interventions will complement and add to existing or planned health systems improvement. Additional benefit/value created will be captured as a separate additionality study or case study adding to the evidence base of Health Systems Strengthening strategies and impact.

The core programme management team will work with the PF Monitoring and Reporting contractor, including through a planned workshop, to define the indicators and measure different dimensions of equity. Programme indicators will link to the fund level indicators.[1] These will include poverty reduction and gender and inclusion indicators. In relation to the impact of the programme on women and girls’ health, there will be a deliberate gender emphasis in MREL to measure improved access and quality of care across primary, secondary and tertiary services. Service access and satisfaction data will be disaggregated where possible by gender, disability and socio-economic group. On poverty reduction, the programme will request bidders develop a Poverty Reduction Action Plan for implementation; and poverty reduction impact will be properly monitored as part of risk identification, monitoring and management.

Evaluation and Learning

1. The central programme management team, Posts and implementation partners will work closely with the PF’s appointed partner for Evaluation and Learning to ensure an effective and iterative learning process that benefits the ongoing programme. Scheduled yearly programme evaluation, led by the E&L contractor will provide programme management a tool for testing the plausibility of results and contribution claims of the projects. Programme Evaluations (PE), conducted on an annual basis, will be designed to provide quick information for management decision-making, support course correction and adaption.
2. Core PE questions will contribute towards fund accountability and include questions around contribution of the programme and its projects to the intended outputs and outcomes in the Theory of Change and interventions successful (or not) in contributing to the achievement of primary benefit. In addition, evaluations will include a documentation of the broader effects of the programme on the health system and an identification of causal pathways.
3. Importantly PE will answer questions that relate to implementation context – including social and organizational context, including community linkages (for poor populations most likely at risk from NCDs), linkages with non-formal leaders, the role of the private sector, and the importance of demand creation in bridging health needs with service availability. Measuring the impact of health systems strengthening requires a better understanding of how health systems support community needs, and how communities contribute to health systems strengthening
4. If this programme is selected as one of the sample for PF level evaluation, the core programme team, Posts and delivery partners will work with the PF evaluation and learning contractor to develop the strategic questions that will be required for both the PF evaluation and to provide feedback to the programme on routes to impact. The PF level evaluators and the core programme team will decide the overarching evaluation methodology; and Posts will work to deliver the required coordination with delivery partners at programme level.

MREL cycle
Indicator level	Project Management Cycle and Timeframe	MREL information gathered and VFM rationale
Per Intervention area activity/process/outputs taken from PROSPERO (project indicator reporting against milestones)	Quarterly reporting from Y1 / Annual review (requirement one year following SRO allocation letter)	Cost per activity / Benchmarking comparison with other similar activity types/interventions in comparable Countries / Allows : / -efficiencies to be identified early / -reductions in cost/beneficiary savings related to scaling up decisions / -understanding which cost categories and processes cost the most / - controls to be put in place to ensure maximum efficiency / - capture of non PF funding contribution
Activity, output, outcome Programme level + fund level indicators / Context and system wide monitoring – establish indicators	Programme Evaluation – / Annual from Sept 2018 and each year thereafter.	Year 1 baseline data collection / Formative evaluation (focuses on learning for improvement) in years 1,2 / Defines outcome contribution claims / Determines who is being targeted and how / Looks at sustainability in design and subsequent implementation processes / Determines balance and relationship between primary and secondary benefits / Looks at effectiveness of governance and management arrangements to achieve results and VFM / Looks at effectiveness of gender and inclusion / Rapid results and strong learning agenda to aid active portfolio management
Outcome and trajectory towards impact	Programme evaluation from year 3,4 5 onwards	Summative evaluation (looks at achievements and results). Measures outcome contribution claims / Including: / i. context and system-wide monitoring / ii. monitoring outcomes to explore causal links and contributions towards other health system functions iii. monitoring for unintended consequences
Impact	PF level evaluation (if selected ) / Years 5-10 post project programme evaluation	Strategic level evaluation to determine impact of overall fund / Post implementation (tbd)

### Results Framework
The programme’s indicators will be consistent with the programme’s theory of change and the log frame analysis that flows from this – see page 3 and Appendix A. Established sets i.e. WHO health systems strengthening M&E will be used where possible. Results will be disaggregated where possible by sex, age, disability and socio-economic group so that impact on gender, inclusion and income inequality can be established. Expenditure will be reported monthly and impacts (results) quarterly in line with PF reporting rhythms.
As can be seen from the table above outlining the MREL cycle as part of regular quarterly reporting requirements, partners will provide a proportionate and meaningful assessment of how the programme is contributing to reducing gender inequality and supporting women’s economic empowerment including a specific assessment on progress against gender related indicators and commitments.
### Reporting Frequency and Costs
Consistent with PF requirements, the core programme team will instruct delivery partners to develop a quarterly results reporting system and will work with the PF monitoring and reporting contractor to ensure consistency with PF processes and systems – particularly around data frequency, quality and consistency. Programme data capture and base lining will be the responsibility of the core programme team, Posts and delivery partners.
### Annual Reviews
An annual review process will be led by the central programme team with Posts, involving delivery partners and consulting with key stakeholders and beneficiaries as appropriate. The programme would include an annual review conference to bring together programme teams and suppliers to discuss progress, challenges and lessons learned. Health experts and Gender and Social Development Advisers will play a central role, ensuring programmes contribute to gender equality, inclusion and poverty reduction for achievement of the Fund’s Primary purpose, as well as comply with the Gender Equality Act, align with the Fund’s Gender and Inclusion Policy, and apply international good practice. Guidance will be sought from the PF MREL team to ensure alignment with PF level reviews. The results of the annual reviews will be reported to the SRO and the Strategic Programme Board.
## Communications
1. The programme lead will have overall responsibility for setting the programme’s communication strategy, advised by and working with the FCO Programme Support Team Communications Manager, FCO Media Office, JFU, Posts and delivery partners; and ensuring consistency and coherence across the countries in the programme, especially where related work is being carried out. The programme lead will also be responsible for overseeing development and implementation of a communications plan for pan-programme communications.
2. The key objectives of the communications strategy will be to:
  1. Ensure transparency and accountability for the programme
  2. Map stakeholders and ensure all are actively involved in the programme
  3. Positively influence key stakeholder audiences, whether decisions of policy-makers or promoting healthy behaviours in the wider population
  4. Ensure UK organisations are aware of and responsive to opportunities arising from the programme
  5. Create positive narratives and news stories that demonstrate programme successes
3. The communication strategy will contain (and build upon) a specific plan for each component, working with Posts (including local media managers), partner governments and delivery partners.
4. The programme’s main audiences are:
  1. National/regional decision makers
  2. Beneficiary populations in partner countries
  3. UK business and investors
  4. Partner country businesses and investors interested in partnerships with UK companies
  5. Partner country media
  6. HMG departments e.g. DFID and DIT
  7. HMG Posts and the programme team (internal comms)
  8. International development partners

1. The programme does not expect to directly target UK audiences other than where DIT colleagues may follow up with UK businesses using non-ODA funding. However, if there are significant successes resulting from programme activity, the programme will consult with both the appropriate departmental teams (e.g. the FCO Media Office) and the JFU communications team on the potential for informing UK media.
2. Strategic activities will include:
  1. Engagement with relevant national and regional officials in partner countries to raise the profile of programme activities and, where appropriate, advertise the potential of UK companies;
  2. Monitoring for new and emerging opportunities (e.g. key contracts, reforms) and risks
  3. Meetings and presentations with UK companies that could benefit from the programme (linked to DIT work)
  4. Social and mainstream media opportunities (blogs, tweets, editorials) that highlight programme activities and successes to wide audiences

1. The communications strategy will use the Government Communications Service (GCS) OASIS framework.
  1. Objectives – what the communications is intending to achieve
  2. Audience – who are you targeting and what attitudes or behaviors do you want to influence
  3. Strategy – approach, messages, channels and partners
  4. Implementation – delivery plan
  5. Scoring – monitoring, evaluating and feedback loop

All programme outputs will branded with the UK aid logo and recognise UK Government funding.

## Risk Management
1. The central programme management team owns the risk. The risk register has been developed in the following way:
  1. Risk capture – initial process of risk identification
  2. Risk assessment and evaluation – categorisation of risk and assessment of likelihood and impact
  3. Risk treatment and response – development of options and preferred mitigation strategies and actions to avoid the risk, minimise its likelihood of occurring or reduce its impact
2. All risks will be allocated to risk owners to ensure that the risk is continually assessed and mitigation strategies and actions are implemented.
3. Risk tolerances will be agreed by the SPB and feed into the risk assessment.
4. Risks will be reviewed at the SPB and the Programme Management Committee. The discussions will be used to capture new risks and ensure ongoing risks are being appropriately managed. The annual review process will also include an assessment of programme risks.
5. Risks will be escalated via the programme governance structure depending on severity. The central programme management team will develop and own a programme level risk tracker containing all high severity risks. All high severity risks will be reported to the SPB and SRO.

# Financial Case
## Introduction
1. This section demonstrates that the “preferred option” will result in a fundable and affordable programme. It sets out the capital and revenue requirement for the spending proposal over the expected life span of the service.
2. The FCO assigned a £79.3m budget (no VAT applicable) to the programme, made up of Prosperity Fund ODA funding to be spent over 4 years. This includes all implementing activities, such as administrative costs.
3. The programme has also received non-ODA funding, across 18/19 and 19/20 for non-ODA activity to cover the recruitment of two staff attached to and managed by Healthcare UK that will be responsible for ensuring the programme realises secondary benefits. An accompanying non-ODA activity budget will be able to support initiative to showcase the UK offer in the countries covered by the programme.
## Financial expenditure and cost drivers
The Actual Spend (FY 17/18 and FY 18/19) and projected cost profile for this FY and future programme years is set out below:
	17/18*			18/19*		19/20	20/21	21/22	22/23	Total
£m	0.62			1.39		15.6	25.02	29.03	7.61	79.27

*Actual spend in 17/18 and 18/19 includes Transition Funding
The broad rationale for the above spending profile is
- 19/20: delivery partners build relationships, refine / pilot activities, define additional activities, and determines which activities are in practice most feasible
- 20/21-21/22: spending increases as optimum interventions and methods of delivering them become clearer, lessons learned are integrated and implementers see synergies in experiences across pillars and across countries.
- 22/23: the programme aims to complete by the 1st quarter, but the profile builds in an additional quarter in the event of a later launch date or other delay
The following table shows the breakdown of these costs by requirement, including administrative costs. Note that these figures are based on indicative estimates before procurement (i.e. they were produced before the Actual 17/18 and 18/19 spend recorded above):
Cost item	Cost (£m)
Phase 1 Strategic Partner (transition funding)	£0.7m
Phase 1 (and pre-phase 1) staffing July 2017-July 2018	£0.85m
Phase 2 Strategic Advisory Facility	£3.0m
Phase 2 Programme Delivery Partners	£69.9m
Phase 2 HMG programme staff and advisers (London and Singapore hubs plus Posts) from August 2018	£4.82m (of which £3m front line delivery)
TOTAL	£79.27m

The breakdown of phase 2 intervention delivery by pillar is as follows (Note that these figures are based on indicative estimates before procurement):
Pillar	Indicative Costs (£m)
NCD Strategy	£12m
Provider Performance Improvement	£15m
Education and Training	£12.1m
Digital Health	£16m
Life Sciences	£17m
Strategic Partner costs not integrated above	£0.8m
Programme Staff and Advisers	£4.82m* (of which £3m front line delivery)
TOTAL	£77.72m

*MREL activity (collection and analysis of MREL data by posts and PM partner) included at £0.375m per line.

The table below shows the breakdown of phase 2 intervention delivery by country (Note that these figures are based on indicative estimates before procurement):
Country	Indicative Costs (£m)
Brazil	£16m
Mexico	£18.6m
South Africa	£15m
South East Asia	£22.5m
Strategic Partner costs not integrated above	£0.8m
Programme Staff and Advisers	£4.82m* (of which £3m front line delivery)
TOTAL	£77.72m

*As with preceding table
1. Cost estimates are currently being revised in the programme Inception, as the indicative interventions upon which these costs are derived are becoming agreed interventions.
2. The costs of staffing to support front line delivery of the main programme (HMG staff costs) is estimated at £3.0m, which is equivalent to 3.8% of the programme’s overall cost. 2.2% of overall programme costs will be spent on UK-based admin (London-based programme team). We will collaborate with PFDU to actively manage down staffing costs over time. As indicated in the table at paragraph 4, an additional £0.85m will cover HMG staff costs that apply from, and including, July 2017 through phase 1 to, and including, July 2018. This includes £0.25m to cover costs incurred from July to December 2017 and £0.6m to cover costs due from January to July 2018. The £0.7m figure forms part of the Transition Funding. With the additional £0.85m for pre-phase 1 and phase 1 activity included, staffing costs amount to 4.6% of the overall cost on front line delivery staffing and 2.3% on admin. HMG staff costs cover the following activities:
- Business case development
- Procurement
- Central programme leadership and management
- Regional/Post oversight and government-to-government engagement
Payments will be in arrears and based on outputs/deliverables. The schedule of payments will be agreed with delivery partners.
## Financial Assumptions
The key financial assumptions which underpin the programme are:
- All budgets are indicative and subject to further development and refinement prior to procurement. The budgets have been developed based on known information.
- There are no contingent liabilities. All HMG programme staff will either be permanent UK based civil servants (who can be subsequently redeployed) or locally engaged staff on fixed term contracts matching their role on the programme.
- All contracts will be in pounds sterling
## Accountability
The FCO is the Department responsible for spend compliance. The funds were approved by HMT and FCO in accordance with delegated authority transmitted from Cabinet Office/HMT through FCO PUS.
## Impact on the balance sheet
The proposed expenditure does not cover any assets or equipment and will therefore have no impact on the FCO’s balance sheet.
## Overall affordability
1. The proposed cost of the programme is £79.3m over the expected lifespan of the programme. Funding will be ‘programme’ spending (RDEL). All funds are ODA eligible and there are no contingent liabilities associated with this funding.
2. The cost of risk (any contingency or allowance for risk adjustment and optimism bias) shown separately.
3. There will be no ongoing costs to be covered once this programme has finished, as there are no plans to establish structures with future resource implications under programme design.
## Monitoring and reporting
1. Programme spend and forecasts will be monitored by the Programme team using FCO financial systems. Budgets will be entered onto the FCO's systems using Hyperion, the FCO's online forecasting tool, at the start of each financial year. Accurate forecasting will be managed by ensuring payments follow an agreed schedule defined by clear and time-bounded deliverables and fees. Payment schedules will be monitored monthly, reviewed bi-annually and can be adjusted if necessary.
2. The programme team will formally report spend and forecasts to PFDU and the JFU, in line with their financial requirements. An audit trail will be maintained to show all financial decisions taken.
3. All delivery partners will submit an annual self-audit certificate confirming that charges have been correctly calculated, charged, and appropriately accounted for to enable correct taxes to be paid by the Supplier. The FCO has the right to assess compliance and verify the certificate.
4. The programme team will produce a programme level annual report, which will be approved by the programme’s SRO and contain a summary of historic financial information and forward forecasts.
5. The cost of data collection and analysis for MREL purposes is estimated at £750,000 and accounted for as part of the costs of staff and the programme management functions.
## Scaling
The central programme team will recommend any changes to the programme’s portfolio, including scaling up or down, to the Strategic Programme Board and for subsequent approval by the SRO. Any such changes to the portfolio may have financial implications and these will be thoroughly assessed before any decisions are made, with updates to financial forecasts made after any decisions have been taken. Ideas for scaling up activity will be considered at the transitional phase.
## Financial and Fraud risk assessment
FCO assesses financial and fraud risks as low. They will be mitigated through:
- No funds will be transferred to any partner governments, all payments will be made to appointed delivery partners
- Funds will be disbursed directly by HMG to a limited number of delivery partners
- The majority of funds will be dispersed to pre-vetted delivery partners on the PF Framework. Due diligence will be carried out on all delivery partners not commissioned via the PF Framework before any payments are made
- Delivery partners will be obliged to following similar suitably robust procedures to ensure probity of their supply chain
- All payments will be for services received with appropriate milestone type payment points. Funds will be disbursed in arrears
- Each invoice will be supported by a breakdown of the costs being claimed against each budget line in the contract

Appendix A - Theory of Change

APPENDIX A – LOG FRAME
Log Frame	Programme Description	Indicators	Source	Assumptions
Impact	Primary: Reduction in avoidable disability and mortality (overall and premature) due to NCDs; increased access to healthcare, reduced gender and income inequality; improved patient safety/quality of care; new vaccines, treatments; higher rate of GDP growth due to larger, healthier, and more productive female and male workforce; stronger health systems and human capital due to knowledge transfers / Secondary: Increased UK exports in education, digital health, health systems strengthening, pharmaceuticals and medical products; improved local capacity, standards and transparency, ease of business	+Age-standardised mortality rates / +Life expectancy, lower Disability Adjusted Life Years (DALYs) / +National productivity data (e.g. GDP) / +UK exports in absolute and annual growth rates / +UK share of market / +Progress against SDG targets / +% of females under poverty line / +Gender equality Gap (WEF)	+Life expectancy and mortality data (WHO, IHME, national routine reporting) / +Economic data (World Bank, IMF, national reporting) / +Trade statistics (e.g. Comtrade) / +Business/market research
Outcomes	+More women and men with NCDs (and other common conditions) will receive prevention support, timely diagnosis, and ongoing management for their conditions, in the most appropriate digitally-enabled setting, leading to reductions in disability and avoidable mortality / +Improved access to and affordability of services for poor women and men and other marginalised groups / +Female and male healthcare workers have greater skills and tools to reduce avoidable patient safety incidents / +New diagnostics, vaccines and treatments reach patients / +Together, these lead to a healthier female and male workforce with longer life expectancy and reduced caring burden, especially for women, that is more productive	+Prevalence of risk factors (e.g. tobacco use, BMI/obesity, dietary metrics, exercise, poverty, gender) / +Prevalence of NCDs (e.g. hypertension, diabetes, CVD) / +Rates of patient safety incidents / +Successful trials of vaccines, treatment / +Patient satisfaction for men and women / +Access disaggregated by gender, age, income group	+Epidemiological reporting and surveillance (set up with programme) / +Patient safety surveillance (set up with programme) / +National health surveys/routine data / +Beneficiary impact assessment and feedback	+Trained health workers provide cost-effective guidance, diagnosis and care / +Education for quality improvement is effective in changing practices / +A proportion of Life Sciences projects are successful
Outputs	NCD programme: More health workers are trained in non-communicable disease prevention, diagnosis and management / Digital health: More care is delivered using affordable, accessible digital technology and health information is better integrated and used to inform practice / Education and training: More health analysts, health system leaders, and primary and community care workers receive training / Provider performance improvement: More providers (hospitals/clinics) engage in systematic performance improvement, incorporating patient feedback schemes / Life sciences R&D partnerships: More projects progress to clinical development	+Strategies, policies and plans which support inclusive growth, enhancing women’s health, productivity and helping gender equality and poverty reduction / # people trained by role and training type (disaggregated by sex, socio-economic group, age) / # people with access to affordable digitally-enabled health services (sex, age, income disaggregated) / # providers (hospitals/clinics) participating in system-wider performance monitoring / # of life sciences R&D bids	+Formal reporting – to programme’s management office	+Health system environment able to support and integrate digital providers and data integration / +Training is appropriately targeted and tailored / +Sufficient quality and volume of life sciences R&D bids

Appendix B – Indicative Country Outcomes

The delivery plan for each country will be finalised during the inception phase in collaboration between the delivery partners, strategic partner, FCO, partner governments and other country stakeholders. The indicative areas for collaboration based on the work prior to the inception phase are set out in the table below. These align with the Programme’s indicative Theory of Change in Appendix A.

Brazil
Proposed broad areas of technical collaboration: / Assistance on data infrastructure and resource allocation systems; / Support regulating research and embedding evidence into routine practice; / Support strengthening primary care training and performance improvement to ensure early diagnosis and ongoing management of chronic conditions in the community.
Mexico
Proposed areas of technical collaboration: / Review current national strategy for tackling NCDs, childhood obesity school programme, processes and instruments setup for data collection and use for monitoring NCDs and social inequities in health to inform national policy formulation; / Facilitate opportunities for postgraduate training for health system leaders; / Facilitate a primary care knowledge and transformation Forum that interfaces international experts with national players, allows for the formulation of a National Strategy and facilitates the piloting and national scale-up of training of trainers, guidelines, curricula in light of latest international evidence and best practice.
South Africa
The proposed areas for technical collaboration: / Strengthen capability for regulation and improvement, resolution and management of complaints and litigation; / Strengthen capability to tackle the growing burden of NCDs and mental health through systematic approaches to behaviour change and evidence-informed policy; / Strengthen system-wide capability to support workforce planning and transformation; / Strengthen data collection, analysis and management to support policy development and improvement; / Strengthen leadership development and quality improvement capability at the facility level; / Strengthen national and local efforts to engage people and communities in quality/safety improvement and prevention/management of NCDs and mental health.
Myanmar
Proposed areas of technical assistance: / Support development of greater capability to deliver public health policies informed by evidence and population need / Support development of a sustainable, quality healthcare workforce system aligned with population health needs.
Malaysia
Proposed areas of technical collaboration: / Support for community NCD programmes to improve access to screening and diagnostics, targeted at under-served groups. / Support to design a digital e-learning platform and adapt existing education and training resources for the platform to improve access and target under-served professionals. / Joint-working to stimulate digital innovation for improved patient management technology and information resources.
Philippines
Proposed areas of technical collaboration: / Strengthen the development of national policy for the development of Service Delivery Networks (SDNs) and provide technical support to pilot sites in their development and inception / Support development of the Clinical Workforce through e-learning and enhancing provision of existing DOH courses and programmes / Support strengthening of health literacy through population-level programmes focussed on NCDs with rigorous monitoring and evaluation / Work to support implementation of the academic.
Thailand
Proposed areas of technical collaboration: / Collaboration on primary prevention strategies to tackle NCD risk factors; / Advice on strengthening quality standards and provider performance improvement; / Support to introduce a culture of lifelong learning and CPD through training and digital innovation; / Support a cross-ASEAN reciprocal technical collaboration, specifically on HTAs and digital partnerships.
Vietnam
Proposed areas of technical collaboration: / Technical support to transform the medical education system / Guidance on the implementation of data systems, standards and processes to support NCD surveillance, Electronic Medical Records (EMR), Electronic Health Records (EHR), and death registration.