PROSPERITY FUND
GLOBAL TRADE PROGRAMME: ENABLING FUTURE TRADE

Business Case

Version 1.0 (Final)

December 2019

Contents

Executive Summary
This Global Trade Programme (GTP) Full Business Case (FBC) details the rationale, analysis and approach underpinning the investment of £150 million from the UK Government Prosperity Fund between 2017/18 and 2021/2022. The Case was developed in consultation with relevant government departments, the Foreign & Commonwealth Office’s international network, market experts and civil society.
This programme is designed to respond to the direction of the Prosperity Fund Ministerial Board to establish an adaptable and high-impact programme to promote trade and inclusive economic growth in Middle Income Countries (MICs) through increased international trade in line with the Prosperity Fund’s objectives.
Overview of the programme
Enabling free trade is fundamental to global economic development, and is in the interest of all countries. In the last two decades there have been significant increases in global trade driven by reductions in trade barriers and unprecedented linkages between countries through global value chains.
The GTP will provide technical assistance and other direct support to facilitate free trade and open markets for Official Development Assistance (ODA) eligible MICs, enabling greater investment and interaction with global value chains to create jobs and prosperity, thus reducing poverty. The GTP will deliver secondary benefits through increasing market access for international, including UK, business as well as building bilateral partnerships on trade related issues with key emerging markets in support of the UK trade strategy.

A cross-Whitehall, Senior Level GTP Programme Board (GTPB) has been established to govern this programme. The GTPB will keep under review the priority countries / regions for the programme which will include Indonesia, Vietnam (and wider South East Asia), South Africa, China, Brazil, India, Mexico, Nigeria and Turkey. The cross-Whitehall, senior official governance structures are specifically designed to provide the programme with strategic decision-making capabilities to maximise the adaptability of the programme, both geographically and in policy terms.
GTP High Level Objectives
The GTP seeks to maximise the trade potential of the target countries, but also to help generate secondary benefits in the form of increased flow of international trade, including between the UK and these countries.
The two objectives for this programme are:
1. To enable partner countries to identify and remove non- tariff barriers
2. To create the conditions for increased international trade, where possible in support of the UK Government’s trade objectives.
Focus of GTP interventions
The target countries of the programme are MICs with large and emerging economies, which face continued development challenges, such as high levels of poverty and inequality. They have trade negotiation expertise and experience, both regionally and globally. However, the full potential for trade, and therefore its poverty reduction benefits, are not realised. Beyond tariff measures and the ability to negotiate bilaterally, regionally and through the WTO, a key inhibitor to trade remains the broad (both tangible and intangible) issue of non-tariff barriers (NTBs).
Although sizeable progress has been made on the promotion of global free trade in the last thirty years the use of NTBs has increased. Cutting NTBs could unlock more innovation, trade and inclusive growth. The focus of the GTP is to address the main barriers:

- Regulatory
- Standards
- Customs & trade facilitation procedures
- Protection of intellectual property rights (IPR)

These were identified considering evidence of effectiveness of interventions, expertise and capacity/capability of the UK to support reforms, and what the recipient country wants.
Changes in trade can also have a differentiated impact on women and men depending on the gender composition of the labour force as different sectors expand and contract. Gender issues can often be overlooked due to lack of awareness, data and analysis as to why trade distortions are more discriminatory against women, especially poor and excluded women. As such, the £20m Research and Analysis component of the £150m GTP will have a specific focus on women’s economic empowerment and ensuring equitable growth.
Programme Structure
The programme design responds to the demands of the rapidly developing and evolving trade policy area. It combines a technical assistance programme of at least £40m to address NTBs to trade, with a large, flexible, geographical/thematic programme fund of £60m, and policy and programme development capability with a budget of up to £40m. Total programme management costs are estimated to be up to a maximum of £10m. This flexible capability will deploy trade expertise from the private sector and civil society (including academia), alongside existing Her Majesty’s Government (HMG) resources.
The programme is structured to deliver through three routes. We propose to:
- Work with multilaterals (such as the World Bank Group, International Trade Centre (ITC) or Organisation for Economic Cooperation & Development (OECD)) to develop a programme focused on helping GTP priority countries implement the World Trade Organisation (WTO) Trade Facilitation Agreement.
- Work directly with HMG partner departments. This will include contributing directly to Department for International Development’s (DfID) Aid in the national interest work, which operates jointly with Department for International Trade (DIT), to support work such as economic partnership agreement transition in our priority countries; and working with the Intellectual Property Office and The Department for Business, Energy and Industrial Strategy (BEIS) Regulatory Directorate to support their international capacity building projects to address non-tariff barriers to trade.
- Work with a private sector led company, known as Service Manager (SM), with an expert supply chain, including trade consultants, legal, gender, social development and academic expertise – which will develop and oversee a flexible portfolio of trade programmes. This SM approach is an innovative and new approach for the FCO.
Benefits
To assess programme benefits the GTP conducted an economic analysis of spending £40m (£64m[1] with development & design and management costs) on addressing four types of NTBSs in nine priority countries. The central scenario, shown in Table 1.1 and Table 1.2, assumes all £40m would be invested evenly in addressing all four NTBs areas (trade facilitation, intellectual property rights (IPR), regulations, and standards implementation). This scenario has a high benefit-cost ratio for primary benefits; however, the secondary benefits are below break-even point. Table 1.2 shows that the majority of the benefits are realised by the trade facilitation – it has the highest cost benefit ratio of 124:1 for primary benefits and 1.8:1 for secondary benefits.
[1] This equals £60m in present value. Table 1.1 and Table 1.2 give the present value of costs.

Lower levels of available data and comparable programmes in IPR, standards or regulations, means that there is currently insufficient evidence to be sure what benefits are likely to accrue in those areas. As we invest in developing the evidence base, the intention is that funds will be managed and invested in those areas that demonstrate higher benefits. The GTP is currently undertaking analytical work in these areas and if the analysis reveal positive opportunities, the GTP leadership will consider how best to flex the funds across them. Any future proposal will be subject to further business case approval and will be evaluated against GTP assessment framework.
Table 1.1: Summary Value for Money Position of NTBs Programme – “Central Scenario”
£m	Present Value (PV) Costs	PV Primary Benefits: MIC GDP Impact	Primary Benefit-Cost Ratio	PV Secondary Benefits: UK GDP Impact	Secondary Benefit-Cost Ratio
“Central Scenario” : Invest equally in all four NTB areas	60.0	2,032	34 : 1	31	0.5 : 1

Table 1.2: “Central Scenario” – Benefits / Costs by NTB Area
£m	Present Value (PV) Costs	PV Primary Benefits: MIC GDP Impact	PV Primary Benefit-Cost Ratio	PV Secondary Benefits: UK GDP Impact	PV Secondary Benefit-Cost Ratio
Trade Facilitation (Customs)	15.0	1,863	124 : 1	27	1.8 : 1
Intellectual Property Rights	15.0	113	8 : 1	2	0.2 : 1
Regulations	15.0	37	2.5 : 1	1	0.1 : 1
Standards	15.0	10	0.7 : 1	0.3	0.02 : 1

Commercial Approach
Following a rigorous procurement process, the GTP appointed Ernst and Young as the Service Manager to provide advisory, management and delivery services. The GTP has set the following allocations for the services for prioritisation and budgetary purposes. These will not be contractual commitments.
- The total contract envelope is £25,260,809.47. This is separated into two parts:
- Inception Phase, which will be a Fixed Price of £3,544,830.49.
- Delivery costs approximate £21,715,978.98.
- This second figure is subject to the number and size of projects delivered in operation post Inception. Projects will be priced on a case-by-case basis, using daily rates that were competed in this procurement, and form part of this contract. These projects will be subject to FCO approval processes.

Governance
The GTP has four key levels of governance.
1. The Trade Programme Board: cross-Whitehall, Director/SMS level, strategic steering board which meets quarterly to oversee portfolio level risk, performance and policy alignment.
2. The Trade Programme operational Board: cross-Whitehall, D6/7 grades. Provides monthly programme and portfolio oversight.
3. Programme Management Committee: regular working level committee (D6/D7), managing Service Manager and key suppliers and programme risks.
4. GTP Analytical Group to advise and support the GTP to make investment decisions using the best possible evidence. The Group will also review and approve the methodologies and provide views on the merit of research and analysis proposals.
All spending decisions are subject to FCO departmental rules, legal schedules and defined processes and governance over and above the programme structures.
Beyond the spending decisions within the SM model, the governance bodies will review spend continuously and the portfolio balance and focus. The GTPB and Operational Boards will be able across the programme lifecycle to identify additional priorities, delivery routes, and opportunities.
RISKS

Political risks – The success of the programme will depend upon strong political will (to overcome vested interests), capacity to implement, sufficient resources and widespread ownership and buy in. The GTP programme could also suffer negatively from political change and instability in its priority countries. In addition, due to political change or geopolitical turbulence, protectionism may develop in GTP priority countries. We would mitigate these risks by early and ongoing engagement with local stakeholders to maintain buy-in. Additionally, leveraging international organisations such as the G7, G20, OECD, World Bank and like-minded partners will help to promote free and open markets and the countering of protectionist sentiment.

There are also risks to value for money. The majority of interventions have not yet been designed and so, although the economic analysis in the FBC indicates significant potential returns on investment, this cannot be guaranteed at this stage. To mitigate this risk, each programme within the GTP will be subject to rigorous analysis before being submitted through the appropriate GTP programme and FCO departmental approvals processes.

Strategic case
2.1 The Strategic Context
Organisational overview
The Global Trade Programme (GTP) is in response to the steer of the 2016 Prosperity Fund Ministerial Board to establish an adaptable and high-impact programme to promote international trade and inclusive economic growth in line with the Prosperity Fund’s objectives. The primary purpose of the Prosperity Fund is to support the inclusive economic growth needed to reduce poverty in partner countries. Through this primary purpose, the Fund’s activities will contribute to the UN Sustainable Development Goals. These reforms are expected to create secondary benefits for international businesses, including UK companies. The Fund has a budget of £1.2 billion between 2016 and 2023 to provide expertise and technical assistance to partner countries to improve the business climate, reduce barriers to trade, investment and economic growth and support necessary reforms for poverty reduction. .
The GTP is cross-Whitehall in design. DIT, DFID, BEIS and FCO sit on all levels of programme governance. All departments with a policy interest will be able to work with the programme to support trade interventions. A dedicated programme and contract management team will manage the programme. The resources for GTP have been allocated to the Economic Diplomacy Directorate within the FCO, which will be managed through a cross-Whitehall Strategic Board representing all relevant Government Departments.
Prosperity Fund
The Prosperity Fund forms a small but strategic proportion of the UK’s total ODA commitment of 0.7% of Gross National Income. It represents a step-change in the ODA resources spent on assisting MICs to grow and develop, which will help to make the world a more prosperous place. The Fund is accountable the National Security Council (NSC). Spending departments are accountable for impact (growth and poverty reduction), value for money for the UK taxpayer, and for ensuring that spending meets ODA eligibility requirements and the legal requirements of the International Development Act and the International Development (Gender Equality) Act 2014.
The Prosperity Fund is adopting a portfolio approach to build/support a range of constituent programmes and projects within a matrix of priority sectors/countries. This portfolio focuses primarily on Middle Income Countries (MICs) that remain ODA eligible and face significant development challenges, but where there are significant opportunities for driving future global prosperity. The countries have been identified through a methodology based on a number of factors, including poverty reduction potential, Gross Domestic Product, import market size and business opportunities. The fund focuses primarily on the following areas within the MICs:
1. High growth sectors where UK has a comparative advantage, such as, financial and business services, infrastructure, healthcare, education, ICT, smart cities;
2. Areas where UK’s investment would have a strong impact in order to drive sustainable economic growth, such as, trade, anti-corruption, business environment, energy.
The multi-year GTP seeks to boost economic growth and combat poverty through supporting effective and efficient global trade, consistent with the requirements of the International Development Act 2014. Many of the UN Sustainable Development Goals directly reference trade and the potential to harness trade for development. These are moreover well aligned with the Prosperity Fund and GTP objectives of promoting inclusive growth and development through trade.
Wider HMG strategies
This programme will help to meet one of the four strategic objectives of the UK Aid strategy 2015[2], which is to use ODA to promote economic development and prosperity in the developing world. This will contribute to the reduction of poverty and strengthen UK trade and investment opportunities around the world. Furthermore, this will also help to achieve the UK National Security’s strategic objective of promoting the UK’s prosperity by championing global economic reform and strengthening UK’s relationships with emerging economies[3].
[2] https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/478834/ODA_strategy_final_web_0905.pdf
[3] National Security Objective 3
This programme also aligns with the UK’s long-term vision of becoming a free-trading nation. The Government’s Trade White Paper (“Preparing for our future UK trade policy”), launched on 9 October 2017, and was an important first step in identifying key elements of that policy. The White Paper set out the initial principles and approach that will guide the development of the UK’s future trade policy. In summary it will:
- Pursue prosperity for the UK, including through free trade
- Develop, support and enhance a fair and proportionate rules-based global system for trade
- Develop a trading framework which supports foreign and domestic policy, sustainability, environmental and development goals
- Develop a trade agenda that is inclusive and transparent.
The paper reflects the vital importance of trade to the UK economy (equivalent to over half of our GDP) in driving job creation, raising productivity, and helping share knowledge and innovation. The ability of UK firms to grow exports into existing markets and gain access to new markets is a key contributor to our future growth prospects.
The Trade White Paper specifically recognises the importance of trade in supporting developing countries to reduce poverty:
‘The UK Government has a long-standing commitment to support developing countries to reduce poverty through trade. The government will continue to deliver improved support in the future by helping those developing countries break down the barriers to trade. This will help them to continue to benefit from trade by growing their economies, increasing incomes and reducing poverty. Helping to build developing countries’ prosperity creates the conditions that allow commerce to flourish and in doing so, opens up opportunities for UK business in future markets’
The proposed Global Trade Programme, in vision, design and delivery, is an important vehicle in actively supporting all these principles.
2.2 Case for Change
What is the problem?
In recent years, MICs have witnessed rapid economic development; however, many still face high levels of poverty. The distribution of global poverty has shifted from low-income countries towards MICs (OECD, 2013)[4]. The countries where many of the poor live have experienced drastically rising average incomes, while poverty has not fallen in absolute numbers. Today, MICs are home to more than 59% of the world's poor[5] (those living on less than US $1.90 a day). Poverty is pervasive in some MICs, while in others the problem is one of major concentrations of poverty in specific areas. Many MICs face challenges such as urbanisation, climate change and high and persistent inequality (including gender inequality) which can lower their long-term growth and poverty reduction prospects.
[4] Development Co-operation Report 2013 – Ending Poverty, OECD.
[5] World Poverty Clock (https://worldpoverty.io/)
MICs represent about one-third of global GDP and some countries have made great strides in policy reform to address barriers to growth, but many lag considerably behind and even among the advanced reformers, the unfinished policy agenda is substantial. The countries' institutional capacity to manage reform varies greatly. For example, many MICs still have limited access to international capital markets, a poor record of regulatory reforms and insufficient adoption of international standards to carry out business activities. Trade is a particularly challenging policy area to reform because of its differentiated impacts on local populations and businesses. Changes in trade can have a differentiated impact on women and men depending on the gender composition of the labour force as different sectors expand and contract.
With their growing role and integration in the global economy, there is a strong case for continued engagement with MICs to assist them in addressing these challenges for national and global long-term benefit. Trade openness can bring huge benefits and when accompanied by appropriate domestic policies, trade openness facilitates competition, investment and increases in productivity, jobs and incomes. Better regulations can enable improved social and development outcomes. For example, minimum and enforceable labour standards can improve workers’ work conditions and rights, while addressing gender discrimination, forced and child labour.
Although MICs are increasingly able to finance their own development, the challenges are significant because these countries often lack the technical skills and expertise that are required to undertake reforms. Since the UK has a comparative advantage in trade sectors, such as regulatory reform and intellectual property, the UK is well placed to support partner countries to address these constraints and boost more inclusive economic growth in order to reduce poverty.
Promoting growth and prosperity in these countries through trade could also deliver secondary benefits to international business, including UK businesses. For example, the UK benefits not only from accessing overseas markets via exports and investment, but also from imports, as companies are able to access cheaper and improved quality production inputs. As we leave the European Union, the Prosperity Fund is a vital part of how the UK will be a global, outward-looking nation that is confident on the world stage and has strong, fruitful relationships with countries around the world.

Investment objective
The GTP aims to support priority countries’ efforts to identify and remove Non-Tariff Barriers (NTBs) to trade in order to reduce poverty. The United Nations Conference on Trade and Development (UNCTAD) defines NTBs as “policy measures other than ordinary customs tariffs that can potentially have an economic effect on international trade in goods, changing quantities traded, or prices or both.” NTBs are similar to tariffs (with the exception of export subsidies and quotas) and their removal has the potential to improve competitiveness, reduce trade costs, and improve access to new markets. The removal of NTBs can play a positive role in creating an enabling environment for trade, inclusive growth, and poverty reduction. Removing NTBs can help maintain environment, health and food safety standards for citizens in MICs and developing countries, and ensure that there is a level playing field to reflect international norms and rules.
Sizeable progress has been made on the promotion of global free trade in the last thirty years yet the use of NTBs has increased[6]. The ranges and complexity of NTBs makes it hard to offer an exact measure of how intensely they affect trade. According to some measures, by the OECD and the World Economic Forum, these barriers are higher in MICs, constraining trade and growth. According to the World Trade Organisation (WTO), the main barriers are regulatory, standards, customs procedures and intellectual property. NTBs remain present in many MICs for various reasons, such as vested interests/political economy challenges or protectionist domestic policy priorities (such as import substitution policies). Even if NTBs are in place for good reasons, their implementation and compliance may be complex and bureaucratic, which increases the scope for bribery and corruption. If these barriers are overcome, MICs will be able to trade more internationally. As Wacziarg and Welch (2008) found, trade policy liberalisation raises average trade to GDP ratios by roughly 5 percentage points. Trade is also recognised as an important driver for economic development[7]. By enabling priority countries to identify and remove NTBs to trade (a in Figure 2.1), the GTP is expected to create the conditions for increased international trade in support of priority country and UK trade objectives (b). As a result, the GTP aims to reduce poverty in priority countries through three channels:
[6] UNCTAD’s 2013 study showed that the use of non-tariff measures, particularly technical measures, has increased globally based on a constructed “frequency index” of non-tariff measures
[7] DFID (2014), “Economic development for shared prosperity and poverty reduction: a strategic framework”

- Primarily from more inclusive economic growth (c), which raises incomes and reduces poverty (d)
- Directly (e) as it provides opportunities for increased national wealth and hence poverty reduction and economic empowerment of women, poor people and excluded groups. For instance, by improving poor men and women’s access to a range of goods and services, which tends to reduce prices in the long-term, this offers more choice of affordable products and enables local businesses and male and female entrepreneurs more access to international markets with more consumers to buy their goods and/or services;
- Also indirectly, (f) as a side effect of removing non-tariff barriers, for example, due to improved regulations and standards that are more pro-poor and progressive.

Finally, by increasing trade and investment growth, the GTP is expected to benefit the UK through more exports, inward investment and higher investment returns (g). An evidende review of the theory of change (figure 2.1) is presented below.
Removing obstacles to trade means targeting non-tariff barriers (b in Figure 2.1). Non-tariff barriers (NTBs) are now more important than tariffs in affecting trade. Average applied tariffs have fallen from 22% in 1986 to 8% in 2010, but NTBs are becoming increasingly influential in trade. The ranges and complexity of NTBs makes it hard to offer an exact measure of how intensely they affect trade. According to some measures, by the OECD and the World Economic Forum, these barriers are higher in MICs, constraining trade and growth. According to the World Trade Organisation (WTO), the main barriers are regulatory, standards, customs procedures and intellectual property. If overcome, MICs will be able to trade more. As Wacziarg and Welch (2008) found, trade policy liberalisation raises average trade to GDP ratios by roughly 5 percentage points.
Removing the main trade barriers will increase trade and investment growth (c). Most academic and institutional evidence[8] suggests that trade and openness to trade play an important role in a country’s overall development, particularly MICs. Trade enables countries to diversify their exports and access cheaper production inputs, thus improving productivity and competitiveness. Trade enables countries to diversify their exports and access cheaper production inputs, thus improving productivity and competitiveness. This enables them to achieve economic growth and enable poverty alleviation.
[8] See, for example, Anderson, K. (2014); Winters, McCulloch & McKay (2004); Wacziarg and Welch (2008); Estevadeordal and Taylor (2009)
Many economists have consistently argued that sustained economic growth reduces poverty (d).[9] As DfID’s Economic Development strategy notes: “Economic growth is essential for overcoming poverty and for allowing human potential to flourish. No country can prosper without it. As the Growth Commission puts it, growth ‘can spare people en-masse from poverty and drudgery. Nothing else ever has’[10].” However, the complexities around attributability and long-term monitoring of impact mean growth’s poverty reducing effect has not always been reliably quantified, although research suggests that for periods of approximately 7 years or more, economic growth is by far the largest determinant of a country’s success in reducing poverty[11]. While both low and middle-income countries have made substantial progress in growth and dismantling trade barriers over the past two decades, they have been less successful in using trade to create jobs, increase per capita incomes and diversify their economies. Poor households and communities in lagging regions continue to be confronted with major development challenges. Such heterogeneity of outcomes is the main underlying reason why there is no consensus in the literature about the quantitative impact of trade liberation on economic growth (d) and therein poverty reduction (e).
[9] https://www.oecd.org/derec/unitedkingdom/40700982.pdf; https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/67584/BAR-MAR-summary-document-web.pdf
[10] As quoted in DFID Economic Development Strategy: The Growth Report: Strategies for Sustained Growth and Inclusive Development, Commission on Growth and Development, World Bank, 2008, p.1.
[11] Dollar, D., Kleineberg, T., and Kraay, A. 2016. or Kraay A. 2006.
Empirical studies are not unanimous that increased trade directly leads to poverty reduction, but there is broad consensus that there can be no complacency with trade openness (e). Trade reform and liberalisation has not always delivered the expected benefits in terms of trade expansion, wage growth and poverty reduction. If unchecked the benefits of trade risk being captured by a minority, increasing inequality[12], undermining the goal of the Global Trade Programme. While country characteristics are critical (e.g. the type and value-added of exports, labour market, etc.) in determining how an economy reacts as trade opens[13], social and economic policies are needed to ensure the benefits of trade are genuinely inclusive. Governments have a central role in ensuring there is a fair distribution of benefits and in doing so, mitigate and manage the downside risks of opening trade. Therefore, despite inclusive trade openness, sustained, poverty reduction cannot happen without the appropriate macroeconomic and investment policies.[14]
[12] World Bank (2005); UNDP (2005); Kremer and Maskin (2007).
[13] Turner, Nguyen and Bird (2008); De Melo, Gourdon and Maystre (2006)
[14] Newfarmer and Sztajerowska (2012)
Despite the difference of opinion and uncertainty about the direction of causality, there is a sound evidence economic growth is accompanied by increased trade, which generally leads to welfare gains (OECD, 2009) (c, d, and e). On balance the evidence suggests that international openness to trade can create welfare gains (or poverty reduction), subject to effective complementary government policies. Historical evidence suggests that countries that have liberalised their trade regimes grow several times faster than those that have not.[15],[16] For example:
[15] E.g., Wacziarg and Welch (2008) find that countries that liberalised their trade regimes grew around 2% (or three times according to World Bank, 2009) faster, than those that did not liberalise.
[16] Feyrer (2009) finds that trade growth explains around 17% of the variation in cross-country income growth after controlling for a range of factors including time.
- The IMF found a one-percentage point increase in trade openness raises real per capita incomes by 2-5%.[17]
  [17] Cerdeiro, D. and Komaromi, A. (2017) “The effect of trade on income and inequality: a cross-sectional approach”.
- A joint report by the OECD, ILO, World Bank, and the WTO highlighted evidence that per capita income grew more than three times faster (5% per year) for those developing countries that lowered trade barriers than for other developing countries (1.4% per year) in the 1990’s[18].
  [18] OECD, ILO, World Bank, WTO, 2010. Seizing the Benefits of Trade for Employment and Growth. WTO, 11-12 November 2010.
- OECD trade facilitation Indicators (2013) suggest that reducing global trade costs by 1% would increase worldwide income by more than USD 40 billion, 65% would go to developing countries[19].
  [19] https://eudevdays.eu/sites/default/files/OECD_Trade_Facilitation_Indicators_updated-flyer_May_2013.pdf
- An article from 2014 reviewed key recent literature on the effects of trade liberalisation on poverty in developing countries and concluded that the literature of the past decade reinforces the presumption that trade liberalisation generally raises average incomes and thus reduces poverty[20]. The article also found that women might gain relatively more from trade liberalisation, for example, if trade liberalisation favours female-intensive sectors or if women have a comparative advantage in less physically intensive and more highly skilled activities (trade liberalisation stimulates more productive firms and higher-quality products). If harnessed effectively, trade cannot only play a key role in successful development, it can also promote economic inclusion, poverty reduction and deliver welfare gains to poor communities – all aims of the Global Trade Programme.
  [20] Winters and Martuscelli (2014)

Figure 2.1: Illustrative diagram of the Theory of Change[21]
[21] A full Theory of Change is given in the Economic Case.
Intervention / Policy/ regulatory change / Trade / investment growth / Inclusive economic growth / Secondary benefits for trading partners, including the UK / Poverty reduction / a / b / c / g / f / d / e

The role of the Global Trade Programme

The £150m GTP is designed to support MICs in building trade-related capacity. To reap the full poverty-reducing benefits of trade, MICs require twofold support: to remove trade barriers, such as identifying priority areas and/or overcoming vested interests, and help in implementing policies that facilitate a macroeconomic environment primed for increased international trade that is inclusive and poverty reducing. Therefore, a key component for the GTP in supporting inclusive growth and poverty reduction will be world-class evidence and data on MIC markets and lessons learned, to inform the dynamic challenges of achieving its aim of supporting poverty reduction through greater trade openness.
The GTP, under the direction of Ministers, is designed to be flexible and adaptive to evolving trade policy and opportunities. The GTP’s priority countries include the largest MICs in the world and both lower and upper MICs. The priority countries are Brazil, China, India, Indonesia, Mexico, Nigeria, Turkey, South Africa, and Vietnam. These countries account for a significant share of global economic activity: together they account for 26% of global GDP and 20% of global trade flows.[22]
[22] Based on IMF and World Bank data.
This business case makes clear however, that the flexibility of the programme should extend to ensuring funding is available to other Prosperity Fund priority countries where a need is identified and a case made. These are initial priorities, to enable the programme to focus immediately on areas identified as highest need and benefit. Provision is made in the Advisory budgets, and within the governance structures, to support work in other (Prosperity Fund agreed priority) countries.
As the UK’s trading relationship with GTP priority countries will evolve rapidly over the lifetime of the programme, it is important that the GTP take an approach that is both flexible and adaptive if it is to maximise impact and value for money.
The GTP seeks to maximise the trade potential of the target countries, but also to help generate secondary benefits by creating opportunities for international business, including for the UK in the form of increased flow of trade between the UK and these countries. Therefore, the two objectives for this programme are:
1. To enable partner countries to identify and remove non-tariff barriers;
2. To create the conditions for increased international trade in support of Government trade objectives.
All interventions under the GTP will be assessed against the following (this is further discussed in the economic case):
- Strategic fit: how does it meet the needs and priorities of the partner country and the steer from the ministerial board?
- Outcome: how the programme supports the inclusive economic growth of priority countries and how it creates opportunities for international business, including UK businesses.
- Impact: how the programme supports poverty reduction?
- Value for money (and the four Es: economy, efficiency, effectiveness & equity).
In delivering these objectives, the programme will need to retain sufficient flexibility to respond to evolving political priorities, both in partner countries and in the UK. In doing so the programme will need a delivery model that reflects existing HMG resources and expertise available to manage a programme at this scale including the management, monitoring and evaluation capacity to ensure coherence within a wide portfolio of interventions (including utilising the latest evidence). Since the programme is funded for five years, it will also need to deliver at pace in addition to retaining flexibility.
2.3 Focus of GTP interventions
The target countries of the programme are MICs with large and emerging economies. They have trade negotiation expertise and experience, both regionally and globally. However, the full potential for trade, and therefore its poverty reduction benefits, are not realised. Beyond tariff measures and the ability to negotiate bilaterally, regionally and through the WTO, a key inhibitor to trade remains the broad, both tangible and intangible, issue of NTBs.
Numerous countries and international organisations have spent considerable resources in funding activities to reduce NTBs. For example, the international Aid in the national interest agenda has prioritised reducing NTBs, including by part funding the implementation of the WTO Trade Facilitation agreement. Between 2007 and 2015, an average of approximately $175m per year of ODA funding is spent on AfT classified as support to “Trade Policy and Regulation” in MICs.” During the same period, GTP priority countries received US$610 million in total in AfT funding. The money was spent on programmes such as improving trade policy in Nigeria, providing technical assistance to Mexico, European trade policy and investment support projects in Vietnam, or encouraging open trade, investment and development in China, etc.
Given their political economic nature, NTBs are often challenging to eliminate in MICs and developing countries, but also impose costs defused across consumers and producers. NTBs often restrict imports, benefiting domestic producers at the expense of foreign ones, potentially at the cost of price and quality for consumers. Surveys of business trading across borders also show the negative impacts of NTBs. An ITC business survey in Indonesia (2013)[23] showed that the main impact of NTB’s on foreign firms were time delays (65%), corruption (64%), inconsistent behaviour of officials (56%) and complex customer clearance mechanisms (45%). These cost companies’ time and resources, with small and medium-sized enterprises hardest hit, as they lack the financial and human resources needed in confront such obstacles[24].
[23] ITC, 2013 n=951 companies surveyed: http://ntmsurvey.intracen.org/ntm-survey-data/country-analysis/indonesia/#/tabNonTariffMeasures
[24] WTO Annual Report https://www.wto.org/english/res_e/booksp_e/wtr16-4_e.pdf
Cutting NTBs could unlock more innovation, trade and inclusive growth. Several estimates by international organisations suggest that trade facilitation support could be highly cost effective in relation to overall benefits. However, this has not been proven in evaluations due to data limitations. For example, World Bank estimated a rate of return of $71 per dollar invested in trade facilitation from an associated increase in exports from aid recipients[25].
[25] Helble, Mann and Wilson, (2012).
PF programme synergies
For aid-funded trade programmes to be successful, the challenge is to identify and remove or improve barriers that distort competition, have high transaction costs, or do not reflect international norms. The evidence on the effectiveness of different types of AfT suggest that trade policy and regulation are one of the most effective types (OECD, 2012, 2015). DFID also finds that the most effective interventions to increase trade volumes and reduce costs are:
1. Infrastructure improvements
2. Reforms to improve customs efficiency
3. Reforms to improve the regulatory and business environment.
The first point is addressed by the Prosperity Fund Infrastructure Programme while the second and third which include NTBs would be addressed by the GTP.
2.4 Achieving GTP objectives
To achieve GTP objectives, at least £100m will be spent to deliver interventions; £20m will be spent on research and analysis; £20m on access & enabling funds and £10m on management costs and administration. Table 2.1 provides a breakdown of the £150m that will be invested as part of the trade programme.
Table 2.1 – Breakdown of GTP spend
Flexible funds* - Through IPO, BEIS and other HMG) and World Bank Trade facilitation Partnership (proposed)	EPA Transition Programme	Research & Analysis	Access and enabling fund	Management costs (FCO and Delivery)
£72m	£28m	£20m	£20m	£10m

* A minimum on £40m will be spent directly addressing NTBs to trade as proposed in the initial 2016 concept note.
a) Research and Analysis (£20m) – A maximum of £20m will be used for conducting trade related research & analysis. The GTP will be evidence led. In order to support a high impact adaptive programme, evidence will need to be detailed, relevant and up to date. Building a detailed understanding of the barriers to trade in partner countries and evidence of what works to address these barriers and promote trade that is more inclusive will allow us to develop high quality interventions. This research and evidence will also be a public good, allowing us to underpin collaboration with partner country governments and other development partners. Analytical outputs will also be crucial to affecting change in partner countries, through providing governments with the evidence they need to make informed policy decisions and to highlight areas for further action. Research and analysis will also ensure transparency and accountability to civil society.
As such, the first activities to be carried out by the GTP during inception will be detailed country-specific analytical work to understand the socio-economic and political barriers to increasing free trade, building on available evidence. Where there are gaps in evidence, the research and analysis work will further explore distributional impacts of trade – including on poverty reduction, gender equality and women’s economic empowerment. In addition to being a valuable resource for partner country governments and underpinning the design of GTP interventions, the research and analysis function will have clear benefit to the UK. Although focused on the needs of the partner country, the analysis will provide HMG with significant country-specific detail that could be utilised as the basis for planning any future bilateral trading relationships.
The areas or topics that will be covered under research and analysis will help the GTP to build an evidence base for investing in MICs. This will not only help the GTP and the UK Government to understand the wider trade opportunities that are available in the MICs, but it will also help to understand the key challenges and opportunities in relation to poverty reduction, gender equality and wider inclusion and their links to goods or services that are traded or their supply chain. This will help to understand how UK interventions could make an impact in partner countries for more inclusive growth. The GTP has developed an analytical strategy that sets the direction of building this evidence base. The strategy allows the GTP to, but not limited to:
Carry out detailed socio-economic baseline studies and impact analyses to enable us to understand the current reality and track changes;
- Commence deep sectoral studies to understand industry sectors where the greatest poverty reduction potential lies, and where UK interests are best represented;
- Carry out inclusive growth and poverty reduction diagnostics;
- Work with HMG partners to identify the research and analysis areas that will make the most impact on trade decision making;
- Conduct future programme scoping and evidence gathering for future trade programme activity;
- Provide support to a partner country in building its own economic/sectoral study in support of developing more open trade policies;
- Provide grants for research on a competitive basis to civil society (academia/ universities/think tanks) through call-in tenders.
A Cross-Governmental GTP Analytical Group (with members from FCO, DfID, DIT, HMT, BEIS) has been set up to oversee the delivery of the research & analysis carried out under the GTP analytical strategy. The purpose of the group is to:
- Advise and support the GTP to make investment decisions using the best possible evidence;
- Review and approve the methodologies of high value, complex and high risk projects;
- Provide views on the merit of research and analysis proposals that will be completed / commissioned using the research & analysis budget;
- Propose research ideas and identify collaborative opportunities;
- Sharing the outcomes and results of the research & analysis and feasibility studies across Whitehall to increase trade capability.
The GTP Analytical Group will be part of the GTP governance structure.
b) Flexible Fund (£72m) – The core approach of the GTP is to address barriers to trade and develop partner MIC and HMG trade expertise, while remaining responsive to the UK’s evolving trade policy and emerging Ministerial priorities. The need to respond to opportunities with speed, agility and expertise is an essential policy tool as the UK builds on capability, strengthens relationships, and delivers technical interventions based on evidence and analysis. Ministers were clear in their direction that the Global Trade Programme must be able to deploy this expertise flexibly across the spending period. This means a significant proportion of this Fund’s budget will be allocated in developing longer-term UK government trade policy capability and developing an evidence base for trade programme interventions. This capability will ensure GTP is an adaptive programme, deploying world-leading expertise from private, public, academic and wider civil society sectors alongside UK government officials, to deliver large, flexible, high impact trade enabling programmes. A minimum of £40m of the flexible fund will be spent directly addressing NTBs to trade. The programme will focus on NTBs in which UK has significant comparative advantage and will be delivered through HMG partners such as Intellectual Property Office and Department for Business, Energy and Industrial Strategy, and by establishing partnerships with multi-lateral organisations. The four priority areas are:
1. Bolstering good regulatory practice
2. Trade facilitation and streamlining customs procedures at seaports
3. Supporting and encouraging adoption of international standards
4. Promoting effective protection of Intellectual Property Rights (IPR)
These barriers have also been consistently identified by UK businesses as barriers to trade and investment, and will be tested for impact on target country economies (see the Economic Case).
c)	Economic Partnership Agreement (EPA) transition programme (£28m) – delivered by DFID and FCO
- The EU and country/regional specific EPAs currently govern trading arrangements between the UK and EPA partners. The UK’s departure from the EU has necessitated that we rollover all EU EPAs to which the UK is party, to UK only arrangements. HMG policy is to ‘rollover’ those arrangements to minimise any disruption to trade when the UK leaves Europe. For example, trading arrangements between the UK and Southern Africa Customs Union plus Mozambique (SACUM) are currently governed by the EU- SADC[26] EPA. The HMG and SACUM policy is to continue with those arrangements in a similar form to the current EPA, on the day after the UK leaves the EU.
  [26] Southern African Development Community
- The GTP is working with DfID Trade for Development colleagues to support this rollover process for EPA partner countries [27] to implement and benefit from the trade for development focus of the EPAs. Up to £20 million will be invested in African, Caribbean, Pacific countries and regional groupings; whereas, around £8 million will be invested in SACUM (which could be increased) for technical assistance and capacity building announced by the UK Prime Minister during the Africa visit in August 2018. The FCO will lead on the SACUM EPA, with DfID Trade for Development colleagues leading on the remaining agreements. In rolling-over these trade agreements, the UK will take on the numerous, specific commitments related to development support that are contained within them. In some instances, these commitments include the creation of trade facilitation programmes to support their implementation.
  [27] Programme beneficiaries: Namibia, South Africa, Eswatini, Botswana, Lesotho, Mozambique, Antigua and Barbuda, Bahamas, Barbados, Belize, The Commonwealth of Dominica, Grenada, Guyana, Jamaica, Federation of St Kitts and Nevis, St Lucia, St Vincent and the Grenadines, Suriname, Madagascar, Mauritius, Seychelles, Zimbabwe, Comoros, Fiji, Papua New Guinea, Cote D’Ivoire, Ghana and Cameroon. Non-ODA eligible countries will not receive national level support
- By working alongside the Trade for Development team on the rollover of the EPA agreements and transition, the GTP will combine established expertise and experience to support poorer trading partners through these agreements and deliver on mutual DFID and Prosperity Fund objectives. Moreover, development assistance to support the implementation of existing arrangements will be received positively by the EU, and would mean that increased trade would continue under any UK arrangement that followed.
d) Access & enabling services (£20m) - The programme also makes provision for Access and Enabling services to turn theoretical concepts and analysis into fully practical and designed projects. This will allow new business cases to be developed for these projects, and fund relevant resources at Post or in the UK to ensure design, preparation and delivery is timely. These resources could also be accessed on behalf of FCO London, posts, HMG partners or Ministers for rapid response to emerging priorities that, for instance, could urgently needed to support inclusive economic growth in priority countries.
2.5 Constraints, dependencies and legal requirements
The programme budget is all Official Development Assistance (ODA) and so is governed by the UK International Development Act (IDA) and the Gender Equality Act (2014). All spending will conform with these Acts, and to the rules set for ODA by the OECD. All spending will need to meet the ODA/ IDA and GEA criteria as set out by the DAC/OECD and the UK.
The programme will operate within the context of uncertainly regarding the UK’s future trading relationships until the negotiations for the UK’s exit from the European Union are complete. This will be considered in all programming, and the programme Strategic Board will provide a strategic cross-government perspective.
The programme will operate along-side related Prosperity Fund and other UK-government funded programmes. The Programme Management Policy Team will work closely with related programmes (especially in business climate reform and anti-corruption) to ensure design and delivery is joined-up across government.
2.6 Gender Equality Act Compliance and Women’s Economic Empowerment
This programme takes into account analysis and key measures to ensure compliance with the International Development (Gender Equality) Act (2014). Gender equality and promotion of women’s economic empowerment is an essential part of Middle Income and developing countries fully realising their potential for more inclusive trade and economic growth. This is highlighted in the WTO’s Joint Declaration on Trade and Women’s Economic Empowerment (2017)[28], which aims to increase women’s participation in trade.
[28] WTO, Joint Declaration on Trade and Women’s Economic Empowerment, WTO Ministerial Conference in Buenos Aires, December 2017,
Women are heavily involved in trade - as cross-border and informal traders, producers of traded goods and services, workers in supply chains, entrepreneurs, and as managers and owners of SMEs and exporting firms. However, women have been shown to face specific barriers to trade such as lack of access and control over economic inputs and assets, lack of transparency in trade related regulations and procedures, difficulties in obtaining documents, and constraints in access to trade information and trader networks. Women face more obstacles when participating in cross-border trade, including poor conditions and risk of harassment.
Changes in trade can also have differentiated impacts on women and men depending on the gender composition of the labour force as different sectors expand and contract. For GTP, it is therefore important to know which trade sectors may be female labour intensive, the quality and quantity of jobs created or threatened, and the potential impact on working conditions, earnings and labour market segmentation. It is also important to know how changes in trade may impact household consumption patterns, through price or product quality changes, particularly for food and household items that may directly affect female consumers disproportionately, given their roles as primary household managers and carers.
Gender issues can often be overlooked by policymakers due to lack of awareness, data and analysis as to why trade distortions are more discriminatory against women, especially poor women from different excluded groups. As such, the GTP’s Research and Analysis component will have a specific focus on gender equality and women’s economic empowerment for inclusive growth. This will help to provide the evidence base for ensuring interventions maximise opportunities and benefits for women and girls; to make the economic case for equitable growth in partner countries; and contribute to the global evidence base for understanding gender and trade linkages, including what works.
The GTP will ensure that all interventions and economic analytical work consider and address gender equality and women’s economic empowerment, including identifying risks and mitigating actions where changes in trade policy may have the potential for negative impacts. Evidence will need to be provided that a broad range of stakeholders including civil society, women and excluded groups have been involved in project design. The Programme’s assessment and prioritisation framework for interventions under the flexible component will systematically include poverty, social and gender impact assessments to understand differentiated impacts on women and men and the gender relations between them. Through engagement with the World Bank Group, GTP will use international standard indicators and methodologies for assessing gender and distributional impacts. This will help to ensure legal requirements of the UK Gender Equality Act (2014) are met, that no harm is done and inequality is not worsened. It will also ensure that the GTP takes a proactive approach to harnessing opportunities and benefits for women’s economic empowerment through design and delivery of programme interventions.
The Programme will ensure that monitoring data is disaggregated by sex, age and socio-economic group where possible in order to track and evaluate poverty, inclusive growth, gender equality and women’s economic empowerment outputs and outcomes. It will also look to align its results framework with the World Bank Group Trade and Competitiveness Gender Results Framework (2017) as far as possible to promote good practice.
2.7 Key Risks
Risk and assumptions will be closely monitored and addressed if they materialise in order to ensure that GTP outputs and outcomes translate into the desired impacts. The key risks to the programme are:
- Lack of political will / commitment – The success of the programme will depend upon strong political will (e.g. to overcome vested interests), capacity to implement (e.g. identifying potential negative short-term side effects), sufficient resources (to implement effectively and mitigate negative effects) and widespread ownership and buy in (to ensure sustainable support to doing things differently). This risk would be mitigated through early and ongoing engagement with UK overseas network of posts, local stakeholders and government institutions to maintain buy-in. We have also assessed the benefits of the programme by testing assumptions around successful delivery by conducting an exploratory analysis on removing non- tariff barriers in MICs. This is discussed in the economic case.
- Risk of Political Change – the GTP programme could suffer negatively from political change and instability in its priority countries. There are associated risks such as delays (rebuilding relationships in reorganised foreign ministries/waiting periods for change to be implemented), setbacks (changing priorities of the partner governments) and policy/project cancellations (loss of political will). Whilst political change can lead to many additional risks being realised (some more serious than others), awareness and mitigation planning for the most common eventualities will be imperative to the success of the programme. Mitigation strategies include proactively maintaining a close relationship with our overseas network of posts, to ensure we can react to early analysis and foresight. The GTP team and posts will need to be agile and agree a joined-up strategy to ensure the programme remains on track.
- Risk of Protectionism – There is a risk that due to political change or geopolitical turbulence, protectionism may develop in GTP priority countries. This might lead to a strengthening of international trade barriers and reduction in political will, directly counteracting the programmes objectives. Appropriate mitigation will be to ensure a close relationship with post and foreign ministries, promoting free trade agreements and utilising GTP funds to reduce non-tariff barriers to trade. Additionally, leveraging international organisations such as the G7, G20, OECD, World Bank and like-minded partners can help to promote free and open markets and the countering of protectionist sentiment.
- Lack of complementary and gender-sensitive policies – An integrated approach across all potential policy areas (transport infrastructure, education, health, governance, labour market and social policy) is needed to achieve impact. While addressing complementary policies directly is beyond the scope of the GTP, HMG would seek to communicate (e.g. through diplomatic channels) potential collaboration opportunities to stakeholders, including throughout the Prosperity Fund. In addition, without complementary gender- sensitive policies, the GTP risks lacking impact on poverty reduction and non-compliance with the Gender Equality Act, either not supporting inclusive growth or addressing gender equality and women’s economic empowerment. Mitigation measures will include ensuring suppliers have the relevant gender and poverty expertise and accountability mechanisms are sufficient to avoid being gender-blind in compliance and delivery.
- Lack of sustained support – Benefits of tackling obstacles to trade often do not materialise in the short-term and therefore require sustained support to ensure successful change and impact. Sustained progress beyond project completion is necessary. Sustained support can be facilitated both by financial and institutional sustainability. USAID indicates that its trade projects are most likely to be sustainable when future funding sources are clear[29]. Training of staff, ensuring buy-in from stakeholders and the private sector also further improves sustainability. We have tested this assumption as part of the exploratory analysis and provided results for different scenarios. This is discussed in the economic case.
  [29] USAID (2012)
- Lack of coordination/duplication of effort with other agencies / UK government departments – Most of the NTB intervention areas already receive support in MICs by the UK, in particular customs, and in DfID priority countries. All major international donors are involved in running regional and country programmes. To mitigate the risk of duplication, including with international donors, the GTP will co-ordinate its activities with local stakeholders, international donors such as World Bank and other UK Government Departments to seize opportunities of synergies across programmes. Ensuring coordination will also be managed through the participation of DfID and other relevant government departments on the cross-government Global Trade Programme Board and, where relevant, cross-government partnerships in specific projects.
- Lack of clear and strategically articulated problem definition – Interventions need to be clearly defined and scoped out, and tailored to the countries’ individual needs and binding constraints. The different intervention areas highlight that multiple country factors are important for achieving success, which may change over time. It is therefore crucial to strategically articulate the objectives of each intervention and possible in-country restrictions, and continuously ensure that the objectives remain relevant and appropriate. We would learn from previous experience from the work carried out by other relevant local and international implementing partners (government and non-governmental), UK government departments, especially DfID (where relevant), and local knowledge from the network of posts.

Economic case
3.1 Introduction
An economic case within the business case is intended to demonstrate value for money (VfM) to show that public spending is achieving maximum impact. However, it is challenging to carry out an economic analysis of trade reform programmes because they are generally complex, not least due to the political environment of a country but also due to the involvement of other bilateral and multilateral trade related programmes which play a crucial role in the success of trade reforms. Due to these contributing factors, it is difficult to attribute the success of a trade reform programme to a particular intervention. As discussed in the strategic case, a number of studies have looked at the relationship between trade reforms and economic growth and poverty but there is very limited evidence on how much a country needs to spend to carry out a particular reform and what would be the impact of that spend. Due to data limitations, evaluation studies are rare and this poses additional challenge on carrying out a cost benefit analysis of trade reform programmes.
Despite these challenges, this GTP economic case has carried out a cost benefits analysis of removing NTBs in MICs. This economic case outlines GTP theory of change and provides economic assessment of investing in removing NTBs before discussing the results of the cost benefits analysis.
3.2 Theory of change
Figure 3.1 below provides a high-level theory of change for the GTP investment of £150m. This shows how the GTP will lead to a range of outputs, outcomes and the resulting impact. If planned outputs[30] are delivered as a result of GTP projects and interventions, then priority countries will have better business climates, experience fewer domestic barriers to trade, and take a more strategic and integrated approach to interacting with the global economy. If these intermediate outcomes are achieved, then priority countries will experience more sustainable inclusive growth (e.g. through more employment and lower prices), which will achieve our impact aims – reducing poverty –, but also, as an indirect result, trading partners (including the UK) will experience higher exports and returns on investment to priority countries.
[30] More international standards, better protection of Intellectual Property Rights, improved and more coherent regulatory practice, streamlined customs procedures, less corruption at seaports, more public/political commitment to and understanding of opportunities from trade openness and more capacity to negotiate trade deals
There are a number of assumptions that need to hold for the GTP to achieve its impact. Critical success factors include sufficient political will; domestic capacity/resources to implement changes; identification and resources to address transitional costs and/or mitigate against negative side effects from implementation and widespread ownership /buy-in for the long-term benefits of changes. There are some risks as well, for example, there are ambiguous impacts of protecting Intellectual Property Rights (IPR) on MICs welfare. This is because protecting IPR could end up establishing a monopoly position for foreign company exports into MICs and reducing local production and employment if not replaced with the Foreign Direct Investment. These risks and assumptions will be tracked and monitored, particularly where there are underlying concerns about political will, vested interests, and weak capacity or limited domestic finances necessary to sustain implementation. If the conditions are not in place, or benefits are not forthcoming as expected, then the GTP board will need to consider ending the projects utilising contract break clauses.
Figure 3.1 Theory of Change

Better protection for Intellectual Property Rights
Improved adoption of international standards.
Outcomes
Impact
More inclusive economic growth, due to factors such as higher employment and lower prices that reaches to poor.
Poverty reduction in priority countries
At output and outcome level, we expect approaches to actively support inclusive growth; gender equality and women’s economic empowerment; that no harm is done; that inequality is not worsened and that the approach is Gender equality Act and IDA compliant in line with World Bank Group policies and practice on gender. The assessment framework in the later section shows that the value for money assessment will include an analysis of the equity.
Higher UK GDP growth, due to improved export revenues, returns to capital and lower cost imports
Economic growth in the UK
Intermediate outcomes
Better adherence to international standards and rules creates a better business climate.
Barriers to trade reduced leads to more trade.
Government policies promotes a more strategic integration with the global economy.
Increased openness to international trade promotes sustainable growth paths.
Economic growth and trade openness increase export opportunities for UK businesses
Adherence to international standards and rule increases returns on UK investment and reduces risks
Trade openness lowers the cost of UK imports
Outputs
Streamlined customs procedures at seaports.
Improved regulatory practice.
Increased public and political commitment to trade openness
Enhanced trade negotiation capacity
Greater understanding of the opportunities and potential for trade and interaction with global value chains.
Non-tariff barriers
Targeted programmes of technical assistance on:
- Better regulation
- Reduced corruption and improved customs
- Protection of Intellectual Property
- Promotion of UK and international standards
Trade facilitation
Demand-driven technical assistance and other services delivered by an adaptable Trade Policy Facility targeted at creating the conditions for increased international trade, including supporting market access and new free trade agreements.
£150 million
Inputs
Assumptions:
- Political willingness to overcome challenges of implementation, e.g. vested interests, and managing potential transition costs.
- Complimentary domestic gender-sensitive resources and policies: Sufficient domestic resources available and appropriate gender-sensitive domestic policies are implemented.
- Capacity: No unbridgeable technical capacity gaps that would lessen the impact of GTP.
- Sustained support: Long-term, broad-based support for managing potential short-term costs and risks.
- GTP projects are implemented in coordination and integrated with other actors and stakeholders.
- Trade barriers remain, clearly identifiable and realistically overcome throughout the programme’s lifetime.
- Priority countries have political willingness to tackle vested interest.
- Identify and mitigate risks
- UK firms know of and can access new trade and investment opportunities
- UK trade agreements maintain access to foreign markets
If the context and conditions are appropriate, outputs should contribute to reduced cost of inputs for businesses, improved competitiveness, higher levels of innovation, a more conducive open environment for trade and investment, and greater opportunities for priority countries to expand regional trade and integrate more effectively in global value chains. These improvements have the potential for transformational change in MICs trade performance, benefiting trade partners, including the UK, through higher trade, foreign investment, product innovation, technology transfer and more dynamic, inclusive trade and growth. These outputs also have the potential to improve availability of products and lower prices, contributing to poverty reduction. As the programme progresses, the theory of change will be further developed and refined to understand the linkages, between outputs, outcomes and impact that could be attributable to GTP.
3.3 Economic assessment
Trade openness plays an important role in poverty reduction. Overall, the weight of evidence suggests that trade liberalisation is broadly poverty reducing, although ultimately, the effects depend on country-specific conditions and the beneficial impact is not guaranteed for everybody. Therefore, while the primary objective of the programme is reducing poverty in priority countries by removing non-tariff barriers to trade and implementing other trade programmes that encourage trade openness, this needs to be done in a way that mitigates and manages the potential negative side-effects from trade openness.
A variety of metrics were considered for use in the GTP from the most generic Gross Domestic Product (GDP) to more comprehensive measures (wealth framework) – see Box 1 for more detail. However, the most comprehensive measures of wealth were found not to be practical due to data limitations. As part of the GTP analytical strategy, we are further investigating possible metrics as we refine the Theory of Change. Meanwhile, this economic case uses a change in GDP to measure the potential benefits of the GTP in MIC aggregate incomes (outcome in the theory of change). As a result, the direct impact of GTP on poverty levels is not measured at this stage (d and e in Figure 2.1). As discussed in the strategic case, the GTP analytical strategy has outlined our approach to further analysis to assess GTP’s impact on poverty.
A key mechanism for poverty reduction is through growth. Economic growth has been the main driver of poverty reduction, particularly since 1990 . Cross-country analysis finds strong evidence that rapid and sustained growth is the single most important way to reduce poverty. GDP growth is used in this business case to measure the potential benefits because it offers the most comprehensive coverage for comparability in measuring changes in economies and economic growth. GDP measures the total sum of the final output that an economy produces and therefore, equivalently, measures the income that, as a nation, is earned from production. However, it has limitations; critically GDP is an aggregate measure without reference to the men and women that produce the output or benefit from the income.

Box 1: Measuring Poverty
The World Bank defines poverty in absolute terms. It defines extreme poverty as people living on less than US$1.90 per day. A few countries, however, have chosen to measure their poverty using a relative threshold, that is, a cut-off point in relation to the overall distribution of income or consumption in a country . This view sees poverty largely in monetary terms. However, the concept of poverty is a complex issue because the factors that determines poverty are multidimensional such as political, economic and social. These multidimensional nature of poverty needs to be understood in order to create more effective programme of poverty reduction.
The multidimensional nature of poverty could be understood by assessing well-being because poverty is regarded as pronounced deprivation in well-being (World Bank, 2000). Economic growth is widely used to measure well-being because it is considered a powerful tool to reduce poverty. Over the last 50 years, economic growth has largely been based on information flowing from the System of National Accounts (SNA) framework. A full articulation of the SNA includes many measures of economic activities, one of which is Gross Domestic Product (GDP).
An increase in GDP has led to job creation and improved well-being for many people. While economic growth has produced many benefits – raising standards of living and improving quality of life across the world – GDP has long known weaknesses as a measure of economic welfare or well-being. For example, GDP is defined without reference to the number of people in the population that produce the output it covers and benefit from the income generated. If GDP increases but the population producing it rises by the same percentage, there would be no reason to suppose the well-being of individuals would have increased.
In recent years, there has been substantial discussion about the best way to measure well-being. The Commission on the Measurement of Economic Performance and Social Progress Report (Stiglitz et al. 2009) identified the key dimensions of well-being to include health, education, social connection, political voice, unpaid household work, and present and future condition of the environment. The Commission notes that “all these dimensions shape people’s well-being and yet many of them are missed by conventional income measures.” This could be because GDP only measures activity within ‘the market’; however, much of what maintains and enhances well-being occurs outside of the market. Therefore, the Commission argued that applying a broader definition of wealth, to include natural capital, social capital and human capital, could provide a better understanding of well-being. Several institutions have incorporated these concepts in their conceptual frameworks (OECD, 2013).
Pioneering studies such as those by Kenneth Arrow and others (2012) , and the World Bank (2006, 2009) have provided a framework that provides a single indicator to measure wealth and the changes in wealth over time. There are some limitations in the comprehensive wealth framework, for example, it does not currently include factors such as cultural capital, which is an important factor to determine well-being. However, despite its limitation, Stiglitz, Sen and Fitoussi (2009) recommended comprehensive wealth as one useful indicator of well-being or poverty.
A number of counties have started refining and developing wealth or wealth per capita framework but this is still in the early stages. Using the wealth framework will be challenging because of data limitation; however, as part of the GTP analytical strategy, we will further investigate this framework as we refine the theory of change for the programme. Meanwhile, we will use a change in GDP to measure a change in poverty. GDP currently has the highest profile in regard to changes in the economy and the measurement of economic progress. In its own terms, this prominence is fully warranted. GDP measures the sum total of the final output that the economy produces. Equivalently, it measures the income that, as a nation, we earn from that production. Similarly, it measures what is available to spend – either to consume or to invest in capital for the future.

Trade feeds into growth through a number of channels, for example:
- Trade allows the country to use its resources more efficiently through specialisation;
- Better access to cheap imports provides reduced prices for consumers and prices of intermediate goods and services for producers;
- Better access to external markets increases opportunities to achieve economies of scale beyond the limited domestic market;
- New employment opportunities are created in expanding export sectors;
- In the long run, trade increases productivity through increased competition, access to technology and more advanced inputs and incentives to innovate.
Trade can be a key driver of inclusive growth as it can trigger structural changes in a country’s economy. Increased specialisation, competition, innovation and transfer of technology can lead to new employment opportunities, higher incomes and better livelihoods for the world’s poor. Since 1990, increased integration into global trade has reduced the number of men and women in extreme poverty by around one billion[31]. Since then, openness to trade has had a strong positive correlation with faster growth[32] and higher real incomes of the poorest quintile of the population.[33] In the long-run, growth in countries with more trade openness tends to outperform those less open to trade[34]. In the second half of the 20th century, countries that liberalized their trade (raising trade to GDP ratios by an average of 5%) enjoyed an average 1.5% boost to their rate of growth[35]. In the 1990s, per capita income grew more than three times faster in developing countries that lowered their trade barriers.[36] In the last 15 years, the evidence of trade impact on economic growth is stronger. For example, a number of studies (such as Dollar & Kraay, 2004; Chang, Kaltani, & Loayza, 2009; and Freund & Bolaky, 2008) point to positive relationship between trade openness and long-run economic growth. Overall, this suggests trade openness is good for growth and, as outlined above, growth is good for poverty reduction. This has led some (e.g. Winters, McCulloch and McKay, 2004) to suggest that trade policy and openness could be one of the most cost-effective anti-poverty policies available. Many pro-poor policies and programmes can be administratively complex and expensive to implement, in contrast important trade reforms (e.g. tariff reductions and abolishing non-tariff barriers) are often easy to implement and save resources.
[31] WTO/ WBG (2015), ‘The role of trade in ending poverty’, p. 7.
[32] For example, Wacziarg and Welch’s (2008) analysis of 141 liberalisation episodes concluded that, after controlling for other determinants of growth, per capita growth was some 1.5% higher than before liberalisation, and investment rates were 1.5-2.0% higher. Estevadeordal and Taylor (2009) found strong evidence that liberalising tariffs on imported capital and intermediate goods raised growth rates by about one percentage point annually in the liberalising countries, although changes to tariffs on consumption goods were only weakly correlated with growth outcomes.
[33] IMF, World Bank & WTO (2017) ‘Making Trade an Engine of Growth for All: The Case for Trade and for Policies to Facilitate Adjustment’
[34] See Keho (2017) for a comprehensive literature review.
[35] Anderson, K. (2014) ‘Benefits and Costs of the Trade Targets for the Post-2015 Development Agenda’ Copenhagen Consensus.
[36] OECD, ILO, World Bank, 2010. Seizing the Benefits of Trade for Employment and Growth. WTO, 11-12 November 2010.
If supported by appropriate macroeconomic and investment policies, there is substantial evidence that countries open to trade tend to experience faster growth.[37] The poverty reducing effect of trade openness, either directly or indirectly via growth has been widely debated as the impact of trade on the poor depends on the characteristics and policy response of the country in question. Recent literature suggests that liberalisation can have mixed effects on the poor, at least in the short term, depending on what trade policies are liberalised, how a household earns its living and what adjustment policies are in place to support any transition.[38] Context matters in determining the effect of trade openness on growth and poverty reduction, depending on for instance which sectors are most affected, if they are jobs-rich and the kinds of jobs. Furthermore, the wider public reaction will depend on how men and women interact with affected sectors, whether as consumers, producers and/or employees. The policy framework and response may also negate any potential opportunities opened by more trade openness. Opportunities for the poor may be constrained by a variety of issues, such as labour market rules, rural poverty, insecurity, informality and discrimination[39]. Thus, to effectively reduce poverty in MICs, there can be no room for complacency in removing trade barriers.
[37] Newfarmer and Sztajerowska (2012), “Policy and Priorities for International Trade and Jobs”.
[38] For example, non-competitive producers are being pushed out of business in the sugar and banana sectors as preferences are eroded. Adjustment packages to help these producers increase competitiveness or diversify into other sectors can help. For a more general discussion of the impacts of trade on poverty, see Winters, A. and Martuscelli, A. (2014), “Trade Liberalization and Poverty: What Have We Learned in a Decade?”, Annual Review of Resource Economics.
[39] World Bank & WTO (2015) ‘The Role of Trade in Ending Poverty’
To ensure the benefits of trade liberalisation are inclusive, country context and policy response need to be taken into account. Historically, trade liberalisation has been associated with increased inequality in countries well-endowed with highly skilled workers and capital or with workers that have very low education levels (Turner, Nguyen and Bird, 2008). While inequality decreased in countries that liberalised trade that were well endowed with primary-educated labour (Turner, Nguyen and Bird, 2008), and in low-income countries relatively well endowed in capital (De Melo, Gourdon and Maystre, 2006). However, there are many factors that can increase or decrease inequality, but OECD (2009) found that while trade may reduce inequality, it may not always be the overriding factor. A 2007 IMF study found trade openness reduced income equality in MICs (among others) over the past two decades and concluded that income inequality in-country had risen in most cases due to technological progress (increasing wages of the skilled relative to the wages of the unskilled). In other words, although poverty elasticity of growth can vary significantly between countries and over time, there is no evidence-based support that liberalised trade in of itself has an adverse impact on the poor (OECD 2009). Thus, the GTP will need to garner support for complimentary policies to ensure the opportunities created from this programme are not lost or misused.
Women face particular barriers that need to be considered in their involvement in trade, over and above barriers to wage and employment equality. There is limited literature on the potential effects on trade if these gendered constraints are removed. Greater equality in employment and education generally lead to a more productive workforce, which, in turn, increases expected rates of return on investment, and therefore generates a modest increase in investment. However, wage inequality between women and men may increase competitiveness in labour-intensive export industries, such as garments, in the short term by pushing wage demand down.[40] The question of the impact of trade on women’s lives has been more thoroughly examined, with both positive and negative outcomes identified in many studies. Trade liberalisation is generally linked with increases in women’s share of paid employment, although not with changes in the distribution of women and men in different sectors in the short term. For instance, in agriculture export-oriented jobs tend to go to men, with women concentrated in subsistence farming.[41]
[40] The Royal Institute of International Affairs,(2010), Evidence for Action https://www.chathamhouse.org/sites/files/chathamhouse/public/Research/Energy,%20Environment%20and%20Development/0910gender.pdf
[41] European Parliament's Committee on International Trade (2015), http://www.europarl.europa.eu/RegData/etudes/IDAN/2015/549058/EXPO_IDA(2015)549058_EN.pdf
Trade interventions in the Global Trade Programme must therefore take country context and gender issues explicitly into account and monitor impacts of reforms to ensure a positive contribution to inclusive growth. As discussed in the strategic case, the GTP will ensure that all interventions and all economic analytical work addresses gender equality and women’s economic empowerment, including identifying mitigating actions where changes in trade policy may create risks of negative impacts. The Programme’s assessment framework for intervention under the flexible component will systematically include poverty, social and gender impact assessment. The assessment framework is given in the next section. In addition, given the above evidence suggesting drivers for inequality and obstacle to trade vary, the assessment framework will consider other factors holding back growth in a country. For instance, trade openness is more effective at generating growth if a country has good infrastructure, good governance and is less corrupt. To ensure maximum impact, it will be important to work closely in the design and delivery of projects with the priority countries in tackling these issues, but also where relevant with other development partners, HMG departments and/or Prosperity Fund programmes.
Ultimately, there is sound evidence that economic growth is accompanied (and facilitated) by increasing imports and exports, particularly if country context is taken account of, e.g. inequalities (gender & marginalised groups), job-rich sectors, urban/rural divide, etc. There is a strong presumption that openness to trade generally leads to welfare gains.[42] However, appropriate complimentary policies are essential to manage the risks of liberalising trade, but also to fully capitalise on the opportunities of integrating the global economy. If this is achieved, trade has the potential for transformative change in MICs. A 2009 OECD literature review found open economies are richer and more productive than closed ones, and that the most robust studies found an increase in the share of trade in GDP of one percentage point raised the income level by between 0.9% and 3%. (Nordas et al., 2006). Although there are other quantitative examples that found lower estimates when controlling for institutional quality (0.5%; Feyrer, 2009).
[42] Rodriguez and Rodrik, 1999; Winters, 2004
Case for removing Non-Tariff Barriers
GTP will deliver at least £40m of projects that support removing NTBs and creating favourable conditions in MICs for increasing international trade. The programme will focus on NTBs in which UK has significant comparative advantage – particularly within partner HMG departments such as BEIS and HMRC – and therefore well-placed to advise. These barriers have also been consistently identified by UK businesses as barriers to trade and investment, and tested for impact on target country economies. This section provides the case for removing the four NTBs that are focused by the GTP in partner MICs.
Regulation
Regulations are rules and instruments used by public authorities to influence the behaviour of (public and private) actors. Good regulatory policy overcomes “market failures” and “government failures” to optimise the allocation of resources and maximise the welfare of society.[43],[44] Clear, consistent, and appropriate regulation is vital to productivity and growth. OECD analysis suggests regulatory reforms could boost GDP in G20 countries by 1-1.5%, with MICs benefitting the most given their more restrictive regulatory barriers.
[43] Governments use regulations to correct perceived market failures and improve market efficiency (Veljanovski, 2010).
[44] Market failures include externalities, missing or incomplete markets, information asymmetries and under-provision of public goods.
UK exporters identify regulations as one of the top barriers to exporting. In 2015, 27% of UK service exporters surveyed found that regulatory environment and differences in standards are one of the main barriers to export.[45] As a large services exporter, the UK would benefit from services regulatory reform in MICs therefore could boost UK trade. For example, opening up emerging markets through better regulations offers real opportunities for key UK sectors, e.g. large utilities such as energy, and service sectors including finance, insurance, legal and business services.
[45] British Chambers of Commerce (2015) “2015 International trade survey”.
Our scoping study[46] highlights the large variation in regulatory performance across the priority MICs. In general higher MICs perform better on various measures of regulatory quality while lower MICs (such as Nigeria) perform worse overall. The study shows that there are a number of regulatory challenges identified in the priority countries, including complex and inconsistent regulations (Indonesia and South Africa), market access barriers faced by foreign firms (legal, financial and professional services in Indonesia, telecommunications and finance in Turkey) and price controls. The GTP activities in this area will build on the expertise and analysis of the Regulatory Delivery Directorate and the Better Regulation Executive in BEIS.
[46] The scoping study was completed by PwC.
Customs and Trade Facilitation
Customs in a narrow sense relates to the official department administering and collecting duties for imported goods. In a wider sense, customs-related procedures can involve trade facilitation to move goods across borders. Inefficient and corrupt customs procedures are a major non-tariff barrier to trade and a significant source of expense and uncertainty for exporters and importers in developing countries.
While the literature suggests that improvements in customs procedures in priority countries play a more important role for their exports than imports, it nevertheless demonstrates that customs improvements can deliver greater export opportunities for UK business to these countries. A further benefit to the UK can stem from increased participation of MICs in global value chains, insofar as this does not crowd out UK expertise. Companies benefit from faster deliveries of inputs supplied from MICs, which can have a knock-on effect on UK productivity and competitiveness. Overall, the UK economy also benefits from cheaper imports.
Our scoping study identifies that most of the priority countries of the GTP have already made some headway in improving trade facilitation. For example, seven of them have already implemented more than 70% of general trade facilitation measures as measured by the World Trade Organisation (WTO). However, there is more room for improvement. Indonesia, Vietnam, the Philippines, Nigeria, and Brazil struggle with inefficient or opaque customs procedures and requirements, as well as issues with corruption at border posts. For example, Indonesia sits on the ease of trading across borders index at 108th out of 190 countries, Brazil ranks at 149th and Nigeria at 181th. In Vietnam 66% of companies report bribery being common in customs procedures. For the Philippines, the 2016 WEF Global Enabling Trade report highlights burdensome import procedures to be one of the most problematic factors for importing, as well as corruption at the border.
The success of interventions in part depends on the quality of physical infrastructure, which is still lacking in some countries such as Brazil and Nigeria. Successful interventions could reduce the costs of trade and boost scores such as country performance on the Doing Business Trading across Borders index or the World Bank’s LPI. The UK is a global leader in customs and border efficiency, and following the WTO’s Trade Facilitation Agreement, the GTP will support the necessary capacity building to ensure quick and full implementation. Moreover, the UK is a global leader in customs and border efficiency and the Department for International Development currently support TFA implementation to low income countries.
3. Standards and Quality Infrastructure
Standards often represent a quasi-regulatory means of promoting an important public policy objective, such as environmental protection, consumer safety, food quality, or compatibility between different technical norms and standards. National Quality Infrastructure (NQI) is the institutional framework that establishes and implements standardisation, including conformity assessment services, metrology, and accreditation.
Divergent standards and poor ‘Quality Infrastructure’ (testing and measurement, certification and accreditation) can significantly hinder growth. Adoption of internationally recognised standards enables MICs to participate in global value chains – with which 70% of global trade is now associated. A 1% increase in the number of shared standards increases bilateral trade volume by 0.3%, while poor standards regimes costs developing countries between 0.3 – 0.9% of GDP Growth[47].
[47] British Standards Institution
Improving alignment of standards in priority sectors could generate secondary benefits for the UK through trade and investment opportunities. The British Chambers of Commerce (2012) found that around 20-30% of UK companies view challenges in the regulatory environment and differences in standards to be the key barriers to exports to the BRIC countries.[48] The UK is well positioned to support reform in this area given its strong range of UK expertise and best practice that can be drawn on.
[48] BRIC refers to Brazil, Russia, India and China.
There is scope for the GTP to address gaps in standards alignment and NQI deficiencies in priority countries. For example, standards was noted to be a key factor constraining trade for South Africa, particularly relating to veterinary and agricultural/food products. In Nigeria, agricultural products frequently fall short of international standards and there needs to be a broader awareness of the need for international standards. The British Standards Institute (BSI) also conducted a comprehensive scoping study for interventions “to support the development and adoption of standards and quality infrastructure in targeted ODA-eligible countries”. It identified opportunities in the GTP priority countries such as Mexico, Indonesia and India. In addition to this, the BSI report found that most GTP priority countries should be included in a standards and NQI improvement programme.
The GTP activities will build on international work by the British Standards Institution and UK QI (National Measurement and Regulation Office, UK Accreditation Service, The National Physical Laboratory).
4. Intellectual Property
Intellectual Property (IP) can be protected by IP rights; patents, trademarks, designs and copyright, which bestow monopoly use or licensing rights to the owner, allowing them to benefit from their creation. They incentivise innovation by giving creators confidence that they will secure a return on the time and money they have invested.
The World Intellectual Property Office (WIPO) notes the significance of IP protection for innovation and growth. MICs tend to have weaker intellectual property protection, combined with lower innovation and investment in R&D. The UK’s Intellectual Property Office (IPO) stresses the importance of addressing such shortcomings as a major factor in long-term economic growth for middle-income countries. Effective IP environments can support increased productivity, reduce opportunity for crime, drive investment and trade, and support participation in global value chains.
Our scoping study demonstrates that upper MICs tend to have stronger IP scores, whereas lower MICs still have relatively weak IPRs. Their country profile analysis identified that over half of the GTP priority countries have medium or high needs and opportunities in the IPR intervention space. IPR should be a high priority in China, Vietnam and India. Some of the common challenges these countries face include IP infringements such as counterfeiting of physical and virtual products, trademark squatting, poor enforcement and lack of judicial awareness and experience in IP issues. Countries like those that China, South Africa and Brazil tend to score well on technical and innovative skill are likely to benefit from implementing more sophisticated IPR protection systems.[49] The UK has world-class expertise in IP reforms. The GTP, in partnership with UK IPO, can offer these expertise and promote IP reforms with the appropriate level of IP protection in partner countries, which will drive long-term growth through incentivising innovation and inviting technology transfer through imports, licensing and FDI.
[49] European Commission (2015), USTR (2017).
Improving the intellectual property rights regimes in MICs reduces costs for UK firms in the long term and increases their ability to export and invest overseas. The IPO’s strategy for 2015-2020 aims to ensure UK businesses are more confident in operating internationally as a result of better IP protection globally. The strategy specifically aims to promote strong IP regimes in key overseas markets to reduce risks for UK exporters. The importance of FDI for exporters is corroborated by academic evidence confirming that firms are more likely to export to countries with higher IP scores. Interventions in this area will therefore specifically support the government goals of reaching exports of £1 trillion by 2020.
Challenges for removing NTBs
To maximise the potential gains to the target countries from removing NTBs, the programme will need to overcome inertia from partner governments and opposition from vested interests. These could include:
- Change management: reluctance by country governments and the businesses benefitting from them to change policies and practice, preferring business as usual. We will address this challenge by building relationships with key stakeholders in partner countries.
- One-sided approach: Unilateral dismantling of NTBs by one country may be perceived as surrendering a potentially valuable bargaining chip for wider trade negotiations, even if the programme is focused on harmonisation with international standards. Therefore, the programme will work closely with the wider UK trade strategy to ensure potential synergies are realised.
- Winners and losers: the benefits from more open trade will not necessarily be distributed evenly among men and women or over time, interventions will need to be managed carefully to ensure legitimate concerns about the spread of winners and losers can be anticipated and addressed. This will be fully assessed and planned via scoping studies and business cases at the next stage of the programme.
These challenges have influenced the shape of this Programme as a multi-year, multi-country approach, which can learn from a range of experiences and tackle NTBs in a range of contexts. The geographical focus of activities will be on the priority countries, although where these countries form part of relevant regional trade bodies the programme will retain the flexibility to work at the level most appropriate to delivering results (for instance, supporting reform within a regional trade block as a whole, where this is the most effective route for achieving impact in a priority country). Interventions will also be designed with regard to other relevant UK Government initiatives (for instance DFID aid-for-trade programmes) to ensure synergies are realised and duplication is avoided.
3.4 Economic appraisal / Value for Money of the Non-Tariff Barrier Programme
A. Methodology
An overview of the analytical method used to estimate the costs, primary benefits and secondary benefits of the NTB programme of the GTP is set out in Figure 3.2. This illustrates the calculation steps used to estimate the programme benefits (on the right) based upon the programme investment (on the left). As discussed in section 3.3 above, this analysis calculates the benefits of GTP in terms of potential increase in GDP across the NTB programme countries. As a result, the direct impact of GTP on poverty levels is not measured at this stage (d and e in Figure 2.1). The GTP analytical strategy has outlined our approach to further analysis to assess GTP’s impact on poverty.
On the left hand side of Figure 3.2 are boxes representing the GTP investment in the four NTB areas; trade facilitation, intellectual property rights (IPR), regulation and standards; £16m each in each area, including £6m of development & design cost and management fee. The analysis assumes that the investment of £64m in NTBs will be made in those countries where that NTB is a “high priority”. This has been based on an assessment of NTB reform needs and opportunities in each of the target countries.
Figure 3.2 – Overview of Cost-Benefit Analysis Method for GTP Non-Tariff Barrier Component

2D. Coefficients for impact of change in # Companies Meeting ISO9001 on Trade Flows from Prakash (2009)
2C. Coefficients for impact of change in WGI/RQ on Trade Flows from de Groot et al (2004)
2B. Coefficients for impact of change in G&P on Imports from Fink and Braga (1999)
2A. Coefficients for impact of changes in TFIs on trade flows from Moise and Sorescu (2013)
1A. Use Moise (2013) with OECD Trade Facilitation Policy Simulator
Change in Trade Facilitation Indicators
Trade Facilitation (Customs) Spend: £16.0m
1B . Assume 1 Year of historical improvement in G&P Index
Change in Ginarte & Park Index
IPR Spend: £16.0m
1C. Assume 1 Year of historical improvement in WGI – Regulatory Quality
Change in World Governance Indicator - Regulatory Quality
Regulation Spend: £16.0m
1D. Assume 1 Year of historical improvement in # Companies Meeting ISO9001

Change in # Companies Meeting ISO9000
Standards Spend: £16.0m
3S. Use UK shares of MIC trade flows
5S. Apply impact, sustainability, success and attribution rates to each year of appraisal period to estimate benefits in each year. Discount to 2018/19 @ 3.5%
4 S. Coefficients for impact of changes in trade flows on GDP from Feyrer (2009)
4P. Apply impact, sustainability, success and attribution rates to each year of appraisal period to estimate benefits in each year. Discount to 2018/19 @ 10%
3P. Coefficients for impact of changes in trade flows on GDP from Feyrer (2009)
Change in MIC Total Annual Trade Flows
Change in MIC Annual GDP
Change in UK Total Annual Trade Flows
Change in UK Annual GDP
SECONDARY BENEFITS
PRIMARY BENEFITS
6. Programme costs profile over 2018/19 – 2020/21. Discount to 2018/19 @ 3.5%.
Total GTP NTB Spend: £64m*
COSTS
The NTB reform needs assessment was based on:
1. A review of business and investment surveys from UK Trade & Investment (UKTI) and other similar UK trade and business organisations on the key non-tariff barriers to trade;
2. Reports by the United States Trade Representative (USTR), European Commission and others on their assessment of the key barriers to trade for each of the priority countries of interest;
3. Discussions with FCO overseas posts on the key priority areas that have been highlighted by UK businesses, including their ranking of how important each four NTB was in impeding trade;
4. Assessment of various quantitative indicators that capture each country's performance on each NTB area.
The NTB reform opportunities assessment was based on a review of:
1. The extent of existing political commitment and strategic alignment to address certain NTB areas. For example, where there were examples of greater legislative protections for IPR we took this as an indication of greater political commitment to address IP issues and rights.
2. The extent of existing gaps in terms of other institutions or donors implementing or supporting solutions or interventions in certain NTBs.
3. Where the UK had particular expertise to offer, these areas were more likely to be scored as high opportunity.
B. Value for Money of the Non-Tariff Barrier Programme
This section sets out the value for money (VfM) position of the NTB programme within the GTP. Since the GTP is designed to be flexible and adaptive in nature, the full range of the programme’s activities are still being considered. At this stage, we are certain that at least £40m will be spent on removing non-tariff barriers in MICs. This £40m amounts to £64m with development & design costs and management overheads. Therefore, we have carried out an economic analysis of spending £64m in partner MICs. The strategic case provides an indication where the rest of the GTP will be spent (excluding the DfID EPA programme) and, once scoped, the spend will be subject to full business case. Table 3.1 shows the breakdown of this £64m compared with the breakdown of the full £150m GTP spend.
Table 3.1 – Breakdown of GTP spend
Total	Flexible funds* - Through IPO, BEIS and other HMG) and World Bank Trade facilitation Partnership (proposed)	EPA Transition Programme	Research & Analysis	Access and enabling fund	Management costs (FCO and Delivery)
£150m	£80m[50]	£20m	£20m	£20m	£10m
£64m	£40m	-	£24m
[50] For this table, £8m for SACU+M has been included in flexible funds and excluded from the EPA transition programme.

* A minimum on £40m will be spent directly addressing NTBs to trade as proposed in the initial 2016 concept note.
The cost-benefit analysis in this Economic Case estimates the primary and secondary benefits arising from an investment of £64m to reduce NTBs in the nine target middle income countries; Brazil, China, India, Indonesia, Mexico, Nigeria, South Africa, Turkey and Vietnam.
The primary benefits have been estimated as the increase in target country GDP over a ten year appraisal period of 2018/19 – 2027/28, compared with no intervention. The secondary benefits have been estimated as the increase in UK GDP over the same period. As discussed in section 3.3, the direct impact of GTP on poverty levels is not measured at this stage.
Table 3.2 shows the Value for Money (VfM) position of the NTB programme under three scenarios. The core scenario 1 involves investing £64m (£60m in present value (PV)[51] terms) across the four non-tariff barrier areas as follows:
[51] Present value (PV) is the current value of a future sum of money or stream of cash flows. Economic analysis is carried out in present value terms to ensure future costs and benefits are comparable with current costs and benefits. This concept takes into account that an amount of money today is worth more than the same amount of money in the fute.
- £10m on trade facilitation;
- £10m on Intellectual property rights;
- £10m on regulations;
- £10m in standards;
- £24m on development & design cost (research & analysis and access & enabling) and management cost.
This estimates the impact on the target countries as being £2.0bn additional GDP over the appraisal period, in present value terms. The associated impact on UK GDP, as a result of increasing trade flows between the UK and the target countries is to add £31m.
Table 3.2: VfM Position of NTB Programme – Scenario Analysis
£m	Present value (PV) Costs	PV Primary Benefits: MIC GDP Impact	Primary Benefit-Cost Ratio	PV Secondary Benefits: UK GDP Impact	Secondary Benefit-Cost Ratio
Scenario 1: Invest in addressing all four NTB areas	60.0	2,023	34: 1	31	0.5 : 1
Scenario 2: Invest in addressing all four NTB areas but only realise benefits from Trade Facilitation	60.0	1,863	31 : 1	27	0.5 : 1
Scenario 3: Invest all funds in addressing Trade Facilitation only	60.0	6,831	114:1	99	1.7:1

Note that these figures factor in a 50% probability of success for the programme and also attribute only 3% of the estimated benefits to the programme’s investment. The latter adjustment is because wider spend will be required to deliver the overall benefits. This is discussed in the section below on ‘Estimation of Primary Benefits (Steps 3P – 4P)’.
Figures are present value costs and benefits for the appraisal period 2018/19 – 2027/28. Primary benefits have been discounted at 10%, secondary benefits and costs have been discounted at 3.5%.
It has been challenging to appraise all four NTBs because of the evidence gaps on linking the investment to impact. Only trade facilitation (customs) is evidenced from start to end in terms of linking the investment to the impact; whereas, the other three NTBs were partly linked only. This means the impact in these areas under Scenario 1 are effectively assumed rather than grounded in evidence. To mitigate this issue, the following three scenarios were developed to provide confidence in the VfM position of the programme:
- Scenario 1 (core scenario): All £64m is invested evenly (£16m in each NTB) in addressing all four NTB areas (trade facilitation, IPR, regulations and standards).
- Scenario 2: Invest all £64m in addressing all four NTB areas but only realise benefits from the trade facilitation (customs) interventions i.e. assume intervention in the other three NTBs will not be successful. The purpose of this scenario is to demonstrate that the NTB component of the GTP can still offer value for money even if interventions in IPR, regulation, and standards do not deliver benefits. It is important to show this because the evidence base linking investment in these three NTBs to their potential impact is much weaker than that of trade facilitation.
- Scenario 3: Invest all £64m in addressing trade facilitation only. The purpose of this scenario is to demonstrate the potential value for money position if all of the investments were made in the area with the strongest evidence base.
Scenario 1 is the core scenario which assesses the benefits of investing £16m in each of the four NTBs. Table 3.2 shows that this scenario has a high benefit-cost ratio for primary benefits; however, the secondary benefits are below break-even point. Table 3.3 shows that the majority of the benefits are realised by the trade facilitation (92% primary and 89% secondary benefits) and IPR, regulation and standards NTBs are weaker on VfM compared to trade facilitation. Table 3.3 shows that trade facilitation has the highest cost benefit ratio of 124:1 for primary benefits and 1.8:1 for secondary benefits. The difference in the relative returns for the three NTB areas is driven by assumptions about the different impacts on trade flows and an assessment based on the trade gravity model literature. Since the impacts of IPR, regulation and standards are assumed in scenario 1, we developed scenario 2 to illustrate that the programme is still VfM in terms of primary benefits even if we invest in the other three NTBs (IPR, regulations and standards) and they fail to deliver i.e. do not deliver any benefits (although the secondary benefits would be below break-even point).

Table 3.3: Scenario 1 – Benefits / Costs by NTB Area
£m	PV Costs	PV Primary Benefits: MIC GDP Impact	PV Primary Benefit-Cost Ratio	PV Secondary Benefits: UK GDP Impact	PV Secondary Benefit-Cost Ratio
Trade Facilitation (Customs)	15.0	1,863	124:1	27	1.8 : 1
Intellectual Property Rights	15.0	113	8 : 1	2	0.2 : 1
Regulation	15.0	37	2.5 : 1	1	0.1 : 1
Standards	15.0	10	0.7 : 1	0.3	0.02 : 1

A further scenario 3 is developed to illustrate the benefits of the GTP if all the £64m are allocated to trade facilitation (customs). Table 3.2 shows this option is the highest VfM. This does not suggest that the GTP should not invest in IPR, standards or regulation. This is because, as discussed above, it was not possible to evidence the link between investment in these three NTBs and impact. Instead, the economic analysis has had to assume a level of impact from investing in these three NTBs based on 1 year of historical improvement for these three areas. Since the VfM in these three NTBs is not grounded in evidence, the GTP should not rule out investing in IPR, standards or regulation at this stage.
At this stage, £16m has been allocated to each NTB to illustrate the potential benefits of GTP interventions. However, it is expected that more funds will be invested in those NTB areas which has higher benefits. We are currently undertaking further work to assess how the funds should be allocated across the NTB areas. If the detailed scoping work at the next stage suggests a weaker VfM case for any of the NTBs then the GTP would reconsider how best to allocate the funds among the NTBs. The advantage of GTP is that it is a flexible and adaptable programme and will invest in those interventions that meet the strategic objectives and offer the strongest Value for Money. Any future proposal will be subject to business case approval and will be assessed against an assessment framework, which is given in section 3.5.
Sensitivity analysis
A number of sensitivity analysis have been carried out to test the assumptions made in the central scenario. In summary, sensitivity analysis for scenario 1 as a whole shows that the secondary benefits are not resilient to changes in key assumptions at all. This is because the benefit cost ratio of secondary benefits is approximately 0.5:1 in the central scenario. However, the interventions are very resilient for primary benefits.
Sensitivity analysis for each of the four NTB areas was also carried out. For the trade facilitation intervention, sensitivity analysis indicates the VfM position is relatively robust to changes in the key assumptions. The sensitivity analysis shows that primary benefits of the interventions are very resilient to changes in key assumption used in the analysis. The secondary benefits of intervention in trade facilitation are resilient to the key assumption as well; however, they are less resilient than the primary benefits.
Although sensitivity analysis has been carried out on the other three NTBs (IPR, standards and regulations), an important caveat to the sensitivity analysis for these three NTB areas is that we have not been able to properly evidence the impact of the programme on the NTB measures. Instead, as discussed earlier in this section, we have had to assume the programme’s impact is 1 year of observed historic improvement. As such the sensitivity analysis carried out on these three NTB areas is conditional on the assumptions of the historical improvements.
3.5 Assessment framework
The economic analysis carried out above has shown that it is challenging to appraise trade reform programmes. This is not only due to evidence gaps but also because of the assumptions that need to be made to translate an indicator into a meaningful monetary measure to assess the improvement in a NTB. Some of these challenges would be addressed once more targeted interventions are designed. To ensure that all the future programme interventions meet the GTP strategic objectives, IDA/GEA compliance, and are value for money, we have developed an assessment framework which will be used to assess all the interventions under the GTP (including spending £40m on removing NTBs but excluding the fixed management fee and research and development which is vital for successful delivery of GTP). All the interventions will be subject to separate business cases and will be submitted to FCO (and where required for HMT and Cabinet Office) for scrutiny. Information on these interventions will be published in line with transparency commitments.
This framework will be further refined and finalised in the Analytical Strategy. In summary, all projects funded under GTP will be assessed against the following criteria:
      1. Strategic fit
        1. Meet the Prosperity Fund primary purpose (inclusive growth, poverty reduction) objectives of the GTP outlined in the Executive Summary
        1. Focus country (the project is carried out in one of the 9 priority countries)
        1. ODA/IDA/GEA compliant
      1. Expected Outcome and Impact: Evidence that the project will support GTP outcomes (primary purpose and secondary benefits)
      1. Value for Money: Including the 4 Es: economy, efficiency, effectiveness & equity.
      1. Other criteria: Sustainability and evidence of project management monitoring, evaluation, learning and adaptation.

Commercial case
4.1	Introduction
This section sets out the Commercial Case for the GTP. A mixed delivery model of contracts with HMG partners, multilaterals and commercial supplier will be used to deliver the £150m programme. This section summarises the case for the commercial supplier known as the Service Manager (SM). Following a rigorous procurement process, the GTP appointed Ernst and Young as the Service Manager to provide advisory, management and delivery services. This section explains how the SM model will be implemented commercially to ensure that the FCO procures the right SM supplier under a viable and robust contract that incentivises the right supplier behaviours, allocates risks appropriately and includes the contractual levers to deliver long term VFM.
The commercial case for GTP flexible funds will be progressed by the Service Manager once appointed; whereas, the commercial case for EPA Transition Programme delivered by DfID and WTO Trade Facilitation Programme delivered by multilaterals will be progressed by the programme team as part of their own business cases.
4.2	Delivery options
In order to deliver the GTP, the following five options were considered:
1. Do nothing - No dedicated new Prosperity Fund programme. This does not involve any specific programme spend but would assume a need for increased core departmental resources instead to deliver against strategic essentials described in this case.
2. Non-commercial interventions - Non-commercially sourced interventions where the programme provides funds to British Government agencies and other bodies through grants and Memoranda of Understanding (MOUs) to deliver assistance and share international and UK best practice.
3. Commercial interventions (fully managed in-house) - Commercially sourced arrangements where the Programme Management Team designs and manages competitive tender for suppliers to deliver specific assistance to beneficiary countries.
4. Commercial interventions (managed by external partner) - Commercially sourced arrangements where the programme competitively tenders for a supplier or suppliers to manage a flexible fund. The supplier then supports procurement and delivery of multiple assistance projects (NB: all contracts would be between the FCO and supply chain, not directly with fund manager).
5. A mixed approach of options B, C and D - A mixed delivery model where the Programme Team contracts directly with HMG and multilateral suppliers through MOU where they are providing specialist services; and commercially sourced supplier to support the development and delivery of a competitively tendered portfolio alongside the HMG/multilateral work.
4.3	Delivery option criteria
These options were qualitatively assessed against the following criteria:
- Value for Money (VfM) – It was assessed according to National Audit Office definition of ‘the optimal use of resources to achieve intended outcomes and expanded by DFID’s 4 Es model to mean:
  - Economy; are we or our agents buying inputs of the appropriate quality at the right price?
  - Efficiency: How well do we or our agents convert inputs into outputs?
  - Effectiveness: How well are the outputs from an intervention achieving the desired outcome on poverty reduction?
  - Equity: How well are benefits distributed across society?

- Speed of Delivery – Ensuring services are in place quickly. Effective staffing, making full use of FCO’s existing capabilities where appropriate particularly in terms of overseas network.
- Commercial Viability – Procuring the right supplier(s) with the correct mix of expertise to meet requirements. FCO having the right contract management plans, skills, resources and management information to manage contracts when they are let.
- Impact – The positive and negative, primary and secondary long-term change(s) produced or likely to be produced by the model, directly or indirectly, intended or unintended, after the programme is implemented.
- Adaptability – Retaining the ability to be flexible, move quickly to grasp opportunities and respond to emerging UK trade priorities.
4.4	Assessment results
Each delivery option was assessed against the above criteria. Option E was selected as the preferred option. This does not rely on one single supplier to design and deliver all interventions. The core principles are to:
- Retain FCO control while outsourcing a level of risk and management responsibility to our supplier;
- Minimise conflict of interest and incentives for the supplier to seek profit maximising interventions;
- Maximise flexibility and reach through a fully dynamic supply chain;
- Use a full market test wherever possible when appointing a supplier to maximise value for money; and
- Minimise the procurement risk of signing a contract with a company where they are committing to deliver an as yet largely undefined portfolio.
4.5 Requirements - What is the GTP buying from the Service Manager?
The GTP requires the following services to implement the Fund in support of ODA Trade Policy:
1. Management Services: managing the implementation of the GTP’s trade intervention strategies and a portfolio of trade intervention projects (including those provided by third parties under contracts, MoUs or grants) on a day to day basis on behalf of the FCO across multiple middle-income countries, suppliers and organisations, working in partnership with the FCO (including its overseas network) and other stakeholders to ensure successful delivery and to ensure IDA/GEA compliance and good practice development
2. Advisory Services: advice, research, analysis and support (including economic, governance, gender and social development) on the design of global and country based trade intervention strategies and the scoping of a well targeted pipeline of cost effective and high impact intervention projects designed to provide trade focussed technical assistance to ODA middle income country governments) to support inclusive growth, poverty reduction, gender equality and women’s economic empowerment
3. Delivery Services: delivery of the specific overseas trade intervention technical assistance projects to Overseas Service Recipients which are identified, scoped and contract managed under A and B above to support inclusive growth, poverty reduction, gender equality and women’s economic empowerment
Under Option E, the GTP will procure Service Groups A and B (Management and Advisory Services) from a Service Manager, with Service Group C (Delivery Services) being procured from multiple third parties (private sector , government, multi-laterals, academic and not-for-profit) under contracts, MoUs or grants (whichever is appropriate). The Service Manager (SM) will support the FCO in procuring the third parties and then contract manage them on behalf of the FCO.
## 4.6 Operating Model
The SM will play a central role in the implementation of the Fund by advising the FCO on the strategy, design and operation of the Fund and intervention project pipeline and providing the day-to-day management of the project portfolio on behalf of the FCO. The SM will be required to work closely and collaboratively with the FCO (both in the UK and its overseas Posts), other HMG stakeholders, partner country governments and other third parties for the successful design and delivery of the Fund against ODA and Prosperity Fund objectives. The FCO will retain overall control and oversight of the Fund and contract manage the SM contract through a GTP Policy and Governance function, ensuring that the Fund is used to provide high quality adaptive programming which offers Value for Money (VfM) and can respond to trade policy priorities as they emerge, whilst also contributing to and building HMG’s own knowledge, capability and capacity.
The SM will carry out a number of management functions that would otherwise be carried out by the FCO. It will therefore operate "client-side" for the FCO and will be required to comply with a set of management behaviours, operating principles and ethical duties to act in the best interest of the FCO, VfM and Prosperity Fund. The SM will be excluded from providing Delivery Services to remove the inherent VfM and conflict of interest risks if the SM were allowed to act as both client and supplier by scoping, designing, delivering and contract managing overseas intervention projects.
All Delivery Services to ODA MICs will therefore be provided by other third parties. These will be procured via separate contracts, MoUs or grants (whichever is appropriate). The GTP and associated approval governance will assess, commission, and approve each Delivery Services intervention project using the New Projects Development Approval Process (NPDAP). (See Management Case – section 6.34) The NPDAP will comprise business case, requirements definition, project scoping and procurement stages, together with assurance and sign-off decision points. This process will be integrated into the corporate and external spend control processes, so business cases exceeding £3m will be submitted to FCO departmental spend controls (and, where applicable depending on value, external Cabinet Office and HMT spend controls). Business Cases under £3m will be controlled through the NPDAP process and approved via the programme governance.
The business case for each Delivery Services intervention(s) will assess the most appropriate contract and commercial model and sourcing route. For interventions that will be delivered via a commercial organisation (i.e. non-HMG/non-multilaterals), the supplier will be procured through a competitive procurement process. The default route will be as a “Call-Off” from the FCO’s Prosperity Framework (which has been set up on this basis through the inclusion of a Trade ‘sub-Lot’), but the FCO will retain the option to procure via a discrete procurement. Where an intervention is via HMG or multilaterals, this would be via MOU. In certain limited circumstances, grants would be retained as a potential option for non-commercial not for profit entities.
Whichever route is used, the Delivery Services 3rd parties will be contracted via the FCO. They will not be sub-contracted via the SM as this would break the client-side model, which requires the SM to be excluded from providing Delivery Services. The SM will however support the FCO in this process and will contract manage these third parties on behalf of the FCO on a day-to-day basis, escalating any project delivery or contract/MoU/grant concerns and issues to the FCO’s Policy and Governance function. In addition, the SM will be given ‘delegated responsibilities’ to act on behalf of the FCO when contract managing the third parties (these are responsibilities which would otherwise have to be performed by the FCO itself if the SM contract was not in place).
The GTP will require the SM to be based off-site using its own tools and processes, but a small team (estimated to be three people) will need to be based centrally at the FCO so that they can perform functions that will require access to FCO systems. Although the SM will have some financial management responsibilities in support of the FCO, the SM will not hold the Fund monies. These will continue to be held by the FCO and Delivery Services third parties will be paid via FCO systems, with the support of the SM.
4.7	Contracting Model and Scope
The SM contract will be a client-side output/outcome-based Services Contract. This provides the best fit in terms of the role of the SM, the scope of the requirements and the need to secure appropriate levels of supplier incentive and risk transfer as set out below. The SM therefore shall:
- take the risk for providing an operational solution to meet the requirements;
- be performance measured on how well they set-up the services, design and manage the portfolio of overseas intervention projects and meet other contractual obligations in line with the contractual KPI’s (Key Performance Indicators);
- be expected to ensure they champion Gender Act Compliance, align with the Prosperity Fund’s Gender and Inclusion policy guidance, support poverty reduction, and promote inclusive growth. This will be monitored and measured for the duration of the programme;
- payment to the SM will be linked to their contractual payment milestones and performance[52];
  [52] See section 4.5 below
- the contract includes a mechanism to procure additional services or stand-alone deliverables to provide on-going purchasing flexibility (to allow the Contract to meet the future needs of the GTP, including the adaptive ‘demand led’ features of the Fund) ;
- the contract will be available for use by other parts of HMG, albeit this will be contracted as additional scope via the FCO rather than directly between the SM and HMG customer.
The SM contract allows the use sub-contractors where it does not have specific specialist service capabilities readily available in-house (subject to supply chain controls built into the SM contract).
The FCO will be the Contracting Authority. The Contract will be for 3 years in line with the current lifetime of the Prosperity Fund. This comprises a six-month inception period (with associated milestones and deliverables to mobilise the SM team, processes and tools and reach full operational service capability) followed by a 2.5 years operational service period with an optional contract extension period of up to two years.
The SM Contract will comprise the following Charges:
- a fixed price, fixed outcome to complete the inception based the agreed payment milestones, covering mobilisation, full-operational service ‘go-live’ and confirmation of satisfactory services post-go live (payments subject to meeting milestones/providing satisfactory deliverables).
- An operational charge based on the volumetric provided to cover a core set of Management and Advisory Services (payments subject to meeting Service Levels).
- Variable charge mechanisms based on day rates and/or fixed salary costs and volume discounts to provide the on-going flexibility to purchase new scope or projects on a fixed price or ‘time & materials’ basis, whichever is most appropriate (payment mechanism subject to scope and pricing used for each project) mechanisms to identify any applicable charges in the event of partial or full termination, contract extension, or exit on the expiry of the contract.

The GTP has set the following allocations for the services for prioritisation and budgetary purposes, which will not be contractual commitments[53]:
[53] The GTP has also set aside £60m for 3rd party Delivery Services. As noted at paragraph 4.3 above, the scope, contracting and procurement approach for the Delivery Services will be determined on a case-by-case basis as they are commissioned via the NPDAP.
- The total contract envelope is £25,260,809.47. This is separated into two parts:
  - Inception Phase, which will be a Fixed Price of £3,544,830.49.
  - Delivery costs that, using the requirements as stated, approximate £21,715,978.98.
- This second figure is subject to the number and size of projects delivered in operation post Inception. Projects will be priced on a case-by-case basis, using daily rates that were competed in this procurement, and form part of this contract. These projects will be subject to FCO approval processes.
- All Inception Milestone and Daily Rate prices incurred during Year 1 of contract award are fixed. Thereafter, any increase is subject to agreement with the Authority (FCO) and are bound by RPI and CPI constraints.
- In terms of Daily Rates, the financial analysis sheet, available separately, provides more information, however, for clarity here, this contract will be formed on the following basis:
- the Preferred Bidder has offered a 100% complement of employed staff, at cost rates with transparent profit margin and costs;
- calculating the average daily rate over-person-days on this basis, equates to £511 in inception, and £583 in operation (excluding profit, overheads and on-costs);
- should additional work be required over and above that specified, costed using consultancy advisors, the average daily rate, using a simplistic addition of all bands and dividing by the number of bands, shall not exceed £1,278. This will likely be much lower in delivery, when specific team designs are agreed for each project and further negotiation is concluded.
## 4.8 Commercial Model – What are the key features of the commercial arrangements?
The SM contract is based on 16 Key Commercial Principles (KCPs).These are designed to provide a strong foundation for the SM’s relationship with the FCO. It will maintain long-term value for money (particularly in relation to the flexibility required for the adaptive features of the Fund), secure an appropriate risk allocation between the FCO and SM. It will also incentivise the SM to exhibit the right behaviours and perform at its best on behalf of the FCO and the Fund and mitigate the risk of supplier failure or poor performance. Themes of the Key Commercial Principles are:
- VfM and Quality of Services – ensure VfM by incentivising ongoing competitive pricing and ensure high quality of service through a balanced risk/reward regime.
- SM Behaviours and Conflicts of Interest – ensure the SM has the required management and ethical behaviours and minimise conflict of interest.
- Risk Transfer – ensure risks are transferred to the party best able to manage them.
- Flexibility and Control of Change – ensure the contract can be extended cost effectively in response to higher demand.
- Supply Chain Oversight and Control – ensure appropriate levels of supply chain oversight, transparency and control.
- Ownership of and Access to Assets – ensure the position on asset ownership is clear and the FCO has appropriate rights where assets are created as a result of the contract.
- Business/Service Continuity – ensure continuity of service through business continuity planning.
- Manageability – ensure commercial mechanisms are underpinned by a strong legal framework and simple to operate.

5. Financial case
5.1	Budget Allocations
The GTP has a total budget of £150m over the spending review period 2016 – 2021, which is fully funded from the Prosperity Fund. Following HM Treasury direction, the programme budgets have been profiled across four financial years. This extends beyond the current spending review and assumes one additional year of financing in the next spending period.
£80m of £150m are allocated to the flexible fund to address NTBs and £20m are allocated to DfID EPA transition programme. The rest of the £50m are allocated to receive the following services to implement the GTP in support of ODA Trade Policy:
Management Services - the services which will deliver an effective and efficient operation for the GTP, managing a targeted portfolio of cost effective research, analysis and intervention projects across multiple regions and countries.
Advisory Services - the services, which will design, develop and deliver the GTP Strategic Plan, to include origination, advice, research and support on policy, strategy and project and programme scoping and design.
Delivery Services - delivery of the specific overseas trade intervention technical assistance projects to Overseas Service Recipients, which are identified, scoped and contract managed under one and two above.
5.2	Proposed Capital Required for the Service Manager
As outlined in the commercial case, a Service Manager has been procured to provide capability and capacity for the FCO to support the programme. The services that they will provide will be for Programme Management and Advisory Services to progress. The maximum budget provision will be up to £50m and all expenditure is subject to further FCO assurance and approvals.
The budget allocations that will be in scope for the Service Manager to provide the Management & Advisory Services are:
Research and Analysis Budget – up to £20m – a budget provision, retained by the FCO, supporting grants, research, analysis, and technical assistance, which will focus on priority countries, sectors and evidence gaps, with a specific focus on gender equality and women’s economic empowerment. Selection will be based on impact assessment of inclusive economic growth, increased trade in line with primarily, the host country and, secondary UK Government trade policy objectives, evidence, ODA eligibility, and Value for Money, and likely poverty, gender and inclusion impacts. Building a detailed understanding of the barriers to trade in partner countries will allow us to develop high quality interventions, as well as to underpin collaboration with partner country governments. Analytical outputs will also be crucial for providing governments with relevant evidence for informing policy decisions and to highlight areas for further action.
Access & Enabling Budget – up to £20m – a budget provision, to resource and enable potential projects and interventions identified by the research and analysis. Departments and posts develop proposals and business cases for new projects. This fund will enable ideas that support trade policy objectives. The money will be retained by the FCO and spent using agreed approval process.
Management Costs – up to £10m – a budget allocation, retained by the FCO, for the costs associated with the operation of the programme. This budget provision will cover both internal FCO Global Trade Programme Team Costs and the Service Managers Core Management team costs for the duration of the contract.
The Service Manager will support the FCO in designing and operating a responsive, flexible, timely, and enabling “Flexible Fund”. The Fund will be ‘demand driven’, responding to emerging policy priorities and the needs of HMG and its overseas network and ODA targeted countries. The Service Manager will advise on the design and delivery of the Fund and manage the Fund on a day-to-day basis, acting on behalf of the FCO including where this is delivered by Delivery Parties. As set out in the Strategic Case, this budget provision will be focused on delivering projects and emerging priorities in priority countries and sectors with selection based on impact measures of reducing poverty, inclusive economic growth, gender equality, increased trade in line with the primarily the host country and, secondary UK Government trade policy, evidence, and Value for Money.
All Delivery projects to ODA Middle income countries will therefore be delivered by other third Parties. These will be provided by separate contracts, MOUs or Grants (whichever is appropriate). The GTP will commission, access and approve each intervention using a New Project Development Approval Process (NPDAP).
5.3	Trade Programme Policy Team
Staffing (London)
The FCO policy team will oversee all GTP activity, including (but not limited to):
- The commercial and operational oversight of the appointed Service Manager;
- Commissioning all spend beyond core management services;
- Ensuring core services are being delivered in accordance with contractual requirements;
- Deliverable assurance and approval;
- Communication and engagement with Post and wider stakeholders;
- Programme level reporting and governance secretariat;
- Financial management and reporting, including all FCO processes such as invoice payment
- Ensuring GEA compliance and technical quality assurance for gender, poverty and inclusion and supporting cross-learning for Gender and Inclusion Champions.

The table beow sets out the current best assessment on what will be required to effectively manage the programme during the complex implementation phase.

Spend category	Spent FY17/18	Spent FY18/19	Actuals & Forecast FY19/20	Forecast FY20/21	Forecast FY21/22	Forecast FY 22/23	Total Spend
Non staff admin (inc. travel)	£15,657.37	£102,223.00	£153,120	£120,000	£120,000	£70,000	£581,000
UK Based Staff (GTP & consultants)	£603,527.84	£1,651,628.00	£1,384,346	£1,000,000	£1,000,000	£700,000	£6,339,502
Total spend	£619,185	£1,753,851	£1,537,466	£1,120,000	£1,120,000	£770,000	£6,920,502
As a percentage of £150m programme	0.41%	1.169%	1.02%	0.74%	0.74%	0.51%	4.61%
Accumulative % spend	0.41%	1.58%	2.61%	3.35%	4.1%	4.61%

HMG management / administration staffing costs, based on marginal costs (as advised by Prosperity Fund Delivery Unit - PFDU), are estimated at 4.6% of the total programme cost.
This will be reviewed following final definitions of specific job specifications. The management / administration staffing requirements will be further reviewed once implementation has started to ensure that the delivery mode is fit for purpose, given the complexity of the programme. This will ensure staffing costs are reasonable and required to make sure the programme is effectively managed, governed and benefits are realised. This staffing model allows for a central programme team based in London to actively manage the programmatic and project-level risk and issues that will arise during the implementation phase.
Staffing (Post)
The GTP have made staffing resource available for Post working with the programme to support the development of concepts and programme delivery as required. The programme recognises that each Post has different staffing structures and programme management approaches and governance. For this reason, no “one-size-fits-all” solution is proposed, and instead the programme team will agree requirements on a regional and Post basis across the programme lifecycle.

Management case
6.1	Introduction
This section sets out the Management Case, describing how the overall programme of work will be implemented and governed. The GTP is an integral part of an overarching UK Prosperity Fund programme and the purpose of the governance arrangements is to, amongst other things, provide oversight, direction, accountability and control at the strategic, tactical and operational levels.
Section 6.2 sets out the governance of the Global Trade Programme Boards and Section 6.3 sets out the annual review and remediation plan. Section 6.4 onwards sets out the management case for the Service Manager. The management case for the DfID EPA Transition Programme and WTO Trade Facilitation Programme will be progressed separately as part of their own business cases.
6.2	Governance of the Global Trade Programme Boards
The FCO has established two primary governance committees for the Global Trade Programme (each a "GTP Board" and together the "GTP Boards"):
- The Trade Programme Board – A cross-Whitehall, director level, strategic steering board (chaired by the programme Senior Responsible Owner), which will oversee portfolio level risk, performance and policy alignment. This board will have oversight of all spending decisions, which will also be subject to FCO departmental approval processes. The primary focus of this Board will be to provide leadership, check Value for Money, review overall GTP performance, provide a strategic overview and approve high value Project work and the Escalation route for subjects that cannot be resolved at the Operational Board.
- The Trade Operational Board – A cross-Whitehall, D6/7 grade board, which will provide monthly programme and portfolio oversight and escalate risks to the Trade Programme Board. The primary focus of this Board will be to review and manage the programme performance including management of the Services Manager’s performance, dispute resolution, Value for Money, approvals of Project work and continuous improvement reviews.
In addition, as discussed in the strategic and economic cases, the FCO has established a Cross - Governmental GTP Analytical Group to advise and support the GTP to make investment decisions using the best possible evidence. The Group will also review and approve the methodologies and provide views on the merit of research and analysis proposals.
The GTP Boards will be chaired by the SRO (or nominated delegate).The SRO reserves the right to escalate matters relating to the contract and GTP performance to either board as and when required.
6.3	Annual Review and Remediation Plan
The Annual Review is a key opportunity to assess whether gender, inclusion, conflict sensitivity and human rights are being effectively taken into account and managed in programme design and implementation. The annual review will assess the performance of the overall GTP including the element delivered by DfID and multilaterals. It will also provide an opportunity for the FCO to review the Service Manager’s performance of its obligations under the contract and the Service Manager’s contribution to the overall trade programme. The Annual Review will be held each calendar year and will involve consultation with all stakeholders, including government partners, beneficiaries, other development partners and the Service Manager.
6.4	Service Manager Governance Requirements and Risk Management
The Service Manager, Ernst and Young, will establish appropriate operational governance mechanisms for operational oversight of Sub-Contractors and the provision of other services by the Service Manager, taking account of the Service Manager delegated responsibilities. The Service Manager will pro-actively manage risks allocated to them under this Contract and develop, operate, maintain and amend, as agreed with the FCO.
6.5	Governance of Sub-Committees
Sub-Committees are to be created and managed at the request of the SRO. Any Sub-Committee that is created will follow the same governance when applicable. Where not applicable, the Sub-Committee will agree its own governance structure that is fit for purpose.
The Parties will look to develop a mutually beneficial working relationship for the Term of the Contract. The FCO may use its discretion to establish additional governance committees as and when required throughout the Contract to achieve this, including but not limited to the following:
- Project & Management Services Committee;
- Commercial & Finance Management Committee;
- Communications Management Committee;
- Benefits Management Committee; and
- Any other committee the FCO deems appropriate.
6.6	Management Services
Management services will deliver an effective and efficient operation for the GTP, managing a targeted portfolio of cost effective research, analysis and intervention projects across multiple regions and countries. The Service Manager will provide the following Management Services and the FCO may require additional management services as necessary.
- Help Desk Services – The Service Manager will provide a Help Desk Service to act as the first point of contact for all FCO and other Civil Service Government departments relating to the Global Trading Programme. The help desk will field, monitor, and action all requests related to the Global Trade Programme during Working Hours. These requests include but are not limited to enquiries from FCO staff and enquiries from other Civil Service government departments.
- Promotion, stakeholder management and communications – The Service Manager will directly communicate with government stakeholders as required by the FCO and will assist the FCO in the design, development and execution of marketing activities.
- Portfolio Management Services – The Service Manager will provide this.
- Project and programme management – The Service Manager will provide deliver assurance and support to GTP projects and programmes for the complete project and programme lifecycle.
- Delivery party and supply chain management - The Service Manager will be responsible for managing its own supply chain and managing Delivery Contracts.
- Financial management - The Service Manager will act as first point of contact on all Financial Management for the GTP on behalf of the FCO.
- Procurement management - The Service Manager will cooperate and work with the FCO 's procurement function as part of the service to provide the following:
  - develop ITT documentation using the Cross-Whitehall Prosperity Framework, should this be deemed unsuitable other procurement routes may be used on agreement with the FCO
  - utilise the FCO’s Bravo e-Tendering portal for procurements
  - technical evaluation of all project delivery bid submissions at various stages of the procurement with recommendations for award to be made in writing to the FCO
  - lead the financial/economical and commercial evaluation of tenders
  - advise on how new initiatives can be aligned within the complete GTP portfolio
  - provide detailed recommendation reports
  - lead the development of the award reports for the FCO 's Procurement function and GTP approval
- Benefits management – The Service Manager will prepare, maintain, and revise the benefits realisation strategy and the benefits realisation plan and provide:
  - create and manage a risks and issues log to ensure that all concerns with benefits are raised and dealt with in a timely and efficient manner;
  - provide ongoing benefits reporting to boards at portfolio, fund, project and programme level as appropriate to meet the needs of the GTP and to meet the requirements of the MREL business processes;
  - create business opportunities for businesses (including the UK), to trade more freely in any country where work has been carried out in as part of the GTP; and
  - to continually provide and assist the FCO with the upskilling of in-house capabilities to create trade opportunities for the future.
- Operational management - The Service Manager will work closely with the FCO provide a standing Help Desk Service which acts as the day-to-day front desk for the GTP.
- Continuous Improvement & evaluation - The Service Manager will be responsible for the creation and management of a Continuous Improvement plan for the FCO within the first 12 months from the Operational Services Commencement Date, to be reviewed annually or as and when required by the FCO.
- Business continuity and disaster recovery – The Service Manager will ensure this.
- GTP Management Information System (MIS) – The Service Manager will provide an off-the-shelf cloud-based Management Information System.
6.7	Advisory Services
Advisory services will design, develop and deliver the GTP Strategic Plan to include origination, economic analysis, gender expertise, advice, research and support on policy, strategy and project and programme scoping and design. The Service Manager will provide the following Advisory Services in addition to any further Advisory Services requested by the FCO. The Advisory Services may result in the need for a new Project.
- Policy and Strategy Support Services
- Project scoping design and planning services
- New Project Development Approval Process (NPDAP)
6.8	Risk Management (and mitigation)
Risk Management will be a core function of business and programme management and embedded at every level of delivery. Risk management will be in place not just to avoid losses but to also enhance reputation and business improvement.

6.9	Monitoring, Results, Evaluation and Learning (MREL)
The Service Manager is required to co-operate with and engage with the Prosperity Fund MREL Providers to ensure the success of the MREL system. The Service Manager's obligations in respect of the MR Provider and EL Provider are set out below and as may be required by the FCO from time-to-time:
Monitoring and Results (MR) Provider
The Service Manager will cooperate and engage with the MR Provider in order to design and develop the system, including the finalisation of core Fund level indicators:
- support the implementation of the system;
- work with programmes to develop indicators and associated baselines that will be used to aggregate cross Fund work against the theory of change;
- conduct routine Fund level analysis and reporting of data generated through system;
- conduct in-depth and tailored analysis of data generated through the system; and
- develop indicator frameworks for their programmes and be responsible for inputting indicator data into the Monitoring and Reporting Observatory ("MRO").
Evaluation and Learning (EL) Provider
The Service Manager shall cooperate and engage with the EL Provider in order to:
- arrange and provide notice in advance of interviews / document requests;
- schedule requests to the MR Provider (e.g. for interviews or documents) in a way which minimises disruption to the MR Providers’ everyday work; and
- maintain a constructive approach in evaluating the programme, supporting programme improvements.
Reporting
The Service Manager will provide timely, full, accurate and complete Reports to the FCO, which incorporates the data, in the correct format, required by the Reporting Template. The FCO will have the right from time to time (on reasonable written notice) to amend the nature of the Reports which the Service Manager is required to supply to the FCO.
All Reports must be completed by the Service Manager using the Reporting Template and returned to the FCO on or prior to the Reporting Date every month during the Term.
6.10 Training and Knowledge Transfer for the FCO
The Service Manager will be required to produce a flexible training and knowledge transfer plan during Inception, which will include but not be limited to the following:
- training to help create best practice for the GTP;
- provide knowledge transfer to the FCO during the Term, including via presentations, shadowing, creating materials or training as described below etc.;
- provide ad-hoc training capabilities to the FCO provided as part of the Management Services Fees;
- provide training and knowledge transfer the FCO staff who are at post within the 9 MIC’s detailed (with the potential to include further countries) within this document; and
- provide bespoke training to the management team of the GTP or other nominated HMG staff.
6.11 Stakeholder Management and Communications
Communications will be a vital component to the programme success, in particular ensuring the potential positive spill-over impacts and reputational benefits for the UK are realised e.g. businesses are made aware of the reduction in corruption and improved level playing field created by the programme.
The programme manager will have overall responsibility for setting the programme’s communication strategy, working with the JFU, FCO Media Office, the FCO Prosperity Fund Delivery Unit communications manager, partner HMG Departments, Posts and delivery partners, and ensuring coherence across individual projects within the programme. The programme manager will also be responsible for developing, maintaining and updating a communications plan for pan-programme communications.
The communication strategy will contain (and build on) a specific plan for each project, working with Posts (including local media managers), partner governments, other Prosperity Fund programmes and delivery partners. The key objectives will be to:
- Ensure all stakeholders are actively involved in the programme
- Positively influence partner government anti-corruption policy making
- Ensure UK organisations are aware of the reduced risk of undertaking business in the target countries relating to less corruption
- Disseminate good news stories to help build programme momentum
- Influence national decision-makers to further the impact of the programme
- Use the programme to raise the profile and reputation of the UK