PROSPERITY FUND

GLOBAL ANTI-CORRUPTION PROGRAMME (GACP)

Business Case

Version 2.0

Prosperity Fund – GACP Summary

“To disincentivise corruption, design out opportunities for corruption, recover illegally gained assets and help end impunity.”
Introduction
The Global Anti-Corruption Programme aims to promote inclusive sustainable growth and increase global prosperity, including for the UK, through an integrated set of projects focused on disincentivising corruption, designing out opportunities for corruption and recovering illegally gained assets. Some of the work is global and regional (‘following the money’), combined with a focus on eight countries[1] (Colombia, Indonesia, Kenya, Malaysia, Mexico, Nigeria, Pakistan and South Africa). The programme budget is £45.1m over four years. The programme is led by the Foreign and Commonwealth Office and has been designed by a Cross-Whitehall Steering Group involving the Department for International Development, the Government Digital Service, HM Treasury, the Joint Anti-Corruption Unit and the National Crime Agency.
[1] The country focus will be kept under review to ensure that the programme responds appropriately to opportunities created, for example, by a change in government and/or a change in policy towards transparency
What will the programme deliver?
Due to the complex multifaceted nature of corruption, no single intervention is likely to be successful in isolation. Therefore, through an integrated and coherent set of targeted projects to address corruption, this programme has been designed by a Cross-Whitehall Steering Group to help selected regions and countries:
- Change behaviours and motivations
- Design out opportunities for corruption to take place by increasing transparency and accountability
- Make the penalties and probability of being caught significant enough to deter future offences, and return corruptly gained assets
The programme will realise the above outcomes through implementing nine interconnected projects as set out in the diagram below.

What will the benefits be?
The overall impacts of the programme are defined as:
1. Primary – reduction in corruption, lower barriers to legitimate business and higher corruption penalties, which improve the business environment and improve investment in public services. This can result in higher rates of sustainable development; reduced poverty and gender inequality; greater investment flows; and greater trade flows.
2. Secondary – reduction in corruption, lower barriers to legitimate business and higher corruption penalties based on UK standards, that improve the business environment, improve investment in public services and enhance UK soft power. This results in mutually beneficial two-way increases in international investment and trade, including for UK business. An overview of the Theory of Change (ToC) underpinning the programme is set out below.

Economic analysis of the primary benefits indicates that the programme could improve GDP by ~£230m, improve trade balances by ~£160m or deliver improved population health outcomes valued at ~£33m across the partner countries over a 10-year appraisal period.
The programme will also play a key role in enabling increased levels of international trade and enabling other PF programmes to deliver higher levels of secondary benefits; as well as making a major contribution to the UN SDGs.
CONTENTS

# STRATEGIC CASE
# Context
### Global trends
Corruption impedes national and global economic development by restricting inclusive economic growth. It reinforces a system where a minority can prosper from positions of power and state funds can be misappropriated, resulting in weak institutions, a lack of enforcement mechanisms against perpetrators and poor public service provision[2] that ultimately hinders the development of the majority of citizens, with the effects falling most heavily on the poorest, women and other excluded groups.
[2] Rothstein, Bo; and Varraich, Aiysha (2017), Making Sense of Corruption, Cambridge: CUP
Global corruption has far reaching, cross-border impacts including: sustaining extreme poverty; reducing economic activity, growth, trade and investment; and threatening international security. Tackling corruption is integral to promoting a sustainable global economy where businesses (including UK businesses) can compete fairly and the benefits of economic growth can be shared across society and help bring the poorest citizens out of poverty.
### Social development
Corruption presents a major challenge to achieving the twin goals of ending extreme poverty by 2030 and boosting shared prosperity for the poorest people in developing countries. Studies[3] have consistently demonstrated that, globally, the poor pay the highest percentage of their income in bribes. In addition, corruption discourages poor people from accessing health services and negatively impacts on health outcomes such as infant mortality. The significant impact of corruption on income inequality and the negative effect of corruption on income growth for the poorest 20% of a country have been proven empirically[4]. The World Bank[5] estimates that each year US$ 20 to US$ 40 billion, corresponding to 20% to 40% of ODA, is stolen through high-level corruption from public budgets in developing countries and hidden overseas. Transparency International (TI) [6] found that about 35% of births in rural areas in Azerbaijan take place at home, because poor people cannot afford to pay the high charges for care in facilities where care is supposed to be free.
[3] http://www.worldbank.org/en/topic/governance/brief/anti-corruption
[4] Gupta et al, 2002
[5] World Bank, Baker, 2005
[6] Transparency International Global Corruption Report, 2006
### Economic development
Economic activity is similarly harmed by corruption – with corruption operating as a strong disincentive to foreign investment. Countries capable of controlling corruption are able to use their human and financial resources more efficiently, attract more foreign and domestic investment and grow more rapidly. The World Bank[7] estimates that there is a 300% dividend for improving governance from weak to strong. IMF research[8] has shown that investment in corrupt countries is almost 5% less than in countries that are relatively corruption-free. The World Economic Forum (WEF)[9] estimates that corruption increases the cost of doing business by up to 10% on average.
[7] http://www.imf.org/external/pubs/ft/fandd/2015/09/kaufmann.htm
[8] https://www.oecd.org/cleangovbiz/49693613.pdf
[9] https://www.oecd.org/cleangovbiz/49693613.pdf
### Trade
Corruption is one of the major barriers to trade[10] and interventions aimed at improving the business climate in target markets will particularly benefit UK business as they have historically been more averse than competitors from other countries to entering markets with a high risk of corruption. Indicative evidence from a recent international business survey found 30% of respondents said they believe they have lost deals to corrupt competitors[11]. The same survey identifies that 43% of UK companies chose not to do business abroad due to perceived corruption risks (the highest in Western Europe). Corruption can increase the cost of doing business for individual companies by as much as 10%[12], distorting markets and deterring trade and investment. Worldwide the cost of corruption is estimated to be more than 2% of global GDP (US$2.6 trillion)[13]. The World Bank estimates that over $1 trillion is paid in bribes each year[14].
[10] https://www.oecd.org/cleangovbiz/49693613.pdf
[11] http://rai-see.org/wp-content/uploads/2016/01/corruption-survey-2016.pdf
[12] http://www3.weforum.org/docs/WEF_PACI_BusinessCaseFightingCorruption_2011.pdf
[13] https://www.oecd.org/cleangovbiz/49693613.pdf
[14] http://www.worldbank.org/en/topic/governance/brief/anti-corruption
# UK as a development partner
### Fit with HMG policy
The UK’s strategy to tackle corruption is articulated in the UK’s Anti-Corruption Strategy 2017-2022, which builds on the UK’s 2014 ‘Anti-Corruption Plan’ and sets out a framework and a vision for UK efforts to tackle corruption at home and abroad.
The Strategy identifies three main outcomes that it seeks to achieve:
- Reduced threat to our national security, including from instability caused by corruption overseas
- Increased prosperity at home and abroad, including for UK businesses
- Enhanced public confidence in our domestic and international institutions

The Strategy identifies six priority areas to deliver on these outcomes, and four individual, supporting approaches. This programme seeks to support the Anti-Corruption Strategy in a number of these priority areas, specifically:
- Priority 2 – Strengthen the integrity of the UK as an international financial centre
- Priority 4 – Reduce corruption in public procurement and grants
- Priority 5 – Improve the business environment globally
- Priority 6 – Work with other countries to combat corruption

The vast majority of the Programme set out in this business case directly relates to commitments made in this Strategy.
As mentioned above, tackling corruption contributes to and underpins the successful delivery of priorities across the Government’s agenda including national security, development and prosperity, namely:
- The 2015 National Security Strategy and Strategic Defence and Security Review[15], identifies that “economic security goes hand-in-hand with national security” and contains and places the strength of the UK economy at the heart of national security (Objective 3). The UK’s economic strength is intrinsically linked to the global economy, which is significantly impeded by global corruption.
  [15] National Security Strategy and Strategic Defence and Security Review 2015 (published November 2015) available at: https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/575378/national_security_strategy_strategic_defence_security_review_annual_report_2016.pdf
- The UK Aid Strategy[16] objective of promoting global prosperity including strengthening UK trade and investment opportunities around the world.
  [16] UK aid: Tackling global challenges in the national Interest (published November 2015) available at: https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/478834/ODA_strategy_final_web_0905.pdf
- PM Theresa May set out a vision to forge a truly Global Britain that is strong, confident, united at home and respected around the world. This will be achieved in part through our actions to combat corruption at home and abroad, leading by example in becoming the most transparent government in the world and redoubling our efforts to change permanently how the world tackles corruption.
- The London Anti-Corruption Summit (May 2016), recognised the importance of addressing corruption in fulfilling the commitments made under the SDGs, including to ‘substantially reduce corruption and bribery in all their forms’ and ‘strengthen the recovery and return of stolen assets’. The Summit agreed to promote integrity, transparency and accountability, by exploring innovative solutions and new technologies, and strengthening cooperation[17].
  [17] See Anti-corruption Summit Communique (12 May 2016) available at: https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/522791/FINAL_-_AC_Summit_Communique_-_May_2016.pdf
The UK is uniquely placed to play a leading role in reducing international levels of corruption given its global role in setting standards, creating rules-based order and working with multilaterals on international campaigns. The UK is one of only three[18] of the 26 least corrupt countries[19] to have a national anti-corruption strategy; it is ranked the 8th least corrupt country[20]; it has the 5th largest diplomatic network in the world; and it is the only country to be a member of P5, NATO, Commonwealth, G7 and G20.
[18] http://www.statecraft.org.uk/sites/default/files/documents/EMEA_2384_Bespoke%20brochure__Countries%20Curbing%20corruption%20final%20report_V3....pdf
[19] 2016 TI CPI
[20] https://www.transparency.org/news/feature/corruption_perceptions_index_2017#table
### Fit with the Prosperity Fund
The programme will support the delivery of the Prosperity Fund Theory of Change intermediate outcomes: investment in human capital, innovation and technology; financial and economic reform; and ease of doing business.
This programme has significant levels of synergy with other Prosperity Fund programmes and importantly will amplify the overall impact of the Prosperity Fund by mitigating a portfolio-wide risk that the fund’s impact will be reduced as a result of corruption. The programme will actively manage the linkages with other programmes to ensure synergies are realised, both geographically (in-country) and operationally through delivery. This will be achieved through a combination of the Strategic Programme Board (ensuring strategic linkages are identified and progressed) and the programme management team liaising with their equivalents in other programmes and direct with Posts.
### Fit with international anti-corruption work
This programme will be aligned with and complementary to existing international anti-corruption work, especially those being led by international organisations such as the OECD, IMF and World Bank.
### Fit with Other HMG Programmes
The Programme will complement other existing HMG programming and complete a suite of UK assistance to tackle the problem of international corruption. The particular emphasis of this package is on (i) strengthening international norms and standards in areas related to anti-corruption, thereby contributing to a rules-based international system that, through less corruption, fosters global prosperity; and (ii) creating new channels for better practical collaboration internationally.
The programme complements other related HMG anti-corruption work including:
- The Department for International Development’s International Anti-Corruption Programme (I-ACT)
- The Department for International Development’s UK Anti-Corruption Programme (UK-ACT)
- The Department for Business, Energy and Industrial Strategy’s beneficial ownership work
- Crown Commercial Service procurement
- HM Treasury’s professional enablers, financial/anti-money laundering regulators and international tax reform
- The Home Office’s organised crime work
- Cross-Whitehall work on illicit finance
The programme has been designed by Cross-Whitehall officials from the Department for International Development, Foreign and Commonwealth Office, Government Digital Service, Home Office, Joint Anti-Corruption Unit, National Crime Agency, HM Treasury and Posts. Cross-Whitehall Programme governance has been established which will ensure that synergies with related HMG activity are realised. This includes close working with JACU who co-ordinate anti-corruption work across HMG and with DIT and FCO trade colleagues on secondary benefits.
# Gender Equality Act Compliance Statement
Under the International Development Act (Gender Equality) 2014 the Prosperity Fund must have regard to the contribution its assistance is likely to make to reducing gender inequality and to consider impacts on men and women and the relations between them.

According to consensus[21], corruption disproportionately burdens women. Directly, corruption reinforces women’s social and economic marginalisation by restricting their access to education, markets, credit, and public office. Given women’s role as the primary caretakers of family members, women have a greater need to access public services, with a higher likelihood of placing them in the position of paying informal ‘fees’ for services or bribes. In addition to inhibiting women’s access to basic public services, it can take the form of sexual exploitation. Indirectly, the burden derives from corruption’s greater impact on the poorest people in society, of which women form the majority, meaning women are more likely to be affected[22]. Furthermore, lower literacy rates and more limited access to personal resources mean women are more vulnerable to corruption where it exists. There is also evidence[23] of a negative relationship between corruption and female representation.
[21] Corruption, Accountability and Gender: http://www.undp.org/content/dam/aplaws/publication/en/publications/womens-empowerment/corruption-accountability-and-gender-understanding-the-connection/Corruption-accountability-and-gender.pdf
[22] See Seppänen and Virtanen 2008
[23] Gender and Corruption: http://www.oecd.org/cleangovbiz/Integrity-Forum-2017-SciencesPo-gender-corruption.pdf

This programme will consider the differential impacts of corruption and of the proposed interventions on men and women from different social groups, ensure ‘do no harm’ as a minimum standard, identify any risks and risk mitigation measures, as well as actively maximize opportunities to improve gender equality and women’s empowerment through proposed interventions. The programme will make sure there are provisions for monitoring impact on gender inequality to ensure compliance with the GEA and alignment with the Fund’s Gender and Inclusion Policy. In developing monitoring and reporting systems and metrics to measure impact, the programme will collect and disaggregate data by sex, age and socio-economic group where possible so a more accurate assessment can take place and projects adapted to meet this need.
# Objectives
Based on the above context in middle-income countries and HMG policy, the objective of this programme is as follows:
“To disincentivise corruption, design out opportunities for corruption, recover illegally gained assets and help end impunity”
Achieving this will directly lead to lower levels of corruption, which in turn will directly and indirectly increase global prosperity. The overall impacts are:
- Higher rates of inclusive sustainable growth
- Reduction in poverty
- Increased investment and trade
The programme will deliver distinct and attributable outputs. However due to the complex nature of corruption it may not be possible to directly attribute programme activity at the impact level.
Due to the complex and multifaceted nature of corruption no single intervention is likely to be successful in isolation. Therefore, an integrated and coherent approach has been developed, based on three interconnected themes that the GACP will address:
- Changing behaviours and motivations
- Limiting opportunities for corruption to take place by increasing transparency and accountability
- Where corruption does occur, making the penalties and probability of being caught sufficient to deter future offences, and returning corruptly gained assets

# ECONOMIC CASE

This section of the business case documents the range of options (projects and countries) that have been considered in response to the Anti-Corruption programme’s objective and identified within the strategic case. It also presents the Value for Money (VfM) case for the programme.
# Methodology
The high-level methodology for options selection and economic appraisal of the GACP in the Economic Case is summarised as follows:
Step 1: GACP Country Selection - Options Analysis. This step sets out the rationale for the selection of the eight target countries for the GACP. A combination of qualitative and quantitative analysis was used to determine which of the 18 PF priority countries are most willing to co-operate with HMG to deliver the programme’s projects; which have the highest need to address corruption and offer the best potential for delivering primary and secondary benefits.
Step 2: GACP Project Selection - Options Analysis. This step sets out the rationale for the selection of the recommended projects to be included in the GACP, with 14 potential anti-corruption projects and four options for combining these into different GACP project packages being considered.
Step 3: Cost-Benefit Analysis. This step estimates the primary and secondary benefits for delivering the selected GACP project package across the target countries with comparison to the cost of the programme.
# Strategic options selection
This section sets out the rationale underpinning which countries the GACP will focus upon (the ‘core countries’) and which Anti-Corruption projects it will focus on.
### Global Anti-Corruption Programme (GACP) Country Selection
The programme team worked with HMG Missions in the 18 Prosperity Fund priority countries[24] to understand the likely level of interest in participating in the GACP. This identified twelve countries with significant interest and capacity to participate.
[24] These are Overseas Development Assistance eligible countries, prioritised on the basis of poverty levels and size of market opportunity.
These 12 countries were then prioritised using a set of metrics intended to capture the scale and trajectory of corruption, incidence of poverty and potential export benefits for the UK – the latter two of these corresponding to the potential for realising primary and secondary benefits from the programme.

Table 1 - Prioritisation of Countries by Corruption, Poverty and UK Export Benefit Metrics
Country	Corruption Metrics			Poverty Metrics			UK Exports Metrics		Total
	CPI Score	CPI Score Change / (2012-2017)	Voice & Accountability Index	Population	Poverty ratio	GDP per capita Average	UK exports	Doing Business Ranking
Indonesia	9	2	2	1	4	6	6	7	37
Nigeria	1	7	6	3	1	5	3	11	37
Kenya	2	5	5	10	2	1	8	8	41
Pakistan	5	2	9	2	5	2	7	9	41
South Africa	11	7	1	7	3	7	2	5	43
Mexico	3	11	4	4	8	10	5	2	47
Colombia	9	5	3	9	7	8	9	3	53
Myanmar	4	1	10	8	5	3	12	12	55
Vietnam	7	4	12	5	8	4	11	6	57
Turkey	10	12	8	6	12	11	1	4	64
Malaysia	12	10	7	12	11	12	4	1	69
Algeria	6	9	11	11	10	9	10	10	76

Each country was scored against these metrics with a total used to provide an overall ranking of countries. Eight countries (‘target countries’) were prioritised for participation in the GACP on the rationale of ensuring the programme remains manageable and funds are not spread too thinly across too many countries.

These eight countries tended to rank higher than the four de-prioritised on the basis of: i) stronger accountability of institutions (as measured by the V&A Index), which is likely to make tackling corruption easier; ii) greater populations and poverty ratios (i.e. a greater need to address poverty); iii) they are countries to which the UK has historically exported a greater value of goods and services in absolute terms.

There was one exception to this process. As a result of a change of government and government policy towards transparency in Malaysia in May 2018, and the resulting high degree of political will to address corruption combined with the opportunity to make difference within a relatively short time-period, Malaysia has additionally been included in the programme as a target country. The Malaysian government has demonstrated a real desire to address domestic corruption and has requested help from the UK which includes a country visit by delegation of anti-corruption officials from the UK. Although the analytical assessment did not necessarily prioritise Malaysia, the strength of political support, improved balance of income levels across the country portfolio, with anticipated improvements in the ‘CPI score change’ and ‘voice & accountability’ scores, means there are real opportunities for the programme to make a significant impact.

The GACP’s country selection will be kept under review by the programme management team who will monitor progress and work closely with Posts. Where appropriate, the programme will respond to changing circumstances (e.g. a change in government and/or a change in policy towards transparency) via adaptive programming. Such changes will be subject to recommendations from the Strategic Board and SRO.
### GACP Project Selection
All the programme’s anti-corruption projects will focus on prosperity; removing corruption as a barrier to economic growth; and providing the stable, level playing field needed by businesses (including UK-based businesses) to thrive. These will support the intended aims of the Prosperity Fund and the long-term outcomes of the UK Anti-Corruption Strategy[25].
[25] The UK Anti-Corruption Strategy 2017-2022 aims to contribute to three long-term outcomes: reduced threat to our national security, including from instability caused by corruption overseas; enhanced public confidence in our domestic and international institutions and increased prosperity at home and abroad, including for UK businesses. https://www.gov.uk/government/publications/uk-anti-corruption-strategy-2017-to-2022
As set out in the Strategic Case, the GACP aims to tackle corruption by i) disincentivising people to undertake corrupt activity in the first place, ii) making corruption easier to detect and therefore harder to commit, iii) increasing the penalties and risks for those who engage in corruption, and iv) by returning corruptly gained assets. These aims originate from the objectives of the London Anti-Corruption Summit in 2016. A long-list of fourteen potential programme projects that would support these aims was developed by the programme team in cross-Whitehall discussions with relevant officials and civil society engagement.

Table 2 – GACP Project Options
Project Option	Description	Estimated Cost
1. Implementing UN Convention Against Corruption (UNCAC)	The United Nations Convention against Corruption is the sole legally binding international instrument against corruption. Working with the UN the UK will efficiently match learning and development needs with expertise, with a large body of subject experts, gathered under the auspices of the Convention to deliver programming in a large number of countries. This programme will concentrate on priority deliverables including legal, policy and institutional frameworks, building the capacity of anti-corruption practitioners, and building the capacity of the judiciary and law enforcement agencies to counter corruption.	£8.1m
2. Improving Transparency and Addressing Bribery	The OECD leads on, and champions, a number of work streams internationally relevant to tackling corruption. It collects vast quantities of data for these purposes, but does not currently have capacity to exploit this data for the purposes of tackling corruption. This activity comprises four work streams: creating an online portal for the storage and exploitation of relevant material, supporting the OECD’s Integrity Forum, “partnering” or “twinning” countries to share best practice with one another on tackling corruption, and providing technical assistance to priority countries.	£4.0m
3. International Anti-Corruption Coordination Centre (IACCC)	The IACCC was established by the NCA in April 2017, supported by the Year 1 PF Anti-Corruption Programme. The IACCC will bring together specialist law enforcement officers from multiple foreign jurisdictions into a single location to tackle allegations of grand corruption. Funding will support building multilateral capability to support high priority cases. As countries are able to learn from these cases specific vulnerabilities can be identified and addressed resulting in a safer place to do business minimising the future impact of corruption.	£5.1m
4. Global Forum on Asset Recovery (GFAR)	This project/activity will support the GFAR which supports the return of money to legitimate governments. It seeks to replicate the success of regional forums (the Arab and Ukrainian Fora on Asset Recovery) by expanding the model to ODA eligible countries. The US and UK co-hosted the first meeting in Dec 2017 with focus countries Nigeria, Sri Lanka, Ukraine and Tunisia – the results included a signed MoU for the return of $321m of stolen money to Nigeria. Further work will continue to facilitate technical cooperation in order to ensure the safe return of assets to these countries, expanding the country focus and supporting development of agreed policies.	£2.0m
5. Supporting the Extractive Industries Transparency Initiative (EITI)	Extractive industries are particularly vulnerable to corruption in many countries due to a lack of transparency in contracts, governance and finance. Financial assistance will be provided to strengthen implementation of the new 2016 EITI Standard, including priority areas identified such as beneficial ownership and commodity trading transparency. This will include support for countries to meet the EITI requirement for beneficial ownership disclosure by January 2020, building directly on the PF (Year 1) support.	£3.2m
6. Increasing the Transparency of Company Beneficial Ownership	This activity will support the development of a global platform to host company beneficial ownership information (information on who actually owns companies). The platform will simplify the implementation of standards on beneficial ownership information for countries, companies and users. A global register pilot has already been undertaken and the funding will allow for development of the platform from the pilot stage, testing the platform in countries which made commitments at the 2016 Anti-Corruption Summit and providing support for countries implementing the standard.	£2.8m
7. Combat Money Laundering through FATF Regional Bodies	This project seeks to tackle the financial gain from corruption by strengthening countries’ abilities to tackle the laundering of illicit money. Support will be provided via the FATF to provide greater support to developing countries with underperforming anti-money laundering (AML) systems, including AML training courses, reviews of member country AML systems, and capacity building support to address weaknesses in those systems.	£3.4m
8. Procurement Reform and Digitisation	The Cabinet Office Digital Service (GDS) has developed an online marketplace “the UK Digital Marketplace”. GDS will develop and deploy this platform with partner countries. The focus will be on achieving greater transparency and scrutiny of public procurement decisions, improving people, processes and platforms around public procurement and making it harder for corrupt or criminal interests to win government contracts.	£10.5m
9. Reducing Corruption Through Behavioural Insights	Behavioural change pilot studies have been undertaken on public service supply chains, national beneficial ownership registers and the construction industry. The year 2-5 allocation will develop the pilots into scaled up interventions and facilitate similar interventions in other target countries.	£3.0m
10. Construction Sector Transparency Initiative (CoST)	Launched in 2012, this global initiative combats corruption in commercial contracting by increasing transparency over the letting and delivery of major infrastructure projects. It has a civil society element in monitoring project performance. DFID supported the proof of concept stage. The project would extend the initiative to target countries.	£3.0m
11. Maritime Anti-Corruption Network (MACN)	The MACN promotes collective action in seaports to drive out petty corruption encountered by international shipping using ports. It is run by an industry consortium with 90+ members. It has enjoyed success already in a number of countries, and evidence from business leaders and academics suggests preventing corruption in seaports is a priority. This project would provide target countries with financial support to participate in the network.	£5.5m
12. Basel International Centre for Collective Action (ICCA)	The ICCA is pioneering approaches in joint anti-corruption action by companies in industrial sectors, including ‘difficult’ ones such as aerospace, defence and pharmaceuticals. This project would provide financial support to the ICCA to develop these new approaches.	£1.7m
13. Establish Beneficial Ownership Registers in Developing and Emerging Economies	The UK’s global lead in establishing a public company beneficial ownership register has prompted a desire in other countries to create their own registers. This project would provide the capacity to conduct scoping and impact assessments in several target countries.	£1.5m
14. Promote International Certification of Anti-Bribery Standards	ISO37001 is the newly introduced global standard for organisational anti-bribery standards. It is based on the British Standard (BS10500) introduced to give organisations a guiding standard for meeting the ‘adequate procedures’ requirements of the UK Bribery Act. This project would promote wider use of this certification in target country markets to raise integrity standards.	£0.3m

Consultation at multiple levels was undertaken across Whitehall to assess the above 14 individual projects and identify the main considerations for either including or excluding each from the GACP. Each project was qualitatively assessed against the following criteria: political commitment, impact on prosperity, additionality, suitability to PF funding, cost and risk.

Table 3 – Key Considerations for each GACP Project Option
Project / Option	Key Considerations
1. Implementing UN Convention Against Corruption (UNCAC)	Improved International Coordination. This activity will coordinate the UN response to corruption, bringing together civil society, technical assistance, advocacy, and research and analysis to focus on gaps in UNCAC implementation in target countries. / Innovative. This is a new and innovative way of funding UN anti-corruption interventions and other donors have expressed an interest in building on the planned activity. More generally, this project will also be a catalyst for other donors to change the way they fund the UNODC to improve resource allocation. / Enhances Programme Credibility. Working through the UN is the only way to achieve systematic large-scale change. By delivering our commitments through UNCAC is integral to maximising primary and facilitating secondary benefits.
2. Improving Transparency and Addressing Bribery	Improved International Coordination. Using the expertise and convening power of the OECD, this project will bring business, academia, policy makers and civil society together to learn from each other and develop good practice in countering corruption. It will assist non-OECD countries’ attainment of OECD anti-bribery standards. / Underpins Secondary Benefit Realisation. Using the OECD to drive best practice between governments and businesses is important for realising potential secondary benefits from the governance work in the GACP.
3. International Anti-Corruption Coordination Centre (IACCC)	Improved International Coordination. The IACCC is the first operational centre of its kind. Cross border investigations are critical to progress in successfully investigating and prosecuting the “grand corrupt” – individuals who steal vast sums of public money and hide it in financial centres across the world. / Innovation Risk. This is a new innovation. NCA have worked hard to mitigate delivery risks, but given the sensitive and international nature of the task, it is likely that further challenges will emerge.
4. Global Forum on Asset Recovery (GFAR)	Improved International Coordination. Co-hosted with the US, this event, funded from transition allocation from the PF, delivered four objectives: progress on major cases of grand corruption in four countries; increased capacity through sharing of experiences and best practice; renewed international commitment to advancing asset recovery cases; and increased collaboration among involved jurisdictions. The forum will also provide an opportunity to launch the IACCC.
5. Supporting the Extractive Industries Transparency Initiative (EITI)	Track Record. EITI has consistently delivered against milestones. / UK Reputation/Commitments. The UK has been a lead supporter of the Extractive Industries Transparency Initiative since founding it in 2003, enabling the reporting standard to be adopted by 52 countries by 2017. Continued UK support was pledged at the 2016 Summit and provides a strong signal of continued commitment to extractives transparency to companies and other governments.
6. Increasing the Transparency of Company Beneficial Ownership	Track Record. This partner exceeded delivery milestones. Multiyear commitment recognises this track record and provides security for partner to start building registers in 6 countries by 2021 and seek additional funders to spread UK risk. / Mitigate Delivery Risk. The implementing partner is dependent on UK funding as HMG is the sole funder of this initiative to enable additional countries to adopt transparency in country ownership. Not funding would represent significant delivery risk for the partner / Welcomed by Business. Business highly values open register information when investing overseas in order to obtain information about contracting partners and supply chains as part of investment due diligence.
7. Combat Money Laundering through FATF Regional Bodies	Political Support. FATF has potential to do work with developing countries to support them to raise their AML standards. During the last year the UK has lobbied members (e.g. the US and other G7 countries) and the FATF Secretariat to support a more active FATF role in this area. We now have significant support, and now is an appropriate moment to take this work forwards. / Mitigate Delivery Risk. A multi-year funding commitment is required as FATF needs certainty in its funding levels and cannot take action on a single-year commitment as champion of this work.
8. Procurement Reform and Digitisation	Track Record Similar interventions elsewhere have delivered procurement and operational cost savings for governments. Potential to make target country government procurements more transparent and competitive for UK firms and firms more generally across the globe.
9. Reducing Corruption Through Behavioural Insights	Track Record. Countering the culture of corruption is an essential underpinning factor for all aspects of this programme. Early indications have shown that this work could result in tangible benefits in key sectors. / Political Support. The Behavioural Insights Team (ex-UK Government) has worked closely with Colombia and Mexico on these initiatives. The President of Colombia has name checked this initiative.
10. Construction Sector Transparency Initiative (CoST)	Track Record. Launched in 2012, this global initiative combats corruption in commercial contracting by increasing transparency over the letting and delivery of major infrastructure projects. It has a civil society element in monitoring project performance. DFID supported the proof of concept stage. / Limited Benefits. Benefits would be limited to fully encompassing PF priority countries within the initiative, rather than create new approaches. / Management Costs. There would be significant oversight costs for Posts in the countries concerned.
11. Maritime Anti-Corruption Network (MACN)	Track Record. Collective action in seaports to drive out petty corruption encountered by international shipping using ports. It is run by an industry consortium with 90+ members. It has enjoyed success already in a number of countries, and evidence from business leaders and academics suggests preventing corruption in seaports is a priority. / Better Suited To Other Delivery Models. Work with other Global Programme leaders and geographic desks concluded that this initiative is better managed from both the Trade Business Case and from Posts themselves.
12. Basel International Centre for Collective Action (ICCA)	Track Record. ICCA is pioneering approaches in joint anti-corruption action by companies in industrial sectors, including ‘difficult’ ones such as aerospace, defence and pharmaceuticals. Sister organisation of the DFID-core funded International Centre for Asset Recovery (ICAR). / Value Add Risk. The Programme team judged that support by the PF would simply add to an already existing stream of work, and distinct value added was hard to judge.
13. Establish Beneficial Ownership Registers in Developing and Emerging Economies	Track Record. The UK’s global lead in establishing a public company beneficial ownership register has prompted a desire in many developing countries to create their own registers. Support of this nature would provide the capacity to conduct scoping and impact assessments in a few target countries. / Political Support. BEIS has received many requests from overseas governments for assistance in the legal, technical and practical requirements involved in setting up registers. / Insufficient Capacity. This is a challenge for BEIS, giving competing demands on their time and resources (financial and people). Potential overlap with the Transparency of Company Beneficial Ownership project (Project 6).
14. Promote International Certification of Anti-Bribery Standards	Track Record. ISO37001 is the newly introduced global standard for organisational anti-bribery standards. It is based on the British Standard (BS10500) introduced to give organisations a guiding standard for meeting the ‘adequate procedures’ requirements of the UK Bribery Act. Promoting wider use of this certification in emerging and developing country markets could raise integrity standards in key markets / Benefits long-term. Overall benefits are more likely to be indirect, hard to quantify and of a ‘long burn’ nature. / Substantial Post/Technical Investment Required. It would require mainly trade and diplomatic influencing overseas to persuade others to adopt the approach and significant technical support to implement.

Based on the above assessment, the projects were then grouped into three categories:
1. Projects addressing critical gaps in the international anti-corruption architecture (these generally have high levels of political commitment, the potential to have a high impact on prosperity, are additional, suitable to PF funding and relatively low-level risk)
2. Key innovative projects providing the opportunity to make a significant impact on reducing corruption (these have the potential to have a very high impact on prosperity, are additional, suitable to PF funding and medium-level risk)
3. Sector specific and standards projects (these generally have less clear benefits, a lower level of additionality, less suitable to PF funding, resource intensive and medium-risk level)

Four options were then developed, based on the above three categories and a do-nothing option, all drawn from the list of fourteen projects:

Option 1: Do not deliver a PF GACP

This option would continue with existing HMG anti-corruption programmes but none of the fourteen projects above would be pursued. Some of the projects are new projects which would not commence without HMG funding, others are existing projects in which this programme is considering expanding scope (with the ‘additional’ activity and benefits being the focus of this appraisal). This option would have major UK reputational impacts as the UK would renege on its published commitments.

GACP project cost: £0.0m

Option 2: Implement a GACP including only projects which help address critical gaps in the international architecture

This option would implement a GACP package comprising the first seven projects in Table 2: implementing UNCAC, improving transparency and addressing bribery through the OECD, supporting the IACCC, supporting GFAR, supporting EITI implementation, increasing the transparency of beneficial ownership, and strengthening AML systems (FATF).

The programme team’s view is that these are the projects that would help address critical gaps in the international anti-corruption architecture and would not happen without UK support or leadership.

Total GACP project cost (excluding management costs): £28.5m

Option 3: Implement a GACP including the ‘critical gap’ projects (Option 2) and also innovative projects which could deliver significant benefits

This option would implement a GACP package comprising the first nine projects in Table 2 i.e. as per Option 2 but with the addition of the Behavioural Insights and Procurement Reform & Digitisation projects.

The programme team’s view is that the evidence accumulated from initial pilots in these projects is encouraging and further support would provide tangible results in target countries.

Total GACP project cost (excluding management costs): £42.0m

Option 4: Implement a GACP including the ‘critical gap’ and ‘innovative’ projects (Option 3) plus also sector specific and standards projects

This option would implement a GACP package comprising all projects in Table 2 i.e. as per Option 3 but with the addition of the CoST, MACN, ICCA, Beneficial Ownership Registers and Anti-bribery Standards projects.

GACP project cost (excluding management costs): £54.0m

These package options were assessed by the programme team and presented to the PF’s cross-Whitehall Portfolio Board on 25 January 2018. The Portfolio Board endorsed Option 3.
The programme team’s view is that Option 3 provides the best balance for the following reasons:
- Supporting commitments made at the UK Anti-Corruption Summit
- Potential impact on corruption (and prosperity)
- Maximising additionally
- Fit with the PF as a funding source
- Making best use of HMG anti-corruption expertise
- Balancing well-understood projects with more innovative/riskier activities
- Managing programme complexity (number and nature of projects)
# Cost-benefit analysis
### Introduction
This section sets out the cost-benefit analysis of the GACP in order to assess whether it offers Value for Money. This requires estimating the primary and secondary benefits of the programme and comparing these to the programme costs.

The primary benefits of the programme are intended to capture the impact of the GACP in the target countries themselves. Four different methods have been used to estimate the primary benefits of the programme or its projects.

The first three methods estimate the programme’s overall impact on partner countries’ economic growth (GDP), trade balances and health outcomes. A common assumption is used for the programme’s impact on a country-level indicator of corruption (the ‘Corruptions Perception Index’[26]). The results of empirical studies from the corruption/economics literature are then used to estimate the impact of reduced corruption on these outcome measures.
[26] The CPI is produced annually for almost all countries and uses survey data to score each country on a scale of 0-100, with higher scores representing lower perceived corruption levels. Prior to 2012, the CPI was calculated on a 0-10 point scale and some methodological changes were also made in 2012 to the calculation of the score.

A key limitation of these methods is the lack of evidence in the literature underpinning the likely impact of the anti-corruption programmes on overall corruption levels. As such, the estimated impact of the programme on corruption levels is conservative. [27] The case explores historic changes in country CPI scores to check that the assumed change is ‘feasible’ and relatively conservative (i.e. it does not assume a magnitude of change in the CPI greater than historically observed).
[27] This approach of assuming a small, albeit arbitrary, change in corruption levels has been used elsewhere in HMG cost-benefit analysis of anti-corruption programmes See Mexico Prosperity Fund Programme Business Case and DFID’s International Action against Corruption (IACT) Programme

However, this issue remains a limitation and the fourth method addresses this with a “bottom up” appraisal of the largest of the nine projects within the GACP. The Procurement Reform and Digitisation project, which accounts for almost 25% of the GACP budget, aims to improve standards and processes for government procurement of digital services in order to limit opportunities for corruption and improve competition. There is some evidence of the impact of anti-corruption initiatives on procurement costs from the healthcare sector in Argentina.

The secondary benefits analysis estimates the impact of the GACP on UK exports to the target countries, as an extension of the trade balance analysis for the primary benefits. As such, the impact on corruption levels is assumed to remain as before.
For each appraisal method, the estimated benefits are compared to the programme costs to see if they justify the proposed investment in the GACP.
### Costs
Under the recommended project package, the cost of the GACP would total £45.1m in 2017/18 prices. This includes the cost of the nine interventions, £42.0m, plus £2.7m for GACP staff costs and £0.45m for communication and project review costs.

Table 4 – GACP Costs
£m	2017/18	2018/19	2019/20	2020/21	2021/22	Total
GACP Cost	4.7	8.8	12.2	12.0	7.4	45.1

The total programme cost of £45.1m is discounted at 3.5%[28] to give a present value of £41.9m in 2017/18 prices.
[28] GACP costs are discounted at 3.5% in line with the social discount rate for the UK referred to in the HMT Green Book. https://www.gov.uk/government/publications/the-green-book-appraisal-and-evaluation-in-central-governent

### Primary benefits

Assumed Impact of GACP on Corruption Levels (GDP, Trade Balance and Health Methods)

The first common step in each of the GDP, Trade Balance and Heath approaches to estimating the primary benefits of the GACP is to make an assumption about the likely impact of the programme on country level (i.e. aggregate) corruption levels in the target countries, compared to ‘do nothing’. Various different country-level measures of corruption are available, most of which focus on corruption perceptions rather than objective measures.

Country-Level Corruption Measures

Transparency International (TI) produces a country-level report of perceived corruption, the Corruption Perceptions Index (CPI), annually for most countries[29]. See a wider explanation of this measure under table 2 on page 13.
[29] https://www.transparency.org/news/feature/corruption_perceptions_index_2016

Another measure is the World Bank’s Control of Corruption Index[30], one of six “World Governance Indicators”. The Control of Corruption index captures perceptions of ‘the extent to which public power is exercised for private gain, including both petty and grand forms of corruption, as well as capture of the state by elites and private interests’. This measure ranks countries on a scale running from -2.5 to +2.5 with higher values corresponding to better governance.
[30] http://info.worldbank.org/governance/wgi/#doc

The Corruption Perceptions Index has been used for the estimation of primary benefits as this is a commonly used index in the empirical studies estimating the relationship between corruption levels and economic variables such as growth and trade.
Justification of assumed impact on CPI
Ideally, the assumed impact of the GACP on the CPI would be measured by past evidence of the impact of anti-corruption initiatives similar to those within the GACP. However, this is problematic. For example, the literature review of anti-corruption studies by Johnson et al. (2012) noted the difficulty of attributing the impact of specific anti-corruption initiatives to overall country level indicators of corruption, given the multitude of factors likely to influence those indicators.

For the analysis that follows it has been assumed that the GACP would lead to an improvement of +0.1 in each of the target countries’ CPI scores, relative to a counterfactual of no GACP, by the end of the 4 year implementation period 2018/19 – 2021/22[31].

An improvement of +0.1 in country CPI scores on the 0-100 scale (or +0.01 on the 0-10 scale) is therefore judged as being ‘feasible’ and relatively conservative given the magnitude of changes in scores observed for the target countries and more generally for middle income countries in the CPI dataset. However, it should be stated again that, unfortunately, this does not provide evidence for the likely impact of the GACP itself.

Primary Benefits - Literature

The academic literature has identified a variety of theoretical channels or transmission mechanisms through which corruption can influence economic growth and other economic outcomes such as trade.

In theoretical terms at least, the nature of the impact of corruption on growth is ambiguous. Whilst it is plausible that corruption impairs growth through misallocating resources, increasing transaction costs and increasing uncertainty (the “extortion” hypothesis), there are also circumstances in which corruption could plausibly support economic activity.

The most commonly cited hypothesis is that corruption can be used as a means to circumvent regulation or transaction costs (e.g. trade tariffs) that otherwise inhibit economic trades (the “evasion” hypothesis). Note that where such regulation is welfare enhancing (e.g. pollution laws) the effect of corruption may be to increase growth whilst reducing welfare.

Overall then, the question of what impact corruption has on economic growth is an empirical one. The various transmission mechanism are discussed briefly here drawing in part upon the more comprehensive summary in the OECD’s 2013 ‘Issues Paper on Corruption and Economic Growth’.[32]
[32] https://star.worldbank.org/sites/star/files/oecd_issues_paper_on_corruption_and_economic_growth_2013.pdf

Corruption-Growth Channels
Investment Channels
It is argued that corruption deters private investment by increasing transaction costs e.g. through bribes to expedite regulatory applications and/or through greater uncertainty over the “rules” for doing business in a country. Higher transaction costs will reduce the expected rate of return on investment projects resulting in a misallocation of resources. This may be countered by evasion effects where corruption is used to circumvent regulation or taxation that would otherwise deter investment.

Broadly, empirical studies find that corruption has a negative impact on private investment (e.g. see Mauro (1996), Dreher and Herzfeld (2005), Pellegrini and Gerlach (2004)) though with some qualifications e.g. if the corruption environment is more predictable, then its impact is found to be lower (see Campos et al. (1999), Wei, S. (1997)).

For the same reasons, corruption may deter or support foreign direct investment (FDI) flows. FDI flows can be an important source of knowledge or technology transfer between countries and therefore for economic growth convergence. Here however, the empirical evidence is mixed.

International Trade Channel
Corruption could also have an impact on growth through an influence on international trade flows and a countries’ ability to specialize and expand output. Gil et al. (2017) test the extortion vs. evasion hypothesis on bilateral goods trade flows for 139 countries and territories over 1975-2012. They use gravity models[33] of trade augmented with three different corruption measures, two perception based and one structural (more objective) based measure.

Broadly they find mixed results for the impact of corruption on trade; for example, when using perceptions based measures (Corruption Perception Index and Control of Corruption Index) higher corruption levels in a country are found to negatively impact its exports and imports, with the exception of exports for the CCI where no impact is found. However, when using the structural based measure (the Structural Corruption Index), higher corruption actually increases imports and exports. The results further change when the analysis excludes trade between high income countries; in this case, reducing corruption increases both imports and exports when using the CPI but decreases exports and has no effect on imports for the CCI and SCI measures.

Dutt and Traca (2010) also analyse the impact of corruption on bilateral trade using a corruption-augmented gravity model. They find that corruption negatively impacts trade in the majority of cases, but with the qualification that in high-tariff environments corruption is trade enhancing.

Public Sector Channels
Corruption can adversely impact the provision and quality of public services by: reducing available resources for public services (through lower tax returns, siphoning off of expenditure), consuming public resources to tackle corruption that could be used for other purposes and diverting resources towards less productive uses e.g. to areas of public expenditure where it is easier to commit fraud etc. Secondly, it can act as a barrier to access to public services for those groups (e.g. low income groups) which services are targeted at.
All these factors can distort the allocation of public resources with consequences for long term growth e.g. restricting improvements in human capital (education), health and public infrastructure.

Finally, although not limited to channels through the public sector, corruption may drive higher income inequality by reducing the progressive nature of the tax system, distorting expenditure away from public goods that disproportionately benefit low-income groups and allowing higher income/wealth groups to disproportionately influence public policy generally.
For example, Gupta et al. (1998) find that corruption negatively impacts both income inequality and absolute poverty:
- a 1 point increase (reduction in corruption) on the 0-10 CPI scale reduces the GINI co-efficient by 0.02 points[34]
- a 1 percentage point reduction in corruption growth (as measured by the CPI) increases the annual income growth rate of the lowest income quintile by 6 percentage points

Corruption can therefore influence growth through an inequality channel to the extent that inequality holds back economic growth e.g. a rise in inequality of 3 Gini points is expected to lower economic growth by 0.35% per year for 25 years.[35]
[35] OECD. (2014). Focus on Inequality and Growth. Accessed 30 July 2018 from https://www.oecd.org/social/Focus-Inequality-and-Growth-2014.pdf

Econometric Studies of Impact of Corruption on Growth

In addition to studies of specific channels, econometric studies have attempted to measure the overall impact of corruption levels on economic growth rates. These typically use measures of perceived corruption, taking into account other factors likely to impact growth. A key issue is addressing “two-way causality” (i.e. growth plausibly influences corruption levels as well as vice versa) so instrumental variable techniques have to be employed to isolate corruption’s impact on growth. Broadly, these studies find that lower corruption levels, as measured by perceived corruption, are associated with higher economic growth rates.

On the basis of published academic papers, an assumption is used that a 1 point increase in the CPI increases real GDP growth by +0.55 percentage points, notwithstanding Aidt et al’s qualification regarding institutions (discussed below). Importantly, these studies used data from the CPI when it was measured on a 0 to 10 scale (pre-2012) rather than a 0 to 100 scale so this approximately equates to a +0.055 percentage point increase in growth for a one unit increase on the 0 to 100 scale.

GDP Method - Estimating Primary Benefits

Bringing the assumed impact of the GACP on corruption levels and the results of these corruption-growth empirical studies together enables the estimation of potential costs and primary benefits of the programme under the improved economic growth method.

The World Bank databank data on annual GDP in the target countries from 2013-2016 at purchasing power parity has been used for this purpose. This data, in 2011 international US$ price, has been updated to 2017 prices using the implicit deflator in the World Bank data; annual GDP at PPP is also available in nominal prices in the World Bank dataset. We then used historic real GDP growth rates over the past twenty-year period[36] for the target countries to project their GDP forward over the ten-year appraisal period from 2017/18 to 2026/27, minus the GACP (the counterfactual).
[36] For each target country average annual growth rates over the last 5, 10, 15 and 20 years were calculated and the minimum positive growth rate from these four possible values was used, for conservatism. The intention of this exercise was to estimate long-run growth rates for the countries, whilst also accounting for the possibility of slow-down in growth rates over time e.g. due to convergence.

Although they are not perfect as international comparators of livings standards, GDP values at purchasing power parity have been used as a more appropriate measure of impact on living standards because they take into account differences in the cost of living across different countries. GDP values measured at market exchange rates tend to overstate the cost of living for developing countries; e.g. the collective GDP of the eight target countries in 2017 using market exchange rates was $3.9tn. compared to $10.4tn. using purchasing power parity adjusted exchange rates.

This exercise was then repeated but for the GACP scenario. This assumed an uplift in country growth rates in 2025/26 and 2026/27 in line with a +0.1 increase in the CPI score (strictly: a +0.01 increase in the old 0-10 scale score) and the various assumptions from the empirical studies described above. Typically this calculation elevates growth rates by 0.01 percentage points compared to the counterfactual in these years i.e. a small impact on growth rates.
Growth effects due to the GACP are assumed to occur from 2025/26 onwards. The basis of this assumption is Lucic et al. (2016) who found the strongest causal impact from corruption to growth tends to occur with a six to ten year time lag. This implicitly assumes that the GACP will impact corruption levels from around 2020 onwards.

The elevated growth rate benefit has been assumed to last until at least the end of the appraisal period in 2026/27. For example, Aidt et. al’s short-run growth rate impacts were measured over a five year period (1995-2000). Overall, this means the last two years of the ten year appraisal period (2017/18 – 2026/27) experience an uplift in the growth rate.

The GDP path under the counterfactual scenario of ‘no GACP’ was subtracted from that under the GACP to estimate the additional GDP in the target countries over the appraisal period.

Two further adjustments were made:
- Success Factor: First the estimated additional GDP was multiplied by an overall success factor of 68% for the GACP. This reflects project leads’ estimates of the likelihood of success of delivering their projects’ intended outcomes given delivery and country risks. Given the very limited evaluation evidence for anti-corruption projects it has not been possible to base this upon studies of past initiatives. Estimates ranged from 50-75% with the 68% a weighted average by budget share.
- Attribution Rate: Secondly, the benefits were further multiplied by a 50% ‘attribution rate’ factor. This reflects the fact that some input of resources may be required by target countries themselves in order to realise reductions in corruption e.g. changes to legislation or incremental training of officials that would not occur under the counterfactual.

Given the difficulty of evidencing these factors, both are tested through sensitivity analysis.

The adjusted benefits were then converted to sterling and discounted to 2017/18 using a discount rate of 10%, a typical discount rate for low/middle income contexts.

Table 7 - Primary Benefits of GACP – GDP Method
Paper(s) Analysis Based Upon	Relationship Between Perceived Corruption Level and Growth*	Total Cost (PV) - £m	Total Benefits (PV) - £m	Net Present Value - £m	Benefit Cost Ratio
Aidt et al. (2008): countries with “bad” quality institutions	0	41.8	-	-41.8	0 : 1
Mo (2001) / Aidt et al. (2008): countries with “good” quality institutions, Ugur & Dasgupta (2011)	+0.055% points growth for a +1 point increase in the CPI*	41.8	232	190	5.5 : 1

* On the current 0-100 CPI scale. Estimates in the studies were based upon CPI values when it used a 0-10 scale i.e. +0.55% points growth for a 1 point increase in the 0-10 scale CPI. Benefits and costs figures are in 2017/18 prices, both discounted to 2017/18.
This indicates that if the GACP were to reduce corruption levels (taking an improvement in the average CPI score of 0.1 as a measure of the size of impact), it could yield a net primary benefit of between approximately -£42m (i.e. no primary benefit) and +£190m.

GDP Method - Sensitivity Analysis
Broadly, this indicates the benefits are reasonably resilient to changes in the key assumptions underpinning this method. For example, the assumed change in CPI scores can fall to a fifth of its assumed value before benefits fall below costs. Also, benefits would still outweigh costs if the benefits were delayed by one year or if the success or attribution rates fell to one fifth of their assumed value.
Trade Method – Estimating Primary Benefits
For the trade method, the primary benefits are estimated as the improvement in the target countries’ trade balances due to reducing corruption using the results from Gil et al (2017) – see literature discussion above.

Imports and exports for each of the target countries were taken from the World Bank databank for 2016 in 2010 constant $ prices and converted to 2017 $ prices using a US GDP deflator series[37].
[37] Source: US Bureau of Economic Analysis; Table 1.1.9. Implicit Price Deflators for Gross Domestic Product

Imports and exports for each target country were then projected out to 2026/27 absent the GACP intervention in the following ways:
- Imports: The projected GDP growth rates for the target countries (used in the counterfactual scenarios in the GDP Method) were each multiplied by an income elasticity of demand figure of 0.67[38] to produce an estimated annual growth rate of imports for each country over the appraisal period. Imports were then projected over the appraisal period using the 2016 import values and the estimated import growth rate.
  [38] This is calculated as the average of the long-run income elasticities of imports for the BRICs (0.74) and Middle Income Asia (0.60) in Table 10 of: https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/252490/bis-13-1262-long-run-income-elasticities-REVISED-1.pdf
- Exports: A long-run world GDP growth rate of 2.5% was calculated as the lowest average value of the last 5, 10, 15 and 20 years global growth rates taken from the World Bank databank. This was then multiplied by a global trade income elasticity (1.5) to give an estimate of export growth rates for the target countries over the appraisal period. Exports were then projected over the appraisal period using the 2016 import values and the estimated export growth rate.

To calculate the projected imports and exports for each target country under the intervention scenario (GACP), we applied the results from Table 5 in Gil et al. (2017) to the counterfactual projections of imports and exports in 2025/26 and 2026/27. We do not have evidence for the timing of impact for a change in corruption levels on trade flows so assumed the impact occurs in the last two years of the appraisal period as with the GDP method.

Table 9 – Selected results from Table 5 of Gil et al. (2017). Bilateral trade exclude those between high income countries only
Corruption Indicator	Impact of a 1 unit increase in corruption indicator on exports	Impact of a 1 unit increase in corruption indicator on imports
Corruption Perception Index	+5.6%	+2.6%
Control of Corruption Index	-9.5%	+2.8%*
Structural Corruption Index	-59.6%	-33.3%*

* Not significant at 10%Note the CPI is on a 0-10 scale with 10 being lowest corruption; CCI is on a -2.5 to +2.5 scale with +2.5 being lowest corruption and the SCI values in the sample range from -0.35 to +0.9.

For the CPI this analysis assumed an increase of +0.1 on the 0-100 scale (or approximately +0.01 on the 0-10 scale) as before. For the CCI and SCI measures we assume a proportionate change given the differences in scales/ranges of values vs. the CPI (i.e. +0.005 for the CCI and +0.001 for the SCI), though this is crude as the distribution of scores will not be the same across the different indices.

The difference in imports, exports and the trade balance between the intervention and counterfactual scenarios was then calculated and converted to GBP. The same success factor (68%) and attribution rate (50%) as used in the GDP method were then applied to the trade balance change to produce the undiscounted time series of primary benefits. These were then discounted to 2017/18 using a discount rate of 10% as before.

Table 10 - Primary Benefits of GACP - Trade method
Paper(s) Analysis Based Upon	Total Cost (PV) - £m	Total Benefits (PV) - £m	Net Present Value - £m	Benefit Cost Ratio
Gil et al (2017) – CPI	41.9	161	119	3.8 : 1
Gil et al (2017) – CCI	41.9	-220	-262	-5.3 : 1
Gil et al (2017) – SCI	41.9	-276	-318	- 6.6 : 1

This indicates that, using the CPI measure, the trade balances of the target countries would be projected to improve as a result of the GACP reducing corruption; this measure gives support to the ‘extortion’ hypothesis for corruption. Using the other measures however, suggests that reducing corruption would worsen the projected trade balances (by reducing exports) as the results from Gil et al. here suggest that ‘evasion’ effects dominate ‘extortion’ effects.

Trade Method – Sensitivity Analysis
Notwithstanding the uncertainty over the impact of changing corruption on trade from using different measures of corruption, these results indicate the primary benefits using the CPI measure are reasonably resilient to changes in the key assumptions underpinning this method.

Health Method – Estimating Primary Benefits
The health method draws upon a key result from Gupta et al. (2008) which found that a reduction in corruption levels equivalent to a one point increase in the CPI (on the 0-10 scale) reduces the child mortality rate[39] by 10%. Applying this result, the health method estimates the benefit of the GACP as the value of the life years added through reduced child mortality.

First the projected number of child deaths over the ten-year appraisal period was calculated for each country using World Bank projections of target country populations, live birth rates (per 1000 population) and child mortality rates (per 1000 live births). This forms the counterfactual scenario.

The World Bank projects population numbers over the whole of the appraisal period. Live birth rates data is available up to 2016 and the World Bank provides projections in 2020 and 2025; these are typically on a downward trend, as expected for growing middle-income economies. We have used linear interpolation/extrapolation to generate projections between these points and for 2026. Child mortality rates are only available up to 2016 but inspection indicates these are also on a clear downwards trend though not usually in a linear fashion; we have used exponential/logarithmic lines of best fit for data over 2000-2016 to extrapolate trends out to 2026 for this variable.

This exercise was then repeated but applying the result from Gupta et al. in conjunction with the assumed impact of the GACP on the CPI. Again, in the absence of evidence to inform timing of impact this was assumed to be in the last two years of the appraisal period only i.e. ~5 years after the implementation of the GACP. This is a difficult assumption to substantiate so a lag is assumed for conservatism e.g. even with reduced corruption levels it may take some time for resources to be re-allocated across public services.

The number of child deaths avoided as a result of the intervention was then calculated as the difference between the intervention and counterfactual scenarios. This amounts to approximately 2,250 deaths avoided across the eight target countries in 2025/26 and 2026/27.

The additional number of ‘life years’ realised as a result of the avoided child deaths was then calculated by subtracting 5[40] from the projected life expectancy in each target country in 2025/26-2026/27 and multiplying this by the number of avoided child deaths. The approximate projected life expectancy across the target countries in 2025/26 and 2026/27 range from 57 (Nigeria) to 79 (Mexico) i.e. the additional number of life years per mortality avoided ranges from approximately 52-74 across the target countries.

These life years would be realised over the next 52-74 years from 2025/26-2026/27 onwards so are discounted to those years using a 3% discount rate[41]. This also has the implication that the appraisal period under this method is effectively much longer than the ten years under the GDP and trade methods, though we do not include the life year benefits associated with any avoided mortality impact beyond 2026/27[42].

For each country, the discounted number of additional life years was then monetised by multiplying by 1.5x the projected GDP per capita in 2025/26 and 2026/27 (in 2017 prices)[43]. In health economic appraisals 1.5 – 2x per capita incomes are typically used to value additional life years. Projected GDP per capita values were based upon 2016 values and the application of an estimated long-run per capita growth rate, analogous to the methods used in the GDP and trade methods for GDP growth.
[43] See Stenberg K, Axelson H, Sheehan P, Anderson I, Gulmezoglu AM, Temmerman M, et al. Advancing social and economic development by investing in women's and children's health: a new Global Investment Framework. Lancet. 2014;383(9925):1333-54. Epub 2013/11/23

The same success factor and attribution rates (as before) were then applied to the monetised additional life years and a discount factor of 10% applied to find the present value of the primary benefits in 2017/18.

Table 12 - Primary Benefits of GACP - Health method
Paper(s) Analysis Based Upon	Relationship Between Perceived Corruption Level and Heath	Total Cost (PV) - £m	Total Benefits (PV) - £m	Net Present Value - £m	Benefit Cost Ratio
Gupta at al. (2008)	A 1 unit increase in the CPI (0-10 point scale) reduces child mortality rate (children under age of 5 that die per 1000 live births) by 10%	41.9	32.5	-9.4	0.8 : 1

This indicates the GACP benefits under this measure falls short of programme costs with a benefit-cost ratio of 0.8: 1. However, this method likely understates the benefits from reducing corruption via the public services channel. A key point is that it would be expected that the impact on health service provision would persist for longer than 2026/27 or benefits may be realised earlier than assumed. Although reallocation of public expenditure towards health could occur with a lag, other effects of reduced corruption e.g. tax receipts could have a more immediate benefit. Sensitivity analysis indicates that 1-2 additional years of benefits (e.g. if benefits were realised sooner than assumed) would ensure the programme breaks-even under this method.

Further, this analysis only focuses on one sector of public services where provision is typically impaired by corruption so there would likely be wider benefits than impact on health. For example, Gupta et al. also find that reducing corruption levels reduces drop-out rates in primary education and improves literacy rates, which would be expected to have longer term benefits in terms of economic returns to education.

Health Method – Sensitivity Analysis
Given the benefit-cost ratio estimated for this method, the GACP is much less resilient to a worsening of key assumptions here. For example, the assumed impact on corruption levels would need to be higher than assumed (+0.12 vs +0.10) under the other methods for the programme to deliver VfM under this method.

Poverty and Income Inequality Impacts of GACP
As indicated in the section on corruption and growth above, reducing corruption levels reduces income inequality and improves income growth for low income groups.

First, as discussed above, economic growth is an important driver of absolute poverty reduction, so - to the extent that corruption inhibits growth - it will impact upon the income growth of the poorest. Second, corruption can reduce the impact of progressive tax and transfer policies if higher income groups are able to evade tax obligations. Third, corruption can result in under-investment in social programmes/public services that low income groups particularly benefit from and/or create barriers to access for those groups. Fourth, corruption can perpetuate unequal distributions of wealth (e.g. wealthier groups are able to influence public policy in their favour) with the result that low income/wealth groups lack collateral to invest in education or start their own businesses as a means to escape poverty.

Applying Gupta et al.’s findings to our assumed change in the CPI due to the GACP, we can infer that the GACP would potentially increase annual income growth for the poorest fifth income group in each programme country by between 0.4 and 0.8 percentage points, a significant difference. The impact on country GINI co-efficients would be -0.0001 on a GINI scale of 0-1, a very small change.
### Secondary benefits

The secondary benefits of the GACP have been estimated as the uplift in UK exports to the target countries over the appraisal period. The key transmission channels through which a reduction in corruption levels could be expected to result in increased trade in the target countries and export opportunities for the UK are:
1. Direct benefits: Greater openness to trade (OECD, 2013) as corrupt bureaucrats and politicians can no longer maintain a regulatory environment to extract rents, and foreign businesses are no longer put off by corruption (for example U4, 2014, or TI, 2014). A greater willingness of international firms to export to or invest in countries as a result of lower corruption improves competition - there is freer entry of firms as the “playing field” is levelled (OECD, 2010). This channel should improve the UK’s market share of country imports as UK firms are more willing to do business in the target countries.
2. Indirect benefits: Increased demand for imports as reducing corruption increases the size of the economy through the various channels indicated in Figure 1. This is the corollary impact of the uplift in target country GDP, calculated for the primary benefits. It should benefit all exporting countries to the target countries, including the UK.

Secondary Benefits Estimation

The indirect benefits have been estimated as an additional step to the Trade Method for calculating the Primary Benefits. In that method the value of country imports was projected over the appraisal period with and without the GACP intervention, using the CPI result from Gil et al. (2017).
To estimate the UK’s share of this uplift in imports, the UK’s current share of each target country’s imports was calculated using ONS Pink Book (2018) data for total UK exports to the countries[44] in conjunction with the World Bank data on country imports. The average import share over 2013-2017 was calculated and assumed to apply over the appraisal period.
[44] The exceptions to this were Kenya and Nigeria. UK export data to these countries is only available up to 2015 from ONS Pink Book 2016. 2016 and 2017 exports to these countries were estimated by increasing 2015 exports in line with estimated import demand growth in 2016 and 2017. Import demand growth was based upon these countries’ GDP growth 2016 and 2017 multiplied by the income elasticity of demand used for middle-income countries in the Trade method analysis.

The same success and attribution factors used in the primary benefits analysis were then applied to the estimated uplift in exports and the benefits discounted to 2017/18 using the UK social discount rate of 3.5%.

The estimated secondary benefits of the GACP are set out in Table 14Table 14. These are very low in absolute terms which is chiefly due to the fact that the UK’s share of imports in the target countries is only 1.7% on average.

Table 14 - Secondary Benefits of GACP
Paper(s) Analysis Based Upon	Total Cost (PV) - £m	Total Benefits (PV) - £m	Net Present Value - £m	Benefit Cost Ratio
Gil et al. (2017)	41.9	2.7	-39.2	0.07 : 1

There are several reasons why this analysis could understate the secondary benefits from the programme however.
First, the empirical study upon which the method is based is based upon a cross-section of 139 countries and so captures the “average” impact of changes in corruption levels on trade flows, rather than just UK bilateral trade. Given the relatively risk-averse nature of UK businesses for operating in corrupt business environments, the assumed impact on UK exports could be understated as a result.
Second, this method only accounts for trade flows and not any additional income from a potential uplift in UK foreign direct investment in the target countries. As with trade flows, studies are mixed in terms of whether corruption hinders or helps FDI but again, the former might be more likely in the case of UK outward FDI given risk-averseness.
Third, the GACP has a strategic role to play within the Prosperity Fund and HMG prosperity initiatives more widely; by reducing corruption levels and sending a signal about HMG expectations for ‘doing business’ overseas. This programme will act as an enabler and amplifier of secondary benefits across the Prosperity Fund by providing an improved business climate for UK business to trade. In addition, the programme will provide ‘soft power’ benefits from the UK being seen as a driving force of ‘clean business’ as a result of this programme being seen to provide targeted bilateral support and also wider support to strengthen the multilateral architecture focused on addressing corruption.
These wider benefits such as Foreign Direct Investment (FDI) will be monitored and analysed through the programme’s MREL component.

Risks
The programme, as a whole, is assessed as being medium/high risk. This is a direct result of the high-return ambitious nature of the programme in which it is seeking to achieve impacts with external factors which are not within the direct control of the programme.

Independent economic analysis[45] indicates there are great difficulties in measuring corruption, though broad trends can nevertheless be seen in country experiences. Even more challenging is the task of measuring the impact of specific anti-corruption interventions and the report notes that when applied in isolation over a short time, interventions have had limited success, which is why the programme has been designed to adopt a longer term multi-pronged approach. The report concludes “Both primary benefits and secondary benefits (improved opportunities for UK trade and investment) can reasonably be expected, though they remain hard to measure with any precision”. Although the evidence base to support the linkages between project activity and reduced corruption, and the subsequent reduction in poverty and inequality, is not fully robust, it is generally acknowledged that corruption is a major constraint to economic growth and prosperity[46].
[45] Landell Mills Report Economic Analysis to Support Global Anti-Corruption Programme: Hare, P and Stoneman R.
[46] Clean Business is Good Business, joint publication by the International Chamber of Commerce, Transparency International, the United Nations Global Compact and the World Economic Forum Partnering Against Corruption Initiative (PACI); and Cost of corruption in developing countries – how effectively is aid being spent?, European Union, 2015
Therefore, to address this risk, the programme has been designed to enable adaptive programming to take place. Each project can be scaled up or down as required, typically by altering the countries covered. The contracts and MoUs with suppliers all include a requirement for an annual report to be produced with monies being allocated annually, enabling the programme to adapt to changing situations. If, for whatever reason, a project is underperforming, the budget can be fully or partially reallocated to other projects, where expected impacts will be higher. This process will be managed by the programme management team as part of their ongoing monitoring role with decisions taken by the Strategic Board/SRO. Decisions would be made as part of the annual review process or out of the review cycle by exception. The deliberately designed project structure of the programme means there are multiple ways to adapt the programme to maximise impact and value for money.

In addition, this programme has been explicitly designed (e.g. through the OECD Anti-Corruption Hub) to help address the intelligence gap over the effectiveness of anti-corruption initiatives. This will both reduce any risk to the delivery of this programme by enabling evidence-based adaptive programming decisions and more widely promote global anti-corruption activity.
Corruption is a deeply engrained phenomenon that requires a focused, long term commitment to tackling it from a wide range of players. Given that some of the most highly corrupt people are regularly in positions of power, the challenges are to strengthen the political resolve of heads of government to pursue an anti-corruption agenda (which often enjoys public support); and to build the technical capacity and policies of the institutions to be able to effectively prevent corruption and prosecute those involved when it happens. Changes in governments or policy shifts in host countries could effectively destroy efforts to tackle corruption. The programme management team in conjunction with Posts will actively monitor programme risks, and adaptive programme decisions made as appropriate.

Coordination between government departments and international organisations is challenging but will be necessary to deliver the aims of the GACP. The programme has been designed with this as an integral element with, for example, extensive consultation with multilateral organisations and Posts.
# Sustainability
Much of the GACP is developed with the intention of raising the international bar and creating champions within the international system and in the target countries who will continue to build on these initiatives even when the UK no longer funds them. In addition, once implemented, many of these projects will be self-sustaining, as they have been designed to deliver capacity building and training that establishes a core that can be built upon locally. Cross Whitehall officials will continue to take forward this agenda internationally and indeed much of this work supports longer-term policy efforts that have pre-dated the programme.

Commercial Case

This is a large programme, containing a number of interrelated projects being implemented across multiple countries. The cross-Whitehall Steering Group has driven the development of the delivery and commercial model; designed to maximise the impact of the programme, ensure VfM and mitigate risks.
# Market engagement
Market engagement has been undertaken to assess the capability, capacity and interest of the market to deliver the programme. This has covered UK government departments, multilateral organisations and commercial suppliers and included the running of transition projects as part of year one of the programme. It is clear from the exercise that when viewing the market as a whole there is market capability, capacity and interest in delivering the programme. However no one group has the required portfolio of technical expertise, capacity or geographic footprint to deliver the entire programme. Consequently a multi-partner delivery approach has been chosen.
# Route to market options
The cross-Whitehall Steering Group considered a number of delivery organisation options for each project of the programme using relevant assessment criteria. The results are summarised below.

There are three key options: using commercial suppliers – Option ‘A’; using OGDs and multilateral organisations – Option ‘B’; and using a combination of OGDs, multilateral organisations and commercial supplier(s) – Option ‘C’. Each option was assessed against impact (both primary and secondary), deliverability and cost.
Option ‘A’: delivering the programme through commercial suppliers and NGOs would entail a competitive process to identify the best-placed private sector organisation to implement the programme.
Impact: since this approach would increase capacity in targeted countries and help focus on the most effective reforms, it is likely to have positive outcomes as shown in the scoring below. Particular focus on priority sectors for the UK would further strengthen prospects for secondary benefits to the UK. However, overall impact could be undermined in some focal countries by the extent of engagement with the relevant authorities and perceived credibility of commercial suppliers. In addition to capability, anti-corruption reforms require long-term commitment and sustained effort, which many commercial suppliers may struggle to demonstrate in some of the target countries.

Deliverability: political and institutional barriers are major risks to delivery. In addition to the institutional constraints already mentioned, government policy and reform plans are often subject to the influence of vested interests. Groups tend to lobby against key reforms or encourage more protection for sectors and businesses they represent.
Successful delivery is therefore contingent on continued commitment to reform, which requires effective engagement and credibility. Supported by UK lobbying efforts, commercial suppliers are expected to have a reasonable level of engagement, but this is unlikely to have the breadth and depth enjoyed by multilaterals such as the World Bank, OECD and the UN across the target countries. A commercial approach could work in the majority of the cases, but in some cases and contexts, credibility may be an issue, which in turn could impair the delivery and sustainability of reforms. A single commercial supplier is unlikely to have all the necessary skills and access to operate in all our priority countries and therefore achieve ‘global’ level impact. The one area where a commercial supplier would be unable to deliver would be the IACCC project because of the sensitive nature of the intelligence involved in the delivery.

Cost: Commercial suppliers typically command management fees of a similar magnitude as multilaterals but greater than OGDs.

Option ‘B’: partnership with OGDs and multilateral organisations as delivery partners, building on their track record, expertise, credibility and deep engagement with national governments. Notably, the UNODC own the UNCAC and the OECD own the International Anti-Bribery Convention. This option takes account of the Independent Commission for Aid Impact (ICAI) reports on the effectiveness of DFID engagement with multilateral agencies (e.g. World Bank) to achieve impact. ICAI found that the interventions reviewed performed well and met most of the criteria for effectiveness and VfM.

Impact: OGDs and multilaterals have the majority of the expertise, track record and global coverage to ensure credibility with recipient governments and scope for continued engagement which is essential for the delivery of sustainable reforms. Using the UN, OECD or World Bank as delivery partners brings legitimacy and authority to the projects and they are the right partners to tackle transboundary issues, particularly given the political sensitivities surrounding corruption. However, OGDs and multilaterals lack the expertise to address the ‘demand side’ of corruption, using innovative techniques based on recent developments in behavioural science that commercial suppliers would bring. This would therefore limit the potential impact of this option.
By partnering with a multilateral institution such as the World Bank, UN and OECD with a credible record of supporting anti-corruption reforms, the programme would be more effective in drawing first hand lessons from recent reform efforts to develop more tailored interventions. The likelihood of significant impact, due to the factors above, is reflected in the scoring below for primary impact. The relatively lower score for secondary benefits under this option reflects the fact that multilaterals would not be mandated to identify or support reforms that are focused in the UK’s interest. However, the programme will deliver benefits to focal countries that align with UK interests.

Deliverability: ODGs and multilateral partners possess the global reach and majority of the expertise necessary for successful delivery given their credibility and depth of engagement in the selected focal countries. Multilaterals have all the necessary skills and access to operate in all our priority countries, and therefore create a ‘global’ level impact. However, OGDs and multilaterals lack the expertise to address the ‘demand side’ of corruption, using innovative techniques based on recent developments in behavioural science that commercial suppliers bring. This would therefore limit the ability of this option to fully deliver the scope of this programme.

Cost: Multilateral organisations typically command management fees of a similar magnitude as commercial organisations but greater than OGDs.

Option ‘C’: partnership with OGDs, multilateral organisations and commercial supplier(s) as the delivery partners, building on their track record, expertise, credibility and deep engagement with national governments. Notably, the UNODC own the UNCAC and the OECD own the International Anti-Bribery Convention. This option takes account of the Independent Commission for Aid Impact (ICAI) reports on the effectiveness of DFID engagement with multilateral agencies (e.g. World Bank) to achieve impact. ICAI found that the interventions that were reviewed performed well and met most of the criteria for effectiveness and VfM. This option is complemented by both commercial support in the area of behavioural science (as the expertise does not exist in OGDs or multilaterals), and surge capacity in the area of digital marketplaces (as there is limited capacity in OGDs or multilaterals).

Impact: OGDs and multilaterals have the expertise, track record and global coverage to ensure credibility with recipient governments and scope for continued engagement which is essential for the delivery of sustainable reforms. Using the UN, OECD or World Bank as delivery partners brings legitimacy and authority to the projects and they are the right partners to tackle transboundary issues, particularly given the political sensitivities surrounding corruption. Commercial supplier(s) would bring expertise to address the ‘demand side’ of corruption and would complement the ‘supply side’ focus of OGDs and multilaterals, using innovative techniques based on recent developments in behavioural science.
By partnering with a multilateral institution such as the World Bank, UN and OECD with a credible record of supporting anti-corruption reforms, the programme would be more responsive by drawing first hand lessons from recent reform efforts to develop more tailored interventions. The likelihood of significant impact due to the factors above is reflected in the scoring below for primary impact. The relatively lower score for secondary benefits under this option reflects the fact that multilaterals would not be mandated to identify or support reforms that are solely in the UK’s interest. However, the programme will deliver benefits to focal countries that align with UK interests.

Deliverability: OGDs and multilaterals possess the global reach and the majority of the expertise necessary for successful delivery given their credibility and depth of engagement in the selected focal countries. Multilaterals have all the necessary skills and access to operate in all our priority countries, and therefore create a ‘global’ level impact. Commercial supplier(s) would complement OGDs and multilaterals by bringing the required behavioural science expertise required to deliver the whole programme’s portfolio.

Cost: Multilateral organisations and commercial organisations typically command management fees of a similar magnitude but greater than OGDs.
The summary scores are set out in the table below.
Options	Primary impact (35%)	Secondary impact / (25%)	Deliverability / (20%)	Cost / (20%)	Total Weighted Score
A – delivery through commercial contracts	4	4	4	3	3.8
B – delivery in through OGDs and multilaterals	4.5	3	4	4	3.9
C – delivery through a combination of OGDs, multilaterals and commercial supplier(s)	5	3.5	5	4	4.4

Note – options are scored on a scale of 0-5, with each criterion weighted as shown to emphasise the primary purpose and the relative importance of the respective criteria in achieving the programme objectives. 0 indicates the absence of effect while 5 shows that an option fully meets the criteria.
Therefore, based on the above assessment, it is recommended that the most appropriate delivery model is option ‘C’, a combination of OGDs, multilateral and a commercial supplier(s). This solution will encompass a ‘best of breed’ blend of established HMG expertise and experience; leading multilateral organisations working globally to address corruption; and innovative capability from commercial suppliers.
# Managing performance and value for money

Managing performance and VfM will be assessed against the following general principles:
- Economy (optimising costs and spending)
- Efficiency (insuring thorough and efficient delivery of each project)
- Effectiveness (maximising impact for each project)
- Equity (insuring equal and inclusive output for each project)

FCO, DFID, NCA, HMT and GDS will use their respective management, assurance, and procurement processes and systems to ensure results and good VfM are achieved.
Each project will have an assigned project manager within the delivery department who will be accountable for ensuring sound financial management of their project.
Where implementing partners are delivering projects for the lead department, MoUs/contracts will adhere to best practice and make provisions for flexibility and adaptability appropriate to the project.

Implementing partners will be required to submit regular progress reports setting out progress against plans, KPIs, finances, issues, risks, benefits, communications, scope and lessons. This will include delivery on Gender Equality Act compliance and inclusion components. This will feed into the formal governance arrangements (see management case) and includes the requirement of each delivery partner to produce a formal annual report document.
Progress will be monitored through regular meetings and frequent interactions with implementing partners. HMG’s London-based advisors and programme staff will be in regular contact with DFID Country Offices and UK Embassies/High Commissions in recipient countries to keep up to date with progress on the ground, and will plan visits to recipient countries to monitor progress. Implementing partners’ monitoring and reporting of progress will also be supplemented and verified with regular contact and review from HMG staff in-country. Funding will be provided annually with subsequent future yearly funding dependent on satisfactory delivery during the previous year.
In addition, independent progress reviews and MREL contractor evaluations will be commissioned, as needed, to ensure that lessons and recommendations are captured in a timely manner to support adaptive programming decisions (see Management Case for further information).
At the programme level, annual reviews will be undertaken. Implementing partners will be required to feed into and support this process. This will include verifying the link between project outputs and programme outcomes, and ensuring that leading practice from across the Prosperity Fund, Posts, HMG and multilaterals is built on.
# Contract period
The majority of agreements will be for between three and four years. While there is currently no indication that funding will be required beyond the end dates, in order to maintain future flexibility, an option to extend will be included in the arrangements. Arrangements with delivery partners will be reviewed annually. This will include funding being agreed on an annual basis and break clauses being included within our agreements, to allow the FCO/OGDs to terminate agreements or adapt as required. Clauses will also be included to ensure that delivery partners undertake a managed exit and that the sustainability of project outputs is maximised.
# Risk transfer and management
A mixed delivery model builds inherent complexity into the programme in terms of commercial risk. The following risk transfer matrices sets out risk ownership for all key commercial categories.

Risk ownership between government departments will be defined in an MoU, and governed across the programme in a risk register owned by the Strategic Board (see Management Case). For risks set out below, those owned by the lead department reflect the FCO transferring responsibility for mitigating that risk to a programme partner; for shared risks both the FCO and lead department will be responsible for risk management.

Risk Category		Non-FCO Owned Projects
	FCO	NCA	HMT	DFID	GDS	Shared
1. Design risks		X	X	X	X
2. Implementation risks		X	X	X	X
3. Performance risks		X	X	X	X
4. Control risks						X
5. Financing risks		X	X	X	X
6. Technology risks		X	X	X	X
7. Termination risks						X
8. Legislative risks						X
9. Commercial risks						X

Risk Category		FCO Owned Projects
	FCO	BI	UN	WBG	OECD	Shared
1. Design risks						X
2. Implementation risks		X	X	X	X
3. Performance risks		X	X	X	X
4. Control risks						X
5. Financing risks						X
6. Technology risks		X	X	X	X
7. Termination risks						X
8. Legislative risks						X
9. Commercial risks						X

# Commercial risks
Risk	Description	Mitigating Actions
Poorly defined KPIs and required outcomes (prior to full programme approval)	Inability to specify meaningful KPIs and outputs/outcomes in the agreement could lead to: poor understanding of likelihood of successful delivery; weak mechanism for ensuring satisfactory performance; and ineffectiveness of the output-based funding structure	Draw on best practice across HMG programmes with a common approach / Utilise the MREL contractor and the FCO PF PST expertise to support the development of appropriate programme measures that can be included as KPIs in agreements / Ensure sufficient flexibility in the contract/MoU and programming approach to enable review and refinement of future years’ KPIs and required outcomes
Delivery partner effectiveness	Delivery partners do not deliver the required projects and associated outputs	Close partnership on developing the programme and designing projects to ensure there is realistic ambition and understanding of HMG expectations / Ensure contract/MoUs include well-defined output measures (including KPIs) and associated payment points / Delivery partners will be actively managed by the lead department and overseen locally by Posts as appropriate / Programme management will include quality assurance of outputs and deliverables / Robust and continuous MREL practices
Delivery Partner reliability	Delivery partner withdraws from the project	Close work with delivery partner teams / Monitor wider developments for early signs of change that might give rise to withdrawal / Maintain knowledge of potential alternative partners
Legal challenge	Legal challenge from private sector organisations that would have tendered for the work	Ensure decision on selected delivery route is well-evidenced, subjected to robust challenge and properly recorded / Ensure input of commercial and legal expertise to business case development
Insufficient flexibility in contract/MoUs	MoUs/contract are insufficiently flexible to allow for adaptive programming and quick, VFM responses to changing requirements.	Define requirements as accurately as possible, be disciplined about changes / Align expectations of what adaptive programming means in practice / Have an agreed mechanism for managing changes to requirements
Fraud	Fraud or misuse of funds by delivery partners	Due diligence of delivery partners before appointment / Annual reports will be required from all delivery partners including financial reporting
Organisational failure	Delivery partner organisational failure e.g. bankruptcy	Due diligence of delivery partners before appointment / Milestone based payments where appropriate / A variety of delivery partners reduces the impact of this risk and potentially enables other partners to scale up
Delivery partner failures	Potential delivery partners either do not submit proposals or there are concerns associated with their proposals	The programme team has actively engaged with this community with a positive response / Potential delivery partners include those who have undertaken transition projects and understand the PF context / Engagement will continue with potential delivery partners

# Summary efficiency, effectiveness, economy and equity

In terms of overall efficiency, effectiveness, economy and equity; the proposed OGD and multilateral delivery partner model is assessed as providing overall medium/high value for money, as set out in the table below.
VfM Factor	High/Medium/Low	Rationale
Efficiency	High	As a result of specifying specific projects with strong HMG oversight
Effectiveness	High	As a result of appointing independent expert partners with strong knowledge of anti-corruption, and including annual reviews and adaptive programming
Economy	Medium	As a result of predominately using multilaterals and breaking the programme into specific projects
Equity	Medium/High	As a result of specifying specific projects with delivery partners required to address high levels of poverty, inequality, exclusion and marginalisation

# FINANCIAL CASE

The purpose of this section is to set out the forecast financial implications of the programme (as set out in the economic case section) and the proposed delivery model (as described in the commercial case).
# Financial expenditure and cost drivers
The main cost across the programme relates to project delivery. The key cost driver items for the programme are set out below, together with their projected cost.
# Programme delivery costs
A summary of programme delivery costs[47], split by project, is as follows:
[47] Note that totals do not always appear to sum correctly due to rounding errors
Project	Delivery Partner	Total Cost	17/18	18/19	19/20	20/21	21/22
Implementing the UNCAC	FCO/UNODC	£8.0m	£0.4m	£0.6m	£2.1m	£2.3m	£2.6m
Improving transparency and addressing bribery	FCO/OECD	£4.0m	£0.5m	£0.3m	£1.0m	£1.0m	£1.2m
IACCC	NCA	£5.1m	£1.2m	£1.3m	£1.3m	£1.3m	-
GFAR	FCO/StAR	£2.0m	£0.4m	£0.1m	£0.6m	£0.6m	£0.3m
Supporting the EITI	DFID/EITI/WORLD BANK	£3.2m	£0.7m	£1.5m	£0.5m	£0.5m	-
Increasing transparency of company beneficial ownership	DFID/WEB FOUNDATION	£2.8m	£0.3m	£1.0m	£1.0m	£0.5m	-
Strengthening AML systems and FATF regional bodies	HMT/FATF	£3.4m	£0.5m	£0.9m	£1.0m	£1.0m	-
Procurement reform and digitisation	GDS	£10.5m	£0.4m	£2.5m	£3.0m	£3.0m	£1.6m
Reducing corruption through behavioural insights	FCO/commercial	£3.0m	£0.1m	£0	£0.9m	£1.0m	£1.0m
TOTAL		£42.0m	£4.6m	£8.3m	£11.4m	£11.1m	£6.7m

The cost projections have been built on bottom-up estimates of the cost of each specific project, informed by the results of scoping studies and using examples of the cost of similar interventions elsewhere. The timing of key payments will be predominately output/deliverable based.

The liability for any increase in delivery costs is with delivery partners for the current scope of work (fixed price). If a requirement arises to scale up a particular project (which would requirement Strategic Board and SRO approval), this would mean that either another project would need to be correspondingly reduced (as part of adaptive programming) or additional PF funding would need to be obtained, in advance, via the Joint Funds Unit.
# HMG management costs

FCO will assume overall responsibility for programme delivery although individual project delivery will be the responsibility of the relevant lead government department for the project. Any use of project-level specialist advisors, third party organisations or any other type of external consultants will be the responsibility of the relevant lead government department and within the limits of funds allocated to the project. The table below sets out the planned management staffing costs comprising FCO, HMT, GDS, and DFID resource costs. Any changes in the management staffing levels will need to be approved by the programme team/SRO and PFDU/JFU as appropriate. The estimates assume an annual increase in salaries of 2% beyond 2017/18. Staffing costs are based on the latest available FCO Full Economic Cost Model or equivalent for OGDs for 2017/18, in line with PFDU guidance. As the programme moves to implementation, the FCO staffing levels (either in London or at Post) may need to flex to effectively manage the complexities of the programme, ensure sufficient scrutiny and manage programme level benefits (rather than just project level outputs) – staffing levels will therefore be kept under review. Set out below is the current best assessment on what will be required to effectively manage the programme during the complex implementation phase.
Roles	2017/18	2018/19	2019/20	2020/21	2021/22	Total
FCO D7 (0.25)	£28,591	£29,163	£29,746	£30,341	£30,948	£148,787
FCO D6	£98,777	£100,753	£102,768	£104,823	£106,919	£514,039
FCO C5	£0	£31,626	£80,647	£82,260	£83,905	£278,437
FCO C4	£0	£27,304	£69,626	£71,018	£72,439	£240,387
FCO C4	£0	£27,304	£69,626	£71,018	£72,439	£240,387
FCO C4	£7,361	£27,304	£69,626	£71,018	£72,439	£247,748
FCO C4	£0	£0	£101,362	£103,664	£105,738	£311,034
DFID A2 (D6)	£0	£30,000	£73,440	£74,869	£0	£178,309
DFID HEO	£0	£20,140	£49,302	£50,289	£0	£119,731
HMT SEO	£16,366	£65,465	£66,774	£68,109	£0	£216,714
GDS	£0	£48,000	£48,000	£48,000	£48,000	£192,000
Total	£151,095	£407,059	£761,185	£775,409	£592,825	£2,687,573

HMG management/administration staffing costs, based on marginal costs (as advised by PFDU), are estimated at 4.6% of the total programme cost.
This will be reviewed following final definitions of specific job specifications. The management/administration staffing requirement will be further reviewed once implementation has started, to ensure that the delivery mode is fit for purpose, given the complexity of the programme. This will ensure staffing costs are reasonable and required to make sure the programme is effectively managed, governed and benefits are realised.
This staffing model allows for a central programme team based in London to actively manage the programmatic and project level risk and issues that will arise during the implementation phase. It also provides approval for a further member of staff to be recruited at a later stage, if the needs of the network require it.
# Accountability
The funds will sit in the FCO after being cascaded from NSC/HMT. The FCO is the Department responsible for spend compliance at the programme level. The funds will be approved by NSC/HMT and FCO in accordance with delegated authority transmitted from Cabinet Office/HMT through FCO PUS. The SRO for the programme is the FCO Head of Global Economic Issues Department. Individual MoUs (or equivalents) will be agreed between the FCO and OGDs, setting out relevant responsibilities and funds will be transferred from the FCO baseline to the OGD baselines. OGDs will be responsible for spend compliance at the project level for the projects they lead.
# Overall affordability
The proposed cost of the programme is £45.1m over the expected lifespan of the programme. An allocation of £45.1m has been made by the Prosperity Fund, subject to approval of this business case. All funds are ODA eligible and there are no contingent liabilities associated with this funding.
There will be no ongoing costs to be covered once this programme has finished, as there are no plans to establish structures with future HMG resource implications under programme design.
# Monitoring, reporting and accounting of expenditure
Programme spend and forecasts will be monitored by the Programme team using FCO financial systems. Budgets will be entered onto the FCO's systems using Hyperion, the FCO's online forecasting tool, at the start of each financial year. The central programme team will use the FCO’s financial dashboard, Oracle Business Intelligence Enterprise Edition (OBIEE) and Hyperion systems to monitor and report spend to date and forecasts. The programme team will work closely with OGDs and delivery partners to ensure accurate forecasting. Accurate forecasting will be managed by ensuring payments follow an agreed schedule defined by clear and time-bounded deliverables and fees. Payment schedules will be monitored monthly, reviewed bi-annually and can be adjusted if necessary. The programme team will follow the financial management processes as laid out in HMT’s guidance document Managing Public Money.

The programme team will formally report spend and forecasts to the relevant teams within the Prosperity Fund hierarchy in line with their financial requirements. An audit trail will be maintained to show all financial decisions taken.

All delivery partners will submit an annual report containing audited accounts for each of the financial years covered by the programme.
## Individual government departments will be responsible for ensuring due diligence in the disbursement of funds, and for taking any action deemed necessary. Where appropriate, full details of forecast future spend by financial year against the annual workplan will be included in annual reports.
# Scaling
The programme will adopt the principle of adaptive programming to ensure that the programme’s impact and VfM are optimised. The programme team will recommend any changes to the programme’s portfolio, including scaling up or down, to the Strategic Board and for subsequent approval by the SRO. Any such changes to the portfolio may have financial implications and these will be thoroughly assessed before any decisions are made, with updates to financial forecasts made after any decisions have been taken.
# Financial and fraud risk assessment
The main financial risk is the time taken to reach implementation with possible ensuing delays in commissioning and delivery resulting in the drawdown being delayed. The timeline is based on a realistic assessment of the time needed to undertake the required commissioning activity and project implementation based on similar historic projects. Timelines and associated expenditure will be monitored carefully by the programme team, with corrective action taken as required. This will involve close working with OGDs and delivery partners. Adaptive programming will be deployed if appropriate.
Several of the countries that this programme will operate in have environments that present a fiduciary and fraud risk. These risks will be mitigated through:
- No funds will be transferred to any partner governments, all payments will be made to appointed delivery partners
- Funds will be disbursed directly by HMG to a limited number of delivery partners
- Due diligence will be carried out on all delivery partners before any payments are made
- Standard government procedures will be followed to verify payments before funds are disbursed
- Delivery partners will be obliged to following similar suitably robust procedures to ensure probity of their supply chain
- OGDs and delivery partners will be required to report a breakdown of costs against key budget lines

A zero-tolerance approach is to be taken to fraud and corruption. The programme may be independently reviewed by the FCO’s Internal Audit Department. OGDs and delivery partners may be subject to a formal FCO audit assessment if appropriate.
With the above plans in place, the financial risk and fraud is assessed as low throughout the programme. The financial and fraud risks will be kept under review by the programme via its governance arrangements.

# MANAGEMENT CASE

This section of the business case describes how the overall programme of work will be implemented and governed. All elements will be subject to the governance outlined within this case.
A programme operating model will be developed, together with operating procedures, which will clearly set out arrangements for the following:
- Governance framework
- Reporting framework
- Dependencies management
- Roles and responsibilities of all parties
- Points of contacts for all parties
- Issue and risk management
- Benefits management
- Financial management
- Quality management
# Programme governance
The overall programme will be led by the FCO and the Senior Responsible Owner (SRO) will be the Head of Global Economic Issues Department. Individual projects will be managed by DFID, NCA, Cabinet Office/GDS, HMT and the FCO itself.
The SRO will report to the Prosperity Fund Portfolio Board and the Prosperity Fund Ministerial Board in accordance with standard Prosperity Fund reporting arrangements. Individual Government Departments will put in place further governance arrangements appropriate to support delivery of the projects they lead within the programme, including the active involvement of HMG at Post and partner governments as appropriate.

A small number of delivery partners will be commissioned by project managers in Government Departments. Individual Government Departments will hold these delivery partners responsible for delivery, with the specific Government Department being accountable for project delivery.

For non-FCO led projects, the FCO will agree separate MoUs with each Government Department (DFID, NCA, GDS and HMT).

The governance arrangements are set out in the diagram below. Although the Home Office/JACU does not have any delivery responsibility within this programme, they will sit on the Strategic Board because they have oversight of HMG’s Anti-Corruption Strategy which will help coordinate linkages across HMG and other donor anti-corruption activity.
The Strategic Board, chaired by the SRO, will provide oversight and strategic direction for the programme, and involve senior level representation from the five lead Government Departments plus the Home Office/JACU. The working level Steering Group, chaired by the FCO Portfolio Manager/Global Head of Anti-Corruption, will ensure operational coherence of the programme, with the members being the lead Government Departments’ project managers.

The Strategic Board will meet on a bi-annual basis. The working level Steering Group will meet on a quarterly basis. In addition, Boards and Working Groups will take place on an as-needed basis to support key decision points.

Efficient decision making and issue resolution will be enabled through clear delineation of remits between the working level Steering Group and Strategic Board, meaning that items do not necessarily need to be tabled at the working level Steering Group before being tabled at the Strategic Board. In addition, escalation direct to the SRO for immediate decision-making can take place at any time as needed.
# Programme staffing
Delivery of the programme’s projects will be undertaken by delivery partners (mainly multilaterals). HMG’s role in the programme will be predominately focused on:
- Government to government engagement
- Supplier management
- Ensuring programme outputs subsequently lead to the longer-term planned outcomes and impacts, both primary and secondary. This includes ensuring a development and inclusive approach is observed throughout the whole programme, specifically, but not limited to, gender equality and inclusion.
The broad split of roles between the FCO and OGDs is set out in the table below (the FCO will also undertake Departmental roles for the projects it directly leads).
Function	Role of FCO	Role of Departments
Leadership	Global leadership across the programme	Global project leadership
Delivery co-ordination and assurance	Global co-ordination and adaptive programming adjustments	Project quality assurance
Architecture	Ensure programme coherence and integrity	Ensure intra-project coherence and integrity, and fit with other relevant Departmental programmes/projects and the overall programme architecture
Benefits	Coordinate programme benefits management, including primary, secondary, gender and poverty	Project benefits management, including primary, secondary, gender and poverty
Finance	Programme budgeting and forecasting	Project budgeting, forecasting, payments and ODA compliance
Communication	Programme communications strategy and programme communications	Project communications strategy, project communications and alignment with the programme communications strategy
Stakeholder Management	Management of programme level stakeholders in the UK and with Posts	Management of project level stakeholders in the UK and internationally
Commercial/ Procurement	Programme level agreements across HMG	Agreements with project level delivery partners
Monitoring and Reporting	Monitoring programme performance and reporting to the Strategic Board, PFDU, JFU, Portfolio and Ministerial Boards	Monitoring project performance and reporting to the core programme team and working level Steering Group
Issue Management	Capture and resolve/escalate programme issues	Capture and resolve/escalate project issues
Risk Management	Identify and manage programme level risks	Identify and manage project level risks
Governance	Own and manage the programme governance framework	Own and manage the project level governance arrangements
Staffing	Appoint and manage the core programme team, and obtain JFU approval for all HMG roles across the programme	Appoint and manage local project team members
Learning and Evaluation	Cross programme learning, programme reviews and evaluation	Project learning and project reviews

The programme will be led by the Programme Manager (FCO D6), supported by a PMO (1 x FCO C5 and 1 x FCO C4), 3 x programme managers (FCO C4), and a Policy Team (1 x FCO C4, 1 x FCO B3) at home; and resources at Post (1 x FCO C4). Individual projects will be led by Project Managers (mix of FCO, DFID, NCA, GDS and HMT staff). In addition, the programme team will access expert support from PFDU, PST and others as required.

# Programme management methodologies
The programme will be managed in accordance with the HMG best practice, following MSP and PRINCE2 principles, including Gateway reviews e.g. the programme underwent an IPA Critical Friend Review in July 2018.
The programme team will be supported by technical experts in the FCO, across Whitehall and the Prosperity Fund MREL contractors in their relevant fields; including communications, social development, inclusive growth, gender equality, economics, conflict sensitivity, security and justice, commercial, secondary benefits, governance and benefits management.

Flexible programming
The programme has been designed to enable adaptive programming to take place. Each project can be scaled up or down if required, typically by altering the countries covered. The contracts and MoUs with suppliers all include a requirement for an annual report to be produced with monies being allocated annually, enabling the programme to adapt to changing situations. If for whatever reason a project is underperforming, budget can be fully or partially reallocated to other projects, where expected impacts will be higher. This process will be managed by the programme management team as part of their ongoing monitoring role with decisions taken by the Strategic Board/SRO. Decisions would be made as part of the annual review process or out of the review cycle by exception. The project structure of the programme means there are multiple ways to adapt the programme to maximise impact and value for money.
# Monitoring and evaluation
The monitoring, reporting, evaluation and learning (MREL) for this programme will be consistent with the Prosperity Fund’s (PF) approach to MREL. The programme management team are currently working with the PF MREL contractors to define the indicators that will be developed and base lined for the programme to ensure consistency and quality of reporting across the whole PF portfolio e.g. a detailed Results Framework is under development to support delivery of the programme.

If this programme is selected for the PF Fund level evaluation, the programme management team, project managers and their implementation partners will work closely with the evaluation team to support the process. The programme management team will also work with the PF-level evaluation and learning contractor to define the strategic questions for evaluation and learning.

Partly due to the intrinsic nature of corruption, the evidence base to support the linkages between project activity and reduced corruption, and the subsequent reduction in poverty and inequality, is not fully robust (see Economics Case). Therefore this programme has been explicitly designed (e.g. through the OECD Anti-Corruption Hub) to help address this intelligence gap. This will both reduce any risk to the delivery of this programme by enabling evidence based adaptive programming decisions and also more widely inform anti-corruption activity globally. The MREL approach is being designed to capture performance information in a timely manner to support adaptive programming.
### Results framework
The programme management team are currently working with the PF contractors to develop critical indicators (both quantitative and qualitative) for PF and programme level reporting, identifying aggregate indicators for regular reporting and management indicators to allow the programme manager and Boards to assess progress and impacts. The results framework will form the programme’s core monitoring and reporting mechanism, feeding the PF level Prospero reporting tool. The programme’s indicators will be consistent with the programme’s ToC and the Logframe analysis that flows from Expenditure will be reported monthly and impacts (results) quarterly in line with PF reporting rhythms. The programme’s indicators will include disaggregated results by gender, age and socio-economic group where relevant, in compliance with the Gender Equality Act (GEA). Annual reviews (ARs) will assess the contribution of the programme to gender equality and women’s economic empowerment.
### Reporting frequency and costs
Consistent with PF requirements, the programme management team will instruct the lead Government Department to develop a quarterly results reporting system at the project level and will work with the PF monitoring and reporting contractor to ensure consistency with PF processes and systems – particularly around data frequency, quality and consistency. Project-level data capture and base lining will be the responsibility of each lead Government Department and their implementation partner(s).
### Evaluation and learning
If this programme is selected as one of the sample for PF level evaluation, the programme management team, project managers and their implementation partners will work with the PF evaluation and learning contractor to develop the strategic questions that will be required for both the PF evaluation and to provide feedback to the programme on routes to impact. The overarching evaluation methodology will be decided by the PF level evaluators and the programme management team will work to deliver the required coordination between the various project managers and implementation partners at programme level.

If the programme is not selected for PF level evaluation, the programme management team will work with the PF level evaluation and learning contractor to develop a set of strategic questions that the programme will want to answer as part of the programme level MREL approach. These questions may include PF level questions if appropriate.
### Annual reviews
Annual reviews of the overall programme will take place, fed by sub-reviews of each project. The annual review process will be led by the programme manager and involve project managers and implementation partners as appropriate. Guidance will be sought from the PF MREL team to ensure alignment with PF level reviews. The results of the annual reviews will be reported to the SRO and the Strategic Board.

The results of the annual reviews, together with related monitoring and evaluation artifacts, will be utilised to inform adaptive programming decisions. By ensuring a flexible approach to delivery that responds to the successes of individual projects and emerging opportunities will enable the programme to remain focused on areas of highest impact. This is particularly important given the scarcity of available historical evidence to support the impacts of projects as set out in the Economics Case. Adaptive programming will involve recommending changes to the programme’s portfolio to the Strategic Board and for subsequent approval by the SRO.
### Post implementation evaluation arrangements
This programme will follow the Gateway review process. The entire programme and the projects within it will be subject to review to assess whether the benefits set out within the business case have been realised.
# Communications
Communications will be a vital component to the programme success, in particular ensuring the potential positive spill-over impacts and reputational benefits for the UK are realised e.g. businesses are made aware of the reduction in corruption and improved level playing field created by the programme. The programme manager will have overall responsibility for setting the programme’s communication strategy, working with the JFU, FCO Media Office, the FCO Prosperity Fund Delivery Unit communications manager, partner HMG Departments, Posts and delivery partners, and ensuring coherence across individual projects within the programme. The programme manager will also be responsible for developing, maintaining and updating a communications plan for pan-programme communications.

The communication strategy will contain (and build on) a specific plan for each project, working with Posts (including local media managers), partner governments, other Prosperity Fund programmes and delivery partners. The key objectives will be to:

- Ensure all stakeholders are actively involved in the programme
- Positively influence partner government anti-corruption policy making
- Ensure UK organisations are aware of the reduced risk of undertaking business in the target countries relating to less corruption
- Disseminate good news stories to help build programme momentum
- Influence national decision-makers to further the impact of the programme
- Use the programme to raise the profile and reputation of the UK
# Risk management
The management team will develop and own the risk management strategy and ensure the whole programme complies. The approach will follow these steps:
- Risk capture – initial capture and identification of a risk
- Risk assessment and evaluation – categorisation of risk and assessment of likelihood and impact
- Risk treatment and response – development of options and preferred mitigation strategies and actions to avoid the risk, minimise its likelihood of occurring or reduce its impact

All risks will be assessed and allocated an owner. The risks will be continually assessed and mitigation strategies and actions put in place.

Risk tolerances will be agreed by the Strategic Board and will feed into the above assessment of individual risks.

Risk workshops will take place with both the Strategic Board and the working level Steering Group. These workshops will be used to both capture new risks and ensure ongoing risks are being appropriately managed. The annual review process will also include an assessment of programme risks.

Risks will be reported, and escalated as appropriate, through the programme and Portfolio wide reporting mechanisms. The programme management team will develop and own a programme level risk tracker containing all high severity risks. All high severity risks will be reported to the SRO and Strategic Board.

The programme, as a whole, is assessed as being medium/high risk. This is a direct result of the high-return ambitious nature of the programme in which it is seeking to achieve impacts with external factors which are not within the direct control of the programme.