Indonesia Prosperity Fund / Regulatory Reform / Bilateral Programme / Timeframe 2018 – 2023 / Sectors Regulatory Reform / Version As at November 2018

Contents

List of Abbreviations

ASEAN – Association of South East Asian Nations
BE – Business Environment
BEIS – Department for Business, Energy and Industrial Strategy
BEJ – British Embassy Jakarta
DFID – Department for International Development
DIT – Department for International Trade
FCO – Foreign and Commonwealth Office
GoI – Government of Indonesia
HMG – Her Majesty’s Government
HVC – High Value Campaign
IIOC – Investment, Infrastructure & Operations Committee (FCO)
IMF – International Monetary Fund
MoU – Memorandum of Understanding
MREL – Monitoring, Reporting, Evaluation and Learning
ODA – Official Development Assistance
PFDU – Prosperity Fund Delivery Unit (FCO)
PFMO – Prosperity Fund Management Office
SDT – Sustainable Development Team
RD – Regulatory Delivery International (BEIS)
RR – Regulatory Reform
T&I – Trade and Investment
UK – United Kingdom
UNDP – United Nations Development Programme
VfM – Value for Money
WB – World Bank
WHO – World Health Organisation
# Executive Summary
This business case sets out the rationale for a bilateral Prosperity Fund (PF) programme in Indonesia focusing on regulatory reform (RR) to support inclusive economic development through improvements to the regulatory environment, which will help reduce poverty in the country. The programme also aims to create conditions for international, including British, business to trade, grow and invest (a secondary benefit of the Prosperity Fund).

This business case forms part of the Indonesia Renewable Energy and Regulatory Reform Bilateral Programme and builds on the Concept Note approved by the PF Ministerial Board. The individual strands of that business case, renewable energy and regulatory reform, were separated in April 2019. This business case covers the regulatory reform component of the programme.

The British Embassy Jakarta (BEJ) and Regulatory Delivery (RD) International have supported the Government of Indonesia with its regulatory reform priorities since 2015. However, many aspects of the regulatory environment continue to be challenging. Efforts to tackle these challenges have significant potential to realise both primary and secondary benefits. As such, BEJ proposes to continue to focus on regulatory reform.

This programme will be delivered by RD International in the Office for Product Safety and Standards,[1] which is part of the Department of Business, Energy and Industrial Strategy (BEIS), which leads the UK Government’s agenda on regulatory reform.
[1] https://www.gov.uk/government/organisations/office-for-product-safety-and-standards

RD International is held in high regard by the Government of Indonesia and has a leading role in developing critical thinking and strategic leadership of regulatory reform globally, focusing attention on the whole regulatory lifecycle, from the need for government intervention - controlling the design and stock and flow of regulation, through to its implementation and delivery – enforcement. RD International is internationally recognised as being at the leading edge of regulatory reform and this global recognition puts RD International in a unique position to leverage influence and support the creation of regulatory environments in which domestic, international and UK businesses have the confidence to start up, invest and grow.

Initial inception funding was agreed in October 2017 for RD International to carry out detailed scoping and diagnostic work. Through engagement with key government stakeholders, businesses, donors and NGOs, RD International has tested its proposed intervention options, delivery approach and budget allocation. These inception missions have helped shape this business case, by identifying specific reforms and proposing in-country activities and programme deliverables, which will be further refined during the inception phase.

The regulatory reform programme will be managed by HMA BEJ, supported by a prosperity team with a sound understanding of regulatory reform policy and commercial, programme and project management expertise. The team will draw on FCO, OGD and external expertise within clearly defined delivery and governance arrangements.

The budget for the regulatory reform programme is £1.5m and covers activity between September 2018 and March 2023, subject to the next Spending Review.

The programme is expected to deliver £80m of primary benefits and £23m of secondary benefits over 10 years.

# Strategic Case
## Context

Indonesia is a G20 emerging middle income country in South East Asia and is currently the world’s 16th largest economy, and the 10th largest economy in terms of purchasing power parity.[2] It is predicted to become a top ten global economy by 2030, accounting for almost 35% of ASEAN GDP.
[2] World Bank, 2016

It is the world’s fourth most populous nation, with 250 million inhabitants. It has a democratic government, headed by a President committed to economic reform and development. The country has made significant strides, with World Bank data recording GDP growth of above 5% annually since the millennium and the percentage of the population living under $1.90 a day (the international poverty line in terms of purchasing power parity) falling from 57.3% in 1990 (with a peak of 65.3% during the 1998 economic crisis) to 8.3% in 2014.[3]
[3] World Bank http://povertydata.worldbank.org/poverty/country/IDN

Forecasts predict continuing growth with the OECD predicting an average annual growth rate of 5.5% over 2016-2020.[4] The International Monetary Fund (IMF) has commended the authorities’ sound macroeconomic management and commitment to reform in its most recent review of the government’s performance.[5]
[4] OECD, 2016
[5] International Monetary Fund, 2016

The Human Development Index (HDI) score improved from 0.528 in 1990 to 0.689 in 2015 but there are marked differences in education, nutrition, sanitation and basic infrastructure between different regions and income groups across the country (e.g. Papua has lowest electrification rate and HDI score).

Whilst the national poverty rate has been cut by more than half since 1999, to 10.9% in 2016, the rate of reduction has slowed. Over 28m live below the poverty line, and approximately 40% of the population remain vulnerable to falling into poverty.[6]
[6] World Bank Indonesia Overview http://www.worldbank.org/en/country/indonesia/overview

The gap between rich and poor has risen sharply in recent years as measured by the Gini coefficient (from 30 points in 2000 to 41 points in 2014), with a moderate improvement in 2016 (falling to 39.7).

Gender inequality is reflected in HDI scores (women 0.660, men 0.71) and the significant gap in GNP per capita (women $6.668, men $13.391). The female labour force participation rate is low (50.9% vs. 83.9% for men); most women work in the informal sector as self-employed, casual, or unpaid family workers.

Women earn less than men on average across all sectors, with a particularly pronounced income gap in rural and agricultural roles. But the gender wage gap has shrunk: in 2011 the median woman earned 84% as much as the median man (c.f. 57% in 1990).

Inequality between women and men affects women’s contribution to the economy and, as a consequence, negatively impacts economic growth. Ensuring women’s access to the formal economy has important ripple effects such as smaller and healthier families, higher education rates for children, and overall a positive effect on poverty reduction.[7]
[7] World Economic Forum – Global Gender Gap Report

As in many other developing economies, falls in commodity prices have exposed the weak foundations of growth.8 The main economic challenge facing Indonesia is to make the transition from an economy where growth has been primarily based on commodity exports, to a value-added, investment driven economy.

Structural reforms are required to address constraints to growth and achieve diversification. Strategic, well-designed and targeted interventions from a bilateral regulatory reform programme can make a positive contribution to this transition.

## Indonesia’s Regulatory Environment

Some key obstacles remain in Indonesia’s business environment, and tackling any one of these barriers to growth would be beneficial.

Indonesia is ranked 73 of 190 countries in the World Bank Ease of Doing Business index; 133 of 138 countries on number of procedures required to start a business; and 126 of 138 on number of days taken to start a business. A World Bank study found economies with a good business regulation environment grow faster with output growth 2.3% higher for the best quartile compared to the worst. It also found that impact is felt across multiple sectors, with reforms acting as a catalyst for increased confidence and greater investment.

The programme’s interventions will support reforms to the regulatory environment which will increase incentives for domestic and international (including UK) firms to invest by reducing the uncertainty, risks and costs associated with doing business in Indonesia, contributing to a more level playing field for business. Greater investment by firms leads to economic growth. This will create employment and economic opportunities and contributing to inclusive growth and poverty reduction.

1. The OECD estimates that regulatory and competition policy reforms could boost GDP by 1-1.5% and McKinsey found that increasing infrastructure investment by one percentage point of GDP could generate an additional 700,000 jobs in Indonesia. A potentially virtuous circle.
2. The programme will not target activity on a particular problematic sector or set of regulations. Diagnostic work suggests the need for a more comprehensive and cross-cutting approach, focused on improving systems and structures for long-term change, with potential benefits across the economy as a whole.

The PF Global Trade, Global Business Environment and ASEAN Economic Reform programmes will compliment this work by focusing interventions in Indonesia on other priority areas (e.g. business competitiveness, intellectual property, financial services etc.). The PF Global Anti-Corruption programme will also compliment programmes in the business environment space, supporting macro impact on Indonesia’s business environment.

Whilst other donors are also active in this area, BEJ and RD’s work is highly regarded, the central oversight function is a neglected area and GoI is actively seeking UK support to continue building on previous work.

There is high potential for secondary benefit for international and UK businesses from reforms to ease of doing business: the EU Business Confidence Index and feedback from British and local business leaders in Indonesia shows this is consistently business’ highest concern.
# Implementation Plan
RD International will deliver a blend of technical assistance and capacity building support, working in partnership with a locally engaged Regulatory Attaché, local implementers and other donors.

Previous technical assistance work suggests the need for a comprehensive and cross cutting approach, focused on improving systems, structures and practices for the long-term, with potential benefits across the economy as whole.

RD International’s programme has complementarities and inter- dependencies with existing and planned programmes. It forms part of wider HMG and international efforts to develop business environments in which both Indonesian and international businesses, including from the UK, have to the confidence to trade and invest.

RD International will undertake regular missions of between 1 to 4 weeks to provide specialist technical assistance and capacity building support. These missions will be supplemented by the presence of a locally based Regulatory Attaché for the duration of the programme. The attaché will be the local project manager for the RD International bilateral programme, providing continuity and leading engagement between missions. The attaché will also be responsible for local oversight of the Indonesia strand of the Global Business Environment Programme. RD International will fund 70% of the salary costs of the attaché and the Global Business Environment will fund the remaining 30% of salary costs.

A key learning consideration from previous RD International engagement has been the importance of ongoing, sustainable in-country support to ensure interventions are successful. A locally based attaché with expert market knowledge, understanding of local political economy and the ability and credibility to establish relationships and access to government officials would be best placed to lead this.

1. The Regulatory Attaché will be recruited and employed locally. Recruitment will be led by the BEJ in partnership with RD International.
2. The attaché will be based in the British Embassy in Jakarta to strengthen delivery, management and monitoring capabilities, mirroring good practice elsewhere (e.g. DfID’s Indonesia Multi-Stakeholder Forestry Programme and the South East Asia IPO Attaché).

The attaché will be responsible for establishing relationships and maintaining engagement with key officials from across the Indonesian Government and other key stakeholders, to support the implementation of reforms. They will ensure sustainability by helping to build GoI ownership of and support for new regulatory reform initiatives.

RD International will provide intensive training and skills development to provide the Regulatory Attaché with a sound knowledge of regulatory reform and UK and international best practice. Ongoing strategic direction and support will be provided by the RD International Programme and Delivery Team.

RD International will make use of both internal staff and associated experts to deliver the technical assistance missions. This reflects their current operating model and the use of associated experts will enable them to scale up efficiently, without adding additional overhead costs.

The market for technical regulatory experts in the UK is limited, given tha services requested are specialist and practitioners are in short supply. However, RD International has maintained a pool of expertise of individuals and partner bodies who we work with. Each individual who applies to be an RD International associate expert is rigorously assessed against key knowledge, skills and competencies, and before any deployment, they match experts against the specific requirements of the assignment. RD International also maintains a small number of strategic partnerships with UK professional bodies (e.g. Chartered Trading Standards Institute and the British Standards Institute) with whom they intend to co-deliver missions.

Appropriate sub-contracting techniques and strategies will be utilised to ensure that UK based experts with the right skills and experience are available to meet in-country demand and ensure value for money. For example contract lengths, specific clauses, and project outcomes will be examined on an individual basis to ensure project costs are minimised.

Regulatory Delivery International has significant in house expertise to support the creation of practical tools to support reformers, including skills and experience in regulatory design, enforcement, business engagement, data and intelligence analysis, strategic planning and digital capability, including content design. These skills would support an up scaled RD International programme and delivery team to deliver the programme outputs.

RD International may also utilise local partners to undertake research, provide expertise on the Indonesian political and regulatory context, and to support specific delivery activities, such as training events.

In-country interventions will be complemented by global and regional knowledge sharing and conference events, which will facilitate peer to peer learning by highlighting international best practice on regulatory reform.

RD International will develop a suite of tailored tools and guidance to support technical assistance missions and the work of the regulatory reform attaché, helping to implement and support dissemination of new approaches. Tools will be targeted towards different audiences, including senior reform leaders, policy teams and frontline regulatory officials. Materials will include structured training programmes in key concepts such as risk-based approaches, business engagement and the strategic management of reform.

RD International will adopt a comprehensive and cross-cutting approach, focused on improving systems and structures for long-term change, with potential benefits across the economy as a whole, and will support reforms at different stages of the regulatory life cycle, from the design of regulation, through to its implementation and delivery.

Following detailed diagnostic and scoping work and regular dialogue with the Government of Indonesia throughout the inception phase, RD International has identified the following potential areas of cooperation:

Enhancing the strategic management and coordination of
reforms, specifically Presidential Regulation 91 of 2017;
- Improving the implementation and delivery of regulation by encouraging the professionalisation of regulation and building capacity of frontline regulatory officials; and
- Strengthening formalised mechanisms for public consultation and ongoing business engagement

Table 1 sets an indicative implementation plan with suggested activities and timelines based on the proposed areas of cooperation.

Table 1: Indicative Implementation Plan
Activity	Time (Years)
	1 / 2018/19	2 / 2019/20	3 / 2020/21	4 / 2021/22	5 / 2022/23
Objective 1: Enhancing the strategic management and coordination of reforms.
1.1 Conduct a needs analysis of the current processes for the management and coordination of reform initiatives
1.2 Develop bespoke practical tools and processes to support the coordination and implementation of key reforms
1.3 Develop project and programme management capabilities through bespoke training followed by coaching and mentoring
1.4 Support the development of mechanisms to increase business participation with the review and simplification of business licenses
1.5 Deliver training workshops for key ministries and regions on the Outcomes and Impacts of Regulation
1.6 Develop the skills and knowledge of key officials on good regulatory practice through participation in regional and international learning and knowledge sharing events
Objective 2: Improving the implementation and delivery of regulation by encouraging the professionalisation of regulation and building capacity of frontline regulatory official in a technical area of regulation, such as market surveillance
2.1 Conduct a detailed analysis of the licensing and delivery mechanisms in a sector or region to identify key obstacles to implementation and delivery
2.2 Deliver workshops with regulators in sector or region to develop strategy and tools to support implementation of regulatory reform initiatives
2.3 Train frontline regulatory officials on Regulatory Core Competencies
2.4 Develop processes and indicators to monitor and evaluate performance of regulatory agencies
Objective 3: Strengthening formalised mechanisms for public consultation and ongoing business engagement
3.1 Review current public consultation and business engagement mechanisms
3.2 Develop and deliver a standard training package for policy officials on business engagement
3.3 Broaden dialogue with key domestic and international business communities / business representative bodies
3.4 Develop and deliver training for frontline staff regulatory officials on understanding and working with businesses
3.5 Support the development and implementation of an E – Consultation Platform
3.6 Support the development of formal business engagement mechanisms at national and regional levels

# Appraisal Case
The appraisal case assesses the potential primary and secondary benefits of the proposed interventions in accordance with the requirements of HM Treasury’s Green Book (Appraisal and Evaluation in Central Government)[8].
[8] https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/685903/The_Green_Book.pdf

The appraisal case summarises the estimates of the primary and secondary benefits for the proposed programme at an overall level and a project level as follows:
At overall level: the “macro level” indicator of GDP growth is captured in this approach, consistent with a wide range of studies.[9] This is based on the approved Global Business Environment model which aggregates the individual impacts of successful regulatory reform (e.g. the impact on Foreign Direct Investment (FDI), or domestic business activity into a single measure); and
[9] One of these is Haidar (2012), which considers data from the World Bank’s Doing Business surveys for 172 countries over 5 years, he finds that, on average, each business regulatory reform is associated with a 0.114 percentage point increase in the growth rate of GDP

At project / specific activity level: this provides “micro level” estimates of the benefits of the primary and secondary benefits of the individual project strands of the programme.

For the latter, in the absence of a literature evidence base and data on the impacts of individual regulatory reforms, it is difficult to robustly attribute the primary and secondary impacts for a given reform activity. The resulting estimates provide a basis to collect more detailed information during the programme to robustly monitor and evaluate the impact of individual activities.

## Delivery Options

BEJ engaged with a wide range of potential implementing partners, civil society, academia and wider stakeholders (both in the UK and Indonesia) and OGDs to identify and assess different routes to market. Early market feedback helped determine the capacity and capability of the market to deliver potential programme interventions.

UK Government Technical Assistance – PREFERRED
The preferred delivery model is to build on its programme from Year 1 of the Prosperity Fund and predecessor projects and provide UK Government expertise to help build and develop Indonesian regulatory reform capability. This work will be delivered by Regulatory Delivery International, part of the Department for Business, Energy and Industrial Strategy

With RD International’s expertise and track record as a global leader in regulatory reform, its established and trusted relationship with GoI officials and its existing knowledge of Indonesia’s specific regulatory reform needs, this delivery option has the potential to have more impact than interventions by private consultants or multilateral organisations, who operate without the reputational brand of the UK Government

A locally engaged Regulatory Reform Attaché will provide expertise and on-the ground continuity of relationships, maintaining momentum between RD technical assistance missions.

RD International will make use of both permanent staff and associated experts to deliver the programme. This reflects the current operating model and the use of associated experts will an efficient scale up of activity, without adding additional overhead costs.

Private Sector Technical Assistance – DISCOUNTED

Utilising private sector expertise would entail a competitive process to identify the best placed private sector organisation to deliver the programme, which will increase the lead time to delivery.

There are private sector providers with the relevant expertise to deliver this, and the FCO could contract with multiple partners to mitigate risk. These providers could develop consortiums to ensure a good range of expertise to meet the requirements for the programme.

A commercial approach could entail significantly higher transaction costs and limit VfM. The overall impact of the programme could also be undermined by the perceived credibility and capability of private sector providers, which could in turn impact the delivery and sustainability of reforms.

There is a reputational risk of losing the valued government to government support provided through the Prosperity Fund Year 1 programme. This risk could be mitigated through providing RD International support alongside private sector provision, or private sector expertise engaged by and badged under the UK Government brand.

World Bank Technical Assistance – DISCOUNTED

The FCO could end its bilateral support and instead channel funds into other multilateral programmes. Amongst them, the World Bank is considered a major international delivery partner for business environment reform across the region.

A World Bank intervention would be more focused in addressing business regulations and enhancing business competiveness. As flagged in the strategic case, this work is already being addressed through the Global Business Environment Prosperity Fund Programme that is being delivered in partnership with the World Bank. While adding to this work would enable us to leverage the resources and reach of the World Bank, it would also entail low additionality and reduce control over risk and delivery.

While there is a rationale for the global programme to work with the World Bank (a programme which will also target Indonesia), the World Bank themselves have suggested that the Indonesian Government would benefit from government to government support which would complement their wider work, so this option is discounted.

Preferred Option

UK HMG (BEIS RD) is judged as the optimal and best value implementer of the regulatory reform programme. The HMG brand is highly respected in Indonesia as is BEIS RD has successfully delivered a Year 1 PF regulatory reform project. Private sector suppliers would not be able to leverage a comparable impact and would not be able to build on relations from PF Year 1 project delivery.

The decision not to take this activity through procurement routes has been made as BEIS, being a UK HMG body and having specific expertise in delivering national/local regulatory reform has unique experience, expertise and capability to deliver this work.

Given both bodies are UK HMG departments the only viable delivery mechanism is a inter-departmental MOU.

BEJ has a successful track record in supporting GoI to improve ease of doing business through regulatory reform under PF Year 1 and predecessor programmes, working closely with BEIS RD as the delivery partner. We will add value to this work by leveraging our resources to target and develop specific reforms on a Government to Government basis, while maintaining a healthy dialogue with other donor efforts to harness potential synergies and maximise the impact of the programme’s interventions

Other Donor Activity
A number of donors provide support to the GoI to strengthen the business and regulatory environments. These are considered relevant in terms of cumulative effects, that arise in the combination of the effects from the regulatory reform programme in contributing to the overall reform effort. Coordination with other donors will be essential and could result in significant leverage.

Prominent multilateral donors and activities include:

Asian Development Bank (ADB) – a US$ £1.5million programme, Stepping-Up Investment for Growth Acceleration (SIGAP), to support the country’s economic growth and resilience through improved business climate, increased infrastructure investment, and improved governance framework for more public investment.

OECD – various programmes in Indonesia and South East Asia. Prominent work to date has been through the ASEAN-OECD Good Regulatory Practice Network (GRPN). The OECD-Indonesia cooperation is guided by a biennial Joint Work Programme, which was renewed for the period 2017-2018.

The World Bank – The GoI has received assistance on One-Stop Service (OSS) and Doing Business reforms. This has included the support around the formulation, implementation and the institutional/organisational arrangements to accelerate reforms. The World Bank works with across ministries in the GoI, including the Jakarta administration. It is also working in partnership with the PF in the Business Environment programme (see below), with the potential for significant synergies with the RR programme.

RD International has liaised closely with other donors during the inception and design phase and will maintain regular dialogue over the lifetime of the programme to avoid duplication and identify potential synergies which will help to maximise the impacts of the regulatory reform programme.

Other PF Programmes
This programme has a number of areas of synergy with other Prosperity Fund programmes (see Table 2 below), amplifying the overall impact of the PF. The regulatory reform programme will actively manage the linkages with other programmes to ensure synergies are realised. This will be achieved through a combination of the Embassy Programme Board (ensuring strategic linkages are identified between PF and other HMG programmes), the Programme Steering Committee (ensuring identified linkages are progressed), and at an operational level, the Programme Lead liaising with their equivalents in other programmes.

Table 2: Synergies with other PF Programmes operating in Indonesia

Programme	Link
Global Business Environment Programme	This $3m programme, delivered by the World Bank (WB), supports the improvement of the business environment by addressing policy, legal, regulatory and administrative barriers for business at national and subnational levels and eliminating/reducing restrictions to entry for foreign and domestic investors. WB and RD International’s work will complement each other in a number of key areas including public consultation and business engagement and work within the tourism sector, where the WB will support targeted investment promotion and RD International will support the improvements to the regulatory environment. RD International will benefit from the high-level convening power of the WB generated by its longer-term funding commitments.
SE Asia Economic Reform Programme: Regulatory Reform	This regulatory reform element of this programme also delivered by RD International will work bilaterally with the Governments of the Philippines and Vietnam. Regionally it will work with ASEAN countries to improve regional regulatory efficiency, transparency, predictability and harmonisation. The regional activities of this programme will complement the activities of the Indonesia regulatory reform programme.
Indonesia Renewable Energy Programmme	The renewable energy programme will / increase RE access addressing both the lack of energy access and climate change constraints to growth. / The regulatory reform programme by nature is cross-cutting and considers economy-wide impacts, and will act as an enabler for sector-specific regulatory reforms which will support the objectives of the RE programme.
ASEAN l Low Carbon Economy Programme	The programme will provide low-carbon related technical assistance to a number of strategically important developing countries, including Indonesia, to improve the effectiveness of key institutions (public, private, civil society) to deliver accelerated emission reductions and meet the 2015 Paris Accord’s goals. The Regulatory Reform Progamme will explore supporting improvements to the regulatory frameworks and national standards for energy efficiency and green finance.
Global Infrastructure Programme	This programme will build capacity to design and develop high quality infrastructure programmes. Indonesia has been identified as a 'pathfinder project'. Economy-wide improvements to the regulatory environment will support the delivery of infrastructure programmes.

## Estimated Primary and Secondary Benefits
Approach
The estimated primary and secondary benefits are calculated based on the most reliable information and available data. This builds on previous analysis and is based on:

- A review of the literature evidence base;[10]
  [10] Haidar (2017) shows that regulatory reform unlocks GDP growth, with each additional reform enacted, after adjustments to account for factors including political stability and corruption is, on average, 0.114 percentage points.
- The approved PF Global Business Environment Programme Model;
- Independent methodology reviews by The Adam Smith Institute and BEIS Trade Economists;
- Consultation on the proposed additions to the methodology with FCO team leading the approved Global Business Environment Programme; and
- The SOBC assurance comments from FCO Economist Unit.

Selection of the most appropriate method

Following quality assurance procedures outlined above, we have made reasonable additions to improve the robustness of the Global Business Environment methodology. These are discussed further in the analysis that follows.

Conservative estimates of the input variables and the assumptions applied in the model add credibility to the use of the benefits estimated for decision making as they are at the lower end of what the programme might achieve. This approach is also consistent with the relative size of the Regulatory Reform programme compared to larger scale interventions such as the Global Business Environment Programme.

A 1% contribution rate has been used to reflect the anticipated contribution of this programme to the overall reform effort.

Estimated Primary and Secondary Benefits – Overall Impact
The table below sets out comparisons of the results of the CBA using central (i.e. 5 per cent) and minimum attribution (i.e.1 per cent) rates respectively using a pro-rata calculate. They are based on the methodology and assumptions outlined above. To tackle optimism bias and provide more conservative estimates, a high contribution scenario has not been included.

Table 3: Comparison of Primary and Secondary Benefits at Central and Low Attribution rates (discounted, £ millions)

		Central attribution (5%)			Low attribution (1%)
	Costs £m disc.	Benefits £m disc.	NPV £m disc.	BCR	Benefits £m disc.	NPV £m disc.	BCR
Primary Benefits	1.34	£400	£399	299	£80	£79	60
Secondary Benefits	1.34	£112	£111	84	£23	£21	17

Using a minimum contribution approach, (i.e. using a pro-rate calculation of investment to benefit ratio and a 1 per cent attribution rate) the cost benefit analysis of the regulatory reform programme shows a conservative baseline scenario over 10 years of:
- £80 million in primary benefits; a net present value (NPV) of £79 million; a benefit cost ratio (BCR) of 60
- UK secondary benefit is £23 million over 10 years, with a benefit cost ratio of (BCR) of 17

1. The CBA shows high potential for return on investment and by targeting specific barriers to regulatory reform, the programme is complementary to the activity of other donor activity e.g., the World Bank through activity funded by the Global Business Environment PF programme.
2. Overestimating the level of influence of a programme is common in up front appraisals. Because of this, we have carefully considered the extent to which RD International is pivotal to a successful reform based on the historical number of Doing Business reforms in Indonesia and by assuming a more conservative estimate of the probability of successful reform (50 per cent) to reflect the political economy challenges compared to previous estimates which assumed 100 per cent success in the central scenario

Primary impacts
The regulatory reform programme contributes to an improved business environment which enhances the lives of people directly, in their main capacities as employees; entrepreneurs; and consumers as summarised in Table 4 below:
Table 4: The Role of Regulatory Reform: Promoting Inclusive Economic Growth, Poverty Reduction, and Gender Equality

The Role of Regulatory Reform: Promoting Inclusive Economic Growth, Poverty Reduction, and Gender Equality
Employees
- Employment opportunities (self-employment or as employees)
- Firms that are more productive paying higher wages
Entrepreneurs
- Expansion of economic activity (gains from increased trade and investment domestically and internationally)
- Incentives to be part of the formal economy (e.g. lower entry barriers to start a business) – ILO estimates that 50 per cent of Indonesia’s workforce are engaged in informal employment.
Consumers
- Efficient allocation of resources
- Competitive markets and price competition for goods and services.
- Reduced costs of production and prices - improved consumer welfare

Disadvantaged groups in society (Women; The informal sector; Low paid workers)
- Incentives to work in the formal economy
- Access to markets and take up employment opportunities outside of low paid informal sectors that are often poorly regulated.
- Increased (female) labour force participation – potential to unlock c. 25 per cent of additional productivity, nationally (OECD estimates)

1. A better regulatory environment will make it easier to do business, place less burden on existing businesses and make business startups easier (with a consequent increase in the proportion of small to medium size businesses and those owned by women). Businesses will also find it easier to expand and there will be greater potential for diversification of the business landscape with associated benefits for employment
2. Through enabling greater trade and investment, regulatory reform creates opportunities for poor people to secure employment and move out of poverty (as employees and/or as employers – e.g. by starting their own business and/or creating incentives to join the formal economy). Evidence shows that reducing the number of steps to start a business has a lasting effect on poverty reduction.[11]
  [11] PA McLaughlin, 2016, “Regulation and Income Inequality: The Regressive Effects of Entry Regulations”. An increase by one standard deviation in the number of procedures required to start a new business (i.e. an increase of 3.52 steps to start a new business) is associated with a 1.5 percent increase in the Gini coefficient (a measure of inequality) and a 5.6 percent increase in the share of income going to the top 10 per cent of earners.
3. We anticipate that this programme will generate benefits to reduce poverty directly though stimulating new business growth and job creation for low income groups. Improving the ease of doing business and trading across borders is a key component of this programme’s poverty reduction strategy. We will increase regulatory capacity through tailored interventions, working closely with state agencies and local government to support Indonesian entrepreneurship and innovation as a path to employment and financial prosperity in places with limited job opportunities. This will help to alleviate Indonesia’s youth unemployment – estimated to be 17.8 per cent in 2016 according to the International Labour Organisation (ILO) – over three times the national unemployment rate. [12]
  [12] http://www.ilo.org/jakarta/info/public/pr/WCMS_523917/lang--en/index.htm
4. The programme will also result in significant indirect benefits to the poorest communities, for instance, as recipients of tax-funded services and transfers (e.g. welfare payments). Firms and their activities are the principal sources of tax revenue for governments, and growing economies generate more taxes. By enabling an improved business environment, the programme will expand the resources that the GoI has available to fund public services (including health and education) and transfers to disadvantaged members of society. It is assumed that this could enhance households’ quality of life due to emotional wellbeing, increased awareness of healthy living and reduced vulnerability to economic shocks.
5. The UK’s recently announced Industrial Strategy acknowledges the role of the business environment to strengthening the foundations of productivity. Successful regulatory reform will stimulate growth in the private sector through rising productivity (output per worker) and wages as citizens take up new opportunities to train and up-skill and to secure employment in highly skilled sectors. In the longer term this improved access and rising demand for education and training by households, increases the proportion of Indonesia’s workforce employed in highly skilled jobs, further stimulating GDP growth.
6. National prosperity and poverty reduction depend on a country’s citizens being employed and productive. The ILO estimates that only 9 per cent of Indonesia’s labour force has a university degree – if this trend continues, Indonesia’s local skilled workforce will not be able to keep up with the increasing demand for skilled labour. The programme will help to build technical capabilities in new geographies to tackle skills deficits holding back inclusive economic growth and poverty reduction. Ensuring good jobs and greater earning power for all will bring the labour market into balance – a necessary requirement to drive sustainable and transformative economic growth (targeted at 6.1 per cent annum) for Indonesia to become the fourth largest economy by 2045 – a key priority of the GoI.
7. Lowering barriers to market entry by 10 per cent also has a wider impact of reducing the average price mark-up by nearly 6 per cent – benefiting society as a whole, for instance, by freeing up resources for families to save for future consumption. This has significant impact on the lives of poor people who spend a larger proportion of their income on essential goods such as food and fuel compared to better off households.[13]
  [13] Devlin (2010), Challenges of Economic Development in the Middle East and North Africa Region

Secondary impacts
1. UK exports to Indonesia do not currently match the market size. Whilst UK companies are actively exploring commercial opportunities, they are often deterred by the complicated and burdensome regulatory landscape. By reforming systems for managing and setting regulations, this programme will reduce barriers; making it easier to do business; and lower transaction costs. UK companies will benefit from improved efficiencies through an up-lift in volumes and a reduction in the cost of trade.
2. These improvements will also create secondary benefits, by opening markets further, generating business opportunities for local, UK and international companies. The programme will follow Official Development Assistance (ODA) objectives and rules, and not give preference to UK companies in delivery. However, we expect international businesses, including from the UK, to benefit from Indonesia’s GDP growth. For instance, secondary benefits arising from the UK’s competitive advantage in high value sectors and the programme’s complementary activities to existing HMG investment in Indonesia (e.g. PF Renewable Energy Programme).
3. BEJ will work with Department for International Trade (DIT) at Post and in London to ensure UK businesses are able to take advantage of opportunities and access that arise from reforms by promoting Indonesia as a trade and investment destination and the UK as a preferred business partner. This programme uses Prosperity Fund funding and has been designed collaboratively by FCO, BEIS and DIT to maximise secondary benefits.
## Non-Monetary Impacts
The economic appraisal makes quantified assessments of the potential benefits of the programme through impact on growth and the value of increased exports for the UK. Therefore, by its nature the analysis will ignore wider, potentially substantial benefits that cannot be monetised.

At an overall level we anticipate additional benefits to also include greater financial stability through deeper financial markets, reduced corruption (all primary benefits) and additional secondary benefits to include: positive impacts on UK bilateral relationships in Indonesia and SE Asia overall, the promotion of rules-based system and the spread of UK standards.
## Sensitivity Analysis
A key issue in this appraisal is that the estimated NPVs and BCRs following the standard guidance are quite high - as the analysis is very sensitive to the starting value of GDP. We have applied a conservative estimate of the Haidar model, by assuming that the additional reform will generate a 0.114 per cent increase in GDP, after controlling for a range of variables including political economy challenges. Haidar found that without controlling for a range of different variables the impact increased to 0.150 percentage points.

We have also assumed in the conservative scenario, that HMG assistance will be instrumental to one major reform based on the average reform history over a 10-year period (2007-2017) as shown in the World Bank’s Ease of Doing Business publications.[14]
[14] http://www.doingbusiness.org

We have also applied reasonable additions to the methodology of the Global Business Environment Programme model, following the quality assurance

procedures highlighted above. For instance, the use of constant prices to eliminate the impact of inflation which leads to overestimating the NPV and BCRs; applying historical average exchange rates to account for currency fluctuations; and the use of more up to date and robust estimates of the impact on UK exports than trade shares.
## Gender Impact and Compliance with the Gender Equality Act
In developing this business case, consideration has been given to how the programme can improve the lives of women and girls by removing the barriers to business which hold back female economic empowerment.

Evidence on the impact of the business environment on gender has been assessed in order to better understand how the programme can contribute to improved gender equality. Work by the OECD has shown that women’s empowerment, specifically as entrepreneurs with access to growth markets, is a major contributor to pro-poor growth. Women are more likely to work in the informal sector and are typically disadvantaged by prevailing laws, regulations and customs.[15] A study of the Middle East and North Africa (MENA) found that lengthy procedures for starting a business can have gender differentiated effects, while regions with lower start-up capital and lower exit barriers have higher shares of female entrepreneurs in the formal sector.[16]
[15] Global Environment Business Case
[16] Chamlou, 2008.

Women face greater vulnerability to corruption during business registration as they often lack information more than men and are less aware of procedures. In addition, it is less likely that women can afford the procedures due to lack of collateral or funds for high start-up capital requirements; they may have less time available for completing lengthy procedures due in part to the burden of domestic responsibilities; and may face greater difficulty accessing registration facilities. All of these barriers may negatively affect women, contributing to their choice to not formalise their businesses.[17]
[17] World Bank, 2010; Chamlou, 2008; ADB, 2014; DFID, 2013

Implementation of good regulatory practices which endorse the UN Women’s Empowerment Principles in formulating policy and regulations will create a more positive environment and easier access for women’s participation in running businesses.[18]
[18] UN Global Compact and UN Women, Women’s Empowerment Principles

Most Indonesian women work in the informal sector as self-employed, casual, or unpaid family workers. Women earn less than men on average across all sectors, with a particularly pronounced income gap in rural and agricultural roles. Over 40% of smallholder farmers are women. Nationwide, female SME owners, like all SME owners, find current government systems, particularly regulations, a major constraint. Tackling regulatory barriers could boost female entrepreneurship. Entry into the formal economy will boost female labour participation and could increase women’s incomes and security of employment.

In designing and implementing our regulatory reform interventions, we will work to ensure the programme integrates gender considerations at all stages and that positive gender impacts are maximised. We will take into consideration international best practice to support the development and implementation of gender sensitive business environment reform programmes,[19] including consultation of women and women’s business associations, ensuring that women are represented and participate in the regulatory reform process.
[19] Business Environment Working Group (BEWG), Donor Committee for Enterprise Development, Business Environment reform and Gender 2016

To ensure women reap the benefits of reduced barriers to business, we will:

Incorporate women’s voices from beneficiary communities throughout the design, delivery and evaluation phases of the programme.

Ensure female participation in consultations and other engagement activities, including individual participation and through community groups and women’s business associations.

Require collection and analysis of gender disaggregated data (including quantitative data) in project monitoring, reporting, evaluation and learning (MREL).

Include women in training programmes, e.g. on; regulatory workshops, etc.

Consider delivering positive impacts for women as one of the criteria when selecting specific regulatory reform interventions.

Consider the impact on gender norms at household, community or wider societal levels that could result from improved business opportunities that flow from an improved regulatory environment. We will carefully assess the potential for any unintended negative consequences. For example, changes in status, power and influence between girls/women and boys/men, which could lead to domestic violence and/or increased drudgery for women and girls, etc.

# Commercial Case
### 4.1 Design and Delivery Phasing
Sourcing
RD International will be engaged to deliver the programme, pending approval of the full business case, through an inter-departmental MOU.

Mobilisation

1. The mobilisation phase will involve BEIS RD engaging necessary resource and expertise to meet delivery requirements. This will include recruitment and training of the locally engaged Regulatory Attaché and may include sub-contracting of local partners, for example to conduct research and deliver training.
2. Whilst maintaining an overall lead role for BEIS RD, BEJ RR Business Environment policy leads will ensure programme delivery is aligned with BEJ policy objectives and the Regulatory Attaché will work with GoI Coordinating Ministry for Economic Affairs to drive delivery between RD missions.

Following completion of the scoping exercise conducted during the inception phase, BEIS RD will consult BEJ PMT to agree final programme design.

### 4.2 Commercial and Mobilisation risks
## Table 6: Commercial and Mobilisation Risks
This table takes into account grant model and commercial procurement approach risks.
Risk	Likelihood	Impact	Mitigation	Residual Risk
Delay in Business Case sign off results in unplanned major delay in spend and reduced outputs.	Medium	Medium	Work closely with FCO PFDU to understand timescales for business case sign off and wider FCO assurance process. / Ensure time for revision and potential delay within timescales.	Medium
Unable to agree suitable understanding with BEIS on delivery of regulatory intervention.	Low	High	Stakeholder engagement early to manage expectations. Early mapping of capability and requirements to identify gaps and potential delivery issues.	Low
Misuse of funds or fraud by implementing partner or fund recipients.	Low	High	As a HMG partner, BEIS has strong financial management procedures for the prevention of fraud and misuse of funds. BEIS implements a zero tolerance approach for external partners, including robust due diligence procedures, open book accounting and rolling annual audits.	Low
Inappropriate supplier awarded resulting in ineffective programme delivery and poor VFM.	Low	High	Ensure Terms of Reference are detailed and evaluation criteria are testing. Ensure contract management is robust.	Low
Poor contract management prevents programme delivering impact.	Low	High	Ensure capability and capacity at post for effective contract management. Ensure suitably rigorous KPIs and ensure they are regularly updated. / Provide ongoing supplier management training and senior oversight and ownership.	Low

## Table 7: Implementation Timetable
This table takes into account grant model and commercial procurement approach risks.

Regulatory Reform Programme	Date
Inception phase	November 2017 – October 2018
Full Business Case approval	November 2018
Full MOU Signature	April 2019
Delivery	April 2019 onwards

# Financial Case
The financial case sets out the budget and financial management for the programme.

Programme Budget

The programme is seeking £1.5m Prosperity Fund ODA funding over five years. This includes all inception and implementation costs, such as associated FCO and RD International staffing and administrative costs.

The main costs across the programme are the staff and travel costs for the technical assistance and capacity building activities. FCO staff costs to manage the programme make up 3.5% of the programme which we consider reasonable and good value in ensuring effective oversight and management of the programme.

1. Funding will be ‘programme’ spending from the Prosperity Fund (RDEL). A budget allocation of £1.5m has been made by the Prosperity Fund, subject to approval of this business case. All funds are ODA eligible and there are no contingent liabilities associated with the funding.
2. The budget will be provided over a five-year period from September 2018 to March 2023 (subject to the next Spending Review). At this stage we do not envisage the schedule of disbursements to go beyond the current spending round which expires in March 2023. Table 8 below gives an indicative spend profile for the implementation phase.

Table 8: Indicative Spend Profile
	2018 –2019	2019 –2020	2020-2021	2021-2022	2022-2023
Anticipated Annual Budget (£m)	0.2	0.3	0.3	0.4	0.3

The cost profile below has been created based on the preferred delivery model. Where possible actual cost data has been used (e.g. average salaries by grade), or otherwise estimates based on costs of previous RD International programmes and benchmarking against other technical assistance programmes.

Table 9: Indicative Overview Budget

	FY 2018-19	FY 2019-20	FY 2020-21	FY 2021-22	FY 2022-23	Total
Technical assistance missions	£60,000	£120,000	£120,000	£220,000	£120,000	£540,000
International and regional knowledge sharing events	£18,000	£16,000	£18,000	£16,000	£18,000	£86,000
Regulatory Attaché	£36,000	£72,000	£72,000	£72,000	£72,000	£324,000
Local delivery partners	£10,000	£20,000	£20,000	£20,000	£20,000	£90,000
RD International Programme and Delivery Office - 0.5 FTE G6 Programme Manager, 0.5 FTE SEO Project and Finance Manager and 0.5 FTE EO Project Support Officer	£40,000	£80,000	£80,000	£80,000	£80,000	£360,000
Total forecasted costs per year	£164,000	£308,000	£310,000	£408,000	£310,000	£1,500,000

The regulatory reform programme will start expenditure as soon as possible after the approval of the business case and transfer of funds, likely in quarter 3 of FY 2018-19.

The total costs of the programme will be fixed but the allocation of funds between different components will be reviewed on an annual basis to adapt to changes in circumstances and respond to lessons learnt. This will help to maximise impact, ensuring both the primary purpose and secondary benefits of the Prosperity Fund are met.

Costs for the first year of the programme are low as they do not cover a full financial year and to allow time to scale up delivery.

The costs for the Regulatory Reform Attaché are indicative only at this stage, and are based on FCO C4 (L) salary costs. Further refinement is required to establish exact salary. Estimated costs include, FEC salary costs, management, travel and subsistence, training time in London, flights and initial recruitment costs. These will be refined as the programme develops.

RD International will need to increase capacity within the Programme and Delivery Team to support the effective management of the upscaled programme of activity. This will include greater focus on monitoring and evaluation, programme management and logistical and financial expertise. This business case proposes adding the following additional staff to the Programme and Delivery Team: 0.5 FTE G6 Programme Manager, 0.5 FTE SEO Project and Finance Manager and 0.5 FTE EO Project Support Officer.

Financial Management

Financial reporting will be carried out quarterly in accordance with the MOU provisions. Funds will be disbursed in arrears quarterly to RD International on receipt of a valid invoice supported by a breakdown of activity that has been delivered. Each invoice will be supported by a breakdown of the costs being claimed against each budget line in the MOU.

# 6. Management Case
# 6.1 Governance
A governance structure will comprise a programme steering group, chaired by the SRO; with additional scrutiny from BEJ programme management board; and docking in with wider Prosperity Fund and RD International governance arrangements.

Reflecting the step change in scale and impact of programmes, the proposed management and governance structure aims to:

Maximise programme impact with implementation managed and delivered by third parties that have the expertise and resources to deliver a programme of the scale envisaged and to achieve VfM through outsourcing and economies of scale

Ensure that there is clear responsibility for oversight and management to proactively monitor delivery and manage risks effectively; and

Ensure there is the necessary capability and expertise in BEJ to manage contracts effectively, lead on complementary activities that cannot be delivered by RD International and deliver on central requirements for reporting, evaluation and communications.

The governance arrangements for the Indonesia Prosperity Fund Programme are therefore as follows:

Table 10: Functions and Responsibilities

FUNCTION	LEAD	RESPONSIBILITIES
FCO Oversight	FCO PUS and DG Global Britain	PUS has overall accountability for PF programme delivery within FCO. SRO accountability is via DG Global Britain.
SRO	HMA Indonesia	Overall responsibility for the Indonesia Bilateral RR Programme.
Bilateral Programme Steering Group	Sustainable Development Team	Meets monthly to review programme progress, provide challenge and advise on strategic priorities. Will consider stakeholder engagement and risk mitigation. Chaired by SRO.
Programme Management	Regulatory Reform and Global Business Environment Programme Manager	Bespoke role created to manage the programme and coordinate financial and programme reporting from implementing organisations.
BEJ Programme Board	Sustainable Development Team	Meets bimonthly to monitor progress of all HMG programmes and projects delivered in Indonesia. Chaired by DHM.
FCO Governance	FCO Prosperity Fund Delivery Unit (PFDU)	Ensure programme meets FCO governance requirements.
Portfolio Level Monitoring and Reporting	Portfolio Management Office (PMO)	Manages PF programmes portfolio. Coordinates reporting and presents to PF Portfolio Board. PMT will monitor programme performance and coordinate with implementers to provide reporting to PFMO.

Figure 1: Governance Structure

FCO PUS

Prosperity Fund Ministerial Board

DG Global Britain

Prosperity Fund Portfolio Board

Portfolio Management Office (PMO)

FCO Prosperity Fund Delivery Unit (PFDU)

Indonesia Bilateral Programme SRO (HMA)

Bilateral Programme Steering Group
(Chair HMA/SRO/SBH)

Embassy Programme Board
(Chair DHM)

Indonesia Bilateral Programme Management Team

Regulatory Reform Programme
BEIS RD (MoU)

HMA Jakarta will be the Senior Responsible Officer (SRO) for the programme and hold the budget in accordance with delegated authority. HMA will establish a governance structure at Post to manage delivery and associated risks as detailed above. Dedicated project leads from the Prosperity Team will manage the programme implementer, supported by BEJ policy leads.

The Indonesia bilateral programme is an FCO programme and will meet the governance obligations and requirements for ODA funded activity as set out by the department. The FCO Prosperity Fund Delivery Unit (PFDU), based in London, has responsibility for ensuring these requirements are met. PFDU reports to the Economic Diplomacy Director, who is the FCO representative on the PF Portfolio Board.

The Indonesia bilateral programme will meet all requirements of the Prosperity Fund, as set out by the Portfolio Management Office (PMO). This is set out in more detail in the Monitoring Reporting, Evaluation and Learning section.

The programme will be overseen by the Bilateral Programme Steering Group chaired by the SRO. The Steering Group will consist of the SRO, SDT and selected representatives from the collaborative network who will provide non-executive rigour. These representatives may include academics, government officials (HMG and GoI). The steering group may also invite wider donor stakeholders, and regulatory practitioners. Implementers will be invited to attend as necessary. It will meet monthly with two core objectives:

- Ensure proper strategic oversight of the programme.
- Maximise the impact of the programme to support economic growth and poverty reduction in Indonesia; and exploit synergies with other PF programmes.

In particular the Bilateral Programme Steering Group will be responsible for:

    - Assessing the progress and effectiveness of all programme strands.
    - Providing advice on the engagement strategy with key stakeholders in Indonesia, the UK, and wider international community.
    - Mitigation of systemic programme risks.
    - Consideration of annual programme evaluations and refreshes.

The Prosperity Team will also provide monthly updates on the Bilateral Programme to the Embassy Programme Board. The Programme Board is chaired by DHM Jakarta and meets bimonthly to monitor progress of HMG programmes and projects delivering activity in Indonesia (and Timor Lesté). This includes Prosperity Fund, Newton, Empowerment, GREAT Challenge, DFID programmes delivered by the UK Climate Change Unit, and Defra’s Darwin Biodiversity and Illegal Wildlife Trade Challenge funds. DST will ensure synergies across programmes and projects are exploited, and that programme outputs deliver against HMG policy objectives.

While not part of the formal governance process, the Bilateral Indonesia Programme forms part of the wider portfolio of Prosperity Fund programmes being delivered across SE Asia. Activity and progress across these programmes (as relating to their activities in the region) will be coordinated through the SE Asia Regional Board. The Board will be made up of working level leads responsible for programme delivery in the region alongside HMG stakeholders at post and London (including the FCO Asia Pacific Directorate). It will meet quarterly (in line with the PF requirement for impact reporting) with the following objectives.

    - Assess the impact of Cross – Whitehall ODA Funds across the SE Asia region (including the CSSF).
    - Promote programme synergy and prevent overlap of activity across the SE Asia Region.
    - Support the development of programme management skills across the region.
    - Mitigation of regional systemic programme risks.
### 6.2 Staffing and Resources

FCO
A programme management team (PMT) has been set up to manage the programme, based in Jakarta. The current programme team consists of 1x UKB D6, who will provide oversight to a 0.7 FTE C4 (L) programme manager (Regulatory Refortoxic Attaché) with regulatory, policy, and programme and project management expertise. The remaining 0.3 of the programme manager’s time will be spent providing local oversight to the Global PF Business Environment Programme in Indonesia. This team has been supporting the design and development of the programme, including this country specific intervention as well as advising relevant policy leads within BEJ on regional and global programmes Indonesia specific design and delivery.

1. In addition to the core team, it is expected that specialist expertise will be required from time to time, with particular demand during inception and sourcing, and the programme will - where capacity allows - draw required expertise from FCO or OGD resources on an in-kind basis. To mitigate potential for lack of capacity across HMG, there is provision to engage external resource on either a consultancy or temporary employment basis.
2. MREL expertise will be provided by PA Consulting and ITT, recently engaged by FCO to serve all PF MREL requirements. FCO legal advisers or Government Legal Department will provide legal advice on ODA compliance, sourcing and contracting.
3. Specialist requirements are for:

Economic expertise to support further development of cost benefit models following the results of inception and sourcing.

- Social inclusion expertise during inception and sourcing, with regular in-programme touch points stages to support community engagement and gender equality.
- Commercial expertise to support further market engagement during inception and design and delivery of an appropriate and compliant sourcing exercise, realising identification of an implementer that delivers quality and VfM.

Benefits realisation (‘results’) expertise so that impact and spill-over benefits are identified and maximised. Effort will be required to ensure that international business, including UK companies, are aware and engaged in potential opportunities created via programme activities and outcomes.

Significant in-kind support will also be provided by non-PF BEJ staff and wider HMG on policy, programme management and benefits realisation (e.g. DIT support on secondary benefit) which will help drive forward design and delivery in line with HMG policy objectives.

Alongside the bilateral Indonesia programme, there will be wider additional Prosperity Fund activity occurring in-country for Years 2-5, either with a SE Asia or Global focus. Relevant Indonesia policy leads and PMT will feed into the design and implementation of these programmes.

Where possible, BEJ will look to co-locate Prosperity Fund management staff when based in country, and look to promote synergies and reduce overlaps as appropriate. Precise details will depend on the final delivery models chosen by wider PF programmes but for example BEJ is exploring how any social inclusion and gender equality resource may be engaged to inform all PF programmes in Indonesia.

Programme team responsibilities are set out in Table 11 and Figure 2 illustrates a wider ‘virtual team’ structure including management, frontline and in-kind support configurations.

Table 11: Programme Management Team Roles and Responsibilities

Position	Responsibilities
Head of Programme Team / (UKB D6)	Strategic, operational and financial oversight / Representation of programme externally. / Programme communications manager (internal and external). / Contract and MOU management oversight and escalation point. / Annual reviews. / Adaptive programming lead. / Team management. / Due diligence and fiduciary risk oversight.
Regulatory Reform and Global Business Environment Programme Manager / (C4 L)	Day to day interaction with ministry officials / MOU manager for regulatory reform programme and oversight of BE programme / Stakeholder engagement and outreach to support delivery of primary and secondary benefits. / Arrange RD assistance missions; maintain continuity between missions and provide local expertise to support ministries’ implementation of reforms. / Coordination of MREL.

Figure 2: Programme Staffing Structure (Management, Frontline Delivery and In-Kind support)

Programme SRO HMA Jakarta

Head of Programme Team
(UKB D6)
Key

Policy Officer – Senior Trade and Investment Officer
(C4L)
Better Regulation
Head of DIT
(UKB D6)
Head of Prosperity Team
(UKB D6)
Better Regulation
BEJ Programme Management Oversight
DHM Jakarta

In kind support from BEJ staff (non-PF-funded)

Regulatory Reform and Global Business Environment Programme Manager
(C4 L)
Programme Management
Feedback loop
Governance
Risks

The UK has a strong track record of developing robust and trusted relationships with the Government of Indonesia and delivering international technical assistance programmes. This provides a good basis for the delivery of a multi-year programme like this, however there are many risks which are inherent with any long term reform programmes.

1. During initial programme design and inception phase, the Embassy and RD International have engaged closely with key stakeholders to understand potential risks and mitigation measures.
2. RD International will develop its own risk management strategy. All identified risks will be assessed and if required, allocated an owner to ensure the risk is continually monitored and mitigation strategies are owned and implemented.
3. Additional measures to reduce risks and increase the likelihood of success have been built into the design, delivery and management plan for the project, including:

  - Additional expertise in BEJ to proactively oversee implementation and leverage relationships.

  - An inception phase before full delivery implementation to further test and mitigate the programme level risk

  - A staged, results based approach to delivery meaning interventions can be halted if they are not on track.

  - MoUs and robust governance arrangements to secure active buy-in from stakeholders and create the right conditions for successful implementation.

  - A flexible approach to programme implementation allowing the PMT to respond to the evolving context by addressing under-performance early on and capitalising on areas making the greatest progress.
Table 12: Risk Register

#	Risk Description	Likelihood	Impact	Mitigation	Residual Risk
1	Loss of top level political commitment to reform.	Low	High	i) Secure broad range of support for programme (political and other key stakeholders); ii) Close collaboration with government in programme design; iii) Strong embassy engagement and relationship management; iv) May embed staff in ministry for greater influence and monitoring of results. v) Increase level (and seniority) of engagement with GoI as well as improved donor co-ordination to influence GoI to meet international commitments as a bloc.	Low
2	Implementers have insufficient sector/local knowledge and capacity to deliver the project.	Low	High	i) Rigorous due diligence checks of implementers/ partners; ii) Competitive selection process; iii) Partnerships with local organizations/development of consortia where necessary.	Low
3	Poor performance of implementers.	Low	Low to Medium	i) Programme anticipates and tolerates a degree of failure where novel approaches are adopted; ii) Breadth of programme spreads risk across strands enabling potential for success whilst strands are sufficiently resilient to stand alone.	Low
6	Fiduciary risk, weakening VfM and impact of programme.	Low	High	i) Rigorous due diligence checks of implementers/ partners; and ii) Strong oversight mechanisms including annual audits and open book accounting hardwired into agreements with implementers.	Low
10	Token engagement from partners required to offer in-kind support.	Low	High	i) Careful selection of capable and motivated partners; ii) Early and sustained engagement with partners on requirements; iii) Offer incentives to partners, e.g. ability to use programme brand	Low
11	Collaborative network fails to transfer knowledge to Indonesia and contribute to Programme interventions.	Low	High	i) Careful selection of capable and motivated partners; ii) Early and sustained engagement with partners on any concerns (e.g. on intellectual property); iii) Organise regular events for knowledge sharing, e.g. Annual conference; iv) Offer incentives to partners, e.g. ability to use programme brand.	Low
12	Poor performance of one or more strands leads to negative impact on programme brand.	Medium	Medium	i) Use adaptive programming approach to channel funding into more effective strands; ii) Rebranding of strands as necessary.	Low
13	UK support not widely recognised.	Low	High	i) Comprehensive communications and branding strategy agreed with implementers; ii) Strong embassy engagement with government and recipients to promote UK contribution.	Low
14	Ineffective government implementation due to poor capacity and government coordination, and decentralisation.	Medium	High	i) Involve influential local partners in programme design and implementation; ii) Strong embassy engagement and relationship management; iii) Interventions build local capacity and improve coordination mechanisms	Low to / Medium
15	Security incidents such as natural disasters or terrorism delay or stop programme delivery, e.g. through restricting staff movements or damaging infrastructure.	Low	Medium	i) Careful selection of pilot locations; ii) Implementers required to have crisis management plan; iii) PMT flag FCO travel advice to UK implementers.	Low
16	Programme interventions fail to deliver benefits for women and the poor; interventions undermine gender equality and inclusivity; change in gender or power norms produces unintended consequences (e.g. violence).	Medium	High	i) Careful programme design utilising gender and inclusivity expertise; ii) Robust monitoring and collection of gender disaggregated data; iii) Ensure participation of women and affected communities throughout design, delivery and evaluation phases; iv) Ensure participation of women and the poor in interventions, e.g. training and consultations; v) Careful assessment of possible consequences of intervention outcomes.	Low
17	Secondary benefit doesn’t materialise	Low	High	i) Utilise the collaborative network which will include UK, as well as international stakeholder to communicate programme and market opportunities; ii) Close liaison with DIT and Innovate UK Newton Fund programme raising international awareness of trade and investment opportunities in Indonesia; iii) Programme branding will aid recognition and communications work as above.	Low to / Medium

Results Framework

Working with PA Consulting, the MREL contractor, RD International and BEJ will develop a robust MREL framework with baselines for programme indicators, outputs, outcomes and impact measures to allow assessment of progress. This will include gender disaggregated results (which could include number of women employed; female income, etc.).

Table 13 sets out an indicative results logical framework (logframe) for the programme. It outlines the expected indicators, impacts, outcomes and outputs of the programme. It also shows how the programme links to the intermediate outcomes of the PF Theory of Change (ToC) and the UN Sustainable Development Goals (SDGs).

Table 13: Regulatory Reform Programme Indicative Logical Framework

	Descriptor	Indicator	Source	Assumptions
Impact	Improved business environment leading to increased business growth and investment. / Improved business environment leading to increased international engagement and investment.	GDP rates / Employment rates / Average wage rates / Investment generated / Jobs created (incl. youth and women) / Firm and aggregate productivity	IMF projections / OECD projections / Indonesian national accounts / World Bank statistics / HMRC statistics
Outcome	Reduces the monetary or time costs of doing business / Increases the predictability of the rule of law governing business operations / Promotes fairer and more competitive markets	Ease of Doing Business indicators / No of start ups	Indonesian national accounts / World Bank statistics / HMRC statistics	Regulations are effective and remove key barriers to business growth and investment. / External shocks (i.e. political/ economic) do not create wider barriers for businesses.
Intermediate outcome	Robust system of regulatory oversight and co-ordination put in place by the government of Indonesia. / New regulations are coherent, less burdensome and cut business costs. / Body of trained policy officials and supportive decision-makers.	No of reforms being implemented in Indonesia / Reduced time to regulatory implementation / Capacity/capability of central regulatory body	Indonesian government activity / Indonesian national accounts	New system is implemented and there is increased capacity to produce evidence-based business regulations / Poor regulation doesn’t make it over the line due to more effective consultation, appraisal and scrutiny. / Policy-makers use the tools and are supported to do so. / New system drives greater Ministerial co-ordination and improved coherence between central and local levels.
Output	System of regulatory oversight and co-ordination designed. / Relevant and usable tools and guidance available to Indonesian officials and supporting training programme delivered. / Multi-year implementation plan for regulatory quality developed.	Hours of technical assistance provided / Hours of training provided / Toolkits delivered to Indonesian government	BEIS / PF programme MREL	Sufficient sustained government buy-in to enable development of work plan and systems design. / Good match between TA provided through the programme and the needs of the government.
Activity	Scoping and delivery of a suite of tailored regulatory tools and guidance for policy officials; / Providing expertise and supporting Government with regulatory design and delivery / Technical Assistance for regulatory oversight body and regulatory agencies e.g. Training and mentoring for senior leaders, policy makers and frontline regulatory officials / Guidance on the review of regulatory and licensing regimes / Conferences, dissemination of knowledge and regional engagement / Mapping of regulatory landscape	Service Level Agreement as set out in MoU	BEIS	BEIS has capability/capacity to deliver activity. / Indonesian government remains supportive of UK HMG intervention

The programme MREL will be consistent with the programme’s Theory of Change and the logframe analysis that flows from this. It will report expenditure and impacts (results) in line with central PF reporting rhythms.

Monitoring and Reporting

The MoU established between the FCO and RD International will assign responsibility for data capture, measuring baselines and reporting.

Key Performance Indicators (KPIs) will be included in the MOU used to measure performance. KPIs will include poverty reduction and gender equality, which will require collection of gender-disaggregated data.

1. During the Annual Review process, BEJ PMT will require central support from HMG experts on gender, inclusivity and poverty reduction to ensure a robust evaluation of performance in these areas.
2. RD International will submit quarterly narrative and financial reports to BEJ. This will provide summaries of progress against the work plan deliverables and logframe outputs (with gender-disaggregated data where possible). The reports will enable BEJ to make key decisions regarding the direction of the programme, to ensure efficiency levels are maintained and effective delivery against outputs achieved.

These reports will be scrutinised by BEJ PMT and the Programme Steering Group to ensure the reports are robust and transparent. Reports will be subject to continuous improvement in order to satisfy those requirements.

Regular meetings to discuss results, VfM and performance will take place throughout the duration of the programme and particularly at key stages of implementation. Outputs from these discussions will also be issued to inform the Annual Review Reports. Post will submit quarterly operational reports on the performance of the programme.

Reporting Frequency and Costs

Consistent with PF requirements, RD International will provide quarterly reports that take into account MREL guidance, particularly around data quality and consistency, as well as the PF Annual Review format. Some reporting costs, such as data capture and measuring baselines, may be charged, as instructed, to the central MREL budget. The allowable cost for this programme activity is capped at 1% of the total budget allocation.

Evaluation and learning

The programme will have Annual Reviews where progress and lessons learned are shared with stakeholders and integrated into the communications strategy. In addition, this programme could be selected by the central PF for an independent evaluation. If so, we will work with the MREL contractor to develop and carry out the work. The overarching evaluation methodology will be decided by the MREL evaluators and we will manage the coordination between stakeholders in-country. If the programme is not selected for a centrally-funded evaluation, we may still decide to conduct our own mid-term evaluation and seek support from the MREL evaluators to do this. We further note that not all programmes are ‘evaluatable’ and, as part of the coordination with the MREL contractors, we will put in place best practices on evaluation and learning during the life of the programme.
## 6.3 Communications
Communications will be a vital part of ensuring the Indonesia regulatory reform programme is a success ensuring the potential positive spill-over impacts and reputational benefits for the UK are realised. Given one of the barriers to international and UK companies doing business in Indonesia is a lack of information and inaccurate perception of risk, communications to stakeholders on the reality of opportunities will be a vital to achieving the expected PF impacts.

The key objectives for our communications will be:

- Influence national and local decision-makers to ensure effective implementation and delivery of the programme, including maximising potential spill overs.
- Use the programme to raise the profile and reputation of the UK in Indonesia while facilitating access to stakeholders in national and local government and in the private sector.
- Promote the programme across UK HMG audiences.
- Ensure UK companies are aware and able to take advantage of opportunities and access resulting from programme activities

The main audiences are:

    - Indonesian local and national government, in particular decision makers in key sectors targeted by the programme.
    - Indonesian media and citizens (including targeting women and the poor when appropriate).
    - UK business and investors.
    - Indonesian businesses and investors interested in partnerships with UK companies.
    - UK HMG Departments/Agencies.

We do not expect to directly target UK audiences beyond potential beneficiaries (i.e. UK companies). However, if there are significant successes resulting from programme activity, we will consult with the FCO SE Asia regional hub, Media office and the PFMO communications team on the potential for informing UK media. We will have press lines and FAQs in place on the programme and its pillars/components, in readiness for parliamentary questions and UK media interest.

Strategic activities will therefore include:

Ongoing engagement with relevant national government departments, governors and local government officials in targeted regions to raise the profile of programme activities; advertise the potential of UK companies in key sectors; and ensure we are aware of developing opportunities (e.g. major contracts, policy reforms etc.) and corresponding risks.

Timely media moments (blogs, tweets, editorials) in Indonesia to highlight programme activities and successes to a wide audience capitalising on reputational benefits for the UK.

Communications activities including meetings, presentations and trade missions with UK companies that could benefit from the opening up of opportunities in Indonesia’s regions. This will link to work undertaken by DIT to directly facilitate business wins.

In terms of implementation responsibilities, communications activities will be co-led by the Programme Management Team and RD International. The division of key responsibilities is likely to be as follows:

Embassy
- Develop and continually update strategic communications plan;
- Identify and undertake media publicity for fund activities;
- Identify and communicate with UK and Indonesian companies;
- Ensure programme is promoted through wider Embassy activity and engagement with stakeholders; and
- Coordinate communications activities with implementing partners.

RD International
- Engage with key departments at national and sub-national level to ensure activities are aligned with, and embedded in, wider implementation plans;
- Support outreach to potential beneficiaries e.g. promote opportunities to UK companies; and
- Provide information to the Embassy to support wider media activity.

Working with the communications leads in FCO, BEIS, BEJ and DIT, the programme will develop and deliver a detailed communications strategy.