Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.
Title: Better Health Programme
Programme Value: £79.3m		Review Date: October 2019
Programme Code: / GB-GOV-50-PF-20-BHP (including GB-GOV-3-PF-HEA-911; GB-GOV-3-PF-HEA-913; GB-GOV-3-PF-HEA-926; GB-GOV-3-PF-HEA-BR-921; GB-GOV-3-PF-HEA-MM-921; GB-GOV-3-PF-HEA-MX-921; GB-GOV-3-PF-HEA-MY-921; GB-GOV-3-PF-HEA-PH-921; GB-GOV-3-PF-HEA-REG-921; GB-GOV-3-PF-HEA-TH-921; GB-GOV-3-PF-HEA-VN-921; GB-GOV-3-PF-HEA-ZA-921)	Start Date: / August 2018 (OBC approval)	End Date: / March 2023

Summary of Programme Performance
Year	18/19
Programme Score	A
Risk Rating	Moderate/Major

Summary of progress and lessons learnt since last review
This is the first formal annual review of the Better Health Programme (BHP). It covers the period from the approval of the Outline Business Case in August 2018 until September 2019. Overall, the BHP has made good progress in that period, achieving a number of key process milestones and establishing a good foundation for the delivery of results at output level. However, the time taken to contract delivery partners has been a lot longer than expected and has delayed the start of full implementation.
This review is being carried out four months into the Inception phase of Delivery. It is therefore too early to assess programme delivery fully. Instead, the review focuses on mobilisation of the programme, on the procurement of the Delivery Partners (DP) and the work carried out by the Strategic Partner (SP). The review will focus on the design, planning and governance of the programme.
This assessment of progress is based on a comprehensive assessment of i) what has been done so far and ii) preparedness for future delivery, including taking into account a range of perspectives from key partners and stakeholders. Notably, it will look at whether these phases have achieved key milestones, and have positioned the BH programme for success as it moves into full delivery.
A decision was made for the Prosperity Fund (PF) to invest in health, in recognition of the direct benefits (in terms of reducing mortality and morbidity) as well as the indirect benefits (in terms of promoting a productive workforce, contributing to GDP growth). The strategic case sets out a strong justification to focus on Non Communicable Diseases (NCD) to respond to the growing burden of disease in Middle Income Countries where the PF operates. Five pillars for engagement were selected as the best fit for these goals and would lead to both primary and secondary benefits.

SRO commentary

“I am grateful for this report and accept the recommendations made which we will implement. The coming months will be crucially important for the programme as it moves through the inception phase. This will critically provide greater: confidence on the approach to deliverability, reassurance on partner engagement; and confidence on benefit realisation. I welcome the comments added on the value provided by the programmes strategic partner and the decision to extend PHE’s role from the design to delivery phase. I look forward to the coming year”.

SRO
Better Health Programme
11 November 2019

Joint Funds Unit commentary

JFU notes the good progress the Better Health Programme has made over the last year and agrees with the review scoring and risk rating.

It is good to see that the strategic partnership with the NHS consortium is already help establish relationships with partner country health ministries, and that there is good alignment between primary purpose and secondary benefits.

However, JFU notes the shortened delivery window (2½ years) and the difficulty in being able to demonstrate impact in such a short timeframe. Delivery partner inception reports will be critical in building credible work plans for successful implementation.

The programme has an ambitious spending profile for FY19/20, given some inception reports are delayed and implementation will not start until January. JFU agrees with the reviewers that this assumption should be closely interrogated alongside JFU Finance ASAP.

Head of Prosperity Fund
31 October 2019

List of Acronyms
BHP - Better Health Programme (BHP)
CN – Concept Note
CTAS – NHS Consortium Technical Advisory Service
DFID – Department for International Development
DHSC – Department of Health and Social Care
DIT – Department for International Trade
DP - Delivery Partner(s) (there are 4)
FCO - Foreign and Commonwealth Office
G&I – Gender and Inclusion ALSO: GESI – Gender Equality and Social Inclusion
HEE – Health Education England
IIOC – Investment, Infrastructure and Operations Committee
JFU – Joint Funds Unit
KPIs – Key Performance Indicators
L&D- Learning and Development
LF - Log Frame
MoH – Ministry of Health
MoU – Memorandum of Understanding
MICs - Middle Income Countries
MREL – Monitoring, Reporting, Evaluation, Learning
NICE – National Institute for Health and Care Excellence
ODA - Official Development Assistance
PF – Prosperity Fund
PT – Programme Team
PHE – Public Health England
PM – Programme Manager
PMC – Programme Management Committee
QSB – Quarterly Strategic Board
SOBC – Strategic Outline Business Case
SOR _- Scope of Requirements
SP - Strategic Partner (made up of NHS bodies such as HEE and PHE)
ToC - Theory of Change
WEE - Women’s Economic Empowerment

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://www.gov.uk/government/publications/better-health-programme
DevTracker Link to Log frame:	Not yet published

The FCO-led Prosperity Fund Better Health Programme (BHP) will invest £79.3m over the next three years into improving health, and thereby contributing to economic growth, in eight partner countries (Brazil, Mexico, South Africa, Malaysia, Myanmar, Philippines, Thailand and Vietnam).
Following submission of a successful concept note, the Prosperity Fund Ministerial Board approved the development of the business case in 2017. The Strategic Outline Business Case (SOBC) was approved by the Cabinet Office, the Minister and FCO’s Investment, Infrastructure and Operations Committee (IIOC) by January 2018 and the Outline Business Case had achieved all of its approvals by 17 August 2018. The Full Business Case was approved by IIOC on 2 February 2019. An updated FBC for online publication will be published.

The strategic outline business case identifies five pillars, as the focus areas for intervention that represent best match between partner country priorities, potential for development impact and areas of UK capability. These are shown in the table below.

During the strategic phase, the FCO brought on board NHS partners, to help scope out the BHP intervention areas for each of the eight countries. The results of the scoping work were shared in a report submitted in June 2018 and includes the intervention areas selected by country, outlined below.

Table 1: Summary of BHP five Pillars and eight Countries
Pillars	1. NCD strategies	2. Digital health	3. Education and training	4. Provider performance improvement	5. Life sciences
Brazil					
Mexico			
South Africa					
Malaysia			
Burma			
Philippines					
Thailand					
Vietnam			

In short, by August 2018, the programme had agreed its design, including the countries and the budget split between them, as well as the five pillars in which interventions would be supported. The country budget allocations, were tentatively agreed as Mexico (£20m), Brazil (£15m), South Africa (£13m) and the five South East Asia Countries (£26m). The delivery model was also agreed, consisting of (i) an MoU with the NHS consortium as Strategic Partner (SP), and (ii) commercial contracts with four Delivery Partners (DP), to implement a programme of interventions in eight countries (Mexico, Brazil, South Africa and five in South East Asia). With these parameters set, the programme began its more detailed scoping work to maximise strategic benefits.
By July 2019, the programme has completed the procurement of its four delivery partners who were due to finalise their Inception phase in November 2019. Given the time lag between the scoping and the implementation phase, a number of the country priorities have changed and there has been a need to revisit and seek re-endorsement of from the Health Authorities during Inception.
Before the programme moves into the implementation phase it will be a critical point to clarify how the planned activities, will contribute to the three anticipated outputs and series of higher level outcomes and intermediate outcomes currently set for the programme. The five pillars have played such a strong role in the design and strategic phase that at times this has risked a loss of sight on the outputs, in particular the links to the outcomes and higher results anticipated.
It is expected that the final selection of interventions will be based on a mix of factors, including the available evidence, the national priorities, potential primary and secondary benefits, as well as de-conflicting with other donor/government investments. The interventions delivered will also be determined by the agreed programme delivery model (SP and DPs) and the timeline for delivery.
On programme planning and management, the main achievements over the reporting period have been:
1. Approval of the full business case that underpins programme delivery
2. Setting up all programme governance
3. Scoping interventions and building positive relationships with partner countries
4. Development of a joint MREL plan with BHP Theory of Change (ToC) and programme / country level Log Frames (LF)
5. Successful procurement of the 4 BHP DP and the SP
6. Building a programme team both in London and in-country

On financial spend, the programme received an initial allocation of £70k for FY17/18 but was later awarded transition funds to cover the Strategic Development phase. BHP received £2.25m for FY 18/19. Spend to date through, start up and transition funds, is reported as £ 1,850,000 for first two FYs and £3,146,000 to date.
On the Governance, the programme established a good practice early on during the design phase, by calling monthly Programme Management Committees (PMC) (chaired by the Programme Lead) and Quarterly Steering Boards (chaired by the SRO). These involve key decision makers from across FCO, the Department of Health and Social Care (DHSC), Department for International Trade (DIT), and the NHS. During Inception, in-country steering boards will also be created to ensure local ownership of delivery within the parameters of the global programme. The Programme Lead will be joining the cross-Whitehall Global Health Oversight Group to ensure strategic alignment with wider international health policy and programmes primarily in DfID and DHSC.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment (Primary Purpose)
The overall assessment of progress is an A – that the programme’s Outputs have met expectations. The A rating is given based on assessment against start up process milestones, with the proviso that it is too early to make any assessment against the programme outputs. Significant progress has been made to scope out and pre-position the BHP for delivery, including a high-level launch event in June 2019 at Wilton Park, which involved senior representatives from the eight BHP countries.
Going forward there are a number of moderate/major risks that could affect the programmes performance, these relate to (i) the timelines, (ii) the scope and (iii) country health authority buy in. All need to be carefully managed and mitigated to ensure that the programme performs well.
(i) Timelines: The BHP has gone through a lengthy strategic development phase to design, consult and scope the programme. The programme management processes, including the commercial arrangements were not always clear, which has led to a much longer strategic development phase. The original BC timeline was over ambitious and did not take into account the many steps involved at each stage. The expectation was that procurement would be completed from June 2018 to January 2019.
Table 2. Original and Revised BHP timelines
	Original BC timelines	Revised timelines
Strategic Development Phase	March to June 2018	March 2018 to June 2019 / (includes contracting)
Delivery Phase	January 2019 to March 2023	July 2019 to March 2023 / (includes Inception July-Dec 2019)

While the SP was brought in early in March 2018, the four DPs were only contracted in July 2019 and are still in their Inception phase that is scheduled to end in November 2019. With a number of the DPs struggling to complete their Inception work within this timeline, there are likely to be some further delays and full implementation may not start until early in 2020. This revised timeline suggests that the duration of implementation will be 2.5 years[1], shorter than the 3 years originally planned. This will change if there is an extension of the PF contract beyond March 2023, allowing for possible extension of the BHP implementation period.
[1] The current timeline is to begin from November 2022, to close by March 2023.
(ii) Scope: The programme has set a broad scope and ambitious high-level targets, which it anticipates achieving by March 2023 (Log Frame Version 4). The LF contains specific targets as follows:
- Impact: A healthy and more productive female and male workforce leading to higher rates of GDP growth
- Outcome 1: Reduced premature mortality and morbidity due to non-communicable diseases
- Outcome 2: Reduced avoidable mortality and morbidity from sub optimal patient safety and care
- Intermediate Outcome 1 (IO1): Increased coverage and utilisation of effective support and services for NCD prevention, treatment and management (especially women and marginalised groups)
- Intermediate Outcome 2 (IO2): Improved equitable access to safe and quality healthcare, especially for women and marginalised groups

At this stage, with the Inception still not completed and implementation plans not yet available, it is not possible to assess the likelihood of achievement at intermediate outcome levels or above. However, a review of the current plans and M&E tools shows a large leap between the activities and outputs planned and the intermediate outcomes to increase coverage and utilisation (IO1) and to improve equitable access (IO2). To address, once the implementation plans are available it would be helpful to revisit the extent to which the interventions planned will lead to anticipated changes at output level and above. A realignment may be necessary.
(iii) Health Authority buy in
In the period between the completion of the NHS scoping (August 2018) and the completion of the Inception phase (November 2019), four of the eight BHP countries have experienced elections with political changes (Thailand, South Africa, Brazil, Mexico). This has led to a need for re-endorsement of the programme (including the delivery model itself) and the areas of interventions with the relevant national Health Authority. In some countries, this has been relatively straightforward; in other countries, it has taken a lot more time for the FCO to get the commitment necessary to allow the Inception phase activities to proceed as planned.
Annual outcome assessment (Secondary Purpose)
The primary and secondary benefits are well aligned to promote opportunities from the BHP. Through close collaboration between the FCO and DIT, the BHP has taken steps to ensure links are made to the Healthcare UK campaign as well as with other UK health funding (e.g. Newton Fund, Fleming Fund). During the strategic phase, a number of ‘show and tell’ missions were arranged between the BHP countries and the UK to showcase various parts of the NHS. These efforts have helped to ensure that the Ministries of Health as well as the strategic and delivery partners are aware of the expertise that UK health sector businesses and the wider NHS can offer them.
Overall output score and description
At this early stage, it is not possible to assess progress against the three outputs identified in the BHP Log Frame, and there are no milestones set for this year (since they will be determined during Inception). This first assessment is, therefore, informed by a review of progress against a set of interim process milestones.
Key lessons (findings)
- The decision made to involve NHS partners in the design and scoping phase was extremely positive, opening doors with Ministries of Health (MoHs) – building government-to-government relationships.
- The programme should up its efforts to invest in relationship management at country levels with the MoHs. Out of the eight BHP countries, half experienced requests for changes. The time gap between the NHS scoping and Inception phase has meant that there has been a need to regain the commitment and readiness of the MoHs on the BHP; health ministries are not all fully on board and ready to move into implementation.
- This programme is complex, with multiple stakeholders, with multiple interests and requires stronger coordination, clearer articulation and more active management of roles and responsibilities.
- The BHP strategic governance board was established early in the design phase and has set good practices. However, it has not met since June 2019 and the next planned meeting is for when Inception is completed; it should continue to meet quarterly to review performance, address emerging issues and review risks etc.
- Commercial process: ensure sufficient detail is included in the Statement of Requirements (SoRs), to avoid extensive post-award negotiation and where a tender is for multiple countries/regions each one with its own contract, use one Invitation To Tender (ITT) for each contract.

Summary of Key actions (recommendations)
Governance:
The programme strategic board has not met since June and should revert to meeting quarterly rather than as and when required.
Resourcing:
1. The programme team should consider ways to provide more dedicated staff time to stakeholder coordination efforts and additional MREL expertise.
2. The programme should continue to review whether the countries are receiving the right level of support (PM/Advisory), which is proportionate to the budget allocations by country e.g. to support country teams work to ensure health ministries are fully on board and ready to move into implementation (see Rec. 6).
Inception:
1. Due in part to the anticipated scope changes, it is critical that the programme ensures that Inception report QA and approval mechanism is exhaustive and robust and feeds into properly updated and approved contracts to ensure a successful implementation.
2. When reviewing the G+I Inception plans it will be important for the programme to understand how the poorest will be targeted and how issues of inequity, gender, age, disability will be addressed.
Implementation:
1. Approaching the planned end of Inception it appears that health ministries are not all fully on board and ready to move into implementation. The programme team should carefully review this situation, working closely with Post and the Health Adviser network.
2. Roles and responsibilities of the various stakeholders of the BHP require strong ongoing definition and coordination, with dedicated staff time to this.
3. Once the planned activities and outputs are known, it will be important for the BHP to do a ‘light check’ whether the interventions planned meet the original basis for the strategic and economic cases, to ensure that investments planned are still likely to add value and generate the higher level results anticipated.

VfM and Financial Performance:
1. There is a need for the BHP to review the BHP 2019/20 and 2020/21 financial forecasts and adjust these in line with the implementation delays and remaining delivery timeline.
2. The BHP team to track and benchmark key DP costs including admin costs, consultancy fees and other key cost drivers.
3. The BHP team to review closely the Inception reports to minimise the risk of effectiveness being affected by scope creep.
4. During the planned revision to the ToC and Logframes following Inception, the BHP team should ensure that the logframe still aligns with programme objectives and that appropriate and robust milestones and indicators are in place to provide measurement of successful delivery.
5. The BHP programme team should closely monitor contract delivery and ensure it remains in line with desired outputs and the programme’s Primary Purpose and Secondary Benefits.
6. BHP team to plan specific actions, with monitoring and timelines, on how buy-in reluctance will be unblocked in relevant partner countries.
7. BHP to implement recommendations of G&I Scorecard assessment and ensure that DPs support these deliverables and have that role clearly defined in their contracts – see Equity
8. Progress on G&I to be added as an agenda item at Programme Management Committees and Strategic Board to provide greater focus.
9. It is crucial that mitigating actions (as identified and any additional) to the key risks are clearly identified by the BHP team, with clear ownership and timeframes.
10. The FCO BHP team should conduct regular checks of a sample of delivery partner invoices each year against individual receipts.

Commercial:
1. BHP team should closely monitor contract delivery and ensure it remains in line with desired outputs and the programme’s Primary Purpose and Secondary Benefits
2. BHP team and Post has to pay particular attention to the different approach required to manage the SE Asia Delivery Partner (DP) i.e. one size does not fit all – the DP should be encouraged to be flexible in their approaches in each of the five countries.

Monitoring and Evaluation:
1. Any changes to the LFs need to be dated and approved at the Strategic Board level.
2. The final BHP LFs (at programme and country levels) should include baselines, milestones and targets and link how risks are managed to ensure primary and secondary benefit realisation. This should also be set out in DP contract specifications.
3. All data sources need to be identified - including timelines and who is responsible.
4. The LF needs to include indicators to measure progress on secondary benefits, on gender and inclusion, and VfM.
5. The ToC (at programme and country levels) will require updating following the Inception phase. The links between outputs, intermediate outcomes and outcomes needs to be clearer and a realignment will be necessary for the implementation phase.

Summary of changes to the logframe since the last annual review
The original log frame was drafted as part of the SOBC in June 2018. The Log Frame was revised in 2019 and the latest version (V4) was used for this AR. Additional process milestones have been used for this AR, which are discussed in section C.

## C: DETAILED OUTPUT SCORING

It is too early to assess progress against the three outputs of the programme, as the programme is still at its Inception phase and the Log Frame outputs relate to the implementation phase. In the interim, it is possible to review progress against six process milestones, which the programme has used in its own self-evaluation for 2018-19. These relate to the programme design, scoping and early Inception phase.

Output Title	Pre-implementation - programme set up process completed
Output number per LF		Output Score	A
Risk:		Impact weighting (%):
Risk revised since last AR?	N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
The programme has the expertise and resources it needs to succeed	Number of BHP staff, central and in-country recruited appropriately skilled and in place / Number of delivery partners appointed following a robust and successful procurement process / Number of contracts. MOU that pass quality assurance criteria	FCO global team and country teams in place / 4 Delivery Partners contracted in June/July 2019 / MoU with strategic partner in March 2018
Programme conceptualised, scoped and set up to achieve results,	Full business case meets quality requirements and is approved by IOCC / Programme governance implemented and functioning effectively at a strategic and programme management level / Number of programme management tools developed and in use by programme / Evidence that programme working towards a level of ambition that build assets, capabilities and opportunities for women and marginalised groups	SOBC approved in Aug 2018 / Programme Governance established with four strategic boards held and monthly programme committees. / Tools for MREL and Forecasting in place / VFM score card completed / GEA compliance, G&I score card/plans completed.
NHS Consortium as Strategic Partner brought on to advise FCO	Number of in-country scoping visits which resulted in agreement with partner countries on areas of collaboration / Number of country specific reports and country results chains submitted / Recommendations, advice and proposal developed on the role of the NHS as a Strategic Partner in the delivery phase.	NHS SP scoping work, including country visits, completed June 2018 / NHS MoU revised for implementation support / NHS update reports every 2 months
INCEPTION A clear plan is in place for the detailed design of the programme, following the strategic development phase.	Number of delivery partners successfully completing the 17 inception milestones on time and budget	Inception phase outputs from 4 delivery partners due Nov (with some delays expected)
SH Engagement Support and buy in has been secured from key stakeholders including Ministries of Health and other stakeholders in partner countries.	Number of official communications on the BHP sent to Government partner MOH / High profile launch event of BHP brings together stakeholders from all BHP countries / Number of country stakeholder engagement plans/strategies developed / Number of stakeholder types consulted and involved in strategic development phase / Number of communication materials developed and used by the programme	BHP introduction letters sent to MoHs by SRO / Wilton Park Launch event completed in June 2019 / Stakeholder consultation for design work completed, engagement for the inception phase still underway / Communications strategy developed
Secondary benefits (Healthcare UK) non-ODA -Engaging UK NHS, Business sector, to promote awareness in the opportunities from BHP.	Number of activities conducted in support of secondary benefits	6 inward visits supported, plus several other events to showcase NHS and healthcare UK

The programme has the expertise and resources it needs to succeed
Since the development of the CN, there has made steady progress to bring on board the skills and expertise to manage the programme. At the FCO the central Programme Tean in London consists of a Head of Programme, a Programme Manager (PM) and two part-time Contract Managers. The focus has been on building strong in country capacity, through the recruitment of FCO PM and Health Advisers in Post, which are now all in place. In addition there are FCO G+I, VFM and SB experts who are available to support the programme, plus commercial expertise to advise on contracts. Added to this resource is the NHS team, with the unit in London, including an MREL expert and HSS advisers to provide dedicated support to countries. Within each of the four DPs there are also technical experts available to support delivery work. Together these multiple resources bring a strong range of expertise that suggests that the programme is adequately resourced to succeed. This will need review and given the multiple stakeholders it will require strong ongoing coordination.

Programme conceptualised, scoped and set up to achieve results, with attention to G&I and VFM and an approved business case detailing quality strategic, economic, commercial, financial and management cases

As discussed in other sections, the programme design has been strongly informed by five pillars and eight countries which are set out in the BC. Strong strategic and economic cases are put forward for investing in health and in NCDs, however there is no mention of WHO NCD ‘best buys’[2] which are the recommended interventions for the prevention and control of non-communicable diseases. It is also not always clear whether the BHP has a specific disease focus (diabetes, cancer).
[2] https://www.who.int/ncds/management/best-buys/en/
At the design phase, the programme has considered how it will contribute to reducing gender inequality and it has the potential to be empowering on gender issues. Given that the programme is now nearing the end of its Inception phase, it will be good to recheck the plans against the strategic and economic cases to ensure fit. Equally, it will be important to review where interventions will be delivered and who the intended beneficiaries are in each country.
NHS Consortium as Strategic Partner to the FCO providing technical inputs to programme and collaboration with partner governments in Brazil, Mexico, South Africa, Malaysia, Philippines, Thailand, Vietnam and Myanmar
During the initial phase, the FCO Programme Team brought on board strategic advisory support and specialised health expertise through a MoU with NHS consortium partners, led by Health Education England.[3] The NHS teams conducted a four-month country scoping visits from March to July 2018 to create country buy-in and to refine the priorities and projects based on country needs. This scoping informed the development of the SoR for contracting of DPs. Following the scoping work, it was agreed that the consortium of NHS partners would continue to provide strategic advice to the FCO PT in its delivery phase, in the following four areas.
[3] NHS consortium partners include: Health Education England (HEE), Public Health England (PHE), NHS Improvement (NHSI), Care Quality Commission (CQC), NHS Digital, NHS England.
1. Expert advisory input
2. Critical appraisal and facilitating cross-programme learning and building capacity at Posts;
3. Support to the FCO SRO and Programme Lead in programme level strategic decision-making through technical knowledge-based recommendations;
4. Facilitation of UK Global Health Diplomacy, ensuring the BHP maintains a system to-system dialogue to maximise the benefits of the programme.

The Strategic Partner functions are expected to be performed by the combination of: The BHP NHS Joint Unit (“the Joint Unit”), including a specified number of UK health systems advisors (“the Advisors”) and the NHS Consortium Technical Advisory Service (CTAS). The current MoU (version 21) was signed in May 2019, has an agreement in place until March 2020, with subsequent extensions expected into 2020-21. The NHS partners have established an NHS steering committee to coordinate their work for BHP.

INCEPTION - A clear plan is in place for the detailed design of the programme, following the strategic development phase

The four contracted DPs have been tasked with completing 17 milestones as part of the four-month Inception phase. It is anticipated that the Inception phase may take longer than planned. Two of the DPs have experienced delays and have already requested extensions, mainly due to priority shifts in country with changes in the Ministries of Health. A QA process for review of the Inception reports has been set out; the reports will be reviewed by the programme team, FCO Commercial and the Strategic Partner to ensure delivery and contractual compliance. The clearance of all the Inception phase deliverables will be a large task and any subsequent revisions of contracting arrangements for implementation may take time.

SH Engagement Support and buy in has been secured from key stakeholders including Ministries of Health and other stakeholders in partner countries
Interviews with FCO Health Advisers in-country suggest that support and buy in from the health ministries in partner countries has not yet been universally gained. Changes in government since SP scoping was concluded in Brazil, Mexico and South Africa have unsurprisingly required a re-establishment of relationships and a potential re-scoping of the interventions. However, it is still a concern that approaching the planned end of Inception it appears that health ministries are not all fully on board and ready to move into implementation. The programme team should carefully review this situation, working closely with Post and the Health Adviser network.
Secondary benefits (Healthcare UK) non-ODA - Engaging UK NHS, Business sector, to promote awareness in the opportunities from BHP

Through close collaboration between the FCO and DIT, the BHP programme has made good progress to ensure links are made to the DIT Healthcare UK campaign as well as with other UK funding (Newton Fund, Fleming Fund), where they exist. During the last year, a number of inward ‘show and tell’ missions were arranged between the BHP countries and the UK to showcase various parts of the NHS (e.g. Brazil, Malaysia, South Africa, Mexico - NHS Innovation, NICE, UK digital). There was also a high level BHP launch event at Wilton Park in June 2019, which included senior delegations from all eight countries. These efforts have helped to ensure that the Ministries of Health as well as the strategic and delivery partners are aware of the expertise that UK health sector businesses and the wider NHS can offer them. As a result, the primary and secondary benefits are well aligned to promote opportunities from BHP.
Output Title	Increased use of digital technology and improved integration and utilisation of health information and data to inform practice and tackle the burden of NCDs and improve quality of care
Output number per LF	1	Output Score	NA / Still under development
Risk:	Minor/Moderate/Major/Severe	Impact weighting (%):
Risk revised since last AR?	Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
Key Points: Key indicators are under revision. No milestones were set.

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendations
Output Title	Capability building through education and training, knowledge exchange, strategy and policy development/implementation to tackle the burden of NCDs and improve quality of care
Output number per LF	2	Output Score	NA / Still under development
Risk:	Minor/Moderate/Major/Severe	Impact weighting (%):
Risk revised since last AR?	N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Key Points: Key indicators are under revision. No milestones were set.

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendations
Output Title	Life sciences research and development and health technology assessment capability to tackle the burden of NCDs and improve quality of care
Output number per LF	3	Output Score	NA / Still under development
Risk:	Minor/Moderate/Major/Severe	Impact weighting (%):
Risk revised since last AR?	N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Key Points: Key indicators are under revision. No milestones were set

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendations
The recommendations set out below are linked to the six process level milestones used to review progress in 2018/19.
Governance:
The programme strategic board has not met since June and should revert to meeting quarterly rather than as and when required.
Resourcing:
- The programme team should consider ways to provide more dedicated staff time to stakeholder coordination efforts and additional MREL expertise.
- The programme should continue to review whether the countries are receiving the right level of support (PM/Advisory), which is proportionate to the budget allocations by country e.g. to support country teams work to ensure health ministries are fully on board and ready to move into implementation.
Inception:
- It is critical that the Inception report QA and approval mechanism is exhaustive and robust and feeds into properly updated and approved contracts to ensure a successful implementation.
- When reviewing the G+I Inception plans it will be important to understand how the poorest will be targeted and how issues of inequity, gender, age, disability will be addressed.
Implementation:
- Approaching the planned end of Inception it appears that health ministries are not all fully on board and ready to move into implementation. The programme team should carefully review this situation, working closely with Post and the Health Adviser network.
- Roles and responsibilities of the various BHP stakeholders of the BHP require strong ongoing coordination, with dedicated staff time to this.
- Once the planned activities and outputs are known, it will be important to do a ‘light check’ whether the interventions planned meet the original basis for the strategic and economic cases, to ensure that investments planned are still likely to add value and generate the higher level results anticipated.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
To date (at 8 October 2019) expenditure on the programme has been £3,146,000 compared to an approved budget of £79.3m.
In the first year FY2017/18 there was an over-spend, caused by a faster mobilisation of staff at Post than expected. This was followed by an under-spend in FY2018/19 because the process of achieving the sign off for the business case took longer than anticipated and it was envisaged early on in that FY that delivery would start towards the end of the year. This led to the budget that was originally allocated to delivery being moved to staff budgets during FY2018/19 (hence, the apparent under-spend on staff).
The original 2019/20 budget was £15.6m, however due to procurement and Inception delays, £1.6m was returned to the centre. The revised end forecast is that spending will be on budget. However once Inception is completed, this forecast should be revisited.
The SP underspend forecast is due to uncertainties surrounding the end of their scoping role and the start of their revised role as strategic advisers on the programme, making it difficult to accurately forecast spend. In particular, it is not clear the extent to which the NHS CTAS drawdown facility will be called upon by DPs and how NHS costs will be covered if fewer drawdowns take place than anticipated.
During 2019/20, the key area of spend has shifted to the delivery partners following the signing of contracts in July 2019. Delivery phase spending is currently forecast to be close to budget, however the Inception phase that was originally planned to be completed by October 2019, allowing implementation to start in November, is at significant risk of delay. Thus, implementation may not start until January 2020, leaving a significant proportion of the 2019/20 delivery phase budget to be spent within three months, which seems highly ambitious.
VFM R1 There is a need to review the BHP 2019/20 and 2020/21 financial forecasts and adjust these in line with the implementation delays and remaining delivery timelines.
The expected delay to delivery should only have a marginal effect on benefits. The NPV is unlikely to be significantly affected because benefits should not be more severely delayed than the costs; the benefits are expected to be delivered after the programme has ended by which time it is likely that the interventions will be completed. See Section F – Commercial, for learning from contractual delays to mitigate these risks in future.
Administration costs are currently running at around 23%, above the 3.5% guideline for ODA programmes. The business case did not analyse this profile. However, it is not an unusual profile for such a programme due to the upfront costs involved in setting up the programme (including scoping and procurement phases and very limited delivery spend to date). Over the life of the programme, the admin costs are expected to be below guideline at around 3.3% of the total programme allocation of £79.3m.
VfM performance compared to the business case and assessment of VfM in the programme
As the programme has yet to enter implementation, the review will consider the initial scoping work, the procurement of suppliers and the potential the programme has to achieve VfM as planned.
In late September 2019, evaluation and learning (EL) advisors completed a VfM scorecard, which concluded that the programme has good evidence to suggest that appropriate processes are in place to ensure the future delivery of VfM. The findings were summarised as follows:
Overall, there is good evidence to suggest that appropriate processes are in place to ensure the future delivery of VfM, albeit with further attention required in some areas.
A summary of the VfM scorecard can be found at Annex A.
The review team’s interviews and review of evidence supports the VfM findings of the scorecard, as follows.
Economy and Efficiency
To assist with the scoping and development phase, the BHP PT brought in two expert partners to support the design work. A consultancy company with an established track record in healthcare and ODA work was contracted to undertake an initial feasibility report, and an NHS Consortium was requested to partner (via MOU) with the FCO to act as the strategic design partner. A comprehensive series of country scoping visits took place with tailored assessments and reports for each. The SP team also worked with FCO Post teams to engage and build relationships with the health ministries in each partner country, thereby establishing the groundwork for the current Inception work.
The evidence from the scoping phase led by the SP suggests a good level of economy. A competitive tender process was run with the support and oversight of FCO Commercial to select commercial DPs. The four winning suppliers were tendering under the FCO’s PF Procurement Framework; to get on to this framework the bidders had already undergone a series of quality, financial and legitimacy tests before winning the BHP ITT. The programme should consider benchmarking of DP costs in order to ensure economy going forward.
VFM R2 the BHP team to track and benchmark key DP costs including admin costs, consultancy fees and other key cost drivers
The efficiency challenges for the programme centre on the ability of the DPs to implement the programme in line with the objectives. The inception delays are largely due contractual and political delays and are therefore not a reflection of breakdowns in efficiency.
It is important that the Inception reports due next month are carefully reviewed to ensure the revised scope still delivers the overall objectives of the programme as described in the business case and that subsequent contract delivery is closely monitored. In addition, clear, tightly managed and robust governance processes will be key to ensuring the efficient running of the programme (see also Recommendation 1: Governance).
VFM R3 the BHP team to closely review the Inception reports to minimise the risk of effectiveness being affected by scope creep.
VFM R4 It is equally important that the ToC and LF are revised after Inception and have robust and measurable milestones and indicators to provide measurement of successful delivery.

VFM R5 BHP programme team should closely monitor contract delivery and ensure it remains in line with desired outputs and the programme’s Primary Purpose and Secondary Benefits.

Effectiveness
The BHP has not yet commenced delivery, so effectiveness is assessed in terms of whether the programme’s performance to date suggests a variance from the estimation of expected programme benefits in the business case.
The BHP business case estimated that the programme would deliver discounted primary benefits of £69m, measured in terms of the intrinsic value of improved health to citizens. The overall impact is expected to be a higher rate of GDP growth due to larger, healthier and more productive female and male workforce.
The benefits estimates in the business case are themselves uncertain given the difficulties of estimating VfM of healthcare system strengthening interventions up front. Moreover, the appraisal is based on conservative predictions covering only some elements of expected benefits, therefore those benefits are already an under-estimate of the likely outcome. The programme’s activities so far suggest that it has the right building blocks to enable it to deliver against the conservative primary benefit-cost ratio estimate of 1.3. Principally:
- The programme has assembled a strong team of in-country Health Advisers that, with proactive Post support, is already providing excellent support and liaison in-country
- The continued involvement and commitment of the NHS consortium is a major ongoing strength of the programme in particular with their support to the DPs
- Four DPs have been appointed each of which is an experienced and recognised aid delivery organisation, notwithstanding the Inception delays

The main risk to benefits is that not all the partner countries will successfully implement all or some of the proposed interventions due to lack of commitment from the health ministries. Although there is evidence of insufficient buy-in in some countries at this stage, it is likely that the programme DPs and Health Advisers, supported by the NHS consortium, will unblock any initial reluctance and successfully implement in most, if not all partner countries.
VFM R6 BHP team to plan specific actions, with monitoring and timelines, on how buy-in reluctance will be unblocked in relevant partner countries.
This slow adoption is linked to the second risk of delayed timelines. In particular, delays to Inception in some countries are likely to reduce the implementation period available, thereby potentially reducing impact. Nevertheless, provided the sustainability efforts described in the business plan are carried through, it is likely that the benefits will accrue as planned beyond the formal end of the programme. MREL activities will continue beyond the end of the programme (organised and sponsored by JFU) and which will be reflected in the M&E plans. DIT will be the main drivers of ongoing secondary benefits.
The third risk is that any change to the original scope of programme interventions agreed at Inception may reduce the primary benefits identified in the business case. The elapsed time between the SP scoping done for each country and the inception work by DPs makes it a risk specific to this programme. It is likely that this risk will materialise, however any changes in scope may be positive rather than negative. Nevertheless, provided the Inception reports are carefully reviewed, it’s likely that any scope change can be either minimised or changed in a direction that is still beneficial to programme outcomes and hence benefits.
The business case also estimated that the programme would deliver discounted secondary benefits of £55-66m from export opportunities arising from NCD strategy and education. This also represents a relatively conservative benefit-cost ratio of 1.1:1. The programme’s intervention areas should result in opportunities for international providers of health services, including organisations in the UK. For example, improving provider quality may involve training and education of healthcare workers; UK health organisations have a significant comparative advantage due to the reputation the NHS has for quality, efficiency and fairness. UK health companies also have expertise across the thematic areas relevant to the BHP.
Whilst the same timeline risks (outlined above) apply to secondary benefits, the efforts of the programme to engage and liaise with DIT and Healthcare UK suggest a good likelihood of achieving the SB expectations. Indeed, early indications are that there have already been some positive signs on secondary benefits. In particular, DIT commented that they are beginning to see a flow of opportunities building in response to the BHP activities. They are also ensuring that their High Value Campaign on health is linking with BHP initiatives.
Equity
The programme has worked closely on the equity objective with the Social Development Advisers and the PF’s Evaluation and Learning partner, WYG. The result of the latest G&I Scorecard (September 2019) is ‘Green’ overall with a Gender Equality Measure (GEM) Score 1 – significant, meaning gender equality is an important and deliberate objective of the programme. Key recommendations were for the programme to take further steps to ensure distribution of benefits to support inclusive growth and to define how the indicators in the LF will be measured in the lifetime of the programme.
VFM R7 BHP to implement recommendations of G&I Scorecard assessment and ensure that DPs support these deliverables and have that role clearly defined in their contracts:
- Specifically analyse the G&I-specific dimensions of proposed interventions such as health care worker training, a guidance/curriculum, diagnosis of diseases, health data systems, and health policies/regulation, and use this to inform its interventions.
- Specific outcomes for poorer and female populations should be clearly described
- More specific analysis of the G&I dimensions and barriers in each of the country contexts, and an exploration of how the programme and its specific interventions will address these.
- Consultation with civil society, concerning G&I issues would be important in the design phase.
VFM R8 Progress on G&I to be added as an agenda item at Programme Management Committees and Strategic Board to provide greater focus.
Overall VfM Assessment
Overall, the programme performance on budget, milestones and progress towards outputs to date suggests it still represents value for money, even if the full forecast spend is not achieved in FY2019/20, since programme spend is likely to accelerate sharply in FY2020/21 and return to the original overall spend profile.
The caveat is that the programme is still at a relatively early stage i.e. before Inception has been completed and implementation commenced therefore this assessment is only based on programme organisational and preparation activities. A network of strong country Health Advisers, experienced Delivery Partners and the NHS consortium strategic input are all positive factors that point to the programme being well placed to help deliver VfM, notwithstanding the engagement and timeline risks discussed.
VFM R9 It is crucial that mitigating actions (as identified and any additional) to these key risks are clearly identified by the BHP team, with clear ownership and timeframes.
Quality of financial management
The BHP has put financial management processes in place including setting up appropriate number of project codes, allocating budgets and monitoring expenditure and invoicing. There is some evidence that some early budget allocations were, in hindsight, poorly forecasted. It appears lessons were learnt and the current year allocations were better forecasted at the beginning of the FY. However, as described, the supplier spend forecast now looks less likely to be met although this will not be certain until Inception reports have been received and the forecasts have been revised.
The quarterly reports to the PF’s Joint Funds Unit explain the financial position in adequate detail and describe the financial risks and issues. There is evidence that financial matters are discussed and actively managed at the Strategic Board and the Programme Management Boards.
The MOUs between the FCO and the NHS consortium have expenditure limits defined providing high- level cost control. As the programme’s SP, the NHS has reported current and forecast spend against budget, project progress and risks via monthly dashboards to the FCO BHP team since February 2018.
The FCO BHP team have set up purchase orders for each DP, each of which submits invoices for services provided to the programme, with accompanying deliverables schedule, for payment against FCO Purchase Orders. The FCO Programme Manager checks these before being passed for payment and an audit trail of all approvals is kept.
PT experience so far with DPs in terms of timeliness and accuracy of financial reporting has demonstrated early evidence of good documentation and the following of good practice. Nevertheless, in order to manage fiduciary risk, a more thorough check of DP invoices against receipt evidence should be regularly made.
VFM R10 the FCO BHP team should conduct regular checks of a sample of delivery partner invoices each year against individual receipts.

Table 3: Financial Report and Statement
Date of last narrative financial report	6 October 2019 (PST Programme Monthly Spend September 2019)
Date of last audited annual statement	None

E: RISK
Overall risk rating: Moderate/Major
The review’s conclusion is that the main risks to the programme are that:
- The revised scope following Inception revisions might not remain aligned with the programme’s desired outcomes (see recommendation VFM R3)
- The delay to the timelines may have left insufficient time for the programme to deliver against planned Intermediate Outcomes and Outcomes (see Implementation recommendation 7)
- The political shifts and subsequent changes in the Ministries of Health in each of the partner countries may impact on implementation, requiring a re-establishment of relationships and buy-in in a number of countries.
Overview of programme risk
There is good evidence that risk on the programme is well managed. Programme and country risk registers are maintained and Health Advisers report back on in-country risk. Risk is reported and analysed in detail on the quarterly reports to the JFU, and risk is discussed at the Strategic Board and PMC meetings.
The primary risk to the Better Health Programme is that timetable for implementation is short, and the rate of mobilisation required is rapid. If the programme goes into implementation by January 2020 this leaves around two and a half years of implementation. This risk has been increased because the contracting process was extended far longer than the programme anticipated (see commercial section), delaying Inception by 3-4 months. In several countries, there is also an emerging risk that the Inception phase itself (currently expected to complete in November) may experience further delays; the evidence suggests a high likelihood of this risk materialising with subsequent impact on implementation timelines. The impact of these delays is primarily that they result in is there being less time and budget available to deliver the programme interventions, reducing the programme’s ability to deliver its intermediate outcomes and outcomes.
As detailed design is completed, individual country projects will build a clearer picture of the delivery risks in each country, which will feed into the overall programme risk profile. Managing these risks to prevent them from becoming issues will be key. This will require good communication between the BHP team, Health Advisers and Delivery Partners so that the programme team can maintain good visibility of the risk and the progress of the mitigations being deployed.

F: COMMERCIAL CONSIDERATIONS
Delivery against planned timeframe
The programme undertook a lengthy procurement process which resulted in some delays to the original programme timetable. ITTs went out at the end of October 2018 and tender evaluation took place in Jan/Feb 2019. Contracts were awarded in March/April 2019 and following contractual negotiations, contracts were signed with all successful delivery partners in June/July 2019 and Inception commenced. Three contracts are to deliver support to a single country (Brazil, Mexico, South Africa) and the fourth was a regional contract covering five SE Asia countries (Vietnam, Malaysia, Thailand, Myanmar, Philippines).
The programme wrote the SoRs for the ITT with review and assistance from the Strategic Partner and FCO Commercial. The tender and evaluation process was conducted within the programme time-scale. Eight Framework suppliers submitted a total of 12 bids.
The evaluation phase was carried out in compliance with FCO Commercial guidelines and included a representative team of evaluators. The evaluation panel members felt that the bids were generally of a high standard and panellists had a credible range of options to consider. Following completion of the evaluation of the bids, four moderation meetings – one per Lot – were held and winning bidders agreed.
The main delay took place during the post award contracting phase that lasted around 3 months. This was due to extensive contract negotiations that were required to finalise the contracts with suppliers prior to final signing. The main reasons for this extended process were that i) it was not originally understood how much detail was required in the SoRs, consequently this had to be negotiated during the contract phase ii) one ITT went out covering four contracts whereas in hindsight it would have been better to have four ITTs (the process followed on other PF tenders). Learning points on this are recorded at the end of this section.
Overall, the evidence suggests that a comprehensive and thorough procurement exercise took place and that FCO Commercial guidelines were followed throughout.

Performance of partnership(s)
As the programme is only four months into Inception it is hard to judge the performance of the DPs at this stage. However, early monitoring and management of the Inception phase indicates good progress has been made. The engagement by the DPs so far has been positive and constructive, including to managing the risk posed by potential delays to Inception. Many Inception deliverables have already been signed off by the programme team and DPs have responded constructively to feedback where the programme team has asked for further work on the deliverables before signing them off.
The SP performance has been consistent and professional with positive comments noted from a number of stakeholders. They played a critical role in helping to shape the ToC and programme / country log frames, as well as securing initial partner government buy-in. Furthermore, they have fostered close and collaborative relations with the appointed Delivery Partners, including providing themselves as a sounding board for ideas for interventions. They have been a formal part of the review process for all Inception deliverables and have provided valuable feedback to help strengthen those. The programme team has asked them to develop a more analytical appraisal of the proposed DP interventions and expected outputs.
The use of a SE Asia regional contract requires a different approach to contract management of the supplier. There was some evidence that the DP was tending towards a one-size-fits-all approach to the five countries in the region that has the potential to create difficulties. With this in mind, it is recommended that the BHP team and Post HAs pay particular attention to the different approach that will be required to manage the SE Asia DP.
Changes in the Delivery Plan
As set out in the risk section above, there are emerging risks to the Inception timeframe which is currently due to end in November. While the full likelihood and impact of those risks is still being proactively explored with the delivery partners, a reasonable estimate would be that Inception could be delayed in some countries by up to eight weeks which could effectively mean that implementation starts in January 2020.
Commercial learning points and recommendations
- Ensure sufficient detail included in SoRs, to avoid extensive post-award negotiation
- Where a tender is for multiple countries/regions each one with its own contract, use one ITT for each contract
- BHP team and Post Health Advisers to pay particular attention to the different approach required to manage the SE Asia DP.

G: Business Environment

How has the business community and business environment responded to the programme?
The business community is seen as international healthcare businesses, UK based healthcare businesses and NHS Arm’s-Length Bodies that sell NHS services overseas.
DIT has two dedicated BHP business relationship managers who have spearheaded outreach to all aspects of the business community through various channels: fact finding missions in partner countries (e.g. scoping in Brazil), speaking at numerous conferences and exhibitions, organising out-bound (to partner countries) trade missions to Vietnam, Philippines, Malaysia, and in-bound (to UK) trade and fact finding missions for foreign health ministers / trade delegations. DIT so far have engaged 88 market businesses, and engaged 47 government stakeholders from programme partner countries.
Anecdotally, DIT are reporting strong interest from the business environment. Also, when the FCO provided Skype briefing sessions for non-framework suppliers, there was a strong interest in the programme from a range of small to medium sized suppliers who wanted to partner up with the Framework companies. Because the programme is still at a comparatively early point in its maturity, and the interventions have not started, it is still too early to judge:
(a) what interventions could present specific opportunities for international and UK business
(b) how early expressions of interest from international and UK business could / will convert into formalised attempts by them to bid for work
 What role has non-ODA spending played in promoting programme objectives?
Non-ODA spending has helped to articulate what the programme is aiming to achieve (through a series of engaging videos recently released) and has brought it to the attention of the international business and the NHS. With the latter, Public Health England and Health Education England have started to grasp the potential for the programme to form part of a long-term strategic government-to-government partnership and are factoring the role of the BHP into their vision for the NHS over the next 10-15 years.

H: MONITORING & EVALUATION
As with the BHP programme overall, there are multiple stakeholders responsible for M&E of the BHP. To help manage this, one joint MREL plan was developed in August 2019, which sets out who is responsible for what. The main tools for monitoring and evaluation of the BHP are detailed below:
Log Frame - The LF informs the BHP programme. The LF was revised during the scoping phase, based on the country visits. There is a large gap between the outputs and the anticipated intermediate outcomes, outcome and impact indicators. The revised LF was used to guide the SoR for contracting the DPs. Work to finalise the country level log frames is now underway by DPs as part of the Inception tasks.
Theory of Change – The ToC was developed during the scoping phase and sets out the causal pathways and assumptions between interventions and higher level results. Country level ToC are being developed by the DPs as part of their Inception phase deliverables.
Progress monitoring is currently through Country Post submission of monthly flash reports, which are compiled into a monthly programme dashboard for the Programme Management Committee. Areas reported against include delivery confidence, finance, staffing, commercial, risk, key achievements. Monthly progress updates are also provided through a report compiled for the portfolio manager to be discussed with the FCO Head of PF. Quarterly reports are compiled and submitted to JFU. Currently a manual process, this will now be generated through Prospero from October 2019.
Evaluation: An Evaluation approach paper was developed in March 2019 and submitted to EQUALS for approval, scoring a ‘good’ rating. It builds upon the ToC and sets out the approach for the BHP evaluation, with plans for an annual cycle over the implementation period. The Evaluation approach includes a set of evaluation questions and learning needs of the programme and the agreed country sample for cycle 1. In July 2019 it was decided to delay and synchronise cycle 1 evaluation report to just before the next AR (Oct 20) and instead conduct a short evidence review for this AR (delivered Sept 19).
In short, the various M&E tools have been drafted but now need to be finalised.
MREL Recommendations:
- Any changes to the LFs need to be dated and approved at the Strategic Board level
- The final BHP LFs (at programme and country levels) should include baselines, milestones and targets and link how risks are managed to ensure primary and secondary benefit realisation. This should also be set out in DP contract specifications
- All data sources need to be identified (including timelines and who is responsible)
- The LF needs to include indicators to measure progress on secondary benefits, on gender and inclusion, and VfM
- The ToC (at programme and country levels) will require updating following the Inception phase. The links between outputs, intermediate outcomes and outcomes needs to be clearer and a realignment will be necessary for the implementation phase

Annex A – Summary of Value for Money Scorecard
(from ‘Evidence Update – Better Health Programme; September 2019)

Scorecard Element	Quality of evidence	Commentary on quality of VfM evidence
1. Relevance and robustness of VfM measures in place	Adequate	Programme documents mention the concept of VfM and the ‘four Es’ framework and discuss how VfM will be addressed in programme management. However, there are few VfM indicators in the log frame or MREL plan. The Programme Team has agreed to explore this further.
2. Approach to procurement and cost containment	Good	A positive approach to procurement has been adopted, with significant efforts to ensure that Delivery Partner contracts contain costs and ensure VfM. There may be potential to restructure some aspects of the NHS Strategic Partner contract to ensure VfM.
3. Efficient use of resources and inputs by Prosperity Fund interventions	Good	Appropriate processes are in place to track absorption and measures are being considered to monitor efficiency. The significant investment in the Strategic Development Phase has added value and is felt to be appropriate.
4. Validation of PF ToC causal pathways (for primary & secondary benefits)	Adequate	A high-level ToC is in place with some evidence to validate the causal pathways for the generation of primary and secondary benefits. More detail is expected through the country workplans, which would likely upgrade this ranking.
5. Sustainability of programme activities	Little	There is little evidence of programmatic or financial sustainability being considered or planned for, with no sustainability strategies or plans in place.
6. Ability of leadership, management and oversight structures to support delivery	Good	There is good evidence of programme leadership, management and oversight structures in place to support programme delivery, and reflective of good governance.
7. Strategies and measures adopted to enhance delivery and mitigate risk	Adequate	There is adequate/good evidence of strategies and measures adopted to enhance delivery and mitigate risk. Some improvements could be made to systematically follow up on all identified risks.
8. Equity of programme design and approach	Good	There is good evidence that equity has been considered in the design of the BHP, with clear intent (albeit with some concerns on how it will happen) to translate this into implementation.
OVERALL VfM ASSESSMENT	GOOD	There is good evidence to suggest that processes are in place to ensure the future delivery of VfM, with further attention required in some areas.