Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Global Trade Programme
Programme Value: £150 million		Review Date: 10 – 20 June 2019
Programme Code: / GB-GOV-50-PF-11-GTP (including GB-GOV-3-PF-TRA-911; GB-GOV-3-PF-TRA-913; GB-GOV-3-PF-TRA-RSA-925)	Start Date: / April 2019	End Date: / March 2023

Summary of Programme Performance
Year	2019
Programme Score	A
Risk Rating	Moderate

Summary of progress and lessons learnt since last review
This is the first annual review of the Global Trade Programme (GTP). Overall, the GTP has made good progress in the year since its Outline Business Case was approved, delivering a number of key process outputs and establishing a firm foundation for the delivery of its overall objectives. This review is being carried out two months after approval of the GTP Full Business Case, and subsequent commencement of the programme’s inception phase. It is therefore too early to robustly assess full programme delivery; this annual review therefore focuses on mobilisation of the programme as well as assessing the procurement of the GTP Service Manager (the key process output over the last year).
Particular achievements of the programme over the last 12 months include: setting up all programme governance, systems and processes for managing a flexible fund during delivery; successful procurement of the GTP Service Manager (the key delivery contract for the programme); production of a robust full business case that will underpin programme delivery; building positive relationships with key partner institutions (both multilateral organisations and in partner countries); and building a programme team both in London and in-country that is ready to deliver. The programme appears to be on track to deliver the planned outputs of the inception phase, but as none of the key milestones are due for completion until after the review it is currently too early to assess this with any certainty. Similarly, the GTP Full Business Case demonstrates that the programme is expected to deliver value for money (VFM) – however it is too early to test outputs to see whether this expected level of VFM is being achieved.
The GTP faces a number of key risks to delivery. The timetable for implementation is short, and the rate of mobilisation required is rapid (with spend forecast to jump from approximately £3m last year to £39m this year). The GTP has set an ambitious timeline, which includes not just mobilisation of the Service Manager, but also delivery of five pilot projects. In particular the Service Manager has had to move quickly in terms of business case development and procurement for the pilots to be delivered during the inception period. Managing these challenges will be key to starting the delivery phase in the best possible shape. This will require good communication between the EY and GTP teams, especially overseas as efficient sign off and agreement on authorising business cases will be tested in practice. The spend profile will continue to be tested given the acceleration in spend for FY19/20 and careful monitoring of spend and accurate forecasting will remain crucial. VFM will continue to be tracked as programmes move into delivery in order to provide evidence that primary objectives and secondary benefits are being achieved with appropriate governance, monitoring, reporting, evaluation and learning systems built into the process to track these outcomes. This is particularly important to ensure that gender and wider inclusion aspects are being fully monitored and evaluated and that all efforts are made to baseline these given the variability of the evidence base globally on gender and inclusion in relation to trade. There is always a risk that increased benefits to trade do not alleviate poverty or improve gender equality and wider inclusion. All GTP programmes maintain a gender and inclusion-sensitive approach in intervention scoping, design and delivery, and plan to engage with women and other marginalised groups. GTP will work with National Governments to encourage that complementary policies or measures are put in place to identify and mitigate any risks, and maximise the development impact of the intervention.
List of recommendations for the next year
1. Preparing for delivery phase: To ensure the GTP transition into full delivery is smooth, the GTP team should ensure the main supplier and supply chain have as much clarity on the core requirements to prioritise accordingly. This should include potential delivery partners (e.g. key institutions in country). To manage potential bottlenecks, this also means developing a tool to manage multiple processes to support effective financial management, especially between flexible and committed programme funds. While also developing a workforce plan to ensure the GTP team has sufficient capability and capacity and approved by the Strategy board by Oct (or ASAP after).
2. Establishing the programme management framework: The GTP team should fast track the GTP Theory of Change (ToC) and results framework development to help inform project-level ToCs and results frameworks and ensure these align to the overall GTP and Prosperity Fund ToC and GTP results framework. The overall GTP ToC and results framework should provide enough specificity to help guide project selection, design, implementation and reporting but at the same time not restrict the flexibility of the fund given its demand-driven nature. The team should review and refine the ToC and results framework regularly (at least annually) as and when the context changes or new evidence emerges.
3. Assessment framework version 2.0: Greater specificity and prioritisation of criteria is needed (e.g. evidence that the interventions are likely to deliver expected results), which should reflect developments in the overall GTP ToC and results framework.
4. Integration of inclusive growth, gender equality, women’s economic empowerment and poverty reduction issues across the GTP programme and associated projects is essential. The overarching ToC requires strengthening to explicitly cover these issues in the causal pathways including potential distributional effects. The support of the social development adviser and the supplier’s new gender and inclusion adviser (starting formally in September) will help integrate gender, inclusion and poverty reduction priorities. But, they should not substitute building capability within and across teams (and wider-HMG) on understanding potential differentiated effects of interventions (e.g. gender, income groups). The Centre of Excellence (CoE) and research and analysis strand has the potential to help develop understanding, capability and identify good practice interventions. The team should also build from existing research, analysis (e.g. GTP’s Work and Opportunities for Women (WOW) Helpdesk thematic brief) and expertise within the team (e.g. gender and inclusion champions), contractors, partners (e.g. WB, DFID, ITC) and wider HMG, as well as peer-to-peer learning across the PF (e.g. gender and inclusion champions etc.) and learning from the first round of projects before commissioning new research and analysis. The team should identify ‘best practice’ project-level business cases (GTP and wider) and share these across the team and promote greater peer-to-peer learning. We recommend using the GTP WOW guidance (as a starting point) to inform any new research and analysis, as well as consultations with beneficiaries and stakeholders. Developing the proposed programme-level Gender and Inclusion Action Plan (drawing on the G&I scorecard approach) will be an important step to further strengthen integration.
5. Recommendation: Closer engagement with DIT to ensure better alignment and increase efficiency and effectiveness of GTP projects and interventions. Discuss and agree roles and responsibilities (e.g. on design and reporting) at the next Strategy Board.
6. Recommendations: Ongoing/End of inception: Given the need to design and deliver large amounts of the GTP across several trade-related issues and countries, the GTP should set out how it and the wider network are working to minimise delays, for instance:
  1. End of inception phase/Oct 2019: The governance structure includes several layers reflecting the variety, complexity and risk inherent in the programme. However, the structures should be reviewed if they could be made more efficient, if not the next annual review should take a more in-depth look.
7. Recommendation: Given how comprehensive the assessment framework is, the GTP team should consider how it might learn from its application to three programmes. For instance, what were the challenges in its application? How well and consistently was it applied? How could it be improved? How were trade-offs between criteria managed? Are certain criteria prioritised, e.g. gender/social impact evaluations?
8. Recommendation: GTP should consider collating examples of how the strategy is practically informing design and delivery for future annual reviews.
9. Recommendation: the GTP team have an independent stocktake in six months on the skills, expertise and balance of work as it moves towards delivery.
10. Recommendation: the GTP team to evaluate, possibly in the next annual review, once the portfolio is more established, what (if any) transfers from “back office” funding to delivery were achieved?
11. Recommendation: the GTP team consider, as they develop a comprehensive results framework (RF), building a VfM framework to accompany the RF. This should enable the team to develop indicators to help make the VfM case for GTP. This should also help focus the analysis on informing the VfM case and, when changes (e.g. new countries/projects) are proposed, offer a clear framework for assessing VfM. The team should draw on the VFM scorecard developed by the Prosperity Fund’s EL contractor, which includes possible indicators.
  Joint Funds Unit Response to the Annual Review
  JFU welcomes the conclusions of this review and agrees with the reviewer’s scoring and risk rating. The Global Trade Programme has progressed well despite a delay in beginning the inception phase. The programme has ambitious plans for programme scale-up, so it will be increasingly important to monitor the delivery partner’s progress against key milestone. This puts a spotlight on the programme governance to demonstrate it can effectively flex and adapt to maintain oversight capacity
  We note that the GTP team has started dedicating greater capacity to Gender & Inclusion, and we would like to reiterate the importance of the programme considering trade issues from a gender and inclusion perspective. We also agree with the recommendation on the need for the programme to closely align with and complement DIT or DFID led work in this area.

  SRO Comments on the Annual Review
  I endorse this Annual Review and the associated grading.  Whilst recognising the delayed start date for the GTP, the extended period of negotiated procurement - in the end - delivered a lower contract cost of £26m with the Service Manager. I am pleased to see that the AR acknowledged that the decision to extend the procurement, whilst slowing the start, was the right decision.
   The GTP is ambitious and delivery scale and timelines reflect this; the team have responded well to these challenges and continue to work hard to make progress across the Programme. Looking ahead, it is essential that the GTP ensures Gender and Inclusion is at the forefront of the interventions and that the necessary structures and governance are in place as we go into Operations.

List of Acronyms
DFID – Department for International Development
DIT – Department for International Trade
EPA - Economic Partnerships Agreement
EY - Ernst & Young
FCO - Foreign and Commonwealth Office
FSA - Food Standards Agency
G&I – Gender and Inclusion
GTP - Global Trade Programme
IIOC – Investment, Infrastructure and Operations Committee
IP/IPR - Intellectual Property Rights
ISFT – Invitation to submit Final Tender
ISIT - Invitation to Submit and Initial Tender
ITC – International Trade Centre / ITT - Instructions to Tenderers
JFU – Joint Funds Unit
KPIs – Key Performance Indicators
L&D- Learning and Development
MICs - Middle Income Countries
MoU – Memorandum of Understanding
MREL – Monitoring, Reporting, Evaluation, Learning
ODA - Official Development Assistance
OJEU – Official Journal of the European Union
PF – Prosperity Fund
PMO – Programme Management Office
SACUM - Southern Africa Customs Union (SACU) Plus Mozambique
SDA – Social Development Adviser
SM - Service Manager
SQ - Standard Questionnaire
WB – World Bank Group / WEE - Women’s Economic Empowerment
WTO –World Trade Organization

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://www.gov.uk/government/publications/global-trade-programme
DevTracker Link to Log frame:	Not yet published

The Global Trade Programme (GTP) is the largest Prosperity Fund programme. It provides technical assistance and other support to facilitate free trade and open markets for Official Development Assistance (ODA) eligible Middle-Income Countries, enabling greater trade and investment, creating jobs and prosperity, and therefore contributing to inclusive growth and reducing poverty.
In line with the overall Prosperity Fund, GTP’s primary objective is poverty reduction and it also aims to deliver secondary benefits through increasing market access for international businesses, including UK firms, as well as building bilateral partnerships on trade-related issues with key emerging markets in support of the UK trade strategy (see p6 for further detail). The programme aims to achieve these objectives by: (1) enabling partner countries to identify and remove non-tariff barriers and (2) creating the conditions for increased international trade in support of the UK Government’s objectives.
Following the procurement process to obtain a service delivery partner and the subsequent approval of a Full Business Case in February 2019, Ernst and Young (EY) were appointed as Service Manager to the GTP in April 2019. On contract signature, the GTP team began a 6-month inception phase to ensure EY provide value for money against priority deliverables. This review is being undertaken 2 months into that inception phase; as such it is not possible to assess programme impact or indeed probability of success in implementation in any detail. As such the review will predominantly focus on the procurement process, considering whether or not that procurement has delivered a positive and value for money outcome, as well as considering programme governance and whether it is set up to succeed.
Mobilisation of the programme is underway and deliverables and milestones during inception have been clearly defined.  EY will be providing operational and research services to develop projects. The inception phase includes eight fixed cost, fixed output milestones. They include the mobilisation of programme and advisory services, development of in-country programme plans for nine priority countries and pilot projects worth up to £16m including four in-country projects; Brazil Patents Project, Brazil Regulatory Reform, Mexico Regulatory Reform and South Africa Customs Union plus Mozambique Economic Partnership Agreement. The fifth project is to develop a Centre of Excellence that will deliver high quality training to build capacity and expertise for trade practitioners in our priority countries.

B. PERFORMANCE AND CONCLUSIONS (1-2 pages)
Annual outcome assessment (Primary Purpose – inclusive growth, gender equality, women’s economic empowerment and poverty reduction)
Expected results and Theory of Change (ToC): As outlined above and in the overarching business case, GTP aims to create the conditions (namely, policy and regulatory) for increased international trade in support of priority country and UK trade objectives. By reducing barriers to trade, GTP aims to reduce poverty (primary benefits) in priority countries through:
- more inclusive economic growth which raises incomes and reduces poverty
- improving opportunities for trade and increased access to cheaper goods and services
- through improved regulations and standards that are more pro-poor and progressive
Also, by reducing barriers, increasing openness and economic growth in priority countries, GTP aims to provide more opportunities for international firms, including UK firms, to increase exports, investment and investment returns contributing to improved economic growth (secondary benefits).
At present, it is too early to assess GTP’s contribution to primary and secondary benefits as the programme is in the early stages of starting up (two months into the inception phase, with the service manager contracted in April 2019) and the first approved smaller scale pilot projects are only now starting. Estimating the potential scale and contribution of the fund at the outset is also challenging given a significant proportion (approximately 50%) will be allocated through the demand-driven fund.
The team are in the process of developing the results framework, including improving the existing GTP Theory of Change (ToC) in the business case and developing the results framework, as well as developing project-level ToCs and results frameworks as projects come on-stream. This is part of the benefits management processes led by the service manager with support from the programme team and MR contractor. The current ToC provides a useful high-level depiction of the expected results and some of the underlying assumptions underpinning the causal pathways. However, there are large leaps between some of the results (e.g. from inputs to outputs and intermediate outcomes to outcomes) in the ToC diagram with more detail needed on intermediate results and pathways to change (i.e. cause-and-effect relationships - how X leads to Y), some of which the narrative provides.
GTP aims to contribute to policy and regulatory changes which often take a long time to occur and for the effects to materialise at the outcome level (e.g. increased trade) and impact level (e.g. poverty reduction). GTP has the potential to contribute to creating the conditions that set the process in motion, but the programme should manage expectations on what it can deliver (at the outcome and impact levels) within the timeframe by 2022/23.
Recommendation: The programme team should fast track the GTP ToC and results framework development to help inform project-level ToCs and results frameworks and ensure these are G&I sensitive and align to the overall ToC and results framework. To the extent possible, the ToC development should draw on existing research, analysis and expertise within the team, contractors, partners and wider HMG. The GTP ToC and results framework should provide enough specificity to help guide project selection, design, implementation and reporting but at the same time not restrict the flexibility of the fund given its demand-driven nature. The team should review and refine the ToC and results framework regularly (at least annually) as the portfolio of projects develops and evidence emerges.
Project selection and ex-ante assessment framework: In selecting projects, the programme team and service manager aim to ensure that all projects are in line with GTP objectives, expected outcomes and impact (including inclusive growth, gender equality and poverty reduction) by applying an assessment framework for all possible interventions. The current assessment framework as outlined in the business case includes broad criteria on strategic fit, outcomes, impact and value for money.
The existing framework and list of criteria is comprehensive but in places quite broad, lacking specificity, indicators and prioritisation. The programme team have tasked the service manager to develop the assessment framework further including the criteria, concept notes and assessment templates and agree these during August 2019 (as part of the GTP Analytical Strategy, overseen by the GTP Analytical Group). The service manager will apply this framework in selecting and designing projects for funding under the flexible fund, including business case development. For approved projects, there is evidence that the GTP programme team used the existing assessment framework to develop project-level business cases.
Recommendations: When developing the assessment framework further, we recommend greater specificity and prioritising criteria that will help GTP achieve its objectives (e.g. evidence that the interventions are likely to deliver expected results). As above, the assessment framework should draw on existing research, analysis and expertise within the team, contractors, partners and wider HMG. We recommend developing both the assessment framework and results framework (ToC and results framework) alongside each other to help align the portfolio of projects to GTP objectives and expected results.
Inclusive growth, gender and inclusion and poverty reduction: The GTP business case considers issues related to inclusive growth, gender equality and poverty reduction, but does so quite broadly, partly since GTP is a flexible fund with 50% of interventions un-programmed. However, the team improved the coverage of inclusive growth, gender equality and poverty reduction in the final business case compared to the earlier outline business case. The programme team benefited from advice in developing the GTP and project-level business cases from the Social Development Adviser (SDA) in the Global Programme Support Team who allocates 10% of her time to GTP. In addition, the SDA commissioned work through the Work Opportunities for Women (WOW) helpdesk to improve integration of gender and inclusion in the programme and inform the Research and Analysis Fund. The SDA also recently briefed the supplier on G&I requirements, supported the service manager to recruit a gender and inclusion adviser to support the programme and has worked with the programme team to identify and support gender and inclusion champions across GTP (one in London and one in South Africa).
Currently, the GTP ToC does not explicitly include gender and inclusion dimensions in the causal pathways except referring to:
- “more inclusive economic growth, due to factors such as higher employment and lower prices that reaches to poor” at the outcome level in the diagram
- an assumption on “complementary domestic gender-sensitive resources and policies: sufficient domestic resources available and appropriate gender-sensitive domestic policies are implemented”
- “at output and outcome level, we expect approaches to actively support inclusive growth; gender equality and women’s economic empowerment; that no harm is done; that inequality is not worsened and that the approach is Gender equality Act and IDA compliant, and in line with World Bank Group policies and practice on gender. The assessment framework in the later section shows that the value for money assessment will include an analysis of equity”.
A lack of details on possible causal pathways related to distributional effects in the GTP ToC poses a potential risk for coverage of these issues in project-level ToCs that draw on the GTP ToC. However, from a review of the project-level business cases, these all highlight the importance of gender, inclusion and poverty reduction and alignment to the GEA, with varying levels of analysis on specific challenges different groups (e.g. women) face and potential effects of projects/interventions on different groups. For example, the SACU+M integrates the importance of gender throughout the business case and the TFA business case attempts to model the potential effects of trade facilitation projects on women. In most cases, the coverage is deeper than the overall GTP business case given greater specificity on potential interventions that allows more detailed analysis.
The programme team highlighted limited evidence and understanding of the effects of non-tariff barriers on inclusive growth, gender equality and poverty reduction as a key challenge to operationalising priorities. This includes limited evidence and understanding on the transmission mechanisms (causal pathways) from interventions designed to reduce non-tariff barriers and the effects on different groups including the poor and women. To help address this, the SDA commissioned a G&I and Trade thematic brief to identify key linkages and evidence gaps. This aimed to help inform the team’s development of an analytical strategy to ‘set the direction’ to building evidence, understanding and capability amongst the team and wider HMG to enable the programme to make investment decisions and deliver the programme efficiently and effectively. The programme has allocated £20m to research and analysis overseen by the analytical strategy. The team intend to use this fund to undertake research and analysis and feasibility studies to better understand the country contexts (e.g. barriers to trade for women) and potential distributional effects of interventions (for example, on gender and inclusion) which will inform the design and implementation of interventions. The programme also intends to consult with women and other marginalised groups to understand the challenges they face which will feed into project design.
The paper commissioned through the WOW helpdesk provides useful review of the evidence and guidance on how to undertake research and analysis to understand effects on different groups (e.g. women) and poverty as part of appraisals and ex-ante impact assessments to inform design, implementation, monitoring and evaluation. Also, several of the partners (e.g. DFID and ITC; World Bank) have undertaken research and analysis and have extensive knowledge in these areas that the GTP team can draw on.
Where research and analysis points to any potential negative effects, the programme intends to identify potential complementary policies and mitigating measures to reduce any potential negative effects and ensure ‘no harm’. However, the ability of the programme to influence complementary policies in priority countries, and the strategy to do so, is unclear but may be quite low.
- Recommendation: To ensure integration of inclusive growth, gender equality and poverty reduction issues across the GTP programme and associated projects, the overarching ToC requires strengthening to explicitly cover these issues in the causal pathways including potential distributional effects.
- Recommendation: The support of the FCO social development adviser and supplier’s new gender and inclusion adviser is very useful to ensure integration of gender, inclusion and poverty reduction priorities but it should not be a substitute for building capability within and across the team (and wider-HMG) on understanding potential differentiated effects of interventions. The Centre of Excellence and research and analysis strand has the potential to help develop understanding and capability. But, before commissioning new research and analysis, the team should also prioritise learning from existing research, analysis (e.g. WOW Helpdesk report) and expertise within the team (e.g. gender and inclusion champions), contractors, partners (e.g. The World Bank Group (WB), DFID, International Trade Centre (ITC) and wider HMG; as well as peer-to-peer learning across the PF (e.g. gender and inclusion champions etc.) and learning from the first round of projects. The team should identify ‘best practice’ project-level business cases (GTP and wider) and share these across the team and promote greater peer-to-peer learning. We recommend using the WOW guidance (as a starting point) to inform any new research and analysis, as well as consultations with stakeholders.
Team expertise:
Following on from the successful procurement of the Service Manager the GTP’s skill set and expertise covers a wide range of specialisms.  The GTP Team have maintained a lean team model working in partnership with the Service Manager; their key expertise in the following areas:
- economic;
- commercial;
- contract management;
- stakeholder and relationship management;
- understanding of Non-Tariff Barriers (NTBs) and the landscape of all nine Middle Income Countries
The programme also benefits from 10 per cent of the time of a full-time Global Social Development Advisor (SDA) in the Global Programme Support Team from July 2018, alongside support on Monitoring, Reporting, Evaluation and Learning (MREL) and on finance.
The procuring of EY (Service Manager) has now expanded and complemented the GTP Team which bolsters the areas above as well as bringing additional expertise in several areas such as:
- Policy specialist in gender and inclusion, intellectual property, customs, standards, regulation and trade facilitation & negotiation;
- Additional economists with global expertise;
- Specialist business case writers;
- Access to a large ecosystem to support any unique GTP request;
- A PMO function to support all GTP monitoring and reporting activities.

The lean team model working with the Service Manager with access to high quality inputs aims to provide value for money, complementing not duplicating roles to create ‘One Team’.  The ‘One Team’ model has created a knowledge-sharing environment where both public and private sectors can learn from each other. To ensure sustainability, improving HMG staff skills and promoting learning is an integral requirement for the programme.

Annual outcome assessment (Secondary Purpose)
The GTP team recently worked with an external contractor to develop a secondary benefit plan (currently a draft). It outlines the context in each priority country; main barriers to UK companies (standards, regulations, intellectual property, trade facilitation); existing HMG activities to address these constraints; estimates of expected secondary benefits; how the programme will contribute to secondary benefits; as well as the team’s capacity to deliver. When developing business cases, the team intend to use the plan to inform the secondary benefit analysis and sections. The team are awaiting comments on the plan, including from DIT and DFID.
Given the plan covers the whole programme and the portfolio is under-development, the plan is deliberately quite vague. The plan outlines a range of potential secondary benefits, both direct and indirect, ranging from benefits related to direct procurements to UK exports expanding due to increased growth in priority countries. The plan acknowledges that some of these benefits may not occur within the timeframe of GTP with most secondary benefits materialising in the longer term (5 years +).
Project-level business cases outline how each project intends to contribute to secondary benefits. Engagement across HMG on secondary benefits, especially DIT, has picked up over the last year, with early engagements by DIT quite intermittent, but this was largely due to the stage of development of the programme. There is significant potential to draw on DIT’s expertise, for instance, on design inputs and research and analysis. DIT’s involvement in the research and analysis committee helps source inputs from DIT and avoid potential duplication of effort across HMG. So far, DIT are not closely involved in the design of projects and there is potential for closer engagement to improve efficiency and effectiveness. In general, determining and agreeing roles and responsibilities on secondary benefits across HMG, the service manager and implementing partners is work in progress at this stage.
Recommendation: Closer engagement with DIT to ensure better alignment and increase efficiency and effectiveness of GTP projects and interventions. Discuss and agree roles and responsibilities (e.g. on design and reporting).
Overall output score and description
The overall output score for the programme is A.
The key outputs planned over the past year have been delivered:
- procurement of the service manager was well executed, with additional time taken to maximise value for money;
- the service manager has started mobilisation, though success here will be more effectively measured at the end of the inception phase;
- whilst an encouraging and well-balanced portfolio of projects has been developed (and in some cases commenced ahead of schedule) there have been some delays to starting project implementation, largely to ensure alignment with the main commercial process but also due to political circumstances;
- and finally, all programme governance, systems and processes are in place and will offer the crucial assurance needed for the programme to succeed.
The challenges ahead for the programme centre around the medium term capacity and capability to deliver a wide portfolio and ensuring that the projects deliver a coherent set of primary and secondary benefits.
Key lessons
Consult the Market – It is critical the programme engages and consults the market from concept, developing the model and requirements and throughout the procurement. Expectations align. Market appetite and risks are fully understood and legal (and other) programme challenges reduce.
Using a Competitive Negotiation Procurement (CPN) Process - The contract value when compared to the initial budget achieved significant efficiencies and VFM through the procurement route chosen
Secure appropriate specialists – never try to scope, design or model programmes without the appropriate technical expertise.
Key actions
- Creation of a one-page key actions/decisions taken by various committees for circulation to the Boards.
- Financial management processes to be assessed in more detail at the next annual review.
- Put in place a development plan around contract management ahead of the end of the Inception phase, review contract management performance at the end of 2019.

## C: DETAILED OUTPUT SCORING (1 page narrative per output)

Output Title	Procurement procedures for service manager finalised, successfully completed by the programme and learning shared within GTP and Fund wide
Output number per LF			Output Score	A
Risk:		Severe	Impact weighting (%):	50
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number and type of activities to support market engagement with potential suppliers	Questionnaire to bidders administered / Meetings with bidders	Market engagement exercise March 2018 a) a detailed questionnaire issued to ensure that the market fully understood the requirements; b) individual, structured meetings with bidders to help inform the procurement documentation ahead of issuing the Contract Notice.
Service manager contract: Number of bids received	Bids received that met the minimum standards for compliance	69 Expressions of interest / 9 bids received / 5 compliant bids received
Quality added through additional negotiation phase	Better quality technical scores received	Technical scores improved for 4 of the 5 bidders / The revised bids represent a cost avoidance of 50%, of the initial outlay, noting that some of the money saved may still be needed
Learning from procurement process documented and shared across PFD, including embedding into Post training	Learning sessions targeting PMs Posts and commercial colleagues	5 day training in contract management delivered to 7 Post managers from GTP network / 2 learning sessions conducted through PFLearning – reaching Post and central teams see link

Key Points
The procurement process for GTP started with different routes to procuring the Service Manager (SM) being considered. GTP engaged with the market from the outset, with a high level operating model and requirements, and continuously as the requirements and model became more detailed. Continual dialogue and feedback from the market on the GTP SM requirements was necessary, but time consuming, to ensure the requirements were understood, realistic and of interest to the market. This also reduced the risk of procurement challenge for the FCO. On award and post-standstill period, no challenge was made by the market.
Adding the Invitation to Submit Final Tender (ISFT) stage did add time into the process, but also avoided unnecessary costs in the contract, although it will be important at the next annual review, once the portfolio is more established whether there were savings for HMG.
Specialists
The programme recognised it required external specialist support for developing the requirements into legal schedules and legal expertise. A managed procurement service was procured and legal advisory services secured. Both of which reported to the GTP. These are specialist skills not available within the GTP or wider FCO (at the time required) and they were crucial to the successful procurement.
Contract Commencement
The procurement process for GTP started with different routes to procuring the SM being considered. GTP engaged with the market from the outset, with a high-level operating model and requirements, and continuously as the requirements and model became more detailed. Continual dialogue and feedback from the market on the GTP SM requirements was necessary, but time consuming, to ensure the requirements were understood, realistic and of interest to the market. This also reduced the risk of procurement challenge for the FCO. On award and post-standstill period, no challenge was made by the market.
Adding the ISFT stage did add time into the process, but also avoided unnecessary costs in the contract; although it will be important at the next review, once the GTP is more established, to identify whether savings have been made.
Evaluation and moderation
Following the initial Moderation Meeting held on 11 October 2018, in terms of the technical areas, all bidders showed clear competence in how they would deliver the service with some key areas of strength highlighted in all. Notwithstanding the level of detail provided within market engagement, the tender documentation, and in-tender clarification process, the bidders responses showed a wide range of service offerings and resource models;
1. concerns were identified across all submissions including legal, commercial and technical:
2. the Authority was unable to identify a Preferred Bidder and selected the option to negotiate with all bidders by the SRO on the 5 November 2018. Adding this additional stage extended the original procurement timetable by about two months;
3. in evaluating each bidders’ Initial Tender submission, each aspect was scored using a perceived risk-based approach. These were drawn into themes creating bidder-specific Negotiation Packs for each to consider areas for improvement;
4. meetings were organised between 26 and 28 November, and each bidder was offered the opportunity to meet the Authority team where the feedback provided within their Negotiation Pack was discussed. The specific intention of this process was to mitigate the perceived risks identified within their respective submissions, clarifying Authority requirements and expectations, ensuring all bidders had an equal understanding and could submit a compliant, reduced-risk Final Tender;
5. the ISFT was received on the 18 December 2018 and then evaluated in accordance with the award criteria stated in the ISIT and ISFT;
6. Ernst Young LLP submitted the Most Economically Advantageous Tender to the ISFT on the basis of the Award Criteria contained within the ITT.
Lessons:
Decision making – There were occasions, exacerbated by changing personnel on boards, to reopen decisions or seeking reiteration of rationale. This can be time consuming and encourage GTP to focus on short-term, reactive rather than longer-term strategic thinking. GTP should consider keep a decision log to avoid unnecessary calls on their time/focus.
Consult the Market – Critical that the programme team engages and consults the market from concept through to developing the model and requirements and throughout the procurement. This ensures that expectations are aligned, market appetite and risks are fully understood and legal (and other) challenges are reduced.
Using a Competitive Negotiation Procurement (CPN) Process - The contract value when compared to the initial budget achieved efficiencies and better VFM for HMG through the procurement route. By the end of the Inception period, the lessons from the CPN procurement model should be shared across the Prosperity Fund and the approach is considered for future procurement exercises.
Secure appropriate specialists – never try to scope, design or model programmes without the appropriate technical expertise.
Recommendations
This CPN procurement model and approach is considered for sub projects of GTP and other Prosperity Fund Programmes, as well as sharing experience with FCO CPG colleagues to help general FCO procurement performance.
August 2019: The GTP programme team should strengthen its contract management to maximise the relationship with the SM.
End of 2019: report on how the partnership has learnt lessons and adapted as GTP moves towards delivery.

Output Title	Successful completion of inception period with Service Manager to support effective mobilisation
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	15
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number and description of inception actions completed to support mobilisation	Inception planning initial meeting and beginning of inception tracker developed / Inception tracker with over 500 separate inception related tasks monitored and tracked for onboarding of service manager / August 2019: The GTP programme team should strengthen its contract management to maximise the relationship with the SM. / End of 2019: report on how the partnership has learnt lessons and adapted as GTP moves towards delivery. / Completion of inception actions required in preparation for service manager arrival: / 1 SM team mobilised; / 2 SM supply chain mobilised (e.g. research analysis, scoping/design specialists and gender specialists) / 3 Arrangements mobilised for the Authority team to operate from Service Manager's site; / 4 Produce a baseline inception plan (GTP + SM) / 5. GTP monitor and approve milestones in inception plan using acceptance criteria	Inception period started 15th April. / The inception baseline plan is almost agreed (05/06/19), but final checks are required. / FCO plans and EY submission form one master IQSC plan. / 80% mobilised. / SM Supply Chain expected to be in place by end of inception / Complete / 98% complete / Monitoring is in place IQSC
Number and description of products and processes supporting interim (priority) deliverables / Inception period	Governance discussions with Senior Team including discussion on ownership of chairs and secretariat / SC clearance started for key contacts within EY team / Collection of organisation details and team profiles, including DSC agreement on what can share / Inception and other governance structures in place (MO1 implemented (from month 2) / Global teams tasked to produce paper on potential interventions. / Deliverables and process mapping plan developed / Prep work for delivery towards : / Effective Mobilisation (MO1 implemented (from month 2) EY to produce; / Plan for 5 of the 9 countries including the following details / Economic Analysis / List of potential Projects / List of potential Interventions / • Feed into the overarching programme plan which will be produced at the end of Inception / • Project Services operational process established / • A programme training plan for the first 12 months of operation / • Create and Finalise the following key items: / • RAID log	Complete all governance in place and working well. / SC clearance 85 percent complete / Team details and project sheets complete / Complete and operational / Full briefing packs prepared and presented. / Effective mobilisation ongoing / Plan for 5 of the 9 countries ongoing / List of possible projects and interventions being developed which will feed into the overarching plan. / Project services mostly complete with operational processes being developed with GTP/EY/FCO / Programme training plan needs analysis underway and to be developed over inception period. / RAID log developed and monitored EY PMO owner and guardian.
Pilot 1: Number and quality of processes to support development of Southern Africa Customs Union + Mozambique EPA completed / Programme value £8,100,000	Scoping and design : design reports submitted to Pretoria and approved / Procurement of external contractor to review programme design and OBC / Assurance preparation work for OBC submission to IIOC / IIOC OBC approval / Procurement of delivery partners in region / Handover to service manager for OBC to FBC development / • Support the completion of the outline business case for the South Africa ENA Pilot. / • Working with the South Africa team, manage the assurance and approval process. / • Ensure the programme is on track to achieve final assurance approvals within 3 months of inception period / • Procure 3 party delivery partner by month 6 of Inception / • Contract Manage delivery partner / Preparations for procurement of FBC : preparing the SM for procurement	Landell-Mills scoping and design completed, and assignment closed. Quality of work deemed substandard, colleagues have provided feedback to IMC the Framework manager accordingly. / IMANI development procured to review programme design and OBC / IMANI revised programme design and developed OBC in preparation for IIOC submission. / OBC submitted to IIOC on 13th March 2019 – with an Amber rating from the Economics Unit. / IIOC approval gained for OBC, subject to revisions suggested by the Economics Unit. / Revisions made to the OBC made by IMANI development – Amber Green assurance rating received 14th May 2019. / GTP’s Service manager responsible for developing the OBC into a FBC. / SM team responsible for the procurement of delivery partner(s). / Procurement timeline agreed with the authority. / All working towards confirmed IIOC for FBC approval on 4th September 2019.
Pilot 2 : Knowledge and training is enhanced and maintained for the GTP	SM to prepare a strategy and means for continuous learning and skill enhancement for the GTP.	SM has developed a concept for a Learning Academy for the GTP, proposing a vision and strategy for delivery. Have set at the outset a need to undertake a comprehensive Training Needs Analysis (TNA). Next steps are to test the viability of the strategy with a wider cross section of GTP staff, including from overseas Posts and to comments the TNA process.

Key Points
At this stage (week 7) it is too early to assess the progress of the GTP inception phase. However, early indications show, delivery of the inception activities are on track. The Inception period will, primarily, be used mobilise the services and also to research and analyse the opportunities for investment across the regions, which will determine the number and size of potential investment projects for the programme with relevant value-based criteria being met. Until this work is completed in each country the final number and scale of projects will not be known.
Inception milestones
Whilst it is very early in the process, currently no milestones have been missed.
Recommendations
Lessons learnt: Early engagement helps ensure both the main supplier and their supply chain team have as much clarity of requirements as possible, all parties share a common understanding on timelines and deliverables and suppliers have as much lead in time as possible. The aim is that by the end of the Service Manager can implement instructions with minimal support from the GTP.

Output Title	Portfolio of projects supporting GTP design concept and relevant partnerships and collaborations successfully established, implementation underway
Output number per LF			Output Score	B
Risk:		/Major	Impact weighting (%):	25
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Quality of processes to support business case and MOU in conjunction with Defra, Food Standards Agency (FSA) to enable the UK to join the Codex Trust Fund. / Project value £500,000	Consultations between GTP team and Defra/ FSA including research and gathering evidence to support business case / Business Case development / Business Case finalisation. / MoU preparation in consultation with legal advisors. / GTP funding arrangements with Codex. / Disbursement of GTP funds (£500,000) to Codex Trust Fund. / Implementation from April 2019.	GTP funds of £500K was transferred to Codex Trust Fund (WHO) at end of last FY. MOUs between FCO and Defra, Funding arrangements between FCO and Codex (WHO) and Codex Business case all signed off during April 2019. Implementation started from April 2019. Currently communications strategy being agreed in conjunction with GTP Communications Committee.
Number and quality of processes to support the business case, MOUs, procurement & approvals and implementation of the DFID Economic Partnerships Agreement (EPA) programme / Project value £20 million	EPA Scoping: in the four target regions (Pacific, Caribbean, West and Central Africa, East and Southern Africa). / EPA business case drafted and approved (by TfD Deputy Director) drawing on the scoping reports and TfD’s own knowledge and research / DFID’s standard due diligence process initiated for ITC alongside work on the business case / Expected conclusion of business case (Mid March) / Finalisation of MOU between DFID and FCO (including clarity on DFID owning the assurance process and FCO retaining overall lead). / Developed spend authority delegation letter for FCO SRO to DFID SRO. MOU shared with PF/commercial colleagues for comments and will be signed by end April / Expected launch date of the programme late April / Appoint IP and begin inception period	MOU between GTP and DFID agreed and signed off during May 2019. DFID EPA business case signed off by DFID SRO during May 2019. ITC appointed as delivery partner and project implementation commenced during May 2019. DFID are responsible for reporting on VFM and project impacts during inception and thereafter with Service manager responsible for ensuring EMREL and reporting to GTP team at agreed intervals.
Processes to support improvements in Brazil's Patents registration programme in conjunction with UKIPO Project value £3.6 million	Scoping Study of IP in Brazil / Economic Analysis / Business Case development / Strategic Outline Business Case (SOBC) completed and handed to Service Manager to progress finalisation of business case and procurement of supplier.	Scoping Study of IP was completed during 2018 by Dr Kouzalis. Economic analysis has been developed by UKIPO and GTP economists and currently being finalised by the Service Manager. SOBC was completed and handed over to Service Manager during March 2019 to enable the SM to develop the OBC. SM is currently finalising the OBC.
Number and type of reports /assessments to support WTO TFA implementation	Proposed commencement date / Inception meeting / Delivery of stage 1 - delivery of draft strategic case including in depth country assessment and stakeholder mapping exercise / Delivery of stage 2 - delivery of final strategic case and proposed methodology of the economic analysis / Review of methodology completed by the GTP analytical group / Delivery of final methodology report of the economic analysis– stage 3 / Delivery of interim economic assessment report with cost-benefit analysis – stage 4 / Review completed by GTP Analytical Group / Delivery of final economic assessment report and a draft economic case – stage 5 / Delivery of final OBC – stage 6 / FCO final Assurance Board – stage 7 / OBC signed off on 24 April at IIOC	Business case approved. GTP team are currently engaging with the World Bank and the World Custom Union and are in the process of drafting an agreeing and MoU with them. It is expected that process will be completed by end July and the World Bank will start the inception period from September 2019.

Flexible funds* - Through IPO, BEIS and other HMG) and World Bank Trade facilitation Partnership (proposed)	EPA Transition Programme	Research & Analysis	Access and enabling fund	Management costs (FCO and Delivery)
£72m	£28m	£20m	£20m	£10m

* A minimum on £40m will be spent directly addressing non-tariff barriers to trade as proposed in the initial 2016 concept note.
A significant amount of the programme funding has been tentatively allocated. The high level budget allocation is broken down as shown in the table above.
 Breakdown of GTP spend
£50m is allocated to cover the cost of research, design, delivery and administration of the programme broken down as £20m Research and Analysis; £20m Access and Enabling; £10m Management costs (including Authority and Service Managers). The research and analysis will help the GTP to build an evidence base for investing in MICs. This will not only help the GTP and the UK Government to understand the wider trade opportunities that are available in the MICs, but it will also help to understand how poverty is distributed in these countries and what are the social exclusion challenges and their link to goods or services that are traded or their supply chain, and differential impacts on gender and inclusion. This will help to understand how UK interventions could make an impact in these countries. The Access and Enabling fund is a retained sum of money to develop and design potential interventions. It will provide funding for resources to support departments in the UK and at posts to develop proposals and business cases for new projects and subsequently assure their delivery.
Delivery - £100m has been allocated to projects and interventions of which £60.4m is already programmed, with business cases approved
1. SACUM £8.1m
The purpose of this project is to provide Technical Assistance to support Non-Tariff Barriers across the six SACUM countries.  This is split into 4 main interventions being Access to Information and Trade Promotion, Supply/Value Chain, Trade and Customs and Women in Trade.  The OBC has been approved and procurement activity will commence in June 2019 with delivery expected from September 2019.
2. Trade Facilitation Agreement implementation - £25m
Trade Facilitation Agreement implementation – £25m – Building on the framework for adopting the measures in the WTO Trade Facilitation Agreement, this programme will create a predictable and transparent environment to grow international trade, and promote opportunities for poverty reduction and greater inclusion of women and disadvantaged groups. The OBC was approved by IIOC in April 2019. The GTP team are currently engaging with the World Bank and the World Custom Union and are in the process of drafting an agreeing and MoU with them. It is expected that process will be completed by end July and the World Bank will start the inception period from September 2019.
3. IPO/Brazil – £3.6m
The purpose of this project is to improve the Patent/IP processes within Instituto Nacional da Propriedade Industrial (INPI) that will make significant efficiencies to the process.  The OBC was approved by IIOC on the 19th June 2019 with the expected delivery to start September 2019.
4. DFID Economic Partnership Agreement - £20m
Work led by DFID under MOU: The UK will provide up to £20 million over 3 years to deliver the Economic Partnership Agreements Support Programme. The programme will deliver technical assistance and capacity building required by the countries party to Economic Partnership Agreements (EPAs). Currently, trading arrangements between the UK and EPA partners are governed by the EU and country/regional specific EPAs. The UK, as we leave the EU, is preparing to carry over existing Economic Partnership Agreements (EPAs) with certain Africa, Caribbean and Pacific (ACP) countries and regional groupings. HMG policy is that to minimise disruption to trade, we will seek to ‘rollover’ those arrangements.
5. CODEX - £500k
The Codex Alimentarius Commission (CAC) is a collection of standards, guidelines and codes of practice adopted by the CAC comprising of 188-member countries and 1-member organisation, the EU. The CAC is the central part of the Food and Agricultural Organisation (FAO) / World Health Organisation (WHO) Joint Food Standards Programme established to protect consumer health and promote fair practices in food trade. Food standards are a significant NTB for developing countries. The investment will be managed by the World Health Organisation’s CTF2. The OBC was approved by the FCO in March 2019. GTP funds of £500K was transferred to Codex Trust Fund (WHO) at end of last FY. MOUs between FCO and Defra, Funding arrangements between FCO and Codex (WHO) and Codex Business case all signed off during April 2019. Implementation started from April 2019. Current communications strategy being agreed in conjunction with GTP Communications.
6. Brazil Regulations
The purpose of this project comprises of two key components, embedding improved regulatory practices in federal public agencies and to provide technical assistance.  The intervention opportunities are being reviewed in order to help create the OBC.  This will then be submitted to the next available IIOC meeting for approval to start procurement.
7. Mexico Regulations - £3.2m
The purpose of this project comprises of three key components being i) increasing technical assistance capacity, ii) technical assistance for tech tools and online platform and iii) upskilling of subnational regulators.  The OBC is currently under development and is due to be submitted to IIOC for approval prior to commencement of Procurement.
Recommendations:
Ongoing/End of inception: Given the need to design and deliver large amounts of the GTP across several trade-related issues and countries, the GTP should set out how it and the wider network are working to minimise delays, for instance:

1. How it might manage multiple assurance processes in parallel;
2. When the governance boards might consider the balance between flexible and committed funds;
3. How country teams are identifying/developing a network of development partners (e.g. OECD DAC members) and potential delivery partners (e.g. key domestic organisations/institutions).

Output Title	Effective governance structures designed and operational
Output number per LF			Output Score	A
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
Number of meetings of Trade programme board (post Mar 2018 known as operational board)	1 per quarter	Since June 2018 to end May 2019 there have been 3 Operational Board meetings and there were 3 Programme Board meetings (formerly Strategic Board) / Throughout this AR period, the governance structure has been refined with agreement that programme boards will meet quarterly (the end of the first month after every quarter) and operational boards meeting 6 weekly - timed to flow appropriate level decision making from operation board to programme board. Operational boards may well move to a monthly structure in the future but since the Service manager came on board in mid-April there has been a need to have close involvement as business cases progress at pace.
Number and type of Sub committees established and regularly meeting	6 x advisory groups established MREL, GTP Analytical Group, Commercial and Financial, Inception Quality, Project and Programme, and Communications sub committees. First meetings held. / TOR drafted ready for arrival of service delivery partner to agree. Service Manager sits on each board.	Since October 2018 a small number of sub committees and advisory groups were established to help govern the Service Manager contract and ensure appropriate gateways were in place for approvals. Groups have TORs and have started to meet regularly. The Service Manager became members of these committees on their appointment in mid-April 2019. / MREL sub committee meets monthly and has met 4 times / Analytical Group meets monthly and has met 4 times / Commercial & Financial meets bi-monthly (moving to monthly post June 2019) and has met 6 times / Inception Quality meets bi-monthly and has met 5 times / Communications sub committee meets 6 weekly and has met 4 times. / A Project and Programme subcommittee was also established but then temporarily disbanded. It was agreed that Inception sub-committee would become the Project and Programme group at the end of the Inception Period.
Effective management of programme risk through processes established	Risk Register in place and maintained by advisory committees and closure where appropriate / Reporting of top 5 risks on a quarterly basis / Risk register in place and maintained by advisory committees and Service Manager and closure where appropriate / Agreement with SM on which inception committee "owns" which Risk	The Portfolio Fund hold a central Risk Register. Prior to the Service Manager’s arrival (mid-April 2019) this was reviewed on a monthly basis in order to feed into a monthly report for internal seniors, highlighting the top 5 programme risks. There is also wider quarterly report for seniors which reports on the top 5 programme risks. / Both the Programme Board and the Operational Board review top risks at their meetings. / Since the arrival of the Service manager, the SM maintains the risk register, based on fortnightly risk discussions with project leads, which then gets fed back into the main PF risk register, so there is only one version of the truth. Each committee has been allocated (with their agreement) a number of specific risks which they are accountable for and actively manage.

Governance has been established since pre-procurement with an initial ‘shadow’ boards (now permanent boards) in place to govern the programme, provides steers on trade-offs, and advise on decisions and monitor progress.
Governance Arrangements
The governance is set up and operational, over time it will mature as projects start delivery. There is scope to use cross-HMG experience and knowledge to further inform the GTP.
Part I
The FCO has established two primary governance committees for the GTP
1. The Trade Programme Board – The primary focus of this Board will be to provide leadership, checking Value for Money, review of overall Global Trade Programme performance, provide a strategic overview, approvals of high value Project work and the Escalation route for subjects that cannot be resolved at the Operational Board; and
2. The Trade Operational Board – The primary focus of this Board will be to review and manage the programme performance including management of the Services Manager’s performance, dispute resolution, Value for Money, approvals of Project work and continuous improvement reviews.
Part II
Any Sub-Committee that is created shall follow the same governance when applicable. Where not applicable, the Sub-Committee shall agree its own governance structure that is fit for purpose.
The Parties will look to develop a mutually beneficial working relationship for the Term of the Contract. The Authority may use its discretion to establish additional governance committees as and when required throughout the Contract to achieve this, including but not limited to the following:
1. Commercial & Finance Management Committee;
2. Communications Management Committee;
3. Benefits Management Committee; and
4. Any other committee the Authority deems appropriate.
Recommendations
From the next set of boards: Should ensure that quality papers and clear questions to boards are circulated in advance to focus the boards’ attention and ensure they are prepared.
End of inception phase/Oct 2019: The governance structure includes several layers reflecting the variety, complexity and risk inherent in the programme. However, the structures should be reviewed, and possibly at the next annual review, to consider whether they could be made more efficient.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (2 pages)
Key cost drivers and performance
The programme spend for FY 2017/18 was £905,909 and for FY 2018/19 was £3,261,996 against a budget of £2,810,000 (116% spend against budget). Overspend was the result of a request to bring forward food standards work (CODEX) in order to help balance the overall portfolio profile.
Since 2017/18, the focus of GTP has been identifying programme activity and developing business cases, in particular the Economic Partnership Agreements in SACUM and delivering CODEX food standards and procuring the SM, which is currently onboarding. The latter was critical to support the FCO (as the GTP lead department) in designing and developing future projects, monitoring performance and assessing VFM against spend once activities are fully underway. As a result, since 2017/18 the main spend has been hiring the necessary skills and staff to design projects already identified, establish the necessary network across priority countries and procuring the SM. Therefore, as expected, admin spend has been above forecast during the set up period of the programme (57% in first 2 years), particularly given the requirement for external commercial support during procurement of the SM. The GTP admin costs are 1.6% up to FY18/19.
VfM performance compared to the original VfM proposition in the business case
To assess the benefits of the GTP, the FBC included an economic analysis of spending £40m on addressing four broad types of NTBs (trade facilitation/customs, IPR, standards, regulation). This analysis recognised the challenges in precisely estimating costs and benefits of NTB reforms without specifically identified activities, in particular on the differential impact on women/girls and men/boys. Given the evidence gap, the GTP committed to ensure each new intervention achieved VfM at each level, particularly equity. These would be required to develop a business case and pass a comprehensive assessment framework of criteria, including: The assessment framework was applied to three programmes – £25m WTO TFA, £3.6m IP BRAZIL and £500k CODEX – for which business cases will be published. The review team recommend, given how comprehensive the assessment framework is, the GTP team should consider how it might learn from its application to three programmes. For instance, what were the challenges in its application? How well and consistently was it applied? How could it be improved? How were trade-offs between criteria managed? Are certain criteria prioritised, e.g. gender/social impact evaluations?
In addition, the GTP developed an analytical strategy that set out its approach to close evidence gaps as it moves closer to delivery in four ways: using the Research & Analysis component (both in commissioning new research and feasibility studies), updating how GTP appraises its projects in line with the latest evidence, building a network of stakeholders and experts, and sharing learning and capability. It is too early to assess how this strategy has performed, but the review team recommend GTP should consider collating examples of how the strategy is practically informing design and delivery for future annual reviews.
The GTP is in an incipient stage. Therefore, it is too early to conclusively or comprehensively (across Efficiency, Effectiveness or Equity) discuss VfM performance. That said, the critical deliverable – the SM procurement (50%) – was achieved, albeit delayed by about two months from the original plan. However, this should not have a detrimental effect on GTP’s delivery, if the inception phase is successful in establishing an effective partnership with the SM. An early assessment of economy is positive. The review team noted the particular success of the GTP team in the procurement at getting the right expertise (commercial and legal) to inform the team. Although this has created a critical dependency on a few key individuals in the team, which should be addressed over the coming year. The review team recommend the GTP team have an independent stocktake in six months on the skills, expertise and balance of work as it moves towards delivery.
Furthermore, the GTP team avoided unnecessary costs in procuring SM by judiciously using a negotiated phase (despite the pressure on the team on moving as swiftly as possible to delivery) to improve the markets understanding of the FCO’s requirements. This had two results that suggest GTP have so far got the right quality at the right price. The range of costs in the final bids reduced (mainly from an improved understanding of the FCO’s needs) and ultimately the successful SM was £26m down from an original estimated envelope of £50m. Note: the latter are not necessarily cost savings as the five “back office” components for the GTP remain the same (£20m Research and Analysis; £20m Access and Enabling; £10m Management costs (including the GTP team and Service Managers costs). Although the review team recommend the GTP team to evaluate, possibly in the next annual review, once the portfolio is more established, what (if any) transfers from “back office” to delivery were achieved?
The programme currently has a Gender Equality Marker Score of 0 (i.e. not specifically targeted at gender equality). Against its first G&I Scorecard review rating (March 2019), it has an overall early scoring of potential for alignment with the Fund’s Gender and inclusion Policy – with score improvements expected as work is scoped out. Also recommend that the Analytical Strategy and R&A fund work takes on board G&I evidence gaps and guidance on good practice appraisal tools identified in the GTP WOW Helpdesk brief.
Assessment of whether the programme continues to represent value for money
As stated above, it is too early to make an assessment beyond economy. However, GTP have established a number of processes (research and analysis component, analytical strategy, results framework development) as well as more business cases, which are expected to support GTP in continuing to offer VfM. For instance, work to improve the assessment framework (project selection), undertake research and analysis and improve capacity and learning across teams (FCO and wider) on potential effects of projects/interventions (including on different groups – e.g. women – and mitigating any negative effects) and develop detailed results framework to measure and track results will help inform and improve design and implementation on an ongoing basis, increasing effectiveness, efficiency and equity (and therefore value for money) of the portfolio of projects. The review team recommend the GTP team consider, as they develop a comprehensive results framework (RF), building a VfM framework to accompany the RF, to enable the team to develop indicators to help make the VfM case for GTP and to test how the analysis is informing the VfM case. The team should draw on the VFM scorecard developed by the EL contractor with JFU, which includes possible indicators.
Quality of financial management
Finances are discussed via the commercial and financial sub-committee meetings on a bi-monthly basis. Quarterly financial discussions are held with SRO in depth, along with reporting into the various governance structures, including discussions at the 6 weekly operational committee meetings. There is monthly reporting against under/overspends, exceptional costs and variance to forecast.
In Financial Year 18/19, the programme delivered to forecast and in final outturn delivered an overspend of £451,996. The GTP responded to a request from the Prosperity Fund to bring forward payments to balance underspend elsewhere in the Fund – a good example of strong financial management. However, the systems and processes above are relatively untested. There were some relatively minor teething pains, e.g. 2017/18 country spends that were not appearing to the centre, yet these were identified and resolved. However, a scale-up of 1000% in spend in the next year, across more countries and new programmes coming on stream, will robustly test financial management processes. The review team recommend GTP should ensure its approach and, in particular, how they have adapted to deal with the inevitable issues that arise, should be assessed at the next annual review.

Date of last narrative financial report	May 2019 (covering April 19 forecast)
Date of last audited annual statement	n/a

E: RISK (1 page)
Overall risk rating: Moderate
The programme as a whole is rated as Yellow. However given the balance of risks and mitigations overall, judge it to be RAG-rated at Yellow (according to Prosperity Fund risk rating guidelines), especially given the predominance of Y risks (post mitigation). There is proactive risk management, regular reviews and strong mitigations are in place.
Overview of programme risk
The programme risk register (as at 31 May 2019) has 67 live risks. In addition a total of 30 risks have also been resolved and closed. Risks vary in severity. This risk register is reviewed in full fortnightly by the Service Manager and by the GTP team following discussions with programme managers. All risks are shared out between the various governance structures (e.g. financial risk overseen by commercial and finance committee, communications risks overseen by communications subcommittee etc.) and any changes in risks are discussed and mitigations agreed. Where project risks are significant (none post-mitigation) they can be escalated accordingly.
The SRO oversees all risks and reviews them on a quarterly basis for discussion and agreement on the top 5 programme risks. Programme Board and Operational Board also discuss the top 5 programme risks. The risk register is in line with JFU guidelines for the management of programme risk, including pre and post mitigations, RAYG ratings, detailed mitigation plans, proximity and impact. Main risks during this period of review centred around readiness for the GTP team to on-board the service manager, including ensuring appropriate contract management upskilling and training or the GTP teams (completed and closed). As inception period began (from mid-April 2019), risks are now around ensuring the Service Manager is delivering against inception milestones given the steep ramp up of programme activity in the new FY.
Outstanding actions and recommendations from risk assessment
The Programme RAID log forms part of the requirements for the Service Manager. There are no outstanding actions but recommendations are for close monitoring and assigned responsibility for overall programme risk management should be assigned from the outset.

F: COMMERCIAL CONSIDERATIONS (1 page)
Delivery against planned timeframe Y with some delay
The original estimated timescales from GTP Outline Business Case (Jan 2018) are below:
Activity	Estimated timescale
IIOC Approval Outline Business Case	Feb 18
Procurement Commences Service Manager	April 18
Full Business Case for board approval to appoint SM	Nov/Dec 18
Inception and mobilisation period	Dec 18

This suggests there has been a delay of about three months compared to the FBC timescales (below). This was mainly due to the need to proceed to negotiation. The risks identified during the evaluation process (Oct 2018) were such that the FCO was unable to identify a Preferred Bidder. As a result, the SRO agreed to proceed to negotiation in Nov, with final bids received end of Dec 2019. Thereafter and until the award in March, both the size of contract and programme required internal quality assurance of the FBC and approvals from HMT and Cabinet Office.
This Competitive Procedure with Negotiation (CPN) process was one of the longer procurement processes. The complex nature of GPT and requirements of SM, and the fact that this had not been procured before using the CPN, meant the FCO took a perceived risk-based approach. This ensured that the FCO were able to ensure the market were better informed on the requirements of the SM role, and the FCO were more confident in their selection the best possible bidder based on the qualitative and pricing elements. And, although this implied about four months of delays in the award, the length of the contract (3 years) suggests there will be scope to make up lost time, if the inception phase is used to rigorously test the effectiveness of the partnership.
Activity	Estimated timescale
IIOC Approval Outline Business Case	30 Jan 2019
HMT & Cabinet Office Approval	30 Jan -28 Feb 2019
Standstill period	10 days
Contract Award	12 March 2019

Performance of partnership(s)
Two months into the SM partnership is too early to provide an assessment. Early monitoring and management of the inception indicates good progress has been made, although there were teething issues with the SM in identifying the individuals with the right skills. A fuller assessment is expected at the end of the inception phase, which should recommend improvements on making the partnership more effective.
Changes in the Delivery Plan
Only one change occurred during the procurement which was for the FCO to exercise the right to enter into negotiations as a clear outcome from the initial tender could not be identified. This was a change from the core, ambitious timetable, but had been included as an option at the initial project and procurement plan.
Asset monitoring and control
NA

G: Business Environment (½ page)
How has the business community and business environment responded to the programme?
The business community has responded positively to the programme. Reaction from both the UK and overseas businesses has been good, with interest in the programme across its four target non-tariff barriers. The Brazilian IPO, Brazilian Regulation and Mexico Regulation interventions have been warmly received.
(Where relevant) What role has non-oda spending played in promoting programme objectives?

H: MONITORING & EVALUATION (½ page)
Evidence and evaluation
The programme made early progress in engaging with the monitoring and reporting (MR) and evaluation and learning (EL) contractors ahead of selecting and contracting the service manager. The first meeting took place in June 2018 and an MREL sub-committee was set up early 2019 ahead of the service manager coming on-board. The programme team developed the sub-committee Terms of Reference (ToR) in consultation with the MR and EL contractors ahead of the service manager contract. The programme team has instigated collaborative working between the MR and EL contractors and the service manager to develop the MREL approach and establish roles and responsibilities. The MR and EL contractors and service manager are all part of the MREL monthly sub-committee, chaired by the GTP Head of Economics. The MR and EL contractors developed a joint MREL work plan, including actions and timelines, shared and discussed at sub-committee meetings. The service manager is currently developing their MREL work plan that they will integrate into the joint work plan. Also, the programme team is currently finalising a RACI (responsible, accountable, consulted and informed) matrix with roles and responsibilities across the different actors (programme team, service manager, MR and EL contractors). The aim is that the different actors involved in MREL are all clear who does what and when, ensuring the MREL service is as efficient and effective as possible.
Monitoring progress throughout the review period
Given the programme does not have a results framework, the programme team developed an interim (‘early years’) framework for the annual review. This framework outlines four outputs on procurement, inception, projects, and governance and associated indicators and milestones. Results framework development is a priority for the team and will take place after the ToC/benefits review (both led by the programme team, service manager and MR contractor). The results framework will include relevant indicators disaggregated by gender and other aspects of social inclusion drawing on and aligning with, for example, World Bank methodologies and indicators (e.g. World Bank’s Trade and Competitiveness Gender Results Framework).
Evidence and evaluation
The GTP business case includes the latest ToC, including pathways for both primary purpose and secondary benefit and high-level assumptions. The GTP ToC aligns to PF fund-level ToC and contributes to the trade intermediate outcome along with other programmes that are part of the ‘trade family’. Work to review and update the ToC will start very soon as part of the upcoming benefits workshops, organised by the service manager. This is an opportunity to review the ToC and make any revisions to ensure that the GTP ToC remains aligned with the fund-level ToC. MREL actors (programme team, service manager, MR and EL contractors) will collaborate and discuss the ToC to ensure the final ToC robustly reflects the programme’s expected results, change pathways and underlying assumptions/risks, as well as considering how the programme can build into its change pathways its intention to scale up and maximise impact, both qualitatively and quantitatively.
Originally, the programme evaluation approach paper was due in November 2018, followed by the cycle/year 1 evaluation report in March 2019, based on an earlier ambitious estimate of service manager start dates and preliminary work on ToC development. The programme team and EL contractor agreed to postpone the dates to coincide with the timings of the service manager contract. During June/July 2019, the EL contractors will work closely with the programme team to identify EL needs and priorities, including evaluation questions, themes and learning priorities, and develop and share a draft approach paper for discussion with the programme team by the end of July. The current timeline for the approach paper assumed that the revised ToC would be ready to feed into the development of the approach paper. Given this is now unlikely, this may reduce the value of doing the approach paper now. Nevertheless, the EL team consider there is enough information to develop the approach, that it is possible to determine the team’s EL needs and priorities now and develop the EL approach in response, and that it is useful to outline the approach to the programme team and service manager at this stage. However, the EL team suggest revisiting and adding details to the approach closer to the start of the cycle 1 evaluation report to reflect updates to ToCs, results frameworks, project portfolio, in consultation with the programme team and service manager.