Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.
Title: Prosperity Fund – Mexico
Programme Value: £60 million		Review Date: July – August 2019
Programme Code: GB-GOV-50-PF-15-MEX [GB-GOV-3-PF-MEX-911, GB-GOV-3-PF-MEX-912, GB-GOV-3-PF-MEX-921, GB-GOV-3-PF-MEX-922, GB-GOV-3-PF-MEX-923, GB-GOV-3-PF-MEX-924	Start Date: April 2017	End Date: March 2023

## Summary of Programme Performance
Year	2019	2020	2021	2022	2023
Programme Score	A
Risk Rating	Moderate

SRO Comments:
I have reviewed the Mexico Programme Annual Review (AR) and agree with its findings. The positive scoring against the outputs reflects the hard work of the programme team and implementers to set up the programme for success in the design and inception phases. As SRO, I will be working with the team to consider how we take forward the recommendations made in this AR.

JFU Comments:
The JFU recognise the clear ownership and commitment of the Mexico team in ensuring this Annual Review was delivered on time and resulted in a genuinely useful learning and refining process, and opportunity to refine the programme.
 It is particularly encouraging to see clear evidence of thoughtful engagement with and testing of the programme’s Theory of Change under the individual strands, with adjustments guided by a clear vision on both primary purpose and secondary benefit.
 Clear systems and well-understood internal accountability emerges as a strength of the programme. Strand teams have a good degree of ownership and autonomy, with strong strategic direction provided at the centre by the Head of the Prosperity Fund in Mexico City.
 There is evidence of a good understanding of primary purpose and routes from this to secondary benefit that the recommendations will help to embed further. Ambition to deliver on gender and inclusion objectives is evident throughout, with a realistic assessment of the work that needs to be done to support this.
 Supplier management emerges as an area for future focus. It is evident that the team are aware of the improvements needed in this area and the review has been useful in taking stock of this.

Summary of progress (and lessons learnt) since last review
N/A – first Annual Review
List of Acronyms
Abbreviation
ACROL	Anti-corruption and Rule of Law
AMLO	Andres Manuel López Obrador
APF	Agile Programming Fund
API	Application Programming Interface
BC	Business Case
CDU	Central Delivery Unit
CNBV	Comisión Nacional Bancaria y Valores (National Bank & Securities Commission)
COI	Conflict of Interest
CONEVAL	Comisión Nacional de la Evaluación de la Política de Desarrollo Social (National Commission for the Evaluation of Social Development Policy)
DFID	Department for International Development
DIT	Department for International Trade
E&L	Evaluation & Learning
EQ	Evaluation Question
FCO	Foreign and Commonwealth Office
FC	Future Cities
FDI	Foreign Direct Investment
FIC	Fintech Innovation Centres
FRG	Family Reference Group
FS	Financial Services
GEA	Gender Equality Act
G&I	Gender & Inclusion
GN	Guardia Nacional (National Guard)
HMA	Her Majesty’s Ambassador
HMG	Her Majesty’s Government
IBS	Industrial Baseline Study
ICF	International Climate Fund
IO	Intermediate Outcome (of the fund Theory of Change)
IIOC	The FCO’s Infrastructure, Investment and Operations Committee
ITPD	Instituto de Políticas para el Transporte y Desarrollo (Institute of Policies for Transport and Development)
JFU	Joint Funds Unit
KII	Key Informant Interviews
KPI	Key Performance Indicator
MEAT	Most Economically Advantageous Tender
M&R	Monitoring & Reporting
MREL	Monitoring, Reporting, Evaluation & Learning
MSME	Micro-, Small and Medium-Enterprise
NDP	National Development Plan (of the Mexican government)
OBC	Outline Business Case
ODA	Official Development Assistance
ODB	Operational Delivery Board
ODI	Overseas Direct Investment
OSJA	Overseas Security and Justice Assistance
PEL	Programme Evaluation Lead
PF	Prosperity Fund
PFDU	Prosperity Fund Delivery Unit
PM	Programme Manager
PMC	Programme Management Committee
PT	Programme Team
PwC	PricewaterhouseCoopers
SB	Secondary Benefit
SDG	Sustainable Development Goals
SGB	Strand Governance Board
SoR	Statement(s) of Requirement
SRO	Senior Responsible Owner
TAC	Transparency & Anti-Corruption (family)
ToC	Theory of Change
UK	United Kingdom
VCC	Voice, Choice and Control
VfM	Value for Money
VT	Virtual Team
WRI	World Resources Institute
WOW	Work and Opportunities for Women

A. Introduction and Context
DevTracker Link to Business Case:	https://www.gov.uk/government/publications/prosperity-fund-mexico-programme
DevTracker Link to Log frame:	Not yet published

The Prosperity Fund’s purpose in Mexico is to support inclusive economic development to reduce poverty in Mexico, and increase prosperity and security in Mexico and, in turn, in the UK. The Mexico Programme comprises four strands: Anti-Corruption and the Rule of Law (ACROL), Energy, Future Cities and Financial Services. The programme builds on previous Embassy initiatives which informed the 2017 Outline Business Case for the programme, and provided real-world examples of programme potential.
The Programme in Mexico is still within the inception phase at the time of writing this Annual Review. During this period, all four strands are revising their respective theories of change and developing implementation plans. This is to assure the integrity of the logic within each design, strengthen alignment with the overall programme theory of change and consolidate the programme’s positioning with respect to the new government which took office in December 2018. The Inception Phase began in February 2019 and will end in September 2019 for three strands (Energy inception ends in November 2019), when the implementation phase will begin.
This is the first Annual Review of the Mexican Prosperity Fund, and it follows rapidly upon the comprehensive Cycle 1 Evaluation Report, covering the period June 2017 – May 2019, including the procurement and transition phases and some of the inception phase. It was submitted on 1 August for approval. . The objectives of the Evaluation Report were to:
1. Ensure that the design and positioning of each strand and the overall country programme are strong, drives interventions toward the stated outcomes and goals (as defined by the Programme Team, PT), and aligns with the overall Fund objectives.
2. Provide findings and insights to the PT at the mid-point of the inception period so that the PT and suppliers have the opportunity to make any necessary adaptations to better achieve outcomes and goals (as defined by the PT) and to support the Fund's primary and secondary benefits.
3. Support the PT as it prepares to draft the first Annual Review of the PF Mexico Programme.
As such, the Evaluation Report has made recommendations for the PF in Mexico at programme and strand level, and also made recommendations for the wider Prosperity Fund. Therefore, this Annual Review does not attempt to recreate the findings or recommendations of the Evaluation Report, although there are many findings in common, and the Report has informed the Annual Review team’s thinking on areas of enquiry. Instead, this Review seeks to make practical recommendations for the implementation phase in Mexico based on the experiences of those working on the PF for the past year, to test some of the evaluation findings with them, and to highlight key lessons learned by them which may of wider value across the teams in Mexico, and those working on Prosperity Funds in other countries.
The Mexico Programme has often been among the earliest movers among PF bilateral programmes, and so there are many lessons to be shared.

## B: PERFORMANCE AND CONCLUSIONS

## Overall output score and description
The focus of the PF this year has been to lay strong foundations for the implementation phase, and address issues as they arise. Therefore, the Annual Review team have weighted the scoring for the Review as 60% programme level (60% output 1; 40% output 2), and 40% strand level (o/w 10% per strand). For within each strand, the output weightings used are those that were given in the SoRs version of the logframe, which, at the time of this writing, is still the operative one for the programme as a whole.
The Prosperity Fund has met the majority of its logframe process indicators, showing that it is on track to achieve the expected impacts. The Annual Review team recognises that the Mexico PF team is committed, enthusiastic and resilient; we have seen a great deal of developing good practice that is replicable across the Prosperity Fund as a whole.

Programme level
At programme level, the Annual Review team has given the Prosperity Fund programme a score of ‘A’ for this year – outputs met expectations. . At programme level, all output indicators have also been met (see Annex 1). These indicators focus on the supporting processes, successful procurements, signing contracts and recruitment of relevant technical expertise on secondary benefits. These achievements have improved the robustness of the programme and its likelihood to be able to deliver over the longer term.
Table 1: Programme level inception indicators from logframe
Indicator(s)	Milestones	Progress	Score
Programme
Number of SoRs/ITTs issued to market	2 by Aug 2019	Achieved	A
Number of bids received (All strands)	17 by Sept 2018	Achieved	A
Number of contracts signed	4 by Feb 2019	Achieved	A
Number of FBCs approved by IIOC	1 by Dec 2019	Achieved	A
Publication of Business Case on Gov.uk	By June 2019	Achieved	A
Secondary benefits indicator: Non-ODA Secondary Benefit Advisor recruited	By Feb 2019	Achieved	A

Strand level
At strand level, the Annual Review team has given the Prosperity Fund programme a score of ‘A’ for this year – outputs met expectation. This is because the majority of strand inception indicators have been met. It is important to note that the logframe indicators are being revised by the programme teams and suppliers in the current inception phase. The greater value for this annual review is the narrative recommendations made in each section.
Therefore, the Annual Review scores an A overall. The Programme Team performed at a strong level, navigating much ambiguity due to availability of operational guidelines at the time that action was required. Other programmes will have greater clarity, tools and processes as a result of Mexico’s initiative.
## Annual outcome assessment (Primary Purposes – inclusive growth, gender equality, women’s economic empowerment and poverty reduction)
For this first year of procurement and inception, the annual outcome assessment will not be based on progress towards outcomes, but rather upon progress against the programme level inception indicators, the strand level inception indicators, and the wider programme progress.
While the programme is still in inception phase in Mexico, the Annual Review team assess that the Prosperity Fund is well-placed to achieve this impact over the longer term.
Anti-Corruption and Rule of Law (ACROL). The ACROL strand seeks to address the problem of corruption and unequal access to justice through three main interventions: (i) increasing the accountability of public service by streamlining and standardising processes for identifying and investigating serious crime and corruption; (ii) capacity-building for male and female officials working in the investigation and detection of serious crime and corruption to increase the quality of public service in ensuring justice and security for all and; (iii) improving the coordination between security, justice and anti-corruption institutions. Through this strategy, we aim to benefit the poorest and positively affect inclusive economic growth and development, leading to a more inclusive and competitive business environment.
The ACROL strand has met its inception objectives to date, although within the phase there was some adjustment of deliverables based on the challenges of refining the strand’s logframe and theory of change (discussed below). The redesign has strengthened the causal pathways to achieve inclusive economic growth and to support indicators within other strands. This is important as ACROL regards its objectives as cutting across those of the other Mexico programme strands. There is room to further improve this linkage, which would further support the primary purpose of the strand and the Mexico programme. The links to secondary benefits, particularly as they relate to improved business environment are also more identifiable as a result of the strand redesign during the inception phase. Overall, the ACROL interventions are well-aligned with national priorities, which further strengthen its position and potential for positive impact.
Energy: The energy programme focuses on three main interventions: (i) developing a local female and male workforce that has the necessary skills and/or international certifications to fulfil industry demand; (ii) building the capacity of female- and male-owned Mexican small and medium-sized enterprises (SMEs) to support increased supply chain integration; and (iii) capacity-building for energy regulators and male and female officials to promote best practice in the implementation and enforcement of regulation. These interventions are designed to contribute to the promotion of inclusive economic growth and social development through more productive and resilient men and women, businesses and government officials who are best placed to lead Mexico’s transition to a low-carbon economy. Cleaner and more affordable energy, as a result of a successful transition to a low-carbon economy, will positively impact on the quality of life for low-income families through increased use of labour-saving, energy-intensive technologies and higher disposable income.
The Annual Review assesses that the energy programme has achieved a significant amount over the period of this review, and has been given an A rating against its logframe. The programme has developed a business case and negotiated the appropriate approvals processes including HMT. Excellent collaboration and relationship building stands out as a particular achievement of the energy programme. The energy team have had to face a challenging environment, and have negotiated uncertainty by being flexible and managing risk well, with excellent collaboration. The energy programme is in a strong position to continue to achieve against its logframe outcomes by the end of the programme, and to make progress during the implementation phase.
Financial Services (FS): The problem of financial exclusion is expected to be integrally addressed through three main interventions: (i) financial education to create a more confident and informed user-base of FS; (ii) policies that lead to improvements in the regulatory framework and (iii) support for Fintech companies that offer innovative solutions for micro, small and medium-sized enterprises and male and female users. Through this strategy, we expect to have more inclusive and competitive FS in Mexico that contribute to poverty reduction and positively affect inclusive economic growth.
The Annual Review assesses the progress made by the Financial Services strand in the transition and inception phases brings the programme on track to achieve the three main logframe outcomes during the implementation phase. The strand scored an ‘A’ against its inception logframe.

Good use of transition funding has laid the basis for solid work on fintech in particular. Systems and structures have been put in place to ensure sufficient buy-in from parts of Government, and much of the analytical work needed to guide the programme over the next few years. But care now needs to be taken to embed the FS team given personnel changes, and to revisit Intervention 1 to ensure it remains aligned with new Mexican Government policy.

Future Cities (FC): The FC strand seeks to address the challenges of mobility in Mexican cities through two main interventions: (i) improving connectivity within cities through better governance and planning mechanisms for urban mobility services and; (ii) implementation of pilots to test solutions within a wider integrated transport strategy to deliver inclusive, safer, resilient and sustainable urban mobility services in target cities. The strand exists for women and men in Mexico who can benefit from more accessible urban mobility services, enhancing productivity, improving personal well-being and increasing the levels of social inclusion, including gender equality.
The Annual Review assesses the progress made by the FC strand in the transition and inception phases to position the programme to achieve the two main logframe outcomes of the strand by the end of the programme. The strand has scored an ‘A’ against its inception logframe.
This is because the extra efforts made during the procurement and city selection processes have created strong foundations: for the pilots through robust supporting rationales (including the TOC) for the interventions; good programme management and risk processes within the team and with the supplier; strong local level relationships at city and regional level, and an improved working relationship and management of the supplier which should enable them to deliver. The key challenge for the strand will be turning the outcomes of the pilots into workable solutions and securing buy-in from Mexican authorities.
The FC strand’s success will assist with poverty reduction on a broad and general scale by improving transport, but there are few poverty-specific indicators in the logframe. The TOC and logframe indicate that interventions should be designed over the longer term in consultation with impoverished groups, and this could be fleshed out more after inception phase. The strand has developed good quality G&I strategies, particularly on gender. More could be done on wider social inclusion. There is good potential for secondary benefits as the programme progresses, and for mainstreaming climate change considerations.
## Annual outcome assessment (Secondary Purpose)
The programme has a Secondary Benefits Action Plan which was delivered to JFU in August 2018. However, this Annual Review concludes that the current plan will only maximise the secondary benefits of the programme with further steps, such as: Secondary Benefits Action Plan is redrafted in line with new guidelines; incorporate the innovative ‘Virtual Team’ model which exists in the Embassy in Mexico; and that each strand should develop its own SB strategy. An additional recommendation for London is that it clarifies its definitions of SB and provides further cross-fund guidance on this issue to the teams and the SB Advisor.
## Are the programmes designed to make a positive impact on gender and inclusion issues?
The Cycle 1 Evaluation Report provided an updated comprehensive assessment of G&I issues within the Mexico Prosperity Fund. The key findings and recommendations are summarised below. This Annual Review agrees with the Evaluation Report’s findings, first from the Gender and Social Inclusion Lead, who evaluated the Mexico Programme’s G&I scorecard with a generally “good” finding in February, based on the 2018 revisions to the programme and strand designs between the outline business case (OBC) and the statements of requirement (SoRs); and revised upward during the 2019 evaluation period based on additional primary documentation. While it is too early in the programme’s evolution to discern the qualitative impact the G&I design has had, this will be an area of assessment and review in subsequent cycles.
Initial and February 2019 gender and inclusion scorecard scoring
Programme	Programme Design	Internal capability / institutional incentives	Financial resources	Accountability mechanisms	Partnerships
Mexico 2/2019
Mexico 5/2019

Overall, good efforts have been made to mainstream G&I into the four strands, particularly on gender. The Mexico Programme Team (PT) proactively sought and secured G&I guidance and support from the Joint Funds Unit (JFU) and the Work and Opportunities for Women (WOW) Helpdesk as the PT reworked its strand ToCs ahead of the tenders[1]. The Annual Review agrees with the Evaluation Report that: There is evidence that the Mexico PT and the four strands have accounted for the inclusion of marginalised groups in their evolving strand designs, albeit to a lesser extent as the guidance up to this point has emphasised gender[2]. Wider social inclusion issues concerning marginalised groups and vulnerable populations should now be considered by all strands and the programme team as the programme enters implementation.
[1] See PF Gender Policy March 2018: https://www.pflearning.co.uk/display/PSMDLOPN/DCMS+session+on+primary+purpose%2C+gender+and+inclusion?preview=%2F12354136%2F12354137%2FPF+Gender+Policy+Statement+Update+March+2018.docx and SoRs “Appendix 8: Prosperity Fund Gender and Inclusion Requirements.”
[2] Guidance call 4 December 2018 in which PT, E&L G&I lead and PEL/Mexico joined JFU, inter alia.
The programme’s weakest element in the February 2019 stocktake was related to financial resourcing of the G&I elements, due to the absence of information, including strand budgets, which inform this aspect of the G&I scorecard. This is now being addressed (e.g. via the new G&I suppliers group which has met three times over inception), and budgetary implications of G&I strategies should now be formalised.
The Annual Review agrees with the Evaluation Report’s other recommendation on G&I, namely that: G&I advisors, through the G&I Group, should exchange inclusion indicators and interventions that promote both gender and social inclusion in their discussions before the close of the inception phase and identify shared indicators to enable the programme to assess its G&I impact in a more holistic and balanced manner.
## Positive impact on poverty
The Mexico programme uses a multi-dimensional definition of poverty from CONEVAL, Mexico’s independent evaluation agency, which, in accordance with the General Law on Social Development, includes nine dimensions by which to measure poverty. These nine are: current per capita income; average educational gap in the home; access to health services; access to social security; quality and living spaces; access to basic housing services; access to food; degree of social cohesion; and degree of accessibility paved road. The programme is well designed to make a positive impact against various dimensions of poverty as strand results become aggregated over time.
## Potential negative impacts on poverty
No programme can tackle all dimensions of poverty. The choices that the programme and its constituent strands have made throughout the design process, starting with the Outline Business Case and assessing the current strand logframes and ToCs have been well reasoned and account clearly for the choices made as to what to include and what not to address given existing resources, scope and intended impacts. The programme team has given full consideration to Do No Harm principles throughout the design, procurement, and inception phase as suppliers have also been required to honour the DNH principles. For example, the SoRs required bidders to demonstrate “an understanding and knowledge of how to maximise economic, social and environmental benefits and opportunities for local stakeholders, including women and men and communities, to do no harm and to access and benefits from the Strand interventions” (Section 1.4 of the four strands’ Invitations to Tender document).
After their contracting, suppliers have continued to demonstrate DNH principles in their designs and intervention approaches in key milestone documents such as the Stakeholder and Community Engagement strategies.

## Key Actions and Recommendations
The key actions and recommendations are summarised in the table below. We have shown where recommendations tally (or disagree) with the Evaluation Report. More detail on implementation advice is given in the relevant sections of the Annual Review. The ER was focused on design and positioning. The AR is more focused on operations and finance. In that regard, it is appropriate that these AR findings focus on internal operations and are, therefore, complementary to the ER findings around design and programme structure.
The recommendations follow the formatting sequence of the Annual Review report itself. These recommendations identify the lead actor and a desirable time frame for action to facilitate future assessments as to whether and to what extent these recommendations were taken up.
Table 1: Key Annual Review Recommendations
No.	Recommendation	Annual review section	Lead		Time Frame	Crossover with Evaluation
	Fund
1	Enhanced guidance from London to develop a more in depth climate/resilience strategy for each strand, and possibly for the programme, which moves beyond ‘do no harm’ to consider issues such as encouraging disclosure of investment portfolio CO2 emissions, or supporting diversification of financial products to include climate resilient insurance.	Section C: All Strands	PT		December 2019	Agrees with Section 6.2.2 (p. 29) and Section 9.2 (p. 38) of the Evaluation
2	Financial reporting from suppliers: PFDU standardise common financial management systems across the Prosperity Fund FCO programmes. So far as is possible, this should be harmonised with other government systems, particularly DFID. The PT should hold workshops with suppliers who are not fully compliant to make financial reporting expectations clear.	Section D: VFM and Financial Performance	PFDU		June 2020	None
3	Feedback from cash flow forecasts: The FCO should develop a feedback mechanism for the cash flow forecast data, even if this is just to recognise that is received and the information is adequate.	Section D: VFM and Financial Performance	PFDU		December 2019	None
4	The PT and PFDU consider how to incentivise economies of scale within large suppliers, particularly where one supplier is serving multiple programmes.	Section D: VFM and Financial Performance	PT and PFDU		November 2019	None
5	The PT and PFDU ensure the programme team has access to due diligence expertise, and the results of due diligence screenings are shared with the programme team.	Section D: VFM and Financial Performance	PT and PFDU		November 2019	None
6	PFDU provides training on what to do when suspected corruption or fraud is identified, and that suppliers are warned about this in advance so it does not come as a surprise if this occurs. For example, if all payments are paused until the situation is resolved.	Section D: VFM and Financial Performance	PFDU		September 2019	None
7	JFU/PFDU should avoid adjusting the risk template wherever possible, and if it must be adjusted, this should only be done once a year. This annual review recommends that JFU/PFDU develop more consistent feedback mechanisms on risk.	Section E: Risk	JFU and PFDU		December 2019	None
8	JFU/PFDU should play a larger role in facilitating collaborative working on risk across the Prosperity Fund. This annual review recommends that the Mexico Prosperity Fund programme team liaise with the Brazil and Colombian programmes to work collaboratively on risk and share learnings	Section E: Risk	JFU and PFDU / PT		December 2019	None
9	FCO Commercial provides greater and more timely commercial training and support is given to Post teams, particularly during critical early stages of SOR and bid development.	Section F: Commercial Considerations	FCO Commercial team		As soon as possible	Agrees with Section 9.1 (p. 37) of Evaluation
10	PFDU considers the resource levels required within the central commercial team to manage PFs in many countries.	Section F: Commercial Considerations	London Commercial team / PFDU		As soon as possible	None
11	PFDU should seek to formalise commercial expertise sharing arrangements with DFID where possible, due to DFID’s greater experience than the FCO of managing large multi-year development programmes.	Section F: Commercial Considerations	London Commercial team		As soon as possible	None
12	FCO Commercial provides more guidance to PTs on effective tools for contract management to ensure suppliers are able to meet ambitious timetables.	Section F: Commercial Considerations and Section C.	London Commercial team		As soon as possible	Agrees with Section 9.1 (p. 37) of Evaluation
13	London clarifies definition of Secondary Benefits and communicates this to programme teams. Different definitions of secondary benefits are being used at the moment.	Section G: Business Environment – Secondary Benefits	JFU and SB leads		As soon as possible	Agrees with Section 6.3.2 (p. 31) of the Evaluation
	Programme
14	Wider social inclusion issues concerning marginalised groups and vulnerable populations should now be considered by all strands and the programme team as the programme enters implementation.	Section B: Gender and Inclusion	PFDU, PT and supplier G&I Advisors		Early implementation phase	Agrees with Section 6.1 (p. 28) of Evaluation
15	Mexico Programme team should replicate the work of the Colombia and Brazil Prosperity Funds in contracting in a local gender expert at Post to support in developing the strategy.	Section B: Gender and Inclusion	PFDU, PT and strand G&I Advisors		Early implementation phase	Agrees with Section 9.2 (p. 38) of Evaluation
16	G&I advisors, through the G&I Group, should exchange inclusion indicators and interventions that promote both gender and social inclusion in their discussions before the close of the inception phase and identify shared indicators to enable the programme to better assess its G&I impact.	Section B: Gender and Inclusion	Programme team and supplier G&I advisors		Before end of inception phase (September 2019 / November 2019 - Energy)	Agrees with Section 6.1 (p. 28) of Evaluation
17	A more detailed Secondary Benefits strategy is developed for all strands, using improved guidance from London.	Section C: All Strands and Section G: Business Environment – Secondary Benefits	PT		Early implementation phase	Agrees with Section 6.3.2 (p. 32) of the Evaluation
18	UK based staff costs. The PT team is given access to accurate UK based staff costs. If this is not possible, the central FCO finance teams should provide the programme team with average staff costs to allow more accurate budgeting.	Section D: VFM and Financial Performance	FCO central finance teams		September 2019	None
19	Platform costs: The PT should obtain an explanation from central FCO finance teams of what the platform charges consist of and how they may vary over the life of the life of the programme.	Section D: VFM and Financial Performance	PT and FCO central finance teams		September 2019	None
20	The Joint Funds Unit (JFU) may wish to consider caps on profits for future contracting, based on an assessment of the Department for International Trade’s (DFID) experience.	Section D: VfM and Financial Performance	JFU and FCO central finance teams		December 2019	None
21	Teams consistently make space for identifying new risks as part of their risk management process in addition to regular monitoring activities.	Section E: Risk	PT		Ongoing	None
22	The Programme Management Committee considers if another format for considering risk would provide more space for engagement by PMC members. For example having a deep dive every quarter where all senior staff are required to attend.	Section E: Risk	PMC		December 2019	None
23	The SRO is given full access to risk registers, in addition to the high level risk register already received, every month with high priority risks highlighted.	Section E: Risk	PT and PMC		As soon as possible and ongoing	None
24	In the context of having shared risk registers with suppliers, the PT consider a standard process to manage sensitive information that should not be shared widely within the risks register, whist making sure information can be shared as widely as needed.	Section E: Risk	PT		As soon as possible and ongoing	Indicated in Section 7 (p 35) of the Evaluation
25	The PT have clear responsibilities for risk management, and that they remain proactive in identifying and monitoring risks.	Section E: Risk	PT		As soon as possible and ongoing	None
26	The PT team should work with London to see if their respective financial processes could be more closely aligned and efficient.	Section F: Commercial Considerations	PT		PT, PFDU and FCO finance teams	None
27	The PT should consider the process for allocating agile funding to new, small or rapidly developing projects can be streamlined.	Section F: Commercial Considerations	PT		PT, PFDU and FCO finance teams and Commercial Team	Agrees with Section 1.3 (p. 2) of the Evaluation C
28	The PT team should ensure the current contracts in place are as robust and fit for purpose as possible, to avoid renegotiation of contracts during implementation.	Section F: Commercial Considerations	PT		By end of inception	None
29	This Annual Review recommends that guidance be created to clarify asset monitoring & control, including a threshold and monitoring system that involves FCO personnel.	Section F: Commercial Considerations	JFU/PFDU		Early implementation phase	None
30	All strand teams should create a written common narrative related to the intersections of PF Mexico’s programmes to ensure that all are on message.	Section G: Business Environment – Comms	PT		Early implementation phase	Agrees with Section 7 (p. 34 of Evaluation
31	The PF Comms Strategy is refreshed to clarify roles/responsibilities between the suppliers and the Embassy, working on a principle of subsidiarity - that whatever can be devolved to suppliers, should be.	Section G: Business Environment - Comms	PT		Early implementation phase	Indicated in Section 7 (p. 34) of the Evaluation
32	Suppliers’ Comms Strategies are scrutinised by strategic communications experts in the UK and Mexico to ensure they sufficiently link communications to policy efforts.	Section G: Business Environment - Comms	PT and FCO central comms teams		Early implementation phase	Indicated in Section 7 (p. 34) of the Evaluation
33	The PT conduct an audit of internal communications channels with the aim of rationalising and modernising these communications channels	Section G: Business Environment - Comms	PT		Early implementation phase	Indicated in Section 7 (p. 34) of the Evaluation
34	Responsibility for communications and stakeholder engagement be merged or at least brought more closely together.	Section G: Business Environment - Comms	PT		Early implementation phase	None
35	Strategic communications capacity be increased in the PF team as a whole to mainstream strategic communications into the supplier networks and rest of the programme team.	Section G: Business Environment - Comms	PT		Early implementation phase	Indicated I Section 7 (p. 34) of the Evaluation
36	The Embassy re-clarify the roles/responsibilities of VTs to ensure an appropriate split across Embassy teams.	Section G: Business Environment - Cohesion	Embassy Heads of Section		As soon as possible	Indicated in Section 7 (p. 34) of the Evaluation
37	The SRO consider the merits of broadening out PSAB (as the top-level programme governance advisory structure) to include other HMG programmes, to ensure broader coherence across Embassy programme work.	Section G: Business Environment - Cohesion	SRO		As soon as possible	Indicated in Section 7 (p. 34) of the Evaluation
38	The Secondary Benefits Action Plan is updated in line with new guidance and turned into a more useful strategic document which (a) sets out all different types of secondary benefit on offer including soft power; (b) has a more realistic assessment of secondary benefit potential (c) defines clearly the respective roles & responsibilities of DIT, the programme team, PF suppliers and London.	Section G: Business Environment – Secondary Benefits	PT and JFU		Early implementation phase	Agrees with Section 6.3.2 (p. 32) of the Evaluation Agrees with Section 6.3.2 (p. 32) of the Evaluation
39	Each strand updates its own secondary benefits strategy, which expands on the agreed strand logframes and utilises latest London guidance on secondary benefits.	Section G: Business Environment – Secondary Benefits	PT		Early implementation phase	Agrees with Section 6.3.2 (p.42) of the Evaluation
40	London clarifies its guidance on how suppliers might contribute to secondary benefits (in line with ODA rules). It would be helpful for the JFU to clarify this issue.	Section G: Business Environment – Secondary Benefits	JFU		Early implementation phase	Agrees with Section 6.3.2 (p. 32) of the Evaluation
41	The Secondary Benefits Advisor’s role be better integrated into PT structures. He is currently under-used by the PF team, both compared to expectations of that role and to his counterparts in Latin America.	Section G: Business Environment – Secondary Benefits	PT		As soon as possible.	None
	Strands
42	Ensuring activities are planned strategically to maximise value,	Section C: Energy	Energy PT		TBC	TBC
43	Work with supplier and DIT to get sufficient buy-in and action from small and medium enterprises.	Section C: Energy	Energy PT		TBC	TBC
44	Gender and inclusion dimensions should be more clearly articulated in the final logframe.	Section C: ACROL	ACROL PT		September 2019	Agrees with Annex 6 (p. 134) of the Evaluation
45	The programme team is advised to strengthen the functional cross-linkage of ACROL to the other strands. One approach would be to reflect one indicator per strand within the ACROL logframe.	Section C: ACROL	ACROL PT		September 2019	TBC
46	When Intervention 1 is redesigned to ensure buy-in at senior levels of the Government, it is done in a way which maintains as much as possible the ‘gender transformative’ aspirations of this strand.	Section C: Financial Services	FS PT		TBC	Agrees with Annex 4 (p. 98) of the Evaluation BC
47	The programme team considers how to flex requirements on frequency, quality or rapidity of bureaucratic requirements (e.g. meeting minutes) to increase the supplier’s ability to focus on front-facing work.	Section C: Financial Services	FS PT		Early implementation phase	TBC
48	The Embassy and supplier work to embed a ‘one-team’ approach across both organisations and other members of the implementing consortium.	Section C: Financial Services	FS PT		Early implementation phase	TBC
49	The FC team should feed back their experiences of procurement and evaluation to the central PF team to ensure future procurements are better tailored to the needs and resources of posts.	Section D: Future Cities	FC PT		Autumn 2019	Agrees with Section 6.2.1 (p. 28) of the Evaluation
50	The FC team should continue to work closely with the ICF and relevant policy leads on overlapping policy areas, clearly outlining areas of respective responsibility.	Section D: Future Cities	FC PT		Ongoing	None
51	The FC team should clarify roles and responsibilities with the supplier for the implementation phase and highlight any difficult resource pressures to the centre.	Section D: Future Cities	FC PT		Early implementation phase	None
52	The FC should seek to maintain a large element of flexibility within the implementation phase to flex to the changing needs of cities.	Section D: Future Cities	FC PT		Ongoing	Indicated in Annex 5 (pp 113 and 116) of Evaluation
53	The PT should widen their social inclusion strategy to address the needs of other vulnerable or disadvantaged groups where appropriate.	Section D: Future Cities	FC PT		Ongoing	Agrees with Annex 5 (p. 121) of Evaluation

## Summary of changes to the logframe since the last annual review
The programme theory of change and logframe have not changed since the Statements of Requirement were released in 2018. There is the expectation that once the strand logframes have been finalised at the close of inception, the programme level ToC may be adjusted at the intermediate outcome and outcome levels. There is currently no plan to amend the Mexico programme’s ToC: improved conditions for growth in Mexico, through increased capacity and an improved environment for trade and economic growth.

## C: DETAILED OUTPUT SCORING

The strand output indicators during the inception phase are incorporated into milestone documents for future monitoring and evaluation purposes and are not assessed at this point. For the purposes of the AR, the review is to assess the progress against the inception phase outputs, a.k.a the milestones.
## Strand 1: Energy
Output Indicators	Milestones	Progress	Score
Energy
1a.1 Number of women and men registered for training disaggregated by type (online or on-site) and identified skill gap (total of 5 priority skills gaps will be tracked)	Delivery of outline comms and branding for Centre: July 19	The energy programme created an independent brand ‘EPI’, implemented in three geographical areas epi-centres. The lead supplier hired a subcontractor to create the comms strategy. The outline strategy has been delivered. The next step is to produce a more detailed strategy for implementation. This will be done as part of the inception report in September 19.	A
1a.2 Number of courses taken per person (average)
1a.8 Number of TVET and academic institutions actively reaching out to the Centre
1a.6 Number of initiatives to promote the training Programmes of the Centre
1a.3 % of women and men that achieve certification	Draft ToRs for Centre Advisory board: July 19	The draft terms of reference have been developed and the boards are being formed. The team has been overcoming issues related to conflicts of interest as part of this process.	A
1a.5 Number of training Programmes provided on-site and online
1a.10 Number of companies contacted regarding participation in an apprenticeship Programme
1a.4 Number of initiatives held to attract women to training	Outline gender and inclusion mainstreaming strategy and action plan	The supplier teams have developed a basic outline strategy for gender and inclusion and meetings are taking place within the programme team to discuss elements that could be essential to all strands. The team has had some social development expertise to assist in reviewing the strategy, namely from the World Help Desk.	A
1a.9 Number of initiatives held to attract underrepresented and vulnerable groups (TVET intervention)
1a.11 Number of initiatives held to attract underrepresented and vulnerable groups (Apprenticeship Programme intervention)
1a.7 Number of technical vocational education and training and academic institutions contacted	Agreed stakeholder and community engagement plan for inception phase	This plan has been agreed and is a living document; the plan is structured in several phases. The first phase includes high level stakeholders such as senior advisors in the president’s office and ministers. The second phase is regional engagement with to two hub sites. The end beneficiaries of the programme are not included in the plan. The team has recognised that the plan needs to be developed to include SENER.	A
2a.3 State-owned companies (PEMEX, CFE), MNCs and investors registered in the Centre database
3a.1 Number of Regulatory Agencies engaged for training Programmes
3a.2 Number of meetings with interested Regulatory Agencies (local and national)
SB.1. Number of partnerships formalised with UK education and training providers and employers	Delivery of Secondary Benefits workshop	This completed work shop focused on developing four things: 1) Opening Markets: Open markets and increase market openness in the region, using a range of trade policy levers and encouraging greater alignment across the Prosperity agenda. 2) Trade Support: Support UK companies to win business in the region, and work to soften the trade mechanisms that may prevent them from doing so. 3) FDI Support: Increase the flow of investment from the region to the UK. 4) Promotion: Increase UK companies’ knowledge and understanding of the region as a trading destination, and equally update the perception in the region of the UK as a place to do with business with and from. The team did not have a clear understanding on the action plan following the workshop. Please see the business environment section for recommendations on developing this.	A
SB.2. # of UK companies engaged
2a.1 SMEs registered for training in top 5 key supply chains	Survey firm selected to conduct Industrial Baseline Studies (IBS)	A firm has been selected via a competitive tender process run by the lead supplier to conduct the industrial baseline study. The firm is struggling to get an adequate response rate to the survey. The team are considering how they can edit communications and plans to improve the response rate.	A
2a.2 SMEs certified in top 5 key supply chains
2a.4 Number of companies that SMEs recognize in the energy sector

Key Points
The energy programme is aiming to achieve the following outcomes:
1. A larger pipeline of certified male and female specialists to meet industry demand and a local workforce that is resilient to economic shocks.
2. The incorporation of market ready local male and female-owned SMEs in the supply chain of MNCs in the energy sector.
3. Increased levels of technical proficiency amongst regulators and male and female officials that uphold adherence to international standards in the energy sector.
The energy programme has achieved a significant amount over the period of this review. The programme has developed a business case and negotiated the approvals process including HMT. Excellent collaboration and relationship building stands out as a particular achievement of the energy programme. The energy team have had to face a challenging environment, and have negotiated uncertainty by being flexible and managing risk well, with excellent collaboration. It is notable that the energy strand has survived the transition to the new government, given that other donor initiatives have been ended
The programme team have developed good relationships with the suppliers, establishing common stretching goals and levels of ambition. The team have established effective ways of working with the Ministry of Economy, a key Mexican government department, gaining their buy-in on multiple interventions.
Recommendations
The key areas for the energy programme to focus developing on going forward are:
1. Establishing effective financial reporting systems with suppliers;
2. Ensuring activities are planned strategically to maximise value
3. Getting timely buy-in from small and medium enterprises.

## Strand 2: Anti-Corruption and Rule of Law (ACROL)
Indicator(s)	Milestones	Progress	Score
ACROL
1a. Standards, processes, guidelines and/or policies for investigation processes of serious crime.	One draft detailed costed workplan for Year 1 (Due 9 Aug)	The supplier has undertaken a variety of analyses, using stakeholder interviews and workshops, review of technical literature, and tapping into supplier’s networks to explore the dimensions and factors which define the impunity—the identified key market barrier—of Mexico’s criminal, corruption and cybercrimes. Through an iterative process, these analyses have informed the evolving ToC and logframe for the strand, structuring the interventions around processes, capacity and coordination in relevant government agencies and authorities as they relate to homicides (ROL), illicit enrichment (AC) and cyber-crime (ACROL). / In ongoing dialogue with the programme team and the Embassy’s Anti-corrupion Virtual Team, the strand’s design has improved the causal pathways of the strand’s interventions to support the Mexico programme’s impact of inclusive economic growth compared to what was assessed during the April evaluation data gathering. / The programme team is advised to consolidate the causal pathways in the final logframe and to ensure that indicators reflect the specific nuances the strand’s design now has. The supplier is also advised to articulate specifically how the ACROL interventions support the direction and goals of the other strands, as ACROL is frequently referred to as being “cross-cutting” with regards to those other PF/Mexico strands.	A
1b. Diagnosis and support to implement non-discrimination practices, policies and/or complaint procedures within rule of law and Anti-corruption institutions that are beneficiaries of this programme.
1c. Detailed outline of case building procedures for the investigation of serious crime.
1d. Detailed outline of case building procedures for the detection and investigation of corruption.
2a. Detailed outline of case building procedures for the detection and investigation of corruption.
2b. Training needs analysis for the detection and investigation of corruption.
2e. Pilots of specific investigation processes for serious crime.
2f. Pilots of specific detection and investigation processes for corruption cases.
2g. Scaling up of basic and/or specialised investigation skills training programme on serious crime.
2h. Scaling up of basic and/or specialised detection and investigation skills training programme on corruption.
2c. Design and delivery of basic and specialised investigation skills training programme on serious crime. / 2d. Design and delivery of basic and specialised detection and investigation skills training programme on corruption. / 3c. Multi-agency working groups for serious crime investigations involving multiple hand offs. / 3d. Multi-agency working groups on corruption involving multiple hand-offs.	One draft detailed costed workplan for Year 1 (Due 9 Aug) / One draft regional strategy agreement (Due 20 Aug) / One draft Gender and Inclusion plan (Delivered 17 Jul)	The programme team and supplier have explored the risks and safety concerns of implementers and partners inherent to programming in the three areas of crime selected for this strand’s interventions. The analytical process involved four sequential phases. If a state or region did not meet the criteria of a stage, it was removed from further consideration. These phases included, in order, a safety analysis, a political analysis, an institutional capacity analysis, and an expert analysis. Once the initial recommendations were made, the programme team and the suppliers conducted scoping visits and interviews with stakeholders and beneficiaries in multiple states. / The most recent revision of the ToC, submitted to the programme team on 19 July, provides evidence of these decisions. For example, the team have taken great care in deciding and defining which types of homicides are within the scope of the strand and which are not. The strand team has also divided the state selection for AC (illicit enrichment) and others for ROL (homicide and cyber-crime) due to security and safety concerns of teams. / This iterative process has slightly delayed, by mutual agreement, the delivery of the draft regional strategy. It’s revised due date is 20 August.	A
3a. Mapping of handover points between agencies working in serious crimes cases.	One draft detailed costed workplan for Year 1 (Due 9 Aug) / Stakeholder and Community Engagement plan (Delivered 31 May)	The purpose of the Stakeholder and Community Engagement (SCE) plan is to ensure comprehensive inclusion of relevant stakeholders, create a two-way flow of information, manage expectations, and identify and mitigate risks. The SCE plan identifies roles for the programme team, the supplier coalition, and the Embassy’s VT to take advantage of the strengths and networks. The SCE plan is regarded as a living document as the programme delivery evolves and stakeholders and their roles may change. This change was identified as a high risk in the risk matrix of the document. The programme team and suppliers are correct to anticipate the likely need for managing stakeholder evolution. / The programme team and suppliers are advised to review the SCE Plan to account for secondary stakeholders within the other strands to amplify the cross-cutting nature of the ACROL strand. They are further advised to use the stakeholder engagement to date and translate the experience, insights and detail into a strategic communications plan that also accounts for the ongoing global Anti-Corruption programme.	A
3b. Mapping of handover points between agencies working in corruption cases.
3e. Annual workshop for male and female judges working on corruption and serious crimes in three selected states to socialise new investigation standards and processes introduced by the programme and share international best practice.	Confirmation of dates and draft agenda for visit	The programme team seek first to confirm the regional strategy (due 20 August) prior to finalising the steps required to meet this 2019 deliverable. The process is on track.	A
3f. Diagnosis and support to implement non- discrimination practices, policies and/or complaint procedures within rule of law and anti-corruption institutions that are beneficiaries of this programme.	One draft detailed costed workplan for Year 1 (Due 9 Aug) / Draft Gender and Inclusion plan (Delivered 17 Jun)	In its draft Gender and Inclusion Plan, the supplier provides evidenced analysis of the impact that corruption and crime has on girls, women and other marginalised people. The Plan explores how and where in the process gender and class play a role in cases of crime and corruption. It draws from international and Mexican law and best practice. The Plan also includes a costed-workplan for the ACROL team to monitor financial commitments made to achieve G&I targets. The supplier anticipates collecting data related to gender and inclusion at the output and intermediate outcome level, which at the time of this annual review have yet to be finalised. / Gender and inclusion dimensions should be clearly articulated throughout the final design, including at the outcome level.	A

Key Points
The ACROL strand impact is: Reduced impunity to strengthen counter corruption and the rule of law. Three outcomes support this:
1. Improve the effectiveness of investigation of homicides;
2. Improve the effective detection and investigation of embezzlement of public goods and illicit enrichment; and
3. Improve the effective detection and investigation of fraud and identity theft.
Since the inception phase began, the ACROL team redesigned the strand to strengthen its linkage and potential to support the Mexico programme’s overall objective and to inform the PF’s family and global initiatives related to transparency and anti-corruption. The strand redesign has been a challenging and delicate process due to the nature of the themes identified. The programme team, the Embassy-wide virtual team (VT) for anti-corruption and the supplier have worked collaboratively and constructively to design and position the strand for relevance and impact.
The programme team has leveraged the work and relationships cultivated in previous PF programmes (FY 2016-2017; FY 2017-2018) and in transition programming (FY 2018-2019) to position the current PF plans (resulting analyses and reports were annexed in the 2018 Statements of Requirement which took the strand to market). The supplier team and the VT have supported this positioning with newly appointed government authorities. The joint visits to the states as part of the redesign process noted above has also allowed the programme team to cultivate a wider range of stakeholders at the state level as well as among private sector and civil society.
The ACROL strand is well-aligned with the priorities of the government as presented in its April 2019 National Development Plan (NDP). Anti-corruption is a hallmark of the actual administration and a standing feature in its NDP. The Strand Governance Board is a key mechanism which will provide a venue for a broad range of stakeholders from within and outside the government to further inform and position the ACROL programme on a regular basis as it moves through implementation phase.
Areas for further development relate to the cross-cutting nature of ACROL and the other three PF Mexico strands of Financial Services, Future Cities and Energy. While the programme team make frequent reference to this cross-linkage, there is little in the actual design that support the connections explicitly. There is still time in the inception phase to ensure that the welcomed language of cross-cutting, leveraged programming is realised in programme delivery.
The strand has improved the causal pathways to support inclusive economic growth and its alignment to the impact statement of the broader Mexico programme since the beginning of the inception phase. The indicators and data sources as reflected in July 5th Plan for MREL Engagement provide evidence of these causal pathways
The inclusion of cyber-crime, specifically in connection to financial transactions, represents an important design element to link the ACROL strand to inclusive economic growth and to support the goals of the Mexico programme’s financial services strand. Given the value that Mexico places on UK’s leading role in fighting cyber-crime, the inclusion of this intervention also positions the strand to achieve secondary benefits over the life of the programme.
Recommendations
Gender and inclusion dimensions should be more clearly articulated in the final logframe than is apparent in the currently available document. Consideration of the gender and/or class of individuals most likely to be victims of crime and/or corruption should be indicated, even when the indicator is for the private sector. For example, are female-owned businesses at greater risk of predation or do they pay a higher price for “services” than male-owned businesses?

The programme team is advised to strengthen the functional cross-linkage of ACROL to the other strands. One approach would be to reflect one indicator per strand within the ACROL logframe. In addition, all strand teams should gather to explore and create a common narrative related to the intersections of PF Mexico’s programmes to ensure that all are on message. This relates to the strategic communications recommendations noted in Section G: Business Environment, in this Annual Review.

## Strand 3: Financial Services

Indicator(s)	Milestones	Progress	Score
Financial services
1a(i). Number of female and male government welfare beneficiaries receiving financial education and/or behavioural nudging.	1 Stakeholder and Community Engagement Plan developed	Delivered. May need refining in future to reflect new information about key stakeholders. / Process helped both supplier and Embassy understand better the importance of iterative document design.	A
1a(ii). Level of satisfaction from training programmes
1a(iii). Number of financial institutions receiving training based on CHD
1a(iv). Number of monthly transactions in savings account/use of debit card from trained population
1a(v). Use of digital services form trained population
1a(vi). Secondary benefits indicator to be developed	One Secondary Benefit workshop delivered/ attended	Delivered on 25 June	A
2a(i). Number of secondary regulation issued influenced by international best practice	1 Draft Terms of Reference for sub-contracted Work Package developed	Delivered. Final version on track to be delivered as part of end/inception milestone documentation.	A
2a(ii). Number of UK experts providing professional and related services for Open Financial APIs	One Secondary Benefit workshop delivered/ attended	Delivered on 25 June	A
2b(i). Number of supervisory technology solutions available for Fintechs supported through the programme	1 Draft detailed and costed annual workplan for first year of Intervention activity	Delivered. Final version on track to be delivered as part of end/inception documentation.	A
2b(ii). Number of UK companies providing RegTech solutions for automated reporting and compliance	One Secondary Benefit workshop delivered/ attended	Delivered on 25 June	A
2c(i). % of processed requests to register as "Innovative Business Models" under the Fintech law.	1 Draft detailed and costed annual workplan for first year of Intervention activity	Delivered. Final version on track to be delivered as part of end/inception documentation.	A
2c(ii). Level of satisfaction of Fintechs that are accepted into the Mexican regulatory sandbox
2c(iii). Number of UK companies/products authorised through the Mexican Regulatory Sandbox.	One Secondary Benefit workshop delivered/ attended	Delivered on 25 June	A
3a(i). Number of candidates selected for adoption	1 Draft detailed and costed annual workplan for first year of Intervention activity	Delivered. Final version on track to be delivered as part of end/inception documentation.	A
3a(ii). % of candidates completing adoption programmes
3a(iii). # of UK candidates identified for the accelerator	One Secondary Benefit workshop delivered/ attended	Delivered on 25 June	A
3a(iv). # of UK companies completing the accelerator programme
3b(i). Number of Fintech users reached with socialisation component of the programme.	1 Draft detailed Strategic Communications Plan delivered	Delivered. Final version on track to be delivered as part of end/inception documentation.	A
3b(ii). Number of Fintech users in the lower 40% of the income range reached with the education component of the programme.
3b(iii). Number of beneficiaries of the socialisation and education programme using UK based Fintech products and services	One Secondary Benefit workshop delivered/ attended	Delivered on 25 June	A

Key Points
The Financial Services strand seeks to help ensure that women and marginalised people have higher financial literacy and access to ethical financial services. This is done via three key interventions: (1) improving designing the financial services related behavioural and educational components to complement of Government social programmes; (2) improving the regulatory framework for FintTech; and (3) creating FintTech centres promoting the adoption at regional level.
Transition funding was used in FY18-19 to build the evidence base (e.g. a study on female financial inclusion), engage the new Government (e.g. a Fintech policy mission to the UK), and maintain momentum (e.g. supporting Mexico’s Central Bank to strengthen green finance policy with its counterparts in other countries).  Anecdotal evidence and feedback suggests this has helped generate a strong start for the multi-year Financial Services programme.
The first few months of inception have seen good but mixed progress.  On one hand, the programme has adapted to significant political changes in Mexico, securing buy-in from different parts of the new Government. On the other hand, the programme has been hampered by delays and changes to Government social programmes (which have affected Intervention 1 in particular) and by significant capacity gaps and changes of personnel in the supplier, which have affected the smoothness of communication with the Embassy and the quality of financial reporting.
The programme is now getting back on track, with inception phase (largely) likely to be completed on time and to budget (although, in retrospect, a good case could have been made to front-load more resources to strengthen inception phase - this was also mentioned in the Evaluation Report).  But there will need to be some delay and redesign of Intervention 1 to reflect the changed political environment.
Recommendations
1. When Intervention 1 is redesigned to ensure buy-in at senior levels of the Government, it is done in a way which maintains as much as possible the ‘gender transformative’ aspirations of this strand.
2. As with other strands, a better climate/resilience strategy is developed (on the basis of enhanced guidance from London) which moves beyond ‘do no harm’ to consider issues such as encouraging disclosure of investment portfolio CO2 emissions, or supporting diversification of financial products to include climate resilient insurance.  One option for funding exploratory interventions might be the Agile Programming Fund (although that is relatively small at £1m over 3 years).
3. As with other strands, an updated secondary benefits strategy is developed for Financial Services which uses better both non-ODA resources (funding, DIT Sector Specialists) and ODA levers (mainstreaming secondary benefit work into the central interventions, for example via regulatory convergence).
4. London provides more guidance on effective tools for contract management to ensure the supplier is able to meet an ambitious delivery timetable.
5. The programme team considers how to flex requirements on frequency, quality or rapidity of bureaucratic requirements (e.g. meeting minutes) to increase the supplier’s ability to focus on front-facing work.
6. The Embassy and the supplier work to embed a ‘one-team’ approach across both organisations and other members of the implementing consortium.  A good start has been made, but this will necessarily need to deepen over time.  Bringing the two teams together at the inception/implementation juncture to (re)clarify their common vision and values might be one way to do this.

## Strand 4: Future Cities

Indicator(s)	Milestones	Progress	Score
FUTURE CITIES
1.1A. Number of recommended integrated transport strategies prepared for consideration by the relevant Authority.	Covered under ‘Milestone 2’ targets	All pre-selected cities (5) submitted their mobility proposals for intervention 1. The Programme expected at least 1 proposal per intervention and per city. The Programme received 12 proposals for intervention 1 (governance, integrated transport and data). Three cities were selected for Intervention 1. One strategy per city.	A
1.1B Number of stakeholder groups consulted regarding the recommended integrated transport strategies	Covered under ‘Milestone 2’ targets	Local government groups from each of the 5 pre-selected cities were consulted and these groups submitted their proposals to the Programme	A
1.2A Number of agreements for operation integration and/or data sharing prepared with input from the relevant authority for their approval	Covered under “Milestone 2 targets”	Number of agreements will be determined and finalised during the first stage of the implementation phase of the programme, as part of Intervention 1 (governance, integrated transport and data). Three cities have been selected for Intervention 1.	N/A
1.2B Number of stakeholder groups consulted regarding the agreements for operation integration and/or data sharing	Covered under ‘Milestone 2’ targets	Local government groups from each of the pre-selected cities (5) were consulted and these groups submitted their proposals to the Programme. For implementation phase, this will be defined by end of Inception phase, as part of Milestone 3, deliverables 3.2 and 3.3	A
2.1A Number of city proposals reviewed	Covered under ‘Milestone 2’ targets	All pre-selected cities (5) submitted their mobility proposals for intervention 2. The Programme expected at least 1 proposal per intervention and per city. The Programme received 12 proposals for intervention 2 (pilots). All proposals were reviewed by a panel of UK and MX experts and Embassy's PF Programme team.	A
2.1B Number of cities selected for the pilot	Covered under ‘Milestone 2’ targets	All pre-selected cities (5) submitted at least 1 proposal for intervention 2. Three cities were selected for a pilot.	A
2.2A Total number of potential pilots identified	Covered under ‘Milestone 2’ targets	Three feasibility pilots were identified for Intervention 2, one potential pilot per selected city	A
2.2B Number of stakeholder groups engaged during integrated transport solution pilot identification	Covered under ‘Milestone 2’ targets	Local government groups from each of the pre-selected cities (5) were consulted and these groups submitted their proposals to the Programme. For implementation phase, this will be defined by end of Inception phase, as part of Milestone 3, deliverables 3.2 and 3.3	A
2.3A Number of feasibility studies delivered	Covered under ‘Milestone 2’ targets	Three potential pilots were identified for intervention 2 (one potential pilot per selected city), delivery of the detailed annual workplan for year 1 and delivery of G&I Strategy and Action Plan.	A
2.3B Number of identified solutions deemed appropriate for full-scale pilot implementation following completion of a feasibility study	Covered under ‘Milestone 2’ targets		A
2.3C Number of interventions designed with demonstrable participatory consultation from local communities affected, women and the poor.	Covered under ‘Milestone 2’ targets		A
2.4A Number of Pilots launched in target cities	Covered under “Milestone 3 targets”	Final number of pilots will be confirmed during Y1 of implementation, after pre-feasibility studies are carried out for all shortlisted pilots. List of shortlisted pilots is included as part of detailed annual workplan for year 1 (milestone 3).	N/A
2.4B Number of Pilots delivered in target cities
2.4C Number of male and female users using the pilot

Key Points
The intended impact of the Future Cities strand is: ‘Improved efficient urban development in Mexico’s cities that results in safer, resilient and more sustainable mobility services for citizens, particularly women and girls.’ This will be achieved through two main outcomes:
1. Improved governance, planning and coordination between transport and urban development authorities in Mexico’s cities, and
2. More inclusive, safer, more efficient and more sustainable urban mobility services, in Mexico’s cities, particularly for women and girls.
And through two supporting, intermediate outcomes:
1. Transport authorities in Mexican cities adopt and implement new governance for integrated transport strategies and operation integration and/or data sharing protocols, and
2. Transport authorities in Mexican cities adopt the solutions tested in pilot cities on integrated transport systems.

While the strand is still in the inception phase, there is evidence that the programme is well-placed to achieve these outcomes and impact over the longer term. The Future Cities programme has, so far, been focused on achieving ‘milestone 2’ which includes a number of deliverables, in tandem with the supplier alliance, throughout the inception phase, while the logframe was still being developed (this process is new to the Prosperity Fund country teams and support from London was provided quite late). As a result, the scoring against the logframe is difficult to articulate in this review, although good progress has been made by the strand in all areas, and the indicators have been achieved.
Milestone 2 includes an MREL plan, the first meeting of the Strand Governance Board, a regional cities strategy, a draft G&I strategy and action plan, a draft climate/resilience action plan, revising the Logframe, a costed annual workplan (recently presented at the quarterly review meeting), and a draft outline delivery plan for subsequent years. These are sensible inception targets, which will set the programme up for future success.
The FC strand team learned good lessons from the Transition Phase, which have positively influenced the inception phase.
- The scope of the strand was refined and narrowed to a primary focus on mobility and digitisation, and infrastructure were downscaled, to ensure work focused on areas of greatest primary benefit, alignment with government priorities and likelihood of secondary benefits. This ensured supplier bids were more targeted and easier to evaluate.
- The Virtual Team structure evolved. Collaboration between the team and DIT and policy leads across the embassy, and those located across the country, was very good (for example on the electro-mobility event), and the FC team did well to de-conflict with the incipient International Climate Finance (ICF) programme, to ensure the PF strand was providing additional benefits.
- The team also learned about managing a consortium/alliance, which is different to previous PF work.
- The team took the opportunity to increase engagement with the new government during the transition year, through the use of the three reactive funds.
- It took much longer to migrate from a grant agreement to a commercial contract than expected. This was due to longer procurement processes. As a result, commercial contracts started later than expected which had an impact on the delivery of the project and difficulties on stakeholder engagement with the Mexican Government. For example, for the project with SEMARNAT on the electro-mobility strategy, consultants were required to help draft it (using the reactive funds). Development of the TORS took a long time due to their breadth, and in the delay, SEMARNAT’s requirements changed. In consequence, much effort was needed by the team to clarify the project’s goals and manage the relationship and reputation of the PF with SEMARNAT.
- There are some concerns that the budget for non-ODA in inception phase is less than for transition. However, now the programme is more established, funding can be prioritised more easily and complement commercial activities.

In the transition phase, the team faced a number of capacity challenges around procurement and evaluation of bids. In general, the processes were difficult to handle at post given the strict requirements and the need to adapt them to Posts:
1. Developing the SORs was challenging as the team lacked experience in developing theories of change and logframes. However, the team took the opportunity to build their capacity and expertise.
2. The bid evaluation process was resource-intensive and the two-week window for evaluating very large and complex bids was too short given available resources at Post. The team put in overtime to complete this process. However, many interviewees expressed confidence in the eventual results of the process, given the success of initial projects, such as the PF/DIT non-ODA project to find a supplier for modernisation of transport systems, which is now in a second phase and being funded outside the PF.
3. In general, moderation meetings were well run and consultative. The FC bids tended to be well-structured, due to the clarity of the initial TORs. Bravo, the evaluation collaboration tool, worked well for the team. Policy teams and DIT participated, together with DFID external challenge, and all found the range of views during evaluation helpful.

The team has worked well with the lead supplier, and delivered a lot during the early phases. Managing a consortium has been challenging for both parties in terms of communications and allotting roles and responsibilities. The supplier has been responsive to the PF team in developing ways of working and communications with the centre, and retaining agility in the programme. These are real achievements. However, the FC team should continue to work closely with the lead supplier to ensure the right information flows are in place to ensure all members of the consortia are well-briefed and that intra-consortia conversations and disagreements and handled well by the lead supplier. They have developed a strategy for this and work is underway, and feedback from consortia members has improved. Also, unless further resource is to be allotted to the team, it is critical that the ‘admin burden’ of project management from transition/inception now sits clearly with the consortium rather than the FC embassy team, so roles and responsibilities should be re-visited and clarified.
The FC team and supplier put great effort into stakeholder engagement during the review period, including at regional and city level. This has yielded dividends. The City Managers have been invaluable for managing relationships, clarifying communications and assisting cities to write high-quality bids. The team have also worked closely with SEDATU, raising their profile with CDMX in particular and providing a route to federal engagement.
The FC strand has several key gaps in common with the other PF strands. Gender considerations have been effectively mainstreamed into the FC strand through the team’s design work and close engagement with stakeholders in key cities, and the standard of G&I in the FC strand is high. There is a window of opportunity on wider social inclusion such as disability and other marginalised or vulnerable groups while in inception phase or during implementation, following pilots. This should include work to mainstream the views of impoverished groups into pilot design, to ensure that poverty reduction can be achieved both directly by the programme by widening the beneficiary base, and indirectly through improved transport for all.
Climate change remains a key gap, particularly given new requirements around climate integration in ODA programming, but presents huge opportunities for the programme to mainstream climate in terms of emissions reductions and adaptation of transport systems. This could provide great examples for other PF countries. Guidance and technical support should be provided for this from the centre, and the team should continue working closely with the ICF team and climate policy leads. The FC strand presents some obvious short to medium term secondary benefit opportunities, especially around electro-mobility and vehicles, but in common with the other strands, developing indicators for this has been challenging and further guidance on managing SBs within an ODA programme should be provided by the centre.

Recommendations
The FC team should continue to push for ongoing training and support for contract management, to grow the team’s expertise further and allow strand-to-stand learning.

The FC team should feedback their experiences of procurement and evaluation to the central PF team to ensure future procurements are better tailored to the needs and resources of posts.

The FC team should continue to work closely with the ICF and relevant policy leads on overlapping policy areas, clearly outlining areas of respective responsibility.

The FC team should clarify roles and responsibilities with the supplier for the implementation phase and highlight any difficult resource pressures to the centre (for example, around budgetary pressures causing fractures within the implementing alliance).

The FC should seek to maintain a large element of flexibility within the implementation phase to flex to the changing needs of cities.

In common with the other stands, an improved climate/resilience strategy should be developed with guidance and technical support from London; a focused and prioritised secondary benefits strategy should be developed for FC, and consideration should be given to what opportunities may need to be explored after the pilot phase concludes, and the FC and PF teams should consider how to widen their social inclusion strategy to address the needs of other vulnerable or disadvantaged groups where appropriate.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

## Key cost drivers and performance
The following cost information is from the financial year 2018/2019.

Table D1: Financial spend in 2018/2019
CONCEPT	ALLOCATION	Actual spend	£ Variance	% Variance
STAFF COSTS (UK & local)	£430,000	£470,215	£40,215	9.4%
TRANSITION	£170,000	£169,770	-£230	-0.1%
ADDITIONAL TRANSITION	£98,500	£98,500	£0	0.0%
PLATFORM CHARGES	£278,940	£273,285	-£5,655	-2.0%
MULTIYEAR	£379,990	£443,453	£63,463	16.7%
TOTAL	£1,357,430	£1,455,223	£97,793	7.2%

Transition and additional activities both came in on budget. There was an overspend in the multiyear category because the programme team had the opportunity to bring a payment forward from 2019/2020, and after flagging the possibility with PFDU they were asked to do so, therefore this overspend was properly managed and is not a concern, and in fact shows positive financial management. The actual spend on staff cost is over what was estimated at the beginning of the year, but under the business case estimate. The administration costs, which include staff costs, L&D, and team travel for capacity building and knowledge sharing events and conferences is within the 5 percent cap.
The main driver of the variance is staff costs for three main reasons. First, using PFDU’s guidance, the forecast for UK based staff costs was done based on the average grade costs. Because of sensitivity issues, we were not allowed to receive detailed information. It was not until the end of the fiscal year when the team received a lump sum of this expense category to do our forecast. Secondly, there was a salary increase for both UK based and local staff. Given the first point mentioned above, we do not know the proportion of the change for UK based staff. For local staff, the increase was charged retroactively in March. The team did not have information on how much would the increase be until charged budgets were received. Thirdly, changes in senior management at Post were not adjusted downward by London until this fiscal year, which led to a perception of overspend.

Quality of financial management
The programme team has 1.7 FTE staff dedicated to managing finances.
The internal programme management structures of the Prosperity Team are working well, with systems in place to monitor spend and to allow this to be audited. Staff are aware of the delegated authority they have. The programme holds a monthly finance meeting attended by the head of the programme, finance leads and programme managers. At the monthly finance meetings programme managers are held accountable for their strand’s spend, and decisions are made to adjust allocations where there is an expected over/under spend. Decisions are recorded on the financial management spreadsheet and kept in a central location for audit purposes.
The programme had an embassy wide internal audit in 2017 and another is due in in November 2019. The programme has budgeted money for independent external audits, and they intend to schedule the first one of these in the next year.
Difficulties in the financial management in the programme include:
- UK based staff costs. As noted above, the programme team does not have access to UK based staff cost figures, and the ambiguity around this makes accurate budgeting difficult. This annual review recommends that the programme team is given access to accurate UK based staff costs. If this is not possible, the central FCO finance teams should provide the programme team with average staff costs instead of actual to allow more accurate budgeting.
- Platform costs: The programme team does not have access to the details of what is included in the platform charges. This means that they are not clear on what they are entitled to and they are not able to forecast accurate platform costs for the life of the programme. This annual review recommends that the programme team obtains an explanation from central FCO finance teams of what the platform charges consist of and how they may vary over the life of the life of the programme.
- Financial reporting from suppliers: There were initial teething problems with some suppliers understanding of the financial reporting requirements. Part of this may be because different countries’ Prosperity Fund programmes who commission the same supplier have different systems. This annual review recommends that PFDU standardise common financial management systems across the Prosperity Fund FCO programmes. So far as is possible, this should be harmonised with other government systems, particularly DFID. The PT should hold workshops with suppliers who are not fully compliant to make financial reporting expectations clear.
- Feedback from cash flow forecasts: The programme team submits information monthly as part of a cash flow forecast exercise. The team does not receive any feedback on this, so they do not know if the information is being used, or if there are any issues. This annual review recommends that PFDU develop a feedback mechanism for the cash flow forecast data, even if this is just to recognise that is received and the information is adequate.

VfM performance compared to the original VfM proposition in the business case
The Business Case was approved in December 2018. Whilst the programme has made refinements, there have been no major moves away from the business case, therefore the value for money case within it, which has already gone through significant scrutiny, remains valid.
## Economy:
The main work over the last year to ensure the programme was economical was the procurement process. The tendering process completed in December 2018 and final selections were sent to London for contracting. The negotiations between the PF and the selected strand suppliers continued through January, with each contract concluded in February 2019.

The programme team used the central procurement framework for its procurement. To sense check what the programmes might cost, the programme team deduced rough estimates with support from consulting experts. The programme team then tested the realism of their expectations with the market before releasing the Statement of Requirements.
Members of the programme team submitted questions about the budgets of the bids during the tender process, and submitted clarification questions on the purpose of certain parts of proposed spend. Through these questions, bidders were able to clarify the proposed spend and identified ways to make spend more economical.
This programme is being run on a larger scale than previous grant-based intiatives, aiming to achieve larger impacts, including economies of scale by office-sharing between programmes with the same supplier. Such a programme and scale of impact would not be manageable with a plethora of small contracts. This annual review recommends that the programme team, and PFDU, consider how to incentivise economies of scale within large suppliers, particularly where one supplier is serving multiple programmes.
The programme team has made terrific efforts to upskill themselves in contract management. Yet there were weaknesses during procurement which weakened optimal value for money. The team reported that some of the commercial documents which they cleared were not the documents published by the commercial team. Instead, older versions were published which did not properly reflect the emerging requirements of the team. In addition, the team thinks that had they had better negotiation skills during the bidding process, they would have yielded even greater value for money than is evidenced today. Please see the ‘Commercial Considerations’ section of this review for more information.
Due diligence is an important part of the value for money process. The review found that more transparency could have helped between the central London team and the programme team about the due diligence process and any findings. In addition to this, the main suppliers are expected to conduct due diligence on subcontractors, however the programme does not have the expertise to set exceptions on what this should include, and to check that this has been done adequately. This annual review recommends that the programme team, and PFDU, ensure the programme team has access to due diligence expertise, and the results of due diligence screenings are shared with the programme team.
Part of strong contract management is the ability of the team to have clear knowledge of what to do if suspected corruption or fraud is identified. Currently, the programme team is not fully confident of their knowledge in this area. This annual review recommends that PFDU provides training on what to do when suspected corruption or fraud is identified, and that suppliers are warned about this in advance so it does not come as a surprise if this occurs. For example, if all payments are paused until the situation is resolved.
The Statements of Requirement for each of the four strands suggested a 5% cap on inception phase spending. All bidders submitted commercial bids based on this 5% suggestion and the contracts reflected this expense allocation. However, one lesson learned from the programme team was that this perceived restriction has caused issues for the suppliers during the inception phase. In the future, a suggested cap might lead bidders to understand that the limit is required and lead to undercutting financial flows at a sensitive time of programme design and launch.
The other significant learning point relates to use of the PF Framework Agreement, which is populated by UK-based companies. The ACROL strand team thinks it could have secured more cost effective proposals if the local market was considered in the bids. (Local firms and organizations can participate, but only as resource partners to lead bidders from the Framework). Other PF programmes should therefore consider allowing non-framework national firms to bid when procuring, if the PT know there are strong capabilities in the local market.
## Assessment of whether the programme continues to represent value for money: efficiency and effectiveness
This section summarises the results of the VfM scorecard process. The process is described in more detail below, along with the results for each strand and for the programme as a whole for the eight VfM criteria.
In Cycle 1 the VfM analysis has focused on process issues, in other words, to what extent has the PT selected suppliers and established processes and systems that are likely to generate VfM in future? Actual achievement of VfM will be assessed in future cycles.
Each criterion was scored from 1 to 5, on the basis of whether evidence to support the criterion is not available, weak, adequate, good or strong. The grounds for making this judgement is set out in the E&L guidance note on VfM.
Overall, the programme scores 3.9 (out of 5), on the basis that there is good evidence the programme has put in place suitable arrangements likely to generate VfM over the course of implementation. Scores for each strand are illustrated in Table D3 below.
Table D3: Summary of Value for Money Criterion scores, for each strand and the programme as a whole
VfM Criterion	Energy	Future Cities	Financial Services	ACROL	Average programme score
1 – VfM indicators	3	3	3	3	3
2 – Procurement and cost containment	5	5	5	3	4.5
3 – Efficient use of resources	4	4	4	4	4
4 – Valid causal pathways	3	3	3	3	3
5 – Sustainability	3	4	3	4	3.5
6 - Governance	4	4	4	4	4
7 – Risk management	5	5	5	5	5
8 - Equity	4	4	5	4	4.25
Average Strand score	3.9	4.0	4.0	3.8	3.95

It is notable that the average programme score was 4 (‘good’) or above for five of the eight criteria.
Those criteria with scores of lower than 4 indicate areas for improvement. Of these, less attention is required for: VfM Criteria 1 (Relevance and robustness of VfM measures in place) and 5 (Sustainability of programme activities). In these instances, a lower score reflects the fact that logframes and some other documents (e.g. Climate Resilience Plans) have not yet been finalised and therefore could not be included in this analysis. However, when they are completed by the end of inception, these scores seem likely to rise on account of work that is already in progress.
VfM Criterion 4 (Validation of PF ToC causal pathways for generating primary and secondary benefits) is scored 3.25 for the programme as a whole. There is scope to improve this for the Future Cities, Financial Services and ACROL strands, and it is also important to do so because in assessing the “four E’s for VfM” this criterion is the main test for Effectiveness[3].
[3] The others are Economy, Efficiency, and Equity.
- The broader evidence on financial inclusion supports the view that the Financial Services strand could lead to inclusive economic growth and lower inequality. However, positive impacts on inclusion are only likely to occur in the context of supporting conditions, which are not currently within the ambit of the strand. The strand ToC should therefore be clarified to include the assumption that these supporting conditions do in fact occur, and to highlight the risk that the strand may not achieve inclusive growth if they do not.
- For Future Cities, it is important that the pilots for each city set out the specific causal pathways from strand outcomes to inclusive growth and poverty reduction, including defining how women and girls or other disadvantaged groups will benefit.
- For ACROL, the evidence that greater cyber-security, improved homicide investigations and better access to justice will reduce poverty is highly indirect. The logic that improved commercial, administrative and security dimensions at the state and federal level will improve economic growth is better substantiated. The final design of the ToC and the indicators selected for the strand should therefore set out clearly the pathways for achieving this.
Strand scores for VfM Criterion 4 (Validation of PF ToC causal pathways for generating primary and secondary benefits) could also be improved by developing clearer actions plans for Secondary Benefits (SBs) along the lines indicated in the next section (and in the annex for each strand).
The full assessment according to the Value for Money scorecard is given in Annex B.

## FCO Economics Unit Quality Assurance summary
Strength of evidence to support assessment: Good – the assessment draws heavily on last’s years evaluation report as well as programme documentation and stakeholder interviews.
Key cost drivers and performance
The programme is currently in inception with the majority of milestones having been met on time. Overall there was an overspend of roughly £100K or 7%, primarily due to a payment being bought forward. The main costs driver is staff costs (a variance of +9% last FY) due to inaccurate information when making the original forecast, as well as unforeseen salary and staffing changes. It’s unclear whether these issues are likely to persist. If they are, we recommend that mitigating actions are identified and agreed. Administration costs are within the 5% JFU cap.
Economy
The VfM scorecard rated the programme 5 out of 5 for approach to procurement and cost containment. A competitive tendering process was followed via the PF framework, however the review notes that if staff had better negotiation skills and experience of procurement, then a better outcome could have been achieved. Staff also lacked knowledge on how suppliers should conduct due diligence of sub-contractors. The review recommend JFU provide access to due diligence expertise training to fill capability gaps. We deem these recommendations to be sufficient.
Efficiency
For efficiency the programme was rated 4 out of 5 due to effective use of monitoring tools and processes. It is also noted that there is strong governance structures, including excellent risk management, though little evidence so far that they are working as intended.
Effectiveness
The programme is still in the inception phase so the assessment of the programme’s effectiveness is limited. At present there is no indication that the benefits set out in the business case won’t be achieved. The programme ToC was scored 3 out of 5, noting that casual pathways needed to be better defined for both primary and secondary Benefit. We recommend the ToC is reviewed on a regular basis against programme outcomes, to assess whether the theory and underlying assumptions are realistic.
Equity
Scoring a 4 out of 5 with good evidence that G&I issues were actively considered in programme design, procurement, delivery and monitoring. The programme holds bi-monthly cross-programme gender meetings, to coordinate work between the different suppliers on this issue. Each supplier is required to have G&I strategies and there is a good level of disaggregation in the logframe. It’s too early to evaluate the distributional impact of the programme.
Overall VfM Assessment
There have been no major moves away from programme activities as set out in the business case and annual review finds no reason why the value for money position would not remain valid. The programme scored 3.9 out of 5 on the VfM scorecard overall, based on a good level of evidence that the programme has put in place suitable arrangements likely to generate VfM. We agree with this assessment.
Quality of financial management
There is good financial management, albeit initial teething problems with some suppliers understanding reporting requirements which has now been resolved. Costs are scrutinised on a monthly basis and paid against agreed milestones.
MREL
A Year 1 evaluation report has been conducted, which forms the main evidence base for the annual review. The review notes a good culture of continual learning and improvement. Log-frames are still being finalised.

## E: RISK

## Overall risk rating: Moderate
The annual review found that the Mexico Prosperity Fund programme team is taking a proactive and appropriate approach to risk management. They are front-runners in the Prosperity Fund in terms of risk management, they have developed a risk register and started managing this before the PFDU/JFU had done this. The Prosperity Fund’s risk template is based on the programme team’s work. The programme team has a good level of input from experts and this has allowed them to manage the risks around the change in government well, and to work towards future proofing the programme.
## Overview of programme risk
Guidance, governance and management systems across the Mexico Programme extend from the centre of Whitehall through the Embassy, into the PF and the strands and down into satellite hubs and working groups of the suppliers. The Mexico Programme has been routinely among the vanguard in bringing the PF from design to inception. As such, it frequently needs guidance before many of its PF colleagues. The Head of PF in Mexico noted the value she finds in the annual London PF gathering in December as an efficient way to connect with peers and share challenges and approaches to strengthen the early evolution of PF programmes.
These guidance systems support and improve programme design and positioning when information is timely, fulsome, and relevant. When guidance arrives too late, or not sufficiently detailed or too generic, it can cause delays and even reputational risk.
The evaluation team heard repeatedly that some guidance and training from the Joint Funds Unit (JFU) or the Prosperity Fund Delivery Unit (PFDU) tends to be too generic to utilise in-country without substantial adaptation. The PF team note that sometimes it has requested guidance from London and has been told that the guidance was in development and to wait. But it has found that waiting can create programme delays and risks to reputation. To overcome the situation, the PT has sought outside support and capacity-building or designed tools or process proactively and sought London approval. For example, the team utilised the time between outline business case (OBC) submission and Statements of Requirement (SoRs) to build internal capacity, particularly around Gender and Inclusion (G&I) skills as well as programme management skills[4]. Examples of document creation include finance, commercial, contract management, monitoring and reporting requirements and methods; tolerances (i.e., the flexibility within the terms and conditions of the contracts); the SoR pricing schedule, and carbon offset credits for travel and safeguarding requirements. These were all adapted from previous best practice and existing UK formats, including from Department of International Trade (DIT) and the Department for International Development (DFID).
[4] The PM required all PT staff to undergo PRINCE 2 programme management training to strengthen the future implementation of the four strands.
It is not always clear to the PT why London requires a document. Several PF staff told evaluators about preparing a Secondary Benefits (SBs) plan in early 2018, but little feedback was received. “It went to the JFU and that was it.” It was, indeed, used by stakeholders in London, but that information did not make its way back to the PT in Mexico. In other instances, London changes previous guidance which, the team notes, brings a reputational risk.
At mid-point in the inception phase, the PT is particularly eager to receive JFU/PFDU Guidance for change control at the strand level. The Schedule 11 form is complex and oriented to changes at the programme level. There is no clarity about how individual strands submit these forms, yet now is the time that the strand teams are submitting changes that require oversight.
PFLearning has also been behind the informational needs curve of the Mexico PT to date. The PT expect that once other programmes enter implementation, the online platform will be of greater utility to the Mexico team and its strand suppliers. Until then, Mexico joins selective PF presentations or sources key documents from the platform on a limited basis. The greatest area of interest is in the family reference groups (FRGs), but the PT notes that the intense focus required to bring the strands through procurement and inception limits time available for other, albeit relevant, information sharing.
## At Post
The governance structures of the PF in country are a series of committees and boards which aid the decision-making and oversight processes required of the PT.
Programme Management Committee (PMC). The PMC meets monthly and includes representatives from all the UK programmes underway in Mexico. The committee has a clear terms of reference (TOR), including membership, data required of it prior to its meetings, voting rights and reporting requirements. The Head of the PF in Mexico attends with voting rights, while each PF strand and global programme has observer status on the PMC. The primary function of the PMC is to “ensure proper strategic oversight of all Embassy programmes,” including budgets, risk and mitigation, and to provide guidance where necessary.
Virtual Teams (VTs). First used in the PF with the drafting of the 2017 OBC[5], the VTs include representatives from the Embassy’s departments that have a direct relationship with the PF’s goals and processes – the strand programme managers, FCO’s political and global issues teams, DIT, communications leads, commercial experts, and representatives from other programmes, including Newton, ICF and the International Fund. The VTs provide strategic direction and ensure rigour so that the logic and relevance of each strand is optimal and adapts to national political economy contexts as well as serving broader UK interests in Mexico. The VTs make use of cross-Embassy sector plans, which are approved by Heads of Section in the Embassy Board of Management, and enable different departments within the Embassy to see and understand clearly what their colleagues are doing and to identify linkage and leverage points. Plans also identify the breadth of interventions, including communications, resources and risk. Impact pies consolidate the goals of the respective Embassy departments set against metrics so that a whole-of-Embassy perspective is maintained.
[5] Mexico Prosperity Programme Outline Business Case, June 2017. Page 148.
## Within the Prosperity Fund
There is evidence that the PF programme is well structured to ensure regular review and discussion of PF and strand policy, stakeholder engagement, and challenges. The mechanisms noted below also serve to identify cross-strand leverage and mitigate gaps and/or redundancies in programme implementation.
Prosperity Fund Strategy Advisory Board. The PF Strategy Advisory Board provides a venue for high-level discussions which include senior UK and Mexican authorities to ensure strategic oversight and proper alignment of the PF and “to maximise the impact of the PF programme on Mexican economy/society.” The writ of the Board plays a role in positioning the PF in key ministries in the new administration, the private sector and relevant associations and civil society. The board meets quarterly and has a clear TOR, including membership, reporting requirements and agenda format. The TOR will be reviewed internally in March 2020 to ensure that the board is meeting expectations.
Cross-cutting theme leads. Another mechanism created by the Head of the PF in Mexico to promote cross-learning and ensure that complexity is managed is that each member of the PF team holds a cross-cutting theme which they manage for a year in addition to their technical team roles. The 14 themes include:
- Programme planning
- Risk management
- Gender and inclusion
- Non-ODA
- Safeguarding
- Stakeholder management
- Latin American engagement and conference
- Lessons learned
- Celebrating success
- Learning and development
- Monitoring, reporting, evaluation and learning (MREL)
- Information management
- VfM
- Annual review.
While there is confluence among these themes, there is no duplication and specific ToRs provide definition and focus. Theme leads invest time for learning, sharing and coordination within their respective assignments, which enables them to develop their professional capacities, mitigates stove-piping and strengthens cross-team learning and action related to the themes.
There is strong evidence that these cross-cutting themes have improved the design of the strands and supported peer learning within the PT. For example, the G&I considerations between the OBC and the SoRs were much improved in part due to the attention and coordination that the cross-cutting theme lead for G&I invested in her role. This improvement was noted in the G&I Stocktake conducted in February 2019.
Another example is seen in the way that the PF teams in Latin America regularly exchange information and ideas through informal and formal channels, including the regular LatAm regional meetings[6]. There is evidence that models, such as the VTs, or the insights into contract management are already leading to adoption of regional best practice.
[6] The next LatAm regional conference is scheduled to take place in Mexico in 9-11September 2019.
A third example is related to safeguarding. This cross-cutting theme was added in 2018 and the PT built safeguarding requirements into the SoRs. Following G&I consultations in the ACROL strand, the Cross-cutting Theme Lead realised there was existing DFID guidance which would augment and enhance the safeguarding elements already factored into strand designs[7]. These have since been incorporated into Mexico’s programming.
[7] Requirements based on “DFID Enhanced Due Diligence: Safeguarding for external partners.”
Gender and Inclusion (G&I) Group. The G&I Advisors/Leads from each of the strand supplier teams meet monthly with the PF’s gender theme lead to discuss the mainstreaming and the cross-strand leverage opportunities for G&I. In addition to providing evidence that these discussions support the integration of G&I into strand designs, there is also evidence that unexpected strand coordination can occur from this group’s discussions. For example, during one of the earliest G&I Group meetings, the ACROL and Financial Services strands identified common stakeholders and agreed to collaborate on engaging them strategically. The G&I group is also seeking to identify common indicators as necessary to enable the Mexico Programme to tell as strong a G&I story as possible.
Other thematic groups. The PT has already arranged similar cross-cutting supplier groups related to the APF (met once), SBs (met once) and communications (met three times).
Strand Governance Boards (SGBs). Each strand has its own SGB. The SGB will provide accountable, responsible and transparent delivery oversight for the Energy, Financial Services and Future Cities strands. The final function of the SGB for the Energy and ACROL Programmes is still under discussion at the time of the drafting of this evaluation. The SGBs ensure the collaboration of key stakeholders who are strategic decision-makers, thereby ensuring continued alignment to Mexican government priorities. The membership of the SGBs is at the working level and includes key government agencies and actors to fulfil the board’s mandate, which is to ensure that the programme is oriented to support and help drive the aligned government objectives of key departments.
## Within strands
Based on the Call-Off Contracts and the KPIs, there is strong evidence that strand suppliers have put into place management structures and procedures that support the design and positioning of their respective strands during the inception phase. Many of these management structures are similar across the strands, whereas others are bespoke to a specific strand.
Central Delivery Units (CDUs). The CDUs are the main delivery unit for each strand and include common elements such as in-country staff, head office support from the supplier’s headquarters in the UK and access to the resource pools that each strand supplier identified in their bids. All CDUs are based in Mexico City to facilitate coordination with the PT and federal government stakeholders. All strands will have CDU satellites or hubs to facilitate improved and sustained engagement with local stakeholders (see Table below).
Table E1: Central Delivery Unit satellite/hub by strand
Strand	Satellite/Hub	Details of Satellite/Hub
Energy	Tabasco	Training hub to serve the gulf region (inc. Campeche and Veracruz)
	Jalisco	Training hub to serve the centre region (Inc. nearby states TBD in inception)
Financial Services	Querétaro and Campeche for Y1 / Mexico City, Jalisco, Sonora and Puebla thereafter	Financial Innovation Centres
Future Cities	Queretero, Mexico City, Monterrey, Guadalajara, Hermosillo	Pilot cities which test mobility solutions
ACROL	Mexico City	Centre of policies and largest populations
	Jalisco and Tabasco	Rapid growth area

*Subject to decisions to be taken at the end of inception phase

Monthly reports. There is evidence that the PF Mexico Programme has built learning and development into the reporting system. The PT have incorporated weekly activities logs and monthly logs that capture lessons learned, issues and risk updates from each strand. These logs are reviewed by the respective PF strand management teams and then circulated within strand VTs to ensure that insights, learning and challenges are known to the relevant counterparts within post. These logs are entered into other management systems, including Prospero, the PF programme debriefs and PT–supplier discussions.
Data quality. Each strand supplier will create an agreed plan for MREL engagement and compliance by the end of their respective inception phases[8]. The template for this document was prepared by the monitoring and reporting hub and introduced in April’s joint MREL workshops. The introduction of this template coincided with the release of the guidance notes on data quality, which enabled specific discussions regarding data quality with strand programme managers and strand supplier teams as the revisions to ToCs and logframes were beginning. Once completed by each strand supplier, the plan will include details on the collection, frequency, storage, flows and quality assurance for each indicator identified in the strands’ final approved logframes. Because these details are collected in a single document, it will be easier for this data to be monitored by the PT and in subsequent evaluation cycles.
[8] Milestone 2.1 in the Call Off Contracts.
## Bespoke systems within strands
Within each of the strands there are advisory or working groups, additional oversight bodies or other management and governance systems designed to extend programme reach or improve the positioning of the respective strands closer to their stakeholders and partners.
The Energy strand has an innovative goal for its CDU in that it is not only a strand management body, but it is designed to anchor the strand’s sustainability strategy post-PF (See Annex 3). There is good evidence that the design of the CDU has been well-reasoned, but it will only be relevant to evaluate progress on this goal later in the implementation phase.
## Risk management over the period of the annual review

Over the past year, the risk thinking has started in virtual teams who update strand specific risk logs. The risk lead then cross-references the strand logs and identifies any overlaps, and raises these risks to the Head of Prosperity Fund and Prosperity Councillor. As well as reviewing the strand risk registers, the Head of Prosperity Fund identifies any portfolio level risks that are not captured by the strands. The descriptions of the regular risk reviews teams held were quite focused on monitoring risk and checking on mitigation. This review recommends that teams also consistently make space for identifying new risks as part of their risk management process in addition to regular monitoring activities. Operational staff showed a clear understanding of how and when to escalate risk. To ensure staff were equipped to manage risk effectively, as they had taken bespoke Prince2 training at post, as they found the centrally provided training was too generic.
A risk update is provided to the Programme Management Committee every month. Senior members of staff interviewed, including the SRO, clearly feel ownership of risk. Actively participating in the risk management is incorporated in to the objectives of the political team, reflecting the strong input they have on risk. This is excellent and an example of best practise that should be replicated across the Prosperity Fund. There was evidence of a variable level of input from the Programme Management Committee, depending on who attends and how much time is available. This annual review recommends that the Programme Management Committee consider if another format for considering risk would provide more space for engagement by PMC members. For example having a deep dive every quarter where all senior staff are required to attend.
The annual review recommends that the SRO is given full access to strand risk registers, in addition to the high level risks, every month with high priority risks highlighted to sure she has the ability to have a comprehensive oversight of the risks, and is regularly shown the high priority risks. This will ensure she has access to this information even when she is unable to attend the Programme Management Committee.
There was some evidence of effective support and feedback from PFDU/JFU when the programme teams communicate risk to the centre, however this isn’t consistent and often the team does not get feedback on risk. The programme would be strengthened from a more coherent and consistent approach to risk. One example of disruption is PFDU/JFU consistently adjusting the risk template, leading to a heavy administrative burden on the programme team and putting the focus on protocol procedures rather than excellent risk management. This annual review recommends that JFU/PFDU should avoid adjusting the risk template wherever possible, and if it must be adjusted, this should only be done once a year. This annual review recommends that JFU/PFDU develop more consistent feedback mechanisms on risk.
One area that the team could stretch in to is collaborating with other programmes of risk. This could include a) other Latin America Prosperity Fund programmes b) other Prosperity Fund programmes with the same suppliers c) other Prosperity Fund programmes with similar interventions. This annual review recommends that JFU/PFDU should play a larger role in facilitating collaborative working on risk across the Prosperity Fund. This annual review recommends that the Mexico Prosperity Fund programme team liaise with the Brazil and Colombian programmes to work collaboratively on risk and share learnings.
Governance boards are being set up across the programmes, and as well as having the internal facing Programme Management Committee, the Mexico Prosperity Fund Programme has set up a strategic advisory board made up of representatives of the Mexican Government. The strategic advisory board met for the first time in June, and is due to meet again in September. As this is such a new initiative it is not possible to comment on whether this is enough to ensure buy-in of the programme by the Mexican government, however the evidence points to the foundations being in place for this to be done effectively.
At the time of this review the risk management for the Mexico Prosperity Fund is going into its next phase, as suppliers take an active role in risk management. The programme team are proactively considering how to manage risk through this new arrangement. There were inconsistent points of views of how sensitive information should be managed in the risk registers in this new phase where they will be shared more widely. This annual review recommends that the programme team, in the context of having shared risk registers with suppliers, consider a standard process to manage sensitive information that should not be shared widely within the risks register, whilst making sure information can be shared as widely as needed.
The split of responsibilities for risk management going forward are that the implementer will be responsible for the active risk management, and the programme team will be overseeing this, and some of the programme team said they are still responsible for identifying risks as well. There was some ambiguity across the programme around what the programme team’s responsibilities were in this new phase. This annual review recommends that the programme team have clear responsibilities for risk management, and that they remain proactive in identifying and monitoring risks. This is because a) the implementers may not have sight of all of the risks the programme team does and b) there may be incentives for suppliers to avoid flagging certain risks (for example the risk of corruption within the supply chain).
## Summary
The Annual Review team lacked guidance on how to assess the overall risk rating of the Mexico PF, and suggest that further guidance is provided for future Annual Reviews. The team have suggested an overall risk scoring of ‘Moderate’, which reflects that the programme is being well-run at post, and risk is being increasingly well-managed - and recent learnings from post are the main focus of this Review.
There are external risks to the programme which are hard to mitigate for, including the changing political context. This is not uncommon in large development programmes run by the UK government, for example at DFID, which in general has a higher risk appetite for novel programmes or those in conflict contexts. However, given efforts to align with the Mexican’s government’s priorities, and promising results from some pilot projects, the AR team feel that much is being done to manage these external risks and future-proof the programme within Mexico.

## F: COMMERCIAL CONSIDERATIONS

The TORs for this Annual Review seek answers to the following questions:
1. Are there effective commercial management systems in place?
2. How do we compare to best practice on project management techniques?
  1. Are there sufficient mechanisms in place to maintain flexibility through an agile programming approach?
  2. Does the programme have effective and adequate resourcing in place?

## Key Findings
The PF team managed the commercial procurement process right through, from creating a focused statement of requirements, evaluating bids and negotiating contracts. Many interviewees noted the learning curve of the team and how they have performed well.
Commercial support was provided from the central teams in London throughout these processes, and the teams worked very well together. The Mexico team also benefited from having a colleague with specialist contract management expertise, who led workshops in-country. As a consequence of this and the team committing extra time and effort, the whole procurement process ran on time, which is unusual for large public procurements.
However, many also noted that although formal contract management training was requested by the Head of the Prosperity Fund at an early stage, it was not provided for over a year after this. Whilst the team upskilled quickly, many in the PF team did not know where their commercial gaps were initially, which affected their confidence. However, it was noted that the team supported each other and the programme strands shared knowledge and expertise across the PF at post very effectively and within the Virtual Team framework, and increased their confidence rapidly after training.
Are there effective commercial management systems in place?
The PF team has learned a lot over the last year and have shared knowledge well. The FCO commercial management system is evolving, and should in due course help evaluate providers more efficiently. However, the new system’s implementation has been delayed and the current system (Bravo) does not have sufficient functionality. This makes information sharing and record keeping inefficient, and puts the responsibility onto Post to keep adequate records when they are not commercial experts. The Annual Review team understands that support and IT support will be provided.
How does the Mexico PF compare to best practices on project management techniques?
The PF team is generally strong on project management. Many have relevant PM qualifications such as PRINCE 2. The team made improvements on some of the commercial and contract management guidance and tools presented to them, and tailored them to the Mexican context. There have also been improvements in financial management of the programme in terms of forecasting accuracy in the last three months, for example.
Are there sufficient mechanisms in place to maintain flexibility through an agile programming approach?
The agile programme funds allow for good opportunistic flexibility within the programme strands, and the inception period was specifically designed to build flexibility with focus into the logframes. There are now clear processes in place for managing contract variations and amendments, which are subject to the same scrutiny irrespective of which side proposes them. Through working with the supplier as a partner, the team built good relationships in many cases, which smoothed these negotiations. Again, contract knowledge and clear processes would benefit other PF teams in the future.
Does the programme have effective and adequate resourcing in place?
Commercial skills within the team are now quite strong. The four strand contracts started at around the same time, and lessons were shared across the whole team on problem resolution, as often similar problems arose. While this timing has been difficult to handle from a resourcing point of view, it has ultimately benefited the programme in terms of experience.
Contingency funding has been put in place during the tendering process, and to ensure the programme has the agility to flex to changing needs or develop new ideas over the next five years. The contingency must be used in line with requirements and processes outlined in the original business case, and within the procurement rules.
## Asset monitoring and control
An area of ambiguity now is the degree to which the programme team understands—and has guidance for understanding—what is being monitored, how and in what system. The programme team requires clarity on who is responsible for monitoring high value items and what constitutes a sufficient level of oversight (i.e., spot-check, visual confirmation, etc.). This Annual Review recommends that guidance be created to clarify asset monitoring & control, including a threshold and monitoring system that involves FCO personnel (items over £1000 monitored every X months, over £500 monitored every [frequency], 1 annual review?). This guidance would include clarity around what happens if a supplier is mishandling assets, which aligns with other guidance recommended within this Annual Review.
## Recommendations
At Fund level:
The Annual Review recommends that in future, greater and more timely commercial training and support is given to Post teams, particularly during critical early stages of SOR and bid development. Extra effort put in at SOR stage to ensure that tenders are focused, prioritised and well-structured, will save time later and make contract renegotiation less likely and time consuming. There is currently inconsistency of provision between Posts.

1. Consideration should also be given to the resource levels required within the central commercial team to manage PFs in many countries – a lead point of contact for each country would be more effective than one team member covering three countries in different time periods which are tendering at the same time.
2. The PF should seek to formalise commercial expertise sharing arrangements with DFID where possible, due to DFID’s greater experience than the FCO of managing large multi-year development programmes.

This Annual Review recommends that guidance be created to clarify asset monitoring & control, including a threshold and monitoring system that involves FCO personnel.

At Programme level:
1. The PF team should work with London to see if their respective financial processes could be more closely aligned and efficient.
2. The team should ensure, in line with the original business case and commercial colleagues, that the future process for allocating agile funding to new, small or rapidly developing projects is streamlined (especially when many pilots are running concurrently).
3. The PF team should use the end of the inception phase to ensure the current contracts in place are as robust and fit for purpose as possible, to avoid renegotiation of contracts during implementation as far as possible.

## G: Business Environment

This section considers Communications, Cohesion and Secondary Benefits.
## Communications
Questions from the Annual Review ToRs and template: Is the programme approach to strategic communications sufficient to ensure effective communication of programme activity and impact?  Is the programme designed to be sufficiently visible to target audiences in Mexico and the UK?
The programme has an overall Communication Strategy (using the OASIS model), updated annually and cleared with London.  This umbrella document defines three objectives: raising awareness of the programme, inception in the minds of Mexican stakeholders and building supplier communications capacity.  One B3 (L) officer leads on communications (together with governance), working directly with suppliers, via the Programme Team, and with the Embassy’s communications team.
This has resulted in much good work.  The programme has a set of useable products: one-pagers, core briefs, defensive lines.  It has also generated various communications vehicles including Governance Boards and regional visits.  The SRO highlighted ‘brand recognition’ of the PF as a strength in Mexico.  And it has run two well-received supplier workshops (with tailored advice in the interim) to help them understand better the concept of strategic communications.
The main challenge for the programme in future will be to achieve a ‘gear shift’ on its communications, moving from reactive/tactical communications to proactive/strategic communications which reflect the shift in delivery model to a supplier-based approach.  In other words, more day-to-day communications work will need to be done by suppliers; with the programme team focusing on strategic oversight, communications coherence across the Embassy, and sensitive communications to certain key stakeholders (principally seniors in both the UK and Mexican Governments).
The Annual Review recommends:
The PF Communication Strategy is refreshed to clarify roles/responsibilities between the suppliers and the Embassy, working on a principle of subsidiarity - that whatever can be devolved to suppliers, should be.

1. Suppliers’ Communication Strategies are scrutinised by strategic communications experts in the UK and Mexico to ensure they sufficiently link communications to policy efforts.
2. The programme team conduct an audit of internal communications channels (i.e. communication of impact to the rest of HMG: within the Embassy, across HMG and to Whitehall), given the SRO’s desire to provide greater reassurance to UK stakeholders.  With the aim of rationalising and modernising these communications channels (e.g. increasing the successful use of videos, reducing text/duplication).
3. Responsibility for communications and stakeholder engagement be merged or at least brought more closely together, given the overlap between these functions (and to allow audiences to be defined with more specificity).
4. Strategic communications capacity be increased in the PF team as a whole, either through an enlarged team or through an upgraded role which would mainstream strategic communications into the supplier networks and rest of the programme team.

## Cohesion
Questions from the Annual Review ToRs and template: Is there sufficient cohesion between programme strands and global PF programmes and wider Embassy work?
Overall there is strong cohesion between programme strands.  Key to this is regular communication between the four programme managers, and strong oversight by the Head of Prosperity Fund.  But additionally the programme team has created a number of vehicles to ensure cohesion as the programme develops: weekly meetings of programme managers, the PMC, supplier coordination meetings at Team Leader and Programme Director level, and thematic supplier groupings on cross-cutting issues (e.g. GESI, secondary benefits, communications, Agile Programming Fund).
There is strong cohesion with wider Embassy work.  This is provided top-down by the Ambassador, Prosperity Counsellor and Heads of Section; bottom-up by the Virtual Team model which brings together policy, programme and commercial officers and is praised by all interviewees (as reflected in Section 6 of the Evaluation); and across the Embassy via initiatives such as Regional Champions.  This has helped, for example, mesh together the nascent growing PF and ICF efforts on energy and future cities in particular.
The Annual Review recommends:
1. (as suggested in Section 6 of the Evaluation) The Embassy re-clarify the roles/responsibilities of VTs to ensure an appropriate split across Embassy teams.
2. The SRO consider the merits of broadening out PSAB (as the top-level programme governance advisory structure) to include other HMG programmes, to ensure broader coherence across Embassy programme work.
There is decent cohesion with Global PF programmes in Mexico.  The five main programmes (Skills, Health, Trade, Anti-Corruption and Infrastructure) are at earlier stages of development, enabling their designers and implementers to work around the bilateral PF programme to minimise duplication.  This is a time-intensive process requiring deep sector expertise, but in the case of three of the five programmes, extra PMs have been provided to support this work.
The Annual Review recommends:
1. The Agile Programming Fund be deployed to explore interventions which intersect between PF strands (whether bilateral or global), and if successful be built in to emerging or future PF programmes.
2. The Head of PF make the case for sufficient global programme staffing to ensure coherence: currently each bilateral strand is supported by two staff, but each global programme has between 0-1 staff.  This should be corrected (subject to VFM and parity considerations), to avoid non-PF teams absorbing the extra work or failing to ensure this coherence, and aligning to the staff expenditure considerations.
3. Global Programme leads in London visit Mexico at least 1-2 times a year to ensure oversight of their programme and effective communication.  This was picked up in section 6 of the Evaluation: ‘there is room to improve communications, particularly in the way that London-based global programmes communicate with the Mexico-based strands, and likely vice versa... global programme teams should also educate themselves as to the Embassy-based stakeholders and communicate appropriately and comprehensively’.

## Secondary Benefits
Questions from the Annual Review ToRs and template: Are there sufficient structures and plans in place to deliver secondary benefits?  How has the business community and business environment responded to the programme?  What role has non-ODA spending played in promoting programme objectives?  What engagement has there been with the private sector?  Are there barriers to the programme having a positive impact on the business environment?
The programme has a Secondary Benefits Action Plan (drafted Aug 2018), and has hired a C4 (L) (funded by non-ODA) to oversee implementation via PF and DIT teams (e.g. via a well-received Secondary benefits workshop for suppliers in June).  It also spent some £600k of non-ODA last year (£140k budget for this year).  And the VT model fully-incorporates and increasingly uses the skills/networks of the 45-strong DIT team to generate tactical commercial benefits.  It is notable that, at this stage, the Mexico programme is the only PF programme whose secondary benefit plan currently identifies all 6 of the secondary benefit types as defined by the London-led E&L programme.
The Evaluation (section 6.3) summarises its assessment by saying the programme ‘has good assets with which to achieve SBs, and has also put significant effort into planning and setting up delivery mechanisms’.  The Annual Review concurs and does not propose to repeat the rest of the (valid) analysis.  Indeed, it identifies ‘new’ examples of best practice such as the mainstreaming of secondary benefits considerations throughout inception phase (e.g. in discussions with suppliers over priority States within Mexico).  This is enough to give ‘reasonable confidence’ (in the words of one interviewee) that the programme will generate secondary benefits, over time and as the programme matures.
That said, this approach will likely not maximise the secondary benefits from the programme.
Thus, the Annual Review recommends:
1. The Secondary Benefits Action Plan is updated in line with new guidance and turned into a more useful strategic document which (a) sets out all different types of secondary benefit on offer including soft power; (b) has a more realistic assessment of secondary benefit potential and (c) defines clearly the respective roles & responsibilities of DIT, the programme team, PF suppliers and London.
2. Each strand improves its own secondary benefits strategy, which expands on the agreed strand logframes and utilises latest London guidance on secondary benefits (which, to date, has not matched guidance on GESI, ODA or MREL for substantiveness).  These strategies should crucially be scrutinised by, and use the skills/networks of, the new set of DIT Sector Specialists based in the UK.  This mirrors a key recommendation in the Evaluation.
3. Socialize the standard Secondary Benefits Definition.  Different definitions of secondary benefits are being used now (some include ‘strengthening the Rules-Based International System’ as one, others don’t).  A more restrictive definition focusing on exports/investments would allow easier calculation and be in line with early Ministerial steers on what is being sought; whereas a more relaxed definition including nebulous concepts such as RUBIES or soft power would capture some of the other ‘non-primary’ benefits generated by the PF.

The Secondary Benefits Advisor’s role be better integrated into PT structures.  He is currently under-used by the PF team, both compared to expectations of that role and to his counterparts in Latin America.  He should lead on taking forward the recommendations above; ensure regular (monthly) discussions between suppliers and DIT leads on tactical secondary benefits opportunities (which should in turn direct how to use the very small non-ODA budget); and adapt approaches which have worked in other parts of Latin America.

## H: MONITORING & EVALUATION

## Evidence and evaluation
Since the first outline business case (OBC) was submitted in June 2017, the team has adapted its designs and positioning to meet with changing realities. The evidence shows that the changes made to programme and strand designs were driven by three key factors: (i) a changing political environment; (ii) overly ambitious initial designs; and (iii) resourcing realities. The final business case (BC) approved by the FCO’s Infrastructure, Investment and Operations Committee (IIOC) in December 2018 is a portfolio of four distinct strands with cross-leveraging particularly around G&I.
## Monitoring progress throughout the review period
As the four strands near the conclusion of their respective implementation phases, there is general confidence that monitoring and evaluation systems are in place, but they have not fully consolidated nor have they yet been tested. There is a shared sense among the strand programme teams that once the logframes have been submitted, vetted and approved, that the final details of M&E, including data quality responsibilities, will be anchored into implementation work plans and reporting systems.

The Mexico programme will finalise its logframe after the strands have finalised theirs, with the respective impact statements becoming the programme's outcomes. The Mexico programme's impact remains unchanged: improved conditions for growth in Mexico, through increased capacity and an improved environment for trade and economic growth.

The four strand PMs are struggling with the compliance issues related to requiring the suppliers to include secondary benefits indicators and targets in the final logframe (see Section G of this Annual Review for further discussion).

The status of the four strands in terms of their progress to finalise logframes and ToCs at the time of this AR varies. For example, the Energy strand, which has a longer inception phase than the others, is the most advanced in finalising its logframe and ToCs. The strand has identified one indicator from the 15 PF primary indicators and one from the 3 global secondary benefits-related indicators.

The Financial Services strand has a good ToC, and is working to strengthen the causal pathway to support inclusive economic growth in its logframe. The supplier and the team have yet to select a global PF indicator, but will do prior to finalizing the logframe.

The Future Cities strand has a well-developed ToC, but in light of innovative ideas which emerged through the competitive process of receiving proposals from five candidate cities, there is a current discussion about revising the impact statement for the strand. The PM and the Head of PF in Mexico are weighing the costs and benefits of altering the impact statement.

The ACROL strand teams are still working to optimize the causal pathways to inclusive economic growth, as was recommended in the Cycle 1 evaluation. The PM is working with the supplier to ensure that at least one global PF indicator is included in the indicators, but at this time, no indicators have been finalised.

The strand PMs were introduced to data quality (DQ) methods in a joint MREL workshop in April 2019. Now that the logframes are nearing their final state, the PMs and suppliers are aware of the need to create data quality assessments (aka, birth certificates) for each indicator. The PMs are also aware that the MR Hub is available to assist them as they complete these initial DQ measures. Once approved, these data quality sheets will be entered into Prospero and comprise the underlying architecture of future M&E efforts by the strand PMs and the overall Mexico programme.