## Colombia Prosperity Fund Programme 2019/20 Annual Review

Montería, Colombia, 10 June 2019 – female fish farmers learn how to produce export grade tilapia using sustainable innovations from the UK. The improved production techniques increase yields and quality guaranteeing better market prices and higher incomes. Similar training, with a focus on women’s economic empowerment, was given to the beneficiaries of all seven Colombia Prosperity Fund Agri-Tech Projects.

Title: Unlocking Economic Opportunities in Colombia’s Post-Conflict and Conflict-Affected Regions
Programme Value: £25.5m		Review Date: 20 November 2019
Programme Code: / GB-GOV-50-PF-03-COB (including GB-GOV-3-PF-COB-911; GB-GOV-3-PF-COB-912; GB-GOV-3-PF-COB-913; GB-GOV-3-PF-COB-921; GB-GOV-3-PF-COB-924; GB-GOV-3-PF-COB-925; GB-GOV-50-PF-03-COB)	Start Date: / November 2017	End Date: / March 2022

Summary of Programme Performance
Year	2018	2019
Programme Score	A	A
Risk Rating	Moderate	Moderate

Summary of progress and lessons learnt since last review
- In the first half of the second year of the Programme, a total of 12 new feasibility study tenders, worth almost £11m (43% of total programme budget), went out to market bringing the total to 14 projects up and running in the regional competitiveness, rail, urban development, National Infrastructure Agency (ANI) reform and agriculture-insurance activities.
- Last year, the PF Team and Implementing partners (IPs) agreed it would be more impactful to move from up to 50 small projects each with low numbers of beneficiaries to about a dozen large projects with hundreds of thousands of beneficiaries each. From the first batch of ten urban development, regional competitiveness and rail projects, anticipated beneficiaries are over 13 million, should all the projects move successfully from design to execution phase. There are another anticipated half a million from the seven Agri Tech Catalyst projects. This is substantially higher than the original estimate of 3 million beneficiaries recorded in the Colombia PF Programme Business Case (BC).
- Regional elections held in October 2019 introduced a whole new set of mayors and governors for the Colombia PF Programme; we met half of the new administrators of our eight focus cities and eight target departments in November and immediately began planning with them implementation of existing and future PF investments.
- Working with our partner Findeter, we trained 168 new Colombian mayors and governors on the design of inclusive municipal and departmental economic and social development plans and on inclusive infrastructure project design and implementation, with the support of an ex-DFID Social Development Adviser funded by the Work and Opportunities for Women (WoW) facility. There is tremendous appetite and opportunity for the PF to follow up this work over next year and deepen the Programme’s gender and inclusion (G&I) impact around the country.
- As a result of the new National Development Plan (NDP) that the Government issued in November 2018, we amended our rail development activity to align with the revised transport development priorities. This required adding the Financial Institution for National Development (FDN) as an additional implementing partner. The Embassy signed a new MoU with the Head of FDN in August 2019.
- As demonstrated in several public announcements, the Colombian government recognises the UK as partner of choice on rail development and agri-insurance directly, thanks to progress made by the PF Programme. Increasingly, the UK is also seen as a key ally in infrastructure design and financing, agri-tech and open procurement.
- As a result of the first infrastructure tenders developed by Findeter, we have changed working procedures in a number of key areas: i) PF Commercial Framework companies are developing direct relationships with our implementing partners to address concerns arising from early draft versions of ToRs; ii) a two-stage market survey process ensures that the value of each PF project is aligned with market expectations and accurately reflects the scope of work; and iii) quarterly payments in advance to banks are now based on approval of the final version of project ToRs, an agreed contract value, and a definite date for tender launch.
- A slowdown in performance, first by Findeter and then by CAF, required a revision of timelines for outputs and then, when that did not work, escalation of our concerns to the Country Director of both development banks. This resulted in changes of staff and/or procedures that sped up progress and brought the Programme back to its planned implementation timelines.
- The seven Agri Tech Catalyst projects are ahead of all our other investments. They have put in place gender and inclusion action plans and are actively trialling their new technologies with mostly female farmers. It looks like the first Colombia PF Programme impact on inclusive economic growth, specifically benefitting women and girls, will come for this activity. In addition, these projects are offering early signs of secondary benefits, opening new economic opportunities for international business and mutually economic relationships between Colombia and the UK.
- In June 2019, the Department of Cundinamarca provided co-funding to the PF of £1.6m (of a total of £4m) for the Bogota to Zipaquira rail rehabilitation project. This is a landmark contribution to a UK ODA project in Colombia and is indicative of the positive working relationships that the Embassy has built up with our Colombian government counterparts.
- The bilateral PF Programme continues to have good synergies with the Global Infrastructure, Trade and Anti-Corruption Programmes. For example, the tools of the GIP are being integrated into the bilateral AeroCafe airport design and La Dorada to Chiriguana rail rehabilitation projects. Similarly, the PF works closely with other Embassy teams and programmes. Work is underway to link PF projects with the ICF SIP and PACT initiatives and the Newton Fund in Colombia.
- The Colombia PF Programme was the first to have a climate and environment audit following a recommendation by the JFU Director in January 2019. The audit was conducted in September with the draft report issuing in October. The 11 recommendations in the report include: i) integration of Climate Change linked objectives into the Programme; ii) development of a more explicit climate benefits success narrative; and iii) a more detailed understanding of the long-term impacts of Programme interventions. Support from a Climate and Environment Adviser is required to prioritise and implement the recommendations.
List of recommendations for the next year
1. Working closely with a Climate and Environment Adviser, the Colombia PF Programme should prioritise and implement the 11 Colombia PF Climate and Environment Audit Report recommendations.
2. The PF Team should consider additional support to Findeter and CAF (perhaps through a short-term consultancy assignment) to develop proposal(s) for the Green Climate Fund (GCF). For example, a possible proposal could seek to aggregate several WASH projects from a range of secondary cities, building on those in Valledupar and Ibague. By aggregating relatively small urban resilience projects into a single proposal, the BE team would be well placed to unlock GCF concessional finance.
3. Nature Based Solutions (NBS) is an area that the PF Team could explore with regard to both future funding proposals (for the Green Climate Fund) and with regards to the needs/requests of their city government clients. Two cities, Montería and Valledupar, are seeking to plant trees (a simple form of NBS) at 10-meter intervals along the future sidewalks of their entire new arterial road networks. NBS are important measures for reducing the impact of urban flooding, one of the key constraints facing many secondary cities in Colombia.
4. As part of the preparations for COP 26 in 2020, HMG is engaging with the C40 Cities Climate Leadership Group, a global city network dedicated to tackling climate change. Bogota and Medellin are already C40 members. The PF Team should explore whether the cities of Cartagena and Cali or others are willing to join the C40 and commit to developing Paris Agreement compatible climate action plans. Given the nature of the work that the PF Team is delivering this could be a relatively quick policy win.
5. Once the pilot phase of the Agri Tech innovations has been completed, the seven projects will need to rapidly prioritise scalability and sustainability to achieve primary and secondary benefit targets. The PF Team to look at crowd-in funding to provide Agri Tech projects with longer term sustainability if necessary. The Global Innovation Fund, for example, supports successful tech projects which are scalable.
6. For agri-insurance activity, CAF to ensure that it is ready to measure i) number of producers trained; and ii) number of training sessions provided that include G&I modules, starting in 2020/21.
7. The PF Team should ensure that lesson learning from the PF Centre for Global Disaster Protection Programme, specifically on its insurance work, is incorporated into the Colombia agri-insurance activity.
8. In addition to the regular activity budgets, the PF Team will need to ensure that non-ODA resources are targeted as appropriate to supporting the formation of UK-Colombia partnerships as per the secondary indicator in Output 2.
9. Five of the seven Colombia PF Programme activities will need to have adequate resources and approaches in place to measure the benefits of UK-led innovations.
10. There is strong demand from newly elected mayors and governors for support with preparing the G&I chapters in their development plans and, possibly going beyond that, to support the implementation of their G&I policies and programmes. Working with IPs, the PF Team will need to establish an open and transparent process for selecting and supporting a small number of additional municipalities and departments, beyond those already included in the Programme.
11. OCP to plan and deliver separate G&I sessions during its technical training courses on the International Open Procurement Standards in the departments.
12. When SECOP II is ready for rollout to the departments, the PF Team should work with OCP and CCE to ensure the 8 PF departments are prioritised. Prepare lessons learned from the first pilots to ensure second set of departments benefit from those.
13. The PF Team should continue to support Colombia’s membership of the Construction Sector Transparency Initiative (CoST) and offer to support the CoST application to PF projects such as AeroCafe and the two railway lines.
14. About three months prior to the next Annual Review in November 2020, it would be prudent to review and update the cost benefit analysis calculations and VfM for each Colombia PF Programme activity given the number of anticipated beneficiaries looks like it will change from the original figure of 3 million recorded in the Business Case. This information should be shared with JFU and the FCO Economics Unit.
15. The PF Team should work with the implementing partners (Findeter and CAF) to map out and agree on realistic assumptions for the rail and urban projects regarding the: length of time required for each phase in the project cycle; and costs for each phase of the project cycle, particularly those with higher budgets. This could be aided by having a common visual schematic of the project cycle and building it into the risk register for the programme. Having a shared understanding of the project cycle is crucial for the PF Team to achieve the relevant logframe target under output 4 – “number of urban, rail and regional competitiveness projects designed, structured and ready for investment”.
16. The Manizales Intelligent Transport project will be identifying data on journey times, incomes, job locations, etc. and the contractor should use this information to spot priority areas for improved reliability which can be the determinant of public transport use that cost or speed.
17. The PF Team should explore how they can work with UK organisations (Arup, Argent, TfL, etc.) to develop a transit-oriented development (TOD) approach that is bespoke to Bogota, drawing on case studies from other cities, the World Bank’s 3V methodology and CAF’s expertise. Codifying that TOD approach could be a task supported by the Global Infrastructure Programme team who may be able to subsequently roll it out as a HMG methodology.
18. The PF Team should seek to engage Transport for London’s Commercial team to determine whether there is scope to engage them as a strategic adviser for the rail and urban mobility projects. TfL may be well placed to provide advisory support to the City of Bogota, building an institutional partnership that would demonstrate the impact of UK expertise on integrated transport planning for a major city in the Global South.
19. Findeter should provide evidence of impact with regard to ‘control centres’ that they have implemented in other secondary cities. The draft ToR sets out the need for an integrated control and operations centre (CICO) in Santa Marta but the scope and objectives of the CICO is unclear. The purpose and objectives of the CICO should focus on the tools and technology that will be used for one specific sector (e.g. mobility management), possibly two at most. In parallel, the BE team should encourage Findeter to explore global initiatives that are seeking to use data/technology to improve urban planning including the World Bank’s Municipal Spatial Data Infrastructure, which has been applied in Bogota and Cali and the Bank’s City Planning Labs initiative.
20. The PF Team should consider developing a proposal for funding to the Global Challenges Research Fund (GCRF), possibly in collaboration with UCL and New York University. The proposal could build on global research initiatives and tools that are relevant to the aims of the programme, specifically the Urban KNOW[1] and NYU’s Urban Expansion Initiative[2].
  [1] Urban KNOW is a four year £7m GCRF funded project led by UCL – a UK institution that has already collaborated on urban research projects with Universidad Nacional de Colombia.
  [2] Which provides technical assistance to the cities of Valledupar and Monteria and has produced a database (a valuable global public good) on urban growth in Colombian cities.
21. The PF Team, working with the JFU Economist, more systematically analyses cost-drivers across the seven projects to identify appropriate mitigating measures.
22. When reporting Colombia PF Programme budget figures, the PF Team to use past financial year numbers combined with forecasts for the year in which the AR is taking place.
23. The PF Team to monitor and control risks which could damage the Programme’s value for money (VfM) position.
24. The PF Team to investigate whether international companies are more efficient and effective at delivering high quality feasibility studies than local companies, by reviewing and evaluating the data collected from the first set of rail, urban development, regional competitiveness and agri-insurance projects. This information to be used to decide routes to market for future PF Colombia projects.
25. The PF Team to work with implementing partners (IPs) to complete the remaining baselines, milestones and targets in the Programme-level logframe before the next Annual Review in November 2020.

SRO Commentary
I have reviewed the 2019/20 Colombia PF Programme Annual Review (AR) and fully agree with its findings. The positive scores for each output and for the overall Programme reflect the intense effort and substantial progress made by the PF Team, implementing partners (IPs) and government stakeholders. We have a unique moment in time when the PF is closely aligned to the Colombian government’s priorities as outlined in the National Development Plan (NDP). In our dialogue with senior Colombian government representatives we are constantly demonstrating the relevance of much-needed PF solutions to Colombia’s economic development challenges. Of particular note is the growing impact the Programme is having on gender and inclusion and our partners’ commitment to strengthen policies and programmes in these areas as a result. As SRO, I commit to working proactively with the rest of the PF Team to deliver results on the 25 recommendations made in this AR.

JFU Commentary
The Joints Fund Unit (JFU) notes the good progress the Colombia Programme has made over the last year and agrees with the review scoring and risk rating. It is pleasing to see that targets have been met and in some cases exceeded. With these positive results it is worth exploring whether more ambitious targets can be set for the year ahead. I would also encourage that follow-up interviews and evaluations are conducted on training to ensure it has been effective.

The PF Team has so far reacted well to managing delivery partners and has a clear plan in place to improve climate and environmental impact assessments. Infrastructure programmes delivered through third parties come with significant Environmental, Social and Governance (ESG) risks, and I would encourage the PF Team to continue to ensure its partners approach this holistically in order to adhere to international standards.

List of Acronyms
AGROSAVIA – Colombian Agricultural Research Agency
ANI – National Infrastructure Agency
BC – Business Case
BE Bogota – British Embassy, Bogota, Colombia
CAF – Latin America Development Bank
CCE – Colombia Compra Eficiente (Colombia’s National Procurement Agency)
CIAT – International Center for Tropical Agriculture
Confecameras – Colombian National Federation of Chambers of Commerce
COP – Colombian Peso
CoST – Construction Sector Transparency Initiative
CSSF – Conflict, Stability and Security Fund
DD – Due Diligence
DFID – Department for International Development
DIT – Department for International Trade
DNP – National Planning Department
FCO - Foreign and Commonwealth Office
FDN – Colombian Financial Institution for National Development
Finagro – Colombian Agricultural Development Bank
Findeter – Colombian Financial Institution for Development of the Regions
G&I – Gender and Inclusion
GACP – Prosperity Fund Global Anti-Corruption Programme
GESI – Gender Equality and Social Inclusion
GHG – Greenhouse Gases
GIP – Prosperity Fund Global Infrastructure Programme
GTP – Prosperity Fund Global Trade Programme
HMG – Her Majesty’s Government
IADB – Inter-American Development Bank
ICF – International Climate Finance
IDEAM – Colombian Institute for Hydrology, Meteorology and Environmental Studies
IOPS – International Open Procurement Standards
IPA – Infrastructure and Projects Authority
IUK – Innovate UK
JFU – Joint Funds Unit
KPIs – Key Performance Indicators
L&D- Learning and Development
MoU – Memorandum of Understanding
MREL – Monitoring, Reporting, Evaluation, Learning
NDCs – Nationally Determined Contributions
NDP – National Development Plan
ODA – Official Development Assistance
OCP- Open Contracting Partnership
PACT – Partnering for Accelerating Climate Transitions
PEA – Political Economic Analysis
PF – Prosperity Fund
PFDU – Prosperity Fund Delivery Unit
PPP – Public Private Partnership
RCC – Regional Competitiveness Commission
SECOP II – The Second version of Colombia’s on-line State System for Public Procurement
SIGRA – Risk Information System for the Agriculture Sector
SIP – Sustainable Infrastructure Programme
SRO – Senior Responsible Officer
STEM – Science, Technology, Engineering and Mathematics
ToC – Theory of Change
ToRs – Terms of Reference
UKEF – United Kingdom Export Finance
UPRA – Colombian Unit for Rural Agricultural Planning
VfM – Value for Money
WEE – Women’s Economic Empowerment
WoW – Work and Opportunities for Women Initiative

## A. INTRODUCTION AND CONTEXT
The Colombian PF Programme aims to support economic development, unlock economic opportunities and drive growth in Colombia’s post-conflict and conflict-affected regions. The Programme will benefit about 3 million people with a focus on women and girls in Colombia’s poorest regions and result in up to £1.99bn of primary benefits to Colombia over 10 years. The potential secondary benefits, set within the context of a peaceful, prosperous Colombia, are considerable. The estimated benefits to the UK alone are around £265mn by 2026.
The Programme targets seven activities within the three sectors of institutional strengthening; infrastructure; and agriculture:
Institutional Strengthening
1. Regional competiveness: strengthen economic development in Colombia’s regions by improving their competitiveness. Build government capacity in up to 8 regions; deliver up to 24 competitiveness projects and train up to 200 officials in project development and management.
2. Open, public procurement: more transparent public procurement in Colombia’s regions. Build government capacity to implement the International Open Procurement Standards in up to 8 regions and train up to 200 officials in open procurement and its effective implementation.
3. Corporate governance reform of Colombia’s National Infrastructure Agency (ANI): improve ANI’s corporate governance standards in line with UK best practice. Design a new corporate governance model for ANI and pilot it over one year with an evaluation afterwards.
Infrastructure
1. Urban development: strengthen SMART urban development in Colombia’s second tier cities. Build government capacity to implement existing urban master plans in up to 10 cities; deliver up to 30 urban development projects; and train up to 150 officials on SMART urban development.
2. Rail development: support the rehabilitation of Colombia’s narrow gauge rail network. Complete Colombia’s National Rail Master Plan and develop the regulatory framework; complete up to four feasibility studies and structure at least two of them for market.
Agriculture
1. Agri-insurance: develop and roll out agri-insurance to Colombia’s smallholders and agricultural micro and small enterprises (MSEs). Create and implement a new IT based Risk Information System (SIGRA); design and market agri-insurance products and services in three pilot projects.
2. Agri-Tech Catalyst Challenge Fund: increase productivity and incomes for Colombia’s smallholders and agricultural MSEs through adoption of agri-innovations and technologies from the UK. Through a competitive bidding process, fund up to 10 agri-innovation projects, which either pilot new innovations and technologies or develop the Colombian market for existing ones.
Project Identification
All PF projects are identified and selected through a similar process. Local authorities are requested to prepare a short-list that meets the PF criteria (a one page handout explaining these criteria is provided). IPs and PF Team members then conduct a workshop with those authorities to prioritise the first project. Site visits, with opportunities to speak to potential beneficiaries, are also carried out. Once, by consensus, the first project is agreed, the local authority is requested to complete a basic proposal (known as ficha in Spanish) covering points such as project description, primary beneficiaries, integration of innovation and new technologies from the UK, and cost. IPs and PF Team review the ficha and request amendments. If all is agreed, the IP technical team then develops a full detailed proposal and ToRs for the project to go to market. These documents are reviewed and approved by both the PF Team and the local authority.
Implementing Partners
Following an early market engagement event in October 2016, the Latin American Development Bank (CAF) was selected to implement the Regional Competitiveness, ANI Reform and Agri-Insurance activities while Colombia’s Financial Institution for the Development of the Regions (Findeter) was chosen to manage the Open Procurement, Rail and Urban Development activities. The Open Contracting Partnership (OCP) is helping Findeter manage the Open Procurement activity. Innovate UK was identified as the best partner for implementing the Agri-Tech Catalyst Challenge Fund with support from the International Centre for Tropical Agriculture (CIAT). The three main partners operate under MoUs with the PF while OCP and CIAT have grant agreements.
New Colombia PF Implementing Partner - FDN
Colombia’s 2018 to 2022 National Development Plan (NDP) came out in November 2018. It prioritised three specific rail projects in the transport section and the Financial Institution for National Development (FDN) as the main implementer of these projects. As these were different to the ones previously agreed between the PF and Findeter, the PF Team commenced a period of consultation focusing on government and then partly redesigned the rail development activity. To accommodate the redesign, it was also necessary to add FDN as a new fourth implementing partner. The MoU with FDN was signed in August 2019 and the first rail project, La Dorada-Chiriguana, is scheduled to go to market in November 2019.
Selection of Cities and Regions
For the Regional Competitiveness and Open Procurement activities it was necessary to select eight of Colombia’s 32 departments to include in the Programme. Similarly, for the Urban Development activity, a selection of up to ten intermediate / second tier cities was required. BE Bogota contracted Ernst and Young through an open competition to research which cities and regions would make the best partners based on an agreed set of criteria which included, among others: potential for primary and secondary benefits; track record on economic development and fighting corruption; commitment to working with the UK Government; and historical links with the BE Bogota.
Colombia held municipal and departmental elections on 27 October 2019 and a new raft of mayors and governors will enter office in January 2020. The PF Team has met most of the new leaders in areas with existing or planned Programme investments, and steps are already underway to fast track the next set of PF projects. The election of new majors mean that the Programme can now advance in Cartagena and Villavicencio and that the cities of Bucaramanga and Buenaventura will also be added from January 2020 onwards.
Primary and Secondary Benefits
The Colombia PF Programme supports projects and initiatives that reduce poverty and gender inequality through inclusive economic development. Colombia PF Programme projects such as: water and sanitation for communities displaced by Colombia’s conflict; improved public transport for vulnerable populations; and agri-innovations that increase quality, productivity and incomes for smallholders especially women; demonstrate the potential primary benefits.
Colombia’s 2018 to 2022 National Development Plan has a gender chapter, which the PF Programme will help to implement. It says: ‘The evidence shows that Colombian women are disadvantaged in almost all social and productive activities….Our goal is to reduce inequality to a minimum through policies that empower women economically, politically, physically and through education.’
The Colombia PF Programme has taken a number of steps to strengthen its gender and inclusion (G&I) focus. In August 2017, a senior social development expert revised the Business Case and MoUs with implementing partners to ensure they contained the right policies and practices reflecting global lessons learned and the UK’s International Development (Gender Equality) Act of 2014. The following month, the same expert helped the PF Team and implementing partners devise a G&I Strategy for the Programme that included capacity building for public and private sector stakeholders. The expert returned to Colombia in May 2018 to assist implementing partners the design of G&I Action Plans, which articulate a clear set of commitments to ensure each activity has maximum impact on target beneficiaries. Each of the Agri Tech Catalyst projects prepared G&I Action Plans proportionate to their budgets and timeframes. This was followed in the second quarter of 2019 by G&I workshops with the beneficiaries of each of the Agri Tech projects.

To support increased commercial links between the UK and Colombia, contracts to design projects for the Regional Competitiveness, ANI Reform, Rail and Urban Development and Agri-Insurance activities will be awarded to companies listed in the PF Commercial Framework. CAF and Findeter will manage the procurement processes for the design contracts (usually feasibility studies).
The main secondary benefits from the Colombian PF Programme will be realised when international businesses, including UK companies, win the contracts to construct and / or manage the projects resulting from the design / feasibility phase.
In the case of the Agri-Tech Catalyst Challenge Fund, UK groups will transfer knowledge and technology to their Colombian partners through pilot projects. If successful, the pilot initiatives could expand, be replicated and lead to future export wins. For the Open Procurement activity, the secondary benefits are more transparent public contracts being awarded to international businesses including UK companies at the sub-national level in Colombia.
Programme Implementation
Programme implementation began on 1 April 2018. At the time of the first AR mission (week of 22 October 2018), the Programme had been running for just over 6 months. At the time of the second AR mission (week of 30 September 2019), the Programme had been operational for 1.5 years. During the past year, several issues contributed to delays in Programme implementation, but in each case a solution was found:

Reason for Delay	Solution
Substantial complaints from PF Commercial Framework companies about project ToRs drafted by Findeter	The PF Team logged each complaint and then addressed them one by one with Findeter; this process took around 6 months to complete; now, before each tender goes to market, an early market engagement event is held with Findeter and/or CAF to thoroughly review the scope of each PF project and to identify and address any residual contractual issues; while complaints still arise, the new system has eliminated the worst of these
Project values (i.e. the value of the contract to undertake the technical, financial, social and legal parts of each feasibility study) was often too low and two sanitation projects (Ibague and Valledupar) received no bids as a result	The PF Team worked with Findeter, and then later with CAF, to develop a comprehensive market survey process to ensure PF Commercial Framework companies fully understood the scope of each project before recommending an accurate project value; the new system is working well
Slow project development progress with Findeter	The SRO and the Programme Director visited the CEO of Findeter in December 2018 and then again in February 2019 to push for greater progress; New delivery-focused staff started in April 2019 and the rate of progress has sped up dramatically
Heavy internal bureaucratic processes at CAF (identified as a challenge in the 2018 AR) also resulted in slow project development progress	The PF Team requested timelines for all CAF PF investments; when these were not met, the SRO and Programme Director met with the CAF Country Director in June 2019 to push for greater progress; new timelines were agreed, but CAF was unable to meet most of those; a second meeting with the CAF Director was held in August 2019; since then, CAF has turned around 6 PF projects with another 2 planned before end November 2019

Despite these delays, the Colombia PF Programme is still on track to meet most of its second year milestones (see Section C). The challenges described above were effectively addressed through improved supplier management and the resulting strengthened relations with our implementing partners bodes well for the duration of the Programme.
Monitoring and Evaluation
The Colombia PF Programme Business Case included an overall Theory of Change (ToC), indicative logframe and risk matrix. With support from the Monitoring, Reporting, Evaluation and Learning (MREL) team first visit to Colombia in February 2018, the PF Team and implementing partners CAF and Findeter finalise nested ToCs, logframes and risk matrices for six of the seven activities. The MREL team later worked separately with Innovate UK in London to do the same for the Agri-Tech Catalyst activity. As a result, all of the seven activities have nested TOC, logframes and risk matrices that are being updated quarterly and submitted to the PF team as an annex to their quarterly and annual reports.
The MREL team delivered a second visit to Colombia on the middle of August 2018 to draft the umbrella logframe. Later, BE Bogota and the MREL Team agreed to apply seven Key Performance Indicators (KPIs) also being measured in the wider global PF portfolio. These cover: infrastructure, transport, jobs, foreign direct investment (inwards and outwards), export opportunities and export wins. Finally, a draft Evaluation and Learning (EL) Approach Paper was submitted to BE Bogota in November 2018.
In February 2019, the MREL team returned to Colombia to work with the PF Team and implementing partners to review the nested logframes and to finalise the umbrella logframe. This was followed by a series of exchanges to verify residual details. Review of all the logframes was completed in early August 2019. The final version of the EL Cycle 1 Evaluation Report was signed off in October 2019. It was very positive overall and made four specific recommendations for the Programme to pursue over the next year:
1. The evaluation recommends the inclusion of intermediary logframe indicators for partners to achieve before the next Cycle Evaluation and Annual Review, as well as a supporting narrative that clearly outlines the logic behind each pathway of change and formalises assumptions.
2. G&I-related capacity in many of the implementing partner organisations is still nascent, with ongoing questions around gender dimensions, objectives and resulting projects activities to address gender concerns. Continuous capacity-building and support to implementing organisations is needed to enable plans to come to fruition.
3. The Colombia PF Team’s culture of learning and sharing lessons should extend to the wider PF, and particularly with relevant global programmes, as well as the other two Latin American PF programmes in Mexico and Brazil.
4. The Colombia PT has robust processes in place to track and measure change across the programme, although this report encourages further development and roll-out of high quality, user-friendly and sustainable MREL.
New Umbrella Logframe
For the first AR, progress was measured against the main output in the nested logframe of all seven activities. Now that the umbrella logframe has been agreed, this AR is measuring progress against the main four outputs which aggregate indicators and milestones from the seven nested logframes. For example, whereas last year agri-insurance and Agri-Tech Catalyst had their own detailed output scoring, this year the two activities have been merged together and scored on their joint results.
Programme Governance Structures
In addition to the weekly PF Team meetings and monthly meetings with the Ambassador (as Senior Responsible Officer), the Colombia PF Programme has three main governance structures that between them measure progress against primary and secondary objectives, review spend, evaluate risk and recommend improvements. These are the Internal Programme Review Group (IPRG), the Private Sector Advisory Panel (PSAP) and the Stakeholder Group (SG). The IPRG is composed of representatives from the UK’s Joints Funds Unit (JFU) and the Prosperity Fund Delivery Unit (PFDU) of the Foreign and Commonwealth Office (FCO). The PSAP is made of British businesses with a presence in Colombia, especially the ten companies of the PF Commercial Framework. The SG comprises the three implementing agencies (Findeter, CAF and Innovate UK) and representatives of the Colombian government at the central, departmental and municipal levels. All three groups were meeting twice a year, but due to the frequency of local additional meetings on project progress and during official visits from London PF staff, the PSAP and SG changed their timings to just once a year.
In addition, the Colombia PF Team meets every six months with its counterparts in Brazil, Mexico and London at the Americas PF Regional Conference to harmonise policies and practices at the regional level and to share lessons learned.
Joint Working
The Colombia PF Programme coordinates closely with other UK government funds operating in Colombia, such as the PF Global Infrastructure Programme (GIP), the PF Global Trade Programme (GTP), the PF Global Anti-Corruption Programme (GACP); the International Climate Finance (ICF) especially on the Sustainable Infrastructure Programme (SIP), the Partnering for Accelerating Climate Transitions (PACT) Programme; the Conflict, Stability and Security Fund (CSSF), the Newton-Caldas Fund for research and innovation and the UK’s Chevening Scholarship Programme. Within the Embassy, we hold fortnightly Economic Horizons (EcHo) coordination meetings between all the programmes and DIT, to share lesson learning and to enhance collective progress and impact on the UK’s development objectives for Colombia.
Below is a Recommendation from last year’s AR on better joint working with CSSF and the corresponding Action Taken.
Prosperity Team Recommendations
Recommendation	Action taken
As the Programme becomes more established, BE Bogota should explore opportunities for further joined up programming between the Conflict, Stability and Security Fund and the Prosperity Fund in post-conflict areas, based on the regional development plans (PDTs in Spanish) of the selected departments.	Following a recommendation from Joelle Jenny; the Colombia PF Programme undertook a climate and environmental audit in September 2019, linked to CSSF and ICF. Once recommendations become available to the PF; a sit down with the three teams will be required to take actions forward. / Many of the Agri-tech projects and Agro insurance products and services will benefit CSSF target communities. We will ensure PF and CSSF work together to maximise impact of PF projects to conflict affected populations. / PF team trained 13 colleagues from the wider BE Colombia in Market System Development. Capitalising on learning from a DFID course, the PF Colombia Agriculture Adviser taught participants about how to support the transformation of markets into inclusive economic systems that accelerate pro-poor growth. This methodology will help other Embassy funds, such as Newton, ICF, PACT and CSSF, better integrate poverty-reduction into their programmes, as well as ensure the sustainability of their projects. / PF arranged for a contracts expert to conduct a two-day training in BE Bogota in which three CSSF staff members participated.

Climate and Environment Audit of Colombia PF Programme
The JFU Director visited Colombia in January 2019 to see first-hand progress of the PF and CSSF Programmes. She had two main recommendations: i) that the Programmes should strengthen their G&I focus; and ii) that they should do more to support UK climate and environment priorities. For the latter, the PF Team organised for Dr Rob Daniel, Senior Policy Adviser, Cross Whitehall Funds, to conduct a climate and environment audit of both Programmes. His mission took place 2-6 September 2019, and the report which followed highlighted these recommendations:
- Take steps to integrate Climate Change linked objectives into the causal pathways of the relevant theories of change, developing associated key performance indicators (KPIs) and success criteria.
- Develop a more explicit climate benefits success narrative, especially for the agriculture projects.
- The programme should be more explicitly brought under the umbrella of the UK Colombia Partnership for Sustainable Growth (the name of the UK Colombia government to government umbrella partnership on all climate and environment activities).
- Develop a more detailed understanding the of the of the long term impacts of programme interventions, including unintended consequences, and their support towards the goal of a long term sustainable and Net Zero Colombian economy.
- Make direct linkages between the impacts of the programme and the effects on the Colombia’s Nationally Determined Contributions (NDCs).
- Develop a targeted risk management programme for the Aerocafe Airport project.
- Develop a Scope 1 greenhouse gas (GHG) footprinting programme to support project activity specific GHG disclosure and management.
- Develop a clear scope 3 GHG framework to encourage the development of lowest carbon solutions.
- Review the Rio marker classification of the programme.
- Develop a specific climate change risk register.
- Use the framework of this report to continuously assess the climate sensitivity of the programme.
In addition to the 11 recommendations above, the DFID Cities Adviser, who was one of the two Colombia PF Programme AR external evaluators, made three more climate and environment-related recommendations (see points 2 to 4 below).
Recommendations
1. Working closely with a Climate and Environment Adviser, the Colombia PF Programme should prioritise and implement the 11 Colombia PF Climate and Environment Audit Report recommendations.
2. The PF Team should consider additional support to Findeter and CAF (perhaps through a short-term consultancy assignment) to develop proposal(s) for the Green Climate Fund (GCF). For example, a possible proposal could seek to aggregate several WASH projects from a range of secondary cities, building on those in Valledupar and Ibague. By aggregating relatively small urban resilience projects into a single proposal, the BE team would be well placed to unlock GCF concessional finance.
3. Nature Based Solutions (NBS) is an area that the PF Team could explore with regard to both future funding proposals (for the Green Climate Fund) and with regards to the needs/requests of their city government clients. Two cities, Montería and Valledupar, are seeking to plant trees (a simple form of NBS) at 10-meter intervals along the future sidewalks of their entire new arterial road networks. NBS are important measures for reducing the impact of urban flooding, one of the key constraints facing many secondary cities in Colombia.
4. As part of the preparations for COP 26 in 2020, HMG is engaging with the C40, a global city network dedicated to tackling climate change. Bogota and Medellin are already C40 members. The PF Team should explore whether the cities of Cartagena and Cali or others are willing to join the C40 and commit to developing Paris Agreement compatible climate action plans. Given the nature of the work that the PF Team is delivering this could be a relatively quick policy win.
DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-GOV-50-PF-03-COB/documents
DevTracker Link to Log frame:	N/A

The map below provides a complete list of all the current PF Colombia projects and their value by activity

## B: PERFORMANCE AND CONCLUSIONS
Annual outcome assessment (Primary Purpose)
The seven Agri Tech Catalyst projects are the only Colombia PF Programme activity advanced enough to impact on the targeted beneficiaries. To date, 28 rural communities have received a mixture of technical training and gender and inclusion support. In terms of numbers, that is 224 women and 217 men who received technical training and 189 women and 127 men who had capacity building on gender and inclusion. As the urban development, rail and regional competitiveness projects move from design to execution phase, the number of primary beneficiaries will rise exponentially, but that will be from 2021 onwards. The same is true for the remaining three activities, open procurement, corporate governance reform of ANI, and agri-insurance.
As Output 1 of the Colombia PF Programme umbrella logframe focuses on the increased technical capacity of producers, the two indicators could only be measured against the Agri Tech Catalyst activity. Output 2, which has three indicators related to piloting of UK-led innovations, similarly could only be applied on the Agri Tech activity. Output three concentrates on increased capacity of public officials and has two indicators. In this case, it could only be applied to the open procurement activity managed by the Open Contracting Partnership (OCP). Output 4, on the other hand, measures the number of inclusive, sustainable projects designed and has eight indicators. Here we could report the substantial progress made on the regional competitiveness, urban and rail activities.
Annual outcome assessment (Secondary Benefits)
The first Colombia PF Programme export win was confirmed on 6 November 2019. It is from Vernacare, manufacturers of environmentally-friendly and sustainable medical equipment. The company received support through a PF-funded and managed Roadshow in London in February 2019. As DIT also provided support to Vernacare this export win, worth £348,000, is shared with them. The Agri Tech Catalyst projects managed by Farming Data and Agricompas are negotiating new projects which, if they go ahead, will count as secondary benefits.
Overall output score and description
A – Outputs met expectations
Key lessons
1. Supplier management is critical to achieving the outputs that lead to successful outcomes. Large chunks of the past year have been dedicated to strengthening our working relationships with CAF and Findeter in particular. At times this meant escalating challenges to the Head of the organisation, but that proactive approach eliminated bottlenecks and returned Programme activities to planned timetables.
2. Our Colombian implementing partners (IPs) are not accustomed to UK or PF priorities and modalities. This includes procurement procedures; monitoring, reporting, evaluation and learning (MREL); gender and inclusion (G&I); and climate and environment. The Colombia PF Team has invested substantially in raising our partners’ awareness on each of these issues and in understanding how to apply them to PF investments. We are in a much stronger place now as a result.
3. Working with our IPs, the PF Team have developed and put in place robust, clearly defined procedures for supporting specific project proposals. This includes project selection process, site visits, preparation of project design ToRs, and early market engagement events with potential contractors, and contract implemention. These advances were made through the piloting and lessons learned in the first round of regional competitiveness, rail, urban and Agri Tech projects. We are much better equipped to roll out the second round of project support starting in early 2020.
4. Colombia’s 2018 to 2022 National Development Plan (NDP) focuses on equity and includes a chapter on gender equality for the first time. This has given an impetus to the PF G&I agenda as it dovetails more strongly with messages emanating from central government. The PF Team have conducted G&I workshops with stakeholders; supported IPs to embed G&I empowerment and transformation into PF investments where possible; trained 168 new mayors and governors on how to integrate G&I into development plans and infrastructure projects; and supported Findeter to create a plan on how to mainstream gender across the whole of the bank’s operations, not just PF projects. The PF Team and the wider British Embassy have an unparalleled opportunity to advance gender, women’s economic empowerment and inclusion throughout Colombian government policy and programmes.
5. The pool of PF Commercial Framework (CF) companies with a presence in Colombia is limited (ten businesses) and attracting international companies to invest in the country is challenging, given prevailing negative stereotypes of the Colombian business environment. We have engaged a wide range of partners (DIT, ProColombia, Colombian Embassy and Chamber of Commerce in London, private sector companies, media and other influencers) to support us over the past year. A more joined-up UK government approach on promoting wider opportunities in Latin America combined with a SMART marketing campaign from the Colombian government would help turn around those perceptions and raise awareness of the real, modern Colombia.
6. After the first year of Programme operation, the PF Commercial Adviser produced a cost-benefit analysis of all non-ODA supported activities. She used the analysis to eliminate or reduce those activities which delivered a lower rate of return when designing the 2019/20 secondary benefits (SB) plan for Colombia. The Commercial Adviser also gave greater emphasis to efforts that would help ‘land’ UK and international companies in Colombia. Based on the experiences of our non-ODA investments this year, we will further refine our SB focus and efforts for next year.
7. The Colombia PF Programme had two incidents over the past year that revealed weaknesses in the project contracting processes agreed between the PF Team and Findeter. The first was an advance payment that was not used on time and had to be returned to the Programme. The second was an incorrect process for gauging the correct value for project feasibility studies. On both counts, the agreed process was reviewed and strengthened (see Section F for details) to avoid similar issues from ever happening again. This learning was applied to CAF before any of their tenders went to market and the PF Team have also shared this learning with the newest IP – FDN.
8. The Colombia PF Programme has human and financial resources to implement an ambitious communications strategy. In line with Programme progress, we have moved from simple social media messages and short case studies to diplomatic telegrams and chocolate tasting events that have really raised the profile of the Programme and its primary benefits. We will continue to strengthen our digital skills and invest in novel and creative media opportunities to share the positive stories that the Programme is generating.
9. The Colombia PF Programme was the first to be given a climate and environment (C&E) audit. A total of 11 recommendations (see p10) were made. The support of an expert is required to prioritise and oversee implementation of each recommendation.
Key actions
1. Work with IPs to implement the recommendations in this AR.
2. Employ robust processes and lessons learned from first round of PF project support to the second round which commences in early 2020.
3. Ramp up G&I ambitions and activities next year. Work with Presidency, key ministries, selected mayors and governors and our IPs to embed G&I best practice in policy and programmes. Support Findeter to mainstream gender equality throughout all of the bank’s operations. Ensure correct level of technical expertise is available in or to the PF Team to achieve these ambitions.
4. Repeat cost-benefit analysis of 2019/20 non-ODA investments and further refine SB strategy for the following year. Prioritise activities that ‘land’ UK and international companies in Colombia.
5. Identify Climate and Environment Adviser to support Colombia PF Programme to implement recommendations in recent C&E Audit.
6. Be novel and creative with digital media and communications opportunities to better share good news stories to increase positive momentum around and impact of the Programme.
Summary of changes to the logframe since the last Annual Review (AR)
For the first Colombia PF Programme AR, nested logframes for each of the seven activities were used in the Detailed Output Scoring section. Over the past year, MREL experts worked with the IPs and the PF Team to finalise a Programme umbrella logframe. The four main outputs of the umbrella logframe appear in this AR. This means that instead of looking at each activity on its own as happened in 2018, this AR combines multiple elements from several activities into one output. Output 1, for example, brings together progress from both the agri-insurance and Agri Tech activities on increased technical capacity of producers. Similarly, Output 3 combines increased capacity of government officials to design inclusive and sustainable projects from the urban, rail, regional competitiveness and agri-insurance activities.

Recommendation 12 from the 2018 AR proposed that the Colombia PF Programme (nested and umbrella) logframes be revised to better reflect the wide range of intermediate efforts and activities undertaken by the PF Team and IPs to achieve project indicators and milestones. A specific reference suggested adding the development / issuance of ToRs. With this in mind, 13 new intermediary indicators were added to the seven nested logframes and three to the Programme umbrella logframe, including the number of inclusive ToRs taken to market.

## C: DETAILED OUTPUT SCORING

Output Title	Increased technical capacity of producers and providers in agricultural insurance and agricultural technology products and services, especially female and male smallholders and small companies (including cooperatives, associations and MSMEs)
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	12%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Yes, this figure represents 50% of the value of both the agri-insurance and Agri-Tech activities

Indicator(s)	Milestones	Progress During First 6 Months
Number of female and male producers and providers trained	Planned (2019/20) / Agri Tech Catalyst: / Females: 231 / Males: 165 / Total: 396 / Agri-insurance: Trainings begin in 2020/21	Achieved (2019/20) / Agri Tech Catalyst / Females: 224 / Males: 217 / Total: 441 / Source: Agri-Tech project reports
Number of training sessions and/or modules dedicated to gender and inclusion issues	Planned (2019/20) / Agri Tech Catalyst: / seven gender and inclusion training session (i.e. at least 1 training session per project) / Agri-insurance: / Trainings begin in 2020/21	Achieved (2019/20) / Agri Tech Catalyst: / 35 gender and inclusion training sessions from five of the seven projects; the higher number results from many projects having multiple locations and therefore repeating the training many times / Source: Agri-Tech project reports

Key Points
Agri Tech Catalyst
This activity started first and is well ahead of the other six. By May 2019, all seven Agri Tech Catalyst projects had been launched and started implementation. They will run for 18 months, with the last one finishing in November 2020. So far, the projects are operating in 28 different communities having provided technical training to 441 individuals (51% women) (see summary in table below). The original plan was to complete training in seven communities to 396 beneficiaries. Though there were seven less women trained than planned, that is only a 3% difference. The activity is therefore performing well on these two indicators.
Name of Project and UK Implementing Agencies	Number of Communities Where Project Operates	Total Number of Women and Men Received Technical Training to Date	Total Number of Women and Men Received G&I Training to Date	Total Number of Expected Beneficiaries By End of Project
Improving irrigation management to enhance the livelihoods of smallholder banana growers – Climate Edge, Environmental Systems and Cranfield University	1	-	30 (2 Females and 28 Males)	175 (23 Females)
Integrated trading platform and data analytics for Colombian small farmers – Farming Data Limited	7 Departments of Colombia	239 (98 Females and 137 Males)	145 (64 Females and 81 Males)	1,000 (50% Female and 50% Male)
Controlling cocoa bean fermentation for enhanced chocolate flavour – Luisa Vegan Chocolates and University of Nottingham	3 Females During Pilot Phase	3 Females	42 (40 Females and 2 Males)	15,000 Fedecacao Members
Digitising cocoa production in Colombia – Agricompas Limited	2	148 (73 Female and 75 Male)	48 (33 Females and 15 Males)	207 (66 Female and 141 Male)
SatCafe satellite remote sensing for improved and sustainable coffee production – Remote Sensing Applications	3 Women’s Coffee Growers Associations	-	-	All 540,000 Fedecafe Members
Realising equitable gender opportunities to improve smallholder coffee livelihoods using advances in digital technology - CABI, Climate Edge and Assimila	1	-	-	300 (50% Female and 50% Male)
ESTA extending and supporting tilapia aquaculture – Secure Harvests and FishGen	11 / (50 Farms)	51 (50 Females and 1 Male)	51 (50 Females and 1 Male)	50 Individuals will disseminate to the rest of their communities
Total	28	441 (224 Females and 217 Males)	316 (189 Females and 127 Males)	556,732

- The second indicator for this activity is the number of training sessions dedicated to gender issues. The target milestone for the full year is seven (one training session per project), but already 35 such sessions have been provided by five of the projects (see Table above). Therefore, this target has been exceeded. This is because many of the projects operate in multiple locations and the gender training has been repeated with all of them and because many of the projects received support directly from the PF Team and our local G&I expert. In total, there are 286 (187 women and 99 men) who have received G&I training so far.
- The G&I workshops provided by the PF Team focused on women’s economic empowerment (WEE). The workshops built the capacity of female farmers on: i) the important role they play in their family’s agricultural businesses; ii) how their time and labour can contribute to improving the sustainability and financial success of those businesses; and iii) how their engagement with the Agri Tech projects can lead to improved quality, yields and higher incomes.
- While it is still early days, two of the Agri Tech implementing groups, Farming Data and Agricompas, have seen external interest in their business models which may generate new contracts for them.
Agri-insurance
- For this year, the agri-insurance activity does not have any milestones under this Output as it is not yet working with producers or providers. CAF will have to begin measuring against this Output in 2020/21.
- For this AR, the Agri-insurance activity is solely assessed under Output 3.
Summary of responses to issues raised in previous annual reviews (where relevant)
Agri Tech Catalyst Challenge Fund
Ongoing testing and education of the beneficiaries is needed to ensure they can and are willing to use the technologies. / If resources are secured for a second round of the challenge fund, there is a need to ensure that all the lessons learned from the first one are incorporated especially around gender and inclusion, conflict zones and sustainable crops, and if possible should focus on late stage projects.	Technical and G&I workshops have taken place in the regions, including a wider number of beneficiaries and not just the ones initially targeted at the project design. / No resources have been secured for a second round

Recommendations
1. Once the pilot phase of the Agri Tech innovations has been completed, the seven projects will need to rapidly prioritise scalability and sustainability to achieve primary and secondary benefit targets. The PF Team to look at crowd-in funding to provide Agri Tech projects with longer term sustainability if necessary. The Global Innovation Fund, for example, supports successful tech projects, which are scalable.
2. For agri-insurance activity, CAF to ensure that it is ready to measure i) number of producers trained; and ii) number of training sessions with G&I modules starting in 2020/21.
## DETAILED OUTPUT SCORING

Output Title	UK-led innovations aimed at inclusive, sustainable development piloted and tested in agritech, agri-insurance, urban, rail and regional competitiveness
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Yes, this figure represents 50% of the value of both the agri-insurance and Agri-Tech activities and 25% of the rail, urban and regional competitiveness activities

Indicator(s)	Milestones	Progress During First 6 Months
Number of UK-led innovations piloted and tested	Planned (2019/20) / 7 Agritech projects	Achieved (2019/20) / 7 Agritech projects / Source: Project reports
Number of UK-Colombia official partnerships formed	Planned (2019/20) / None	Achieved (2019/20) / None
Number of women and men benefiting from UK-led innovations	Planned (2019/20) / None	Achieved (2019/20) / None

Key Points
Agri Tech Catalyst
- All seven Agri Tech projects have been up and running since May. They have all introduced UK-designed innovations in their sectors (banana, cocoa, coffee, tilapia and others). The innovations are: digital irrigation systems for bananas; digital agri-produce trading platform; scientifically improved cocoa bean fermentation; digital cocoa production; satellite remote sensing systems for coffee; digital control of coffee pest; and scientifically improved tilapia breeding.
- As per the table on p 17, under Output 1, the number of Agri Tech beneficiaries of the UK-led innovations being piloted are 441 (224 women and 217 men). This is 10% higher than the original number forecast (396), but 3% lower on the number of women expected to receive technical training. However, the benefits of these UK-led innovations has not yet been measured. It will be 2020/21 at the earliest before those measurements can take place.
- The indicators on the number of UK-Colombia partnerships formed will only commence in 2020/21.
Agri-insurance, Urban, Rail and Regional Competitiveness Activities
- These four activities will only commence measurement of Output 2 Indicators starting from 2020/21.
- Agri-insurance was the only one to score a B in 2018. At that time, the activity was unable to clearly define an approach, with accurate costings, to design the IT platforms and systems required to measure and assess agricultural risks in Colombia. Very quickly after the last AR, CAF together with Colombia’s Financial Institution for Agricultural Development (Finagro) and government stakeholders in UPRA, IDEAM and the Ministry of Agriculture worked to reverse this situation. This was achieved through several steps: i) convening more and more regular technical meetings amongst all the stakeholders; ii) liaising with senior Ministry of Agriculture officials to improve government participation in the activity; and iii) a redistribution of the activity budget to the most promising technical design contributions.
- The main outputs for this year are four well-designed project ToRs going to market. Three of these - SIGRA, Geoagro and IDEAM - are IT systems while the fourth - market survey work – is the first stage of the information campaign and capacity building component of the agri-insurance activity. This work forms part of Output 4.
Summary of responses to issues raised in previous annual reviews (where relevant)
Though the indicators in the umbrella logframe are different from last year’s nested logframes, it is worthwhile reviewing the progress the agri-insurance activity has made over the past year. The concern about further delays did not materialise. Rather, the bottlenecks from last year were addressed as described in the table below and all four project tenders went out to market in September 2019. At the same time, the PF Team has an improved understanding of how the CAF Special Funds Committee functions and can plan better for important decisions to be taken within the desired timeframe. This enhanced approach to planning will help streamline processes for the second batch of CAF investments next year.

Agricultural Insurance
Recommendation	Action Taken
BE Bogota and CAF to monitor closely progress and spend on this activity. If it is affected by further delays, the BE Bogota should work with CAF to identify and implement remedial actions.	Spending for this particular activity has been limited as all disbursements are directly linked with the development of the 4 projects. / Despite this, CAF continue to engage with both, the BE and the beneficiaries of the different projects. During the 2018/19 financial year for example, CAF held at least 30 meetings with the Ministry of Agriculture and Rural Development, UPRA, IDEAM and other relevant stakeholder. Additionally, meetings with BE personnel became more frequent and the activity’s coordinator continued to actively contribute to the definition, adjustment and follow-up of the initiatives. / An equally important factor to mention relies on the qualitative benefits that the whole agricultural insurance activity has created. Among other things, CAF and BE’s work on initiatives and created valuable synergies within the government. Entities are becoming more articulated and joint efforts towards the completion of the projects are giving more clarity to the long-term sustainability of the initiatives. / With a budget of USD 1.5, SIGRA went to market on 27 September 2019.
If the SIGRA cost does double, BE Bogota should work with CAF to cut back on one or two of the other parts of this activity, based on agreed criteria of maintaining the aspects most critical to achieving impact and proving the commercial viability of the project.	CAF has already explained BE officials about internal procedures for project origination, approval and implementation. Additionally, CAF has shared a variety of documents that clarify these processes for PF projects.
Similar to the CAF Regional Competitiveness activity, BE Bogota to spend more time understanding CAF internal approval procedures and to agree with CAF how these add value, and ensure the achievement of targets by agreed milestones. At the same time, CAF should look at what it could do to reduce the time between Special Funds Committee Meetings.	Although the time between CAF’s Special Funds Committee meetings cannot be changed purely based on BE requirements, PF projects implemented by CAF are being considered by this committee following a fast-track approach especially designed for initiatives that require expedite procedures, including those one related with the addition and formalisation of activities that require more resources.

Recommendations
1. The PF Team should ensure that lesson learning from the PF Centre for Global Disaster Protection Programme, specifically on its insurance work, is incorporated into the Colombia agri-insurance activity.
2. In addition to the regular activity budgets, the PF Team will need to ensure that non-ODA resources are targeted as appropriate to supporting the formation of UK-Colombia partnerships as per the secondary indicator above.
3. All five of these activities will need to have adequate resources and approaches in place to measure the benefits of the UK-led innovations.
## DETAILED OUTPUT SCORING

Output Title	Increased capacity of public female and male officials to design and structure inclusive and sustainable urban, rail, regional competitiveness, ANI, agri-insurance, and open procurement investments
Output number per LF		3	Output Score	A+
Risk:		Moderate	Impact weighting (%):	18%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Yes, this figure represents 100% of the value of the open procurement and ANI activities and 25% of the rail, urban and regional competitiveness activities

Indicator(s)	Milestones	Progress During First 6 Months
Number of female and male public officials trained	Planned (2019/20) / Urban Development / 150 Officials	Achieved (2019/20) / Urban Development / Females: 8 / Males: 160 / Total = 168
	Rail / 30 Officials	Rail / Data will become available in March 2020, but at least 30 officials
	Regional Competitiveness / None	Regional Competitiveness / None
	ANI / None	ANI / None
	Agri-insurance / None	Agri-insurance / None
	Open Procurement / 75 Officials	Open Procurement / Females: 44 / Males: 31 / Total = 75
	Total = 255 Officials	Total = 273 / Source: Project reports
Number of female and male public officials receiving training sessions and/or modules dedicated to gender and inclusion issues	Planned (2019/20) / Urban Development / 2 Sessions for 150 Officials	Achieved (2019/20) / Urban Development / Females: 8 / Males: 160 / Total = 168
	Rail / 30 Officials	Rail / Data will become available in March 2020, but at least 30 officials
	Regional Competitiveness / None	Regional Competitiveness / None
	ANI / None	ANI / None
	Agri-insurance / None	Agri-insurance / None
	Open Procurement / None	Open Procurement / None
	Total = 180	Total = 198 / Source: Project reports

Key Points
Urban Development
With PF co-funding, Findeter organised and ran a four-day training conference for 168 newly elected mayors (147) and governors (21) in Santa Marta from 12 to 15 November 2019. The target of 150 local officials trained during 2019/20 has therefore been exceeded. The training, managed by Rosario University, had key messages on G&I integrated focused on how to prepare municipal and departmental development plans and how to develop, contract for and implement development projects such as new infrastructure. Two sessions during the four-day event were dedicated solely to the importance of understanding and applying G&I and women’s economic empowerment (WEE) in all municipal and departmental plans, policies and programmes. Many mayors and governors expressed the need for further support from the PF to prepare and implement the G&I policies and programmes in their areas. Given available resources, the PF Team will need to establish an open and transparent process for selecting and supporting a small number of municipalities and departments beyond the 16 cities and regions targeted by the Programme.

Rail
Similar to last year, the PF was requested by the Colombian government to continue to build the capacity of officials from the Ministry of Transport, the National Planning Department (DNP) and the National Infrastructure Agency (ANI) on rail regulation and management of rail operations. Using resources from the Policy Connections budget line of the Colombia Pf Programme, the PF Team put out to tender in early November 2019 a contract to train at least 30 government officials in these areas. The training must be completed by mid-March 2020. The four-day training will integrate G&I throughout and must also have at least one full module on the importance of G&I in rail policies and programmes.

Regional Competitiveness
This activity will only commence capacity building for government and other members of the eight Regional Competitiveness Commissions in 2020/21. The ToRs for this work includes integrating G&I throughout the training and at least one module dedicated to G&I priorities.

Corporate Governance Reform of ANI
This activity started six months later than all the others due to the change on government half way through 2018. Although it took considerably longer than expected, an agreement allowing CAF to support the ANI reform work was signed in August 2019 and the tender for a PF CF company to provide the required inputs went out to tender the following month. The ToRs insist that G&I be a core theme of all the reform work and the PF Team, working with CAF, will ensure that ANI staff members are provided with specific G&I training sessions in addition to the technical capacity building.

Agri-insurance
This activity will only commence capacity building for government and other stakeholders (academia, private sector and agricultural communities) in 2020/21.

Open Procurement
- Open Contracting Partnership (OCP) conducted three mapping and scoping missions to the first two pilot departments Caldas and Valle del Cauca over the past year. These were followed by eight open contracting workshops on the International Open Procurement Standards (IOPS) in the same two Colombian departments. In total, 75 public officials were trained, 39 (18 women and 21 men) in Caldas and 36 (24 women and 10 men) in Valle del Cauca Department. As 75 officials was the agreed target for 2019/20, this milestone has already been met.
- This ‘sensitisation’ campaign is the forerunner to rolling out, from central government to the regions of Colombia, the new public digital contracting system and platform known as SECOP II. Meanwhile, OCP is commencing the second part of its work by carrying out mapping and scoping missions in Magdalena and Atlántico Departments.
- Given the highly technical nature of OCP’s training, they did integrate G&I issues throughout the course, but they did not have a specific session on this PF priority. For the remaining six departments, OCP should look at creating and providing a separate G&I session for government and other stakeholders.
- The PF Team is currently working with Colombia Compra Eficiente (CCE), the national contracting agency, to finalise the design of the second phase of the open procurement activity (i.e. rolling out SECOP II to eight departments). The activity is expected to launch in early 2020 and will be managed by Findeter.
- The PF Programme has helped Colombia progress towards membership of the Construction Sector Transparency Initiative (CoST), which also aims to combat corruption in the public procurement of infrastructure projects. The PF Team should continue to support Colombia and offer to support the application of CoST to PF projects such as AeroCafe and the two railway lines (Bogota-Zipaquira and La Dorada-Chiriguana.) The Bogota Metro is another option for CoST to look at.
Summary of responses to issues raised in previous annual reviews (where relevant)
All recommendations from the 2018 Colombia PF Programme AR have been actioned. Those made for ANI and Open Procurement have all been addressed (see Table below).
Corporate Governance of ANI
Recommendation	Action Taken
BE Bogota to work closely with CAF to ensure ToRs for ANI corporate governance reform go out to market as soon as possible.	This project was subject to repeated amendments over an eight-month period. The TORs went to market on 27 September 2019.
Open Procurement
BE Bogota to work closely with Findeter, OCP and CCE to design the first complementary strand to the activity that allow CCE to ensure full adherence of SECOP II in the PF selected departments.	Findeter was unable to work directly with OCP due to payment barriers such as disbursement in dollars. For that reason, BE had to lead on the OCP activity. For the second phase and the direct involvement with CEE; Findeter will have to step in and co-design the projects.
BE Bogota to design second complementary strand with Findeter and OCP that would allow civil society to better engage with and monitor implementation of SECOP II in the selected departments.	For the second part of this activity, BE Bogota worked directly with CCE to design a project complementing OCP’s work, to implement SECOP II in the 8 PF priority departments. As the Director of CCE changed, there was a gap of 4 months in progress. The second strand has been designed and approved by the PF Team. We are just awaiting clearance from Findeter to go ahead.
Revise open procurement and all nested log-frame indicators to ensure they are SMART and gender and inclusion priorities are fully integrated.	Indicators have been amended; those are now measurable and disaggregated

Recommendations
1. There is strong demand from newly elected mayors and governors for support with preparing the G&I chapters in their development plans and, possibly going beyond that, to needing support to implement the G&I policies and programmes. Working with IPs, the PF Team will need to establish an open and transparent process for selecting and supporting a small number of additional municipalities and departments beyond those already included in the Programme.
2. OCP to plan and deliver separate G&I sessions during its technical training courses on the IOPS in the departments.
3. When SECOP II is ready for rollout to the departments, the PF Team should work with OCP and CCE to ensure the 8 PF departments are prioritised. Prepare lessons learned from the first pilots to ensure second set of departments benefit from those.
4. The PF Team should continue to support Colombia’s membership of the Construction Sector Transparency Initiative (CoST) and offer to support the CoST application to PF projects such as AeroCafe and the two railway lines.

## DETAILED OUTPUT SCORING

Output Title	Urban, rail and regional competitiveness projects are designed, structured and ready for investment in an inclusive and sustainable way
Output number per LF		4	Output Score	A
Risk:		Moderate	Impact weighting (%):	36%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Yes, this figure represents 50% of the value of the rail, urban and regional competitiveness activities

Indicator(s)	Milestones	Progress During First 6 Months
Number of inclusive projects presented to the PF	Planned (2019/20) / Urban Development = 30 / Rail = 7 / Open Procurement = 1 / ANI = 1 / Regional Competitiveness = 25 / Agri Tech = 50 / Agri-insurance = 4 / TOTAL = 118	Achieved (2019/20) / Urban Development = 39 / Rail = 7 / Open Procurement = 1 / ANI = 1 / Regional Competitiveness = 25 / Agri Tech = 54 / Agri-insurance = 4 / TOTAL = 131
Number of inclusive projects prioritised	Planned (2019/20) / Urban Development = 5 / Rail = 2 / Open Procurement = 1 / ANI = 1 / Regional Competitiveness = 4 / Agri Tech = 7 / Agri-insurance = 4 / Total = 24	Achieved (2019/20) / Urban Development = 5 / Rail = 2 / Open Procurement = 1 / ANI = 1 / Regional Competitiveness = 4 / Agri Tech = 7 / Agri-insurance = 4 / TOTAL = 24
Number of inclusive TORs taken to market	Planned (2019/20) / Urban Development = 5 / Rail = 2 / Open Procurement = NA / ANI = 1 / Regional Competitiveness = 4 / Agri-insurance = 4 / TOTAL = 16	Achieved (2019/20) / Urban Development = 4 / (Manizales, Valledupar, Ibague and Santa Marta) / Rail = 2 (Bogota – Zipaquira, La Dorada – Chiriguana) / ANI = 1 / Regional Competitiveness = 3 / (AeroCafe Caldas; CVA Atlántico; and Tilapia Value Chain Magdalena; Transport Hub Santander still being prepared) / Agri-insurance = 4 / (Open competition) / TOTAL = 14
Number of urban, rail and regional competitiveness projects designed, structured and ready for investment	Planned (2019/20) / None	Achieved (2019/20) / None
Number of future city strategies or pilots which meaningfully incorporate disadvantaged groups’ views in to the consultation and design (KPI 2)	Planned (2019/20) / None	Achieved (2019/20) / None

Number of anticipated beneficiaries from urban, rail and regional competitiveness projects	Planned (2019/20) / Urban Development 1,645,413 / Rail 6,204,049 / Regional Competitiveness 5,185,272 / TOTAL: 13,034,734	Achieved (2019/20) / Urban Development 1,645,413 / Rail 6,204,049 / Regional Competitiveness 5,185,272 / TOTAL: 13,034,734
Number of new Commercial Opportunities as a result of PF work	Planned (2019/20) / None	Achieved (2019/20) / 1 Export Win with Vernacare
Value of new export opportunities for International and UK businesses as a result of PF activity (urban, rail and regional competitiveness) (Portfolio KPI 17)	Planned (2019/20) / None	Achieved (2019/20) / £348,000 from Vernacare Export Win

Key Points
- As part of the project identification process, the IPs and the PF Team visited six Departments (Valle del Cauca, Caldas, Magdalena, Meta, Atlántico and Santander), six cities (Santa Marta, Ibague, Manizales, Valledupar, Villavicencio and Rio Negro), and two rail lines (Bogota Zipaquira and La Dorada Chiriguana). In total, municipal and departmental authorities submitted 131 projects proposals (from an expected 118) to the Colombia PF Programme exceeding expectations.
- It was expected that within the first full year of the Programme operating, the PF Team would agree on 24 projects being prioritised for investment. After reviewing the 131 proposals received, five urban development, two rail, four regional competitiveness, seven Agri Tech and four Agri-insurance projects plus one each for ANI and Open Procurement were approved for funding. Thus the target for projects prioritised was met.
- For the number of inclusive ToRs taken to market, the expectation was 16 in 2019/20. So far, 14 projects have been tendered. Only the second Santa Marta project on water and sanitation and the Barrancabermeja (Santander) transport hub project are still preparing their ToRs. Santa Marta is behind schedule due to the issues around the changes in mayor between April and July this year. Barrancabermeja is advancing and the ToRs should be ready in the next month.
- Indicators 4 (projects ready for investment) and 5 (future city strategies or pilots) do not have any milestones for this year. They will be expected to start in 2020/21.
- The anticipated beneficiaries for the urban, rail and regional competitiveness projects that have gone to tender so far is over 13 million people (see table below). These figures come from the project proposal templates (fichas in Spanish) prepared by staff in the mayors and governor’s offices. These figures will change and be more accurate once the social deliverable, part of each project tender, is submitted. The social reports have to study project potential beneficiary populations in depth and present accurate statistics. This will give the PF Team and the IPs evidence-based figures. The logframes will then be updated accordingly.
- Even with the more accurate beneficiary numbers from the social studies of each project, the true number of beneficiaries will only materialise once the projects are successfully taken from design to execution phase. It will take one to two years for all PF Colombia projects to go to market, and then it will be another one to two years before the execution phase is completed and Colombians start feeling the impacts. Given the Colombian PF Programme Business Case (BC) predicted 3 million beneficiaries, about three months prior to the next Annual Review in November 2020, it would be prudent to review and update the cost-benefit analysis calculations and VfM for each activity.
- The Manizales Intelligent Transport project is the only one to have commenced G&I consultations as part of the design process. PF Team staff attended the consultations with women, people with disabilities and afro-descendants in October 2019. The contributions of these groups and many others will help shape the new transport system in Manizales ensuring the services are safer, more accessible and more responsive to the specific needs of women, girls and vulnerable populations. A similar process will be conducted for all urban development, rail and regional competitiveness projects. Additional G&I expertise will be made available to all PF projects to ensure best practices in stakeholder engagement and inclusive project design are adhered to.
- Indicators 7 (new commercial opportunities) and 8 (value of new commercial opportunities) have no specific milestones for the first full year of Colombia PF Programme operation. This is because all seven activities are mostly just getting started. However, through our non-ODA activities, one initial export win was made in November 2019. This is with Vernacare, a medical company that makes environmentally-friendly and sustainable hospital equipment. They attended a PF Roadshow in London in February 2019. The value of the export win is £328,000. As DIT also supported Vernacare, the export win attributed to the PF is 50% of the total or £164,000.
Colombia PF Activity and Name of Project	Anticipated Number of Beneficiaries According to Project Ficha (Project Template)
Urban Development: Manizales Intelligent Transport Design Project	557,060 urban transport users and employees per year
Urban Development: Ibague Sanitation Design Project	564,076 urban users per year
Urban Development: Valledupar Sanitation Design Project	25,000 rural sanitation users per year
Urban Development: Santa Marta SMART City Design Project	499,277 urban users per year
Regional Competitiveness: AeroCafe Airport Design Project, Palestina, Caldas	At maximum use, 3,170,871 airport users and employees per year
Regional Competitiveness: Agriculture Value Added Centre Design Project, Atlántico	2,004, 181 users, employees and clients per year
Regional Competitiveness: Multimodal Transport Logistics Hub Design Project, Barrancabermeja, Santander	10,000 urban users per year
Regional Competitiveness: Tilapia Value Chain Project, Magdalena	220 Tilapia Producers (44 women, 176 men and number of indirect beneficiaries in value chain not yet known)
Rail Development: Bogota to Zipaquira Passenger Railway Design Project	5,417,000 users and employees per year
Rail Development: La Dorada to Chiriguana Freight Railway Design Project	787,049 users and employees per year
Total	13,034,734

Summary of responses to issues raised in previous annual reviews (where relevant)
All recommendation from the 2018 Colombia PF Programme AR have been actioned. For urban development, rail and regional competitiveness, the points raised during the 2018 AR have been addressed (see Table below).
Urban Development
Recommendation	Action Taken
Revise down the next version of the nested and umbrella logframes to say up to 12 urban development projects reflecting the higher cost of each initiative. Re-focus the logframe indicators to account for the quality of the projects selected and how they can be replicated in other cities. / Use the many lessons learned from the first five urban development projects to improve the processes around the rail and regional competiveness activities as well as the remaining (up to) seven urban development projects.	The follow-up of these indicators was commended to the Findeter economic analysis group, who have strictly complied with what was suggested. The above has been reflected in the bidding documents that have been produced in the current year (2018-2019) such as the Manizales, Ibagué, Valledupar, Santa Marta and Bogotá-Zipaquirá Train projects. / The logical frameworks have taken into account to avoid cost overruns both in the product request and in the review of the products, including the corresponding quality indicators; the foregoing as a suggestion issued by the economic analysis group. / Following a further review of project costs with the IPS, the nested log-frame has been amended to say “Up to 10 inclusive urban development projects designed and structured, ready for investment” / The Early Market Engagement (EME) events have consistently improved as a result of experienced feedback. The tender procedures for CAF have improved based on the immense lessons learned from Findeter’s contracts. Payments now have new requirements before they can be approved: i) date of tender; ii) final price of project based on early market testing; and iii) final and approved version of TORs. Finally, the market test for Findeter projects resulted in brand new approaches to test CAF projects, including 1-2-1 consultations with individuals PF Commercial Framework companies.
Rail
Employ BE Bogota bilateral relations and the rail working group to continue to influence the new Colombian administration on the value and potential of rail and to offer on-going strategic support including on transport project finance in tandem with the rail rehabilitation work. / The log-frames for rail and urban development need to be revised to better reflect the wider efforts of BE Bogota in building capacity and ensuring projects are ODA compliant, deliverable and will have impact. This includes capturing better the full range of progress and benefits by breaking down the indicators and including, for instance, activities like the development / issuance of ToRs.	BE Bogota and the railway group supported a section on rail in the new National Development Plan: a successful union between ANI; Min Transport; FDN and Findeter to take forward the Bogota-Zipaquira and La Dorada - Chiriguana projects; a co-funding contribution from Cundinamarca worth £1.6m for the Bogota – Zipaquira project and progress on the Rail Master Plan. / Specific indicators like “ Number of inclusive projects presented to the PF”; Number of inclusive projects prioritised” and “Number of feasibility study TORs for inclusive projects taken to market” have been added to most nested log-frames

Regional Competitiveness Activity
BE Bogota to work closely with CAF to finalise contract with CONFECAMERAS, prepare the second technical assistance ToRs for PF Commercial Framework companies and launch the first projects in Magdalena, Caldas and Valle. / BE Bogota should monitor spend on this activity more proactively. If it is affected by further delays, work with CAF to identify and implement remedial actions. / Explore how the recent MoU between CAF and UK Export Finance can support the delivery of selected Regional Competitiveness projects. / As in the Urban Development activity, the original number of projects (three per department and 24 in total) now seems too ambitious. CAF and the BE Bogota should conduct the first three pilots and then revise the target. The reduction in the Urban Development activity from six to four cities was beneficial to the Programme as it focused efforts. The Regional Competitiveness activity should consider if reducing down from eight departments could help focus efforts and improve impact, and ensure the activity remains within budget. / Same as the Agri-insurance activity, BE Bogota to spend more time understanding CAF internal approval procedures and to agree with CAF how these add value, and ensure the achievement of targets by agreed milestones. At the same time, CAF should look at what it could do to reduce the time between committee meetings.	Contract with CONFECÁMARAS was signed on 31 December 2018 and it is expected to end on 31 December 2019. It is important to highlight that due to the decision of the BE to divide this project in two (and assign just the first phase to CONFECAMARAS), and given the fact that the addendum to the Technical Assistance and Collaboration agreement was not signed until very recently, the second phase of the initiative has not yet awarded. CAF has been working with CONFECAMARAS and the BE in the adjustment of the terms of reference, and they are expected to be published on 27 September 2019. / Magdalena Tilapia project has a provisionally start date of 1 November; Caldas Aerocafe project by 4 October; Atlántico Value Added Centre by the same date; and Santander Transport Logistic Hub by 15 November. Valle del Cauca did not submit an acceptable project proposal. / Three disbursements for a value of USD 187,072.5 corresponding to the CONFECAMARAS contract have already been made. Additionally there have been additional disbursements to consultants that have participated in the structuring of projects and other additional activities (events, seminars, translations and trips to prioritised regions) for up to USD 18,964.72[3]. / Although regional competitiveness projects are still in a feasibility phase, CAF has repeatedly mentioned the MOU with UK Export Finance as a mechanism that regions can consider in the future at the time of examining financing options for their projects. Nonetheless, the 20% British-component requirement has proven to be a challenge, especially for public-run initiatives. Nevertheless, CAF continues to promote the instrument, not only for PF-projects, but for other potential initiatives in the region. The office in charge of this is the Direction of Institutional Financing Resources, located in Lima, Perú. / Following instructions from the BE, the target number of projects to be supported was reduced to eight, meaning, in principle, up to one per department. This decision was the initial proposal and was indeed very ambitious, but especially, because of the identification that the support to fewer but larger projects would result in bigger and more meaningful impact for the regions. / As of 30 September 2019, CAF is working in the structuring of four regional competitiveness projects: Aerocafe(Caldas); Tilapia Value Chain (Magdalena)[4]; Value-Added Centre (Atlántico); Multi-Modal Logistics Platform (Santander) / For additional projects, CAF is currently working with the government of Colombia in the identification for a project in Valle del Cauca. In terms of initiatives that could be supported for the remaining regions (Antioquia, Bogotá-Cundinamarca and Meta), CAF awaits final decision from the BE. / CAF has explained to BE officials the internal procedures for project origination, approval and implementation. Shared a variety of documents that clarify the processes. Although the time between CAF’s Special Funds Committee meetings cannot be changed purely based on BE requirements, PF projects implemented by CAF are being considered by this Committee following a fast-track approach especially designed for initiatives that require expedited procedures.
[3] As CAF operating currency is the United States dollar, a consolidated figure in pound sterling (GBP) for all disbursements will be provided in the next quarterly report (Q3/2019).
[4] Although this project was not prioritised neither by the region nor by CAF, the BE decided to include it in exchange of the initially-proposed project presented by the Comisión Regional de Competitividad del Magdalena, as this last one was not mature enough for PF guidelines.

Recommendations
About three months prior to the next Annual Review in November 2020, it would be prudent to review and update the cost benefit analysis calculations and VfM for each Colombia PF Programme activity given the number of anticipated beneficiaries looks like it will change from the original figure of 3 million recorded in the Business Case. This information should be shared with JFU and the FCO Economics Unit.

The DFID Cities Adviser made the following additional recommendations:
1. The PF Team should work with the implementing partners (Findeter and CAF) to map out and agree on realistic assumptions for the rail and urban projects regarding the: length of time required for each phase in the project cycle; costs for each phase of the project cycle particularly high cost activities. This could be aided by having a common visual diagram of the project cycle and building it into the risk register for the programme. Having a shared understanding of the project cycle is crucial for the PF Team to achieve the relevant logframe target under output 4 – “number of urban, rail and regional competitiveness projects designed, structured and ready for investment”.
2. The Manizales Intelligent Transport project will be identifying data on journey times, incomes, job locations, etc. and the contractor should use this information to spot priority areas for improved reliability which can be determinant of public transport use that cost or speed.
3. The PF Team should explore how they can work with UK organisations (Arup, Argent, TfL etc.) to develop a transit-oriented development (TOD) approach that is bespoke to Bogota, drawing on case studies from other cities, the World Bank’s 3V methodology and CAF’s expertise. Codifying that TOD approach could be a task supported by the Global Infrastructure Programme team who may be able to subsequently roll it out as a HMG methodology.
4. The PF Team should seek to engage Transport for London’s Commercial team to determine whether there is scope to engage them as a strategic adviser for the rail and urban mobility projects. TfL may be well placed to provide advisory support to the City of Bogota, building an institutional partnership that would demonstrate the impact of UK expertise on integrated transport planning for a major city in the Global South.
5. Findeter should provide evidence of impact with regard to ‘control centres’ that they have implemented in other secondary cities. The draft ToR sets out the need for an integrated control and operations centre (CICO) in Santa Marta but the scope and objectives of the CICO is unclear. The purpose and objectives of the CICO should focus on the tools and technology that will be used for one specific sector (e.g. mobility management), possibly two at most. In parallel, the BE team should encourage Findeter to explore global initiatives that are seeking to use data/technology to improve urban planning including the World Bank’s Municipal Spatial Data Infrastructure, which has been applied in Bogota and Cali and the Bank’s City Planning Labs initiative.
6. The PF Team should consider developing a proposal for funding to the Global Challenges Research Fund (GCRF), possibly in collaboration with UCL and New York University. The proposal could build on global research initiatives and tools that are relevant to the aims of the programme, specifically the Urban KNOW[5] and NYU’s Urban Expansion Initiative[6].
  [5] Urban KNOW is a four year £7m GCRF funded project led by UCL – a UK institution that has already collaborated on urban research projects with Universidad Nacional de Colombia.
  [6] Which provides technical assistance to the cities of Valledupar and Monteria and has produced a database (a valuable global public good) on urban growth in Colombian cities.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
The key cost drivers for the implementing agencies (IPs) are the procurement of contractors to undertake feasibility studies on medium to large scale capital projects. Payments on the contract deliverables (the technical, financial, legal and social components of the feasibility study) are fixed as a percentage of total value, so costs are held steady without fluctuation. The key cost driver in the programme is therefore the costs of individual contracts, which is determined through market competition. The contracts are procured through competition using the PF Commercial Framework (more detail below in the economy section). In some instances international firms are giving much higher quotes for the contracts, with the rationale being that international firms will bring in international expertise, innovations and more effective long-term solutions. The Agri Tech activity uses a competitive bidding process, but uses a grant-based approach rather than commercial contracts.

The IPs work with PF Team to draft Terms of Reference (ToRs) which then go through a market testing procedure. A range of quotes from UK and Colombian are collected and analysed. If the average quote exceeds the expected contract value, one to one meetings are held with the UK companies to determine what the key cost drivers are. This clarification of project scope results in more realistic quotes. The value of the contract can then be amended accordingly.

All contracts are procured via the PF Framework. This speeds up the process due to the pre-screening of companies on the framework, who competed to be part of the Framework via the Open Journal of the European Union. If an acceptable bid is not sourced through the Framework, then the tender goes out to open global competition via Findeter/CAF/FDN standard routes.

Projects of the Urban Development, Rail Rehabilitation and Regional Competitiveness activities have required larger funding than originally estimated in the Business Case (BC). This was identified in the previous Annual Review (AR), and the PF Team followed the recommendation to lower their ambitious targets to reflect the higher costs and focus on priority projects. This will increase the likelihood of success on each project, as the PF Team will have more time to oversee each individual intervention. Nevertheless, the Programme will deliver fewer feasibility studies overall compared to the original ambitions, which in turn will lower the amount of international and domestic capital unlocked to invest in medium to large scale infrastructure projects.

Overall, the amount of investment that the feasibility projects support is still very large, and this capital is at risk of not being invested if the designs do not lead to project execution for lack of resources. Steps taken by the PF Team to reduce this risk include: i) working with development banks whose main activity is to invest in Colombian infrastructure projects, including all the ones selected for support by the PF; ii) as part of the financial component of each feasibility study, UK companies are expected to scour British and global capital market opportunities to come up with the right mix of domestic and overseas investment resources; iii) the PF has selected projects where national, departmental or municipal resources are already earmarked for the execution of the PF project; and iv) the PF works closely with international investors, who have several billion dollars of resources to invest in Colombia in well-designed infrastructure projects.

Good news was announced in mid-November 2019 that Findeter will move from being solely a second tier bank (providing credit to Colombia’s commercial banks for infrastructure investments) to being a provider of credit directly to cities and departments starting on 1 January 2020. This means that Findeter itself will be able to finance projects designed using PF resources.

The current situation for these projects is similar to the stress tests presented in the Colombia BC. The stress test on the Urban Infrastructure projects in the BC, which dropped the number of projects to 10, found a Net Present Value (NPV) of £127m of Primary Purpose benefits and £20m for Secondary Benefits, from £521m and £128m respectively in the central scenario. The Regional Competitiveness stress tests, which dropped the expected benefits by 50%, found an NPV of £32m for primary benefits and no secondary benefits, down from £102m and £1.8m respectively in the central scenario. Therefore, the projects still result in large cost-benefit ratios (17.2x and 7.5x respectively), maintaining a level of value for money that warrants continuation of the projects. The Programme now has real market data through its activities this year, so the key risks to its NPV centre on delays to contract procurement times, or a lack of market-appetite or capabilities to deliver a successful contract.

The Colombia Programme initially faced delays in having ToRs go out to market as per the original timetables agreed with CAF and Findeter. For CAF; they are a large multi-country development bank with lengthy, legal review processes. However, significant pressure was applied from internal senior stakeholders at CAF. This created a ‘fast track’ for Prosperity Fund projects, and it has significantly sped up procurement process. Findeter projects have returned to the agreed 2019 timetable. The Agri Tech grants were disbursed quickly due to the high demand from UK innovation organisations to work in the Colombia agriculture sector.

The admin rate was 4.52% over the Annual Review period, above the 3.5% cap Programmes are required to meet. This was largely due to the programme having to claw back £2.4m from Findeter in the final quarter of the year – if the £2.4m had been spent as expected, the admin rate would have been 2.93%. Given the lessons learnt and improvement plans put in place after the Findeter clawback, the review team did not see this as a structural concern provided the PF Team spend to budget next year.

By the end of the 2019/20 financial year, the Colombia PF Programme funding will have spent £16m (almost 63%) of the total available budget of £25.5m. A further £8m is programmed for 2020/21 and £1.5m for 2021/22.

Financial spend to date in Financial Year 2019/20

	Allocation	Forecast Spend	£ Variance	% Variance
STAFF COSTS (UK & local)	£339,000	£327,963	£11,037	3%
Urban Development	£800,000	£800,000	£0	0%
Rail Development 1	£3,570,000	£2,923,458	£646,542	18%
Regional Competitiveness2	£1,600,000	£2,030,000	£-430,000	-27%
Reform of ANI	£0	£0	N/A	N/A
Improved Public Procurement	£207,000	£197,894	£9,106	4%
Agri-Insurance	£150,000	£150,000	£0	0%
Agri Tech Catalyst Challenge Fund	£991,000	£972,745	£18,255	2%
TOTAL	£7,657,000	£7,402,060	£254,940	3.3%

1 The variance is due to the lower than expected cost of one rail project (La Dorada – Chiriguana). 2 The variance is due to the higher cost of one project (Value Added Centre in Atlántico).

VfM performance
The Urban Development, Rail Rehabilitation and Regional Competitiveness strands lowered their overall target number of projects due to a shift away from small projects with relatively small numbers of beneficiaries to larger interventions with hundreds of thousands of beneficiaries. The larger projects were also more attractive in terms of commercial viability and they fit more closely with National Development Plan (NDP) ambitions. The national civil aviation authority is having to retender the Santa Marta airport extension (paying a second tranche of about US$2m) because the first feasibility study was of poor quality and attracted insufficient finance. Without international innovation and best practice, the Colombian government and the PF Team were concerned that the PF feasibility design projects would suffer a similar fate. The Programme faced a choice of focussing on economy (by focussing on local implementers) or effectiveness (by focussing on international companies through the Prosperity Fund Commercial Framework), and went for the latter.

Whilst it is too early to tell whether this approach will be successful in delivering more effective outcomes, the estimated impact on cost-benefit ratios is discussed at the start of the VfM section. Furthermore, opening the contracts to international companies could support them to enter the Colombian market through building local understanding, networks, and experience. This could support the greater trade and investment relationships between Colombia and international markets after the life of the Programme.

The evaluation found a “good level of understanding of VFM principals across the PF Team, CAF and Findeter”. FDN were not yet a full implementing partner during the evaluation process.

Economy
The Colombia Programme offers contracts through competitive bidding for PF Commercial Framework companies, and, if that fails, to open international competitive procurement. UK non-CF companies, as well as local and international companies, can enter into consortia with PF CF companies or compete as ‘Prime Suppliers’ (i.e. leading the contracts) through the secondary route. Quotes for project values in market surveys have typically been cheaper with local companies. This could mean there is higher economy VfM arguments for using local companies. These economy VfM considerations would need to be weighed against efficiency and effectiveness considerations. Agritech grants, co-funded by the implementing agencies, are the only projects able to fund capital equipment purchases, however this capital does not sit on HMG books and is low-cost scientific equipment such as sensors and mobile data devices.

Efficiency
The Programme faced significant efficiency challenges early in the year, as internal supplier processes took much longer than anticipated, and information from suppliers was unreliable at times. This caused delays getting contract ToRs ready for market. This would have likely lowered the number of infrastructure projects which the Programme could support if left unaddressed. If the Programme could not convert its funding into meaningfully supporting infrastructure projects, their VfM in terms of efficiency would be poor. However, the Programme team and implementers worked hard to address these issues in the latter half of the year, including the replacement of some key management positions in the IPs, which has improved the reliability of management information and sped up internal approval processes. Overall this has led to a much better working relationship between the Programme and IP management teams. As a direct result of these changes, the Programme looks to be able to meet its targets at the end of this review period.

The PF Team are operating with an admin rate of 4.52% over November 2018 – October 2019. This is above the Prosperity Fund target of 3.5% for Programme team admin, however this is due to clawing back unspent funds. The long-run staffing model from the BC results in an admin spend under the 3.5% over the life of the Programme. The PF Advisers have experience of working in the Colombian sectors they oversee, giving them the required knowledge to be informed customers, hold implementers to account, and appropriately challenge private companies. This supports an efficient deployment and use of PF resources.

The Programme received no successful bids the first time that the Ibague and Valledupar sanitation projects were released in early 2019. This delayed implementation, but these are still on track to meet their targets this year. Lessons were learnt on the Rail strand underspend, which have been incorporated across all relevant implementing partner processes. The PF Team have added new requirements for multilateral implementers before funds are transferred. These include: i) conducting and concluding a full market survey and agreeing the value of the contract; ii) completing the final ToRs for the project tender; and iii) agreeing the date the tender will go out to market. This provides reassurance that the funds will be spent by the agreed timetable.

PF project contracts are awarded using the standard government approach to Most Economically Advantageous Tender, where technical scoring (i.e. what the supplier will deliver, and how) is mixed with cost; coupled with close oversight from IPs and PF Advisers. This is the main driver of efficiency.

Many of the projects now seek a co-financing option. This helps the Programme target more ambitious projects with its money, increasing its efficiency. For example, the Bogota – Zipaquira rail line feasibility studies have £2.5m of programme funding, coupled with £1.6m co-financing from the Department of Cundinamarca. The Manizales Intelligent Transport and Santa Marta Smart City projects have also provided some co-funding (£34k and £39k) from the respective municipalities. These co-investments demonstrate local government commitment to the project and they increase the likelihood of execution, thereby supporting effectiveness.

Effectiveness
The Programme has a robust Theory of Change for each of the seven activities. The causal pathways are backed up by evidence and key assumptions have been identified, which can be tested in future evaluations. The Programme’s evaluation found the Theory of Change was “sufficiently clear and logical to enable Programme partners to align their interventions to the Programme”, and “the causal pathways between most are identified and plausible”. This provides reassurance that the Programme interventions are able to lead to effective outcomes.

On top of standard evaluation criteria, subcontract bids will be scored on innovation. This presents a risk and opportunity in terms of Programme effectiveness depending on how novel the innovation is. If a novel approach successfully improves the type/level of outcome that can be achieved, then the new methods will have had an effective impact. However, if the new approach does not work as well as intended, then consequently the Programme will have a low level of effectiveness. This approach sits within the Programme’s risk appetite; the results will become apparent over time.

The PF Team and implementers work closely with both local and national government partners to ensure all projects have strong political buy-in, increasing their likelihood of success. Furthermore, there is evidence of the Programme working towards sustaining the impacts of the interventions. For example, the anti-corruption implementing partner (OCP) provides ongoing support to regions after their outputs are complete – this helps support short to medium term effectiveness. Another example is the Manizales Regional Competitiveness Commission, who have been working with neighbouring departments to share strengths, weaknesses, opportunities and learning based on the PF capacity building. This supports impact and effectiveness outside of the direct PF project.

The main risk to the Programme’s effectiveness is being unsuccessful in awarding contracts for feasibility studies in a number of its projects. If the Programme is unable to award these contracts, then the Programme will not be able to support large capital deployment/inflow to Colombia in its agri-insurance, infrastructure or regional competitiveness strands. The Programme and IPs (e.g. CAF/Findeter) engage the market at regular points to ensure the Terms of Reference (ToRs) for contracts are well constructed, and analyse variances in quotes to understand the underlying cost factors. This results in better ToRs and stokes market appetite for bidding.

Equity
Gender Equality & Social Inclusion (GESI) strategies have been put in place for all projects, giving the AR Team strong reassurance that GESI impacts are integrated into all the Programme’s activities. The PF Team hired an external GESI specialist consultant to work with implementers and they received support via DFID’s WoW initiative to train 157 of Colombia’s new mayors and governors on how to best integrate G&I into local development plans and infrastructure projects.

There has been a clear shift in the culture of IPs who previously did not fully understand, nor apply, GESI into their policy or project work. The IPs have advanced a long way on G&I since the start of the Colombia PF Programme. Partly as a result of this. Findeter is receiving additional PF support to fully integrate gender priorities in everything it does as a bank. This work is expected to commence shortly. The other IPs have also reported wider application of the PF GESI approach to other parts of their operations. This spill over effect can lead to VFM increases at scale in these organisations.

There are challenges in building gender equity within the Colombian-based, PF CF companies, particularly where STEM skills (strong maths/science/engineering abilities) are required. The PF Team, adhering to Colombian law, have a minimum target of 30% female staff working on their feasibility study contracts. Some CF companies have voiced their concerns about being able to meet this target, as there are significantly less women engineers in Colombia than men.

Logframe indicators are disaggregated by GESI components where appropriate, for example when monitoring the beneficiaries of projects. The table below from the first Colombia Evaluation and Learning (EL) report provides a brief description of how each Colombia PF activity, except rail as it was not sampled, integrates G&I priorities.

Sector	Activity	G&I Objectives
Institutional strengthening	Regional competitiveness	Projects aim to build capacity of officials in Regional Competitiveness Commissions (which include Governor’s Office staff) to ensure that they take G&I priorities into account in scoping, selecting and managing projects. / The Aerocafé project had to commission new socio-economic analysis as the previous G&I study was deemed insufficient. The Aerocafé Master Plan had new G&I and poverty dimensions added to it.
	Open public procurement	This activity considers the differences in fees that the government pays female and male owned businesses. It also addresses the lack of sex-disaggregated data.
	Corporate governance reform of Colombia’s National Infrastructure Agency (ANI)	A new governance structure for ANI will be designed and implemented with the aim of achieving gender balance in the new Board and greater female representation throughout the organisation.
Infrastructure	Urban development	The project focuses on influencing the working practices of municipal officials to ensure that infrastructure projects deliver benefits for women, vulnerable and conflict-affected communities and for people with disabilities. It aims to change mindsets and working practices by institutionalising regular stakeholder engagement and greater accountability towards these groups in infrastructure projects. / G&I issues in the Manizales Intelligent Transport project seeks to address are currently being identified and acted upon via community engagement and socio-economic analyses. This PF investment is expected to benefit women in particular as they tend to have less access to private vehicles than men.
	Rail development	This activity was not sampled in the first EL cycle.
Agriculture	Agri-insurance	This activity supports the design of agri-insurance products and services to take into account access issues faced, for instance, by female smallholders and producers.
	Agri Tech Catalyst Challenge Fund	This activity considers G&I explicitly, with clearly thought-through approaches and activities, mainly focusing on female smallholders and producers, as well as people who do not own land or own or rent small pieces of land. The seven projects aim to increase quality, productivity and incomes for farmers in cacao, banana, coffee and tilapia.

Summary of VFM findings from the Colombia Cycle 1 Evaluation Report

- VfM systems are in place across the PF, with a focus on economy and some evidence of considering effectiveness, efficiency and equity.
- VfM frameworks are not consistent across the programme. Rather, each implementer uses their own VfM assessment criteria, for example when scoring bids.
- Understanding of the implications of contracting UK firms is focused on economy. There is an argument that UK firms may be more efficient (for example with better knowledge, skills etc.) but there is no evidence to prove this.
- VfM is reported against in the AR, not the regular quarterly reports, although the PT has agreed to introduce this following the evaluation findings workshop.
- CAF and Findeter were initially selected due in part to low management costs, although other aspects were also considered, for example experience, networks and track record in Colombia.

Source: Colombia Programme Cycle 1 Evaluation Report, by the Prosperity Fund Evaluation & Learning suppliers

The Colombia Cycle 1 Evaluation Report useful and insightful. The findings are in line with the AR Team’s views. This evaluation document will be published in the near future in line with the Prosperity Fund’s transparency framework.

Quality of financial management
A supply chain mapping exercise has been undertaken as part of this AR to support fiduciary risk assessments and management. The Programme reviewed and approved the implementer approach to Due Diligence. The previous AR had a recommendation (no.2) to more proactively monitor CAF’s spend. This recommendation have been achieved over the course of this year.

The Foreign & Commonwealth Office has just completed an audit of the British Embassy in Bogota. The audit included a full review of the PF Programme and the PF scored the maximum “substantial” or green traffic light. In addition, the IPs also have an annual external audit of their finances and procedures including PF resources. These are forwarded to the PF Team for review. Over the past year, CAF and Findeter received positive external audits.

In 2018, Innovate UK transitioned from being an agency of the UK’s Department for Business, Energy and Industrial Strategy (BEIS) to becoming a UK Research Council (RC) called Innovate RC. As a result, the Colombia Agri Tech Catalyst Challenge Fund no longer fits with the new IRC agenda. This transition has resulted in some delays in IRC’s management of the activity, for example, submitting quarterly and annual reports on time. The other IPs, however, do submit their reports on time and with good accuracy. Last financial year there were some difficulties with Findeter, but the change in the management team there means that compliance in all respects has improved immensely.

As most of the implementers are large development banks, they have a track record lasting decades and are well staffed to provide robust financial management. As is usual practice with developmental banks, funding is typically provided upfront. There are associated risks with providing funding quarterly in advance, however the banks do not disburse payments to contractors until products and outputs meet the required quality standards. These outputs are priced as a percentage of contract values and are therefore completed to satisfaction at the contractor’s expense. This encourages a quick delivery at the required quality level. In some projects, there are ‘success fees’ so that if feasibility studies successfully secure execution funding, the contractor is rewarded for a good quality output. This ensures incentives are aligned.

The Programme faces funding risks (both positive and negative) depending on exchange rates. The IPs OCP and CAF are paid in US Dollars and Findeter in Colombian Pesos. Innovate UK is paid in GB Pounds, however some exchange rate risk may still occur if the smaller grant-funded projects are purchasing Colombian goods and services.

Assessment of whether the programme continues to represent value for money
Overall this AR finds that the Colombia Economic Opportunities Programme offers good VfM. This finding is supported by the independent EL report produced earlier in the year. There are some questions around the Programme’s approach to economy given the price differentials between local and international suppliers, which can only be answered in time by investigating their efficiency and effectiveness. The AR found reassuring evidence that the Programme is well positioned to achieve good efficiency. While it is too early to judge effectiveness, there are mechanisms put in place which provides reassurance that the Programme is likely to achieve reasonable effectiveness, even when considering the reduced outputs in the Urban Development, Rail Rehabilitation and Regional Competitiveness activities. There is clear evidence that equity is embedded throughout the Programme’s work. The Programme faced implementation and timing problems earlier in the year which threatened its ability to deliver agreed outputs and outcomes, however steps were taken to address this and new processes have been put in place. These improvements should enable the Programme to deliver to time and budget over its life, provided further risks on contracting do not materialise.

It is important that the PF Team continue to monitor and control risks which could damage the Programme’s VfM position. The key risk to the Programme’s VfM is the successful tendering of contracts through IPs on medium to large projects (CAF/Findeter/FDN). If contracts are delayed, or no successful bids are received, then the Programme will not be able to deliver its projects and achieve the desired outcomes. It looks likely that, over time, there will be a mix of both local and international companies delivering contracts. Future reviews and evaluations could investigate whether international companies were more efficient and effective than local companies. Those reviews and evaluations could provide useful learning for future ODA-funded work in Colombia.

Recommendations
1. The PF Team, working with the JFU Economist, more systematically analyses cost-drivers across the seven projects to identify appropriate mitigating measures.
2. When reporting Colombia PF Programme budget figures, the PF Team to use past financial year numbers combined with forecasts for the year in which the AR is taking place.
3. The PF Team to monitor and control risks which could damage the Programme’s VfM position.
4. The PF Team to investigate whether international companies are more efficient and effective at delivering high quality feasibility studies than local companies by reviewing and evaluating the data collected from the first set of rail, urban development, regional competitiveness and agri-insurance projects. This information to be used to decide routes to market for future PF Colombia projects.

Date of last narrative financial report
Date of last audited annual statement

## E: RISK

Overall risk rating:
Moderate
Overview of Programme risk
Risk: Change of key local government stakeholders during regional elections on 27 October 2019.

The current local politicians support the Programme interventions. If new politicians do not support the interventions, then the Programme could face significant disruption and have to start again in different municipalities and departments. This would result is loss of sunk-costs, time and political capital, as well as delaying the achievement out outputs/outcomes.

Mitigation: The PF Team and IPs proactively engage with candidates across the political spectrum to inform them of ongoing and planned PF investments. This work began in the run-up to the elections and continued during the Santa Marta Capacity Building event (12 to 15 November 2019). Further engagement will take place via regional visits and BE Bogota Road Shows to our four new cities (Cartagena, Buenaventura, Bucaramanga and Villavicencio) in 2020.

Risk: Delays in procurement and/or lack of bidders for contracts

Procuring effective contractors to perform feasibility studies is a key driver within this Programme. Delays could occur from suboptimal drafting of ToRs having to undergo multiple re-drafts. Even with a well written ToR, there is no guarantee that the IPs will receive good bids. This may result in either price increases to entice a higher number of bidders, or repeating the tender process with non-CF companies. This would make it challenging for the Programme to achieve its desired outputs on time.

Mitigation: The PF Team work with implementers to conduct early market engagement events and market surveys with all potential suppliers to test market appetite for the work, receive feedback on key issues/barriers which would impact bidder’s desire to compete for the contracts, and source a range of indicative quotes. New internal processes have been put in place at CAF to fast-track legal reviews of PF contracts. The costs for various contracts including rail and sanitation projects were higher than expected and this required new negotiations and / or a second round of market surveys. Co-financing from local municipalities has also become a priority as it increases the overall pot of resources available and strengthens commitment of local stakeholders to PF projects, such as the case of the Bogota to Zipaquira rail line.

Risk: Corruption / fraud related to a project

This could result in UK funds being misappropriated. This scenario would negatively impact the Programme’s ability to achieve the desired outputs and outcomes on time.

Mitigation: The PF Team and IPs employ: i) robust due diligence during project and local partner selection; ii) strong governance and proactive programme management to oversee each intervention; iii) MoUs and contracts with break clauses and milestone payments that allow termination; iv) supply chain mapping to identify areas of risk; and v) the FCO audit of the PF in October 2019.

Risk: Major economic downturn in either Colombia, the UK or global economy

This could reduce the availability of capital funds to invest in Colombian infrastructure from local, departmental, national and/or international funding sources. Lack of funding would then lead to Colombia PF projects not being implemented and Programme objectives not being achieved.

Mitigation: Assuming the Programme’s funding is unaffected, the feasibility studies could go ahead, but the Programme would have to accept that Primary Purpose and Secondary Benefit outcomes would be delayed until the credit markets and local government budgets recover. If local government budgets are affected, then the Programme should prioritise their work in locations with resilient finances or where national resources are still available.

Risk: The positive work undertaken by the Programme may not last beyond the Programme’s funding cycle, the benefits are not sustained and long-term change is not delivered

If the projects do not lead to a long-term change in their respective environments, or if they do not secure future funding (i.e. post 31 March 2022), then there is a large risk the benefits will not be sustained beyond the life of the Programme.

Mitigation: The PF rail and agri-insurance investment activities have long-term buy-in from the current political administration at national, departmental and local levels. The UK is widely considered Colombia’s main partner in these two areas. If successfully implemented, the two activities will have benefits that last decades. The digital tools for the open procurement work are already in place, which enables other actors to take forward the transparency work after the Programme ends. The ANI reform activity only lasts two years and will achieve its objectives before the end of the Colombia PF Programme.

The Regional Competitiveness agenda is led by Colombia’s Presidency (like UK Cabinet Office) and is supported by several donors including the World Bank, the Inter-American Development Bank, Canada and Switzerland. It is designed to operate outside of political cycles, so provided local buy-in remains the same, the benefits should continue after the life of the Programme. Therefore the main risk remains in the scalability and sustainability of the Agri Tech and urban development projects which, in turn, depends on international desire to enter or remain in the Colombian market, the availability of quality Colombian infrastructure contracts and a supportive financial context.

Outstanding actions and recommendations from risk assessment
None
## F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The Colombia PF Programme began implementation on 1 April 2018. The original CAF and Findeter MoUs, signed in November 2017, had to be amended in mid-2018 to allow both implementers to use the PF Commercial Framework to procure suppliers. The seven activities are either on track or close to being on track.

Throughout the year it was necessary to make the following MoU amendments:

- An amendment of the CAF MoU was approved on 12 March 2019 by PF team; the legal team of CAF send their approval on 9 July 2019 adding new clauses that covered additional resources for the Magdalena Tilapia Value Chain project and for the implementation of the three PF Global Infrastructure Programme (GIP) tools in the AeroCafe project. The amendment signature was dated 23 July 2019.
- An amendment of the Findeter MoU was signed on 8 February 2019. This covered an increase from 4 to 10% to cover Findeter’s management costs of PF projects.
- Another amendment of the Findeter MoU was signed on 5 June 2019 to allow the return of £2.5m to the Embassy for the Bogotá-Zipaquirá rail project though this project did go out to market in September 2019 and the resources were reallocated to Findeter for it.

Performance of partnership(s)
CAF
The internal approval processes of CAF take a long time. This has strained the relationship at times due to lack of implementation progress. The PF Team had to escalate the issues to the National Director of CAF twice in mid-2019. However, the relationship remains strong and we are addressing challenges as they arise. CAF quarterly and annual reports are the most comprehensive and professional that the Colombia PF Team receives. Two PF Advisers – Governance and Agriculture - meet with the CAF Team regularly.

FINDETER
- UK companies have complained about some aspects of Findeter’s contracting process saying they are overly difficult or inflexible. The PF Team has worked with Findeter staff to address each challenge one by one. Early market engagement events and market surveys have helped to develop direct relationships between many PF CF companies and Findeter. There has been a noticeable improvement in this area.
- Lack of implementation progress became apparent at the end of 2018 and continued to March 2019. The PF Team had to escalate this issue to the CEO of Findeter twice. The whole Findeter team was changed. The new managers at Findeter received written praise in May from the former Colombia PF SRO for a complete turnaround in progress and for bringing the projects back on track. The PF Infrastructure Adviser meets with the Findeter Team regularly.
- Two projects under the Urban Development activity were delayed due to political uncertainty in Santa Marta. Findeter has provided additional technical support to the Mayor’s office. The elections on 27 October 2019 brought a new mayor and more political stability.

Innovate UK
Innovate UK (IUK) changed its identity in 2018 from an agency of BEIS to a UK Research Council. This transition meant that IUK changed its focus to academic research prioritising innovation and intellectual property creation.

OCP
OCP always delivers their work on time to a high standard. The Governance Adviser meets with them on a regular basis.

Changes in the Delivery Plan
Originally, Findeter was going to manage all aspects of the Open Procurement activity. Open Contracting Partnership (OCP) was subsequently identified as the ideal agency to implement the procurement capacity building in the regions. However, being based in the USA and unable to accept payments in Colombian pesos, BE Bogota took over the relationship with OCP and developed a project proposal and grant agreement with them. Currently, it is still planned for Findeter to manage the other half of this activity with Colombia Compra Eficiente, the national procurement agency, and local civil society.

Similarly, when the new National Development Plan came out in November 2018, it became apparent that the planned PF rail investments were not the same as those prioritised by the government administration. The PF responded to this by working with government ministries and agencies to switch resources to the new projects and to channel a proportion of our resources through the government’s preferred IP – the Financial Institution for National Development (FDN). Since then, we developed a new MoU with FDN which was signed in August 2019. The first rail project – La Dorada-Chiriguana goes to tender in November 2019.

Asset monitoring and control
The Programme is not generating any assets nor is expected to later on.

## G: BUSINESS ENVIRONMENT

How has the business community and business environment responded to the programme?
- Several Colombian ministries, agencies and UK companies contributed to the design of the Colombian PF Programme in 2016/17. Since then, we have continued to build strong relations with host market influencers and decision makers and with UK and Colombian companies.
- During the past year, the PF CF companies present in Colombia, together with other local and international companies, have actively engaged with the bilateral Programme. Many have bid or are bidding for the 14 main tenders taken to market so far. They have engaged directly with CAF and Findeter during early market engagement events held in May and August 2019 and have submitted multiple responses to the market surveys which gauge the correct value of PF project contracts.
- Approximately 262 British and 180 Colombian or international companies have participated in the long list of non-ODA activities organised and managed by the PF Commercial Adviser over the past year (see list of activities below). This includes in-depth training for UK companies on how to identify and establish business partners or distributors in Colombia and on how to take advantage of the UK Export Finance (UKEF) offer of £4.5b for Colombia.
- The PF Team has supported CF and other companies to improve the PF contracting process from ToR design to submission of bids. This includes facilitating the creation of consortia to bid for PF contracts.

What role has non-ODA spending played in promoting Programme objectives?
Non-ODA has played a pivotal role in helping raise the awareness of the Colombia PF Programme and its commercial opportunities within the public and private sector in Colombia and in the UK. The Programme has created opportunities for building partnerships between local and UK companies; building the capacity of UK companies to work with local partners; and for showcasing UK innovation and expertise to Colombian public and private sector especially in agriculture and infrastructure.

During the past year, we have promoted PF commercial opportunities through:

Non-ODA activities and events which include outreach to relevant sectors (infrastructure, agriculture, financial services) in the UK via roadshows, forums, events and training; and in Colombia via workshops, conferences, events, trade missions, and Early Market Engagements.

Advertising all 14 PF-generated contract opportunities to the PF Commercial Framework companies on Contracts Finder, directly with UK companies already operating in Colombia, and amongst wider network of PF contacts, DIT Export Opportunities Platform, Chambers of Commerce, and ProColombia among other multipliers.

Different communication channels, including brochures, banners, one pagers, videos, impact stories, monthly commercial bulletin, and our campaign “Get to know the Prosperity Fund” published on Facebook and Twitter.

Non-ODA resources have also helped raise awareness of wider commercial opportunities between the UK and Colombia. In several cases, those resources attracted new companies to visit Colombia, participate in our wider Embassy commercial activities, and understand how they can pursue not only PF contracts, but other business opportunities in the country too.

In addition, non-ODA resources have also allowed us to promote UK expertise, experience, and innovation in specific industries to help position the UK as the partner of choice for Colombian projects.

Some of events used to achieve these objectives over the past year include:

- The National Infrastructure Conference on 20th – 22nd November where we have participation of 3 new companies to the market.
- Early Market Engagement on 14th December in Bogota.
- Roadshows on how to work with local partners in Manchester (25th&26th February) and Birmingham (28th February & 1st March).
- Prosperity Fund Latam Business Forum (27th February).
- Latam Infrastructure Event on 21st May in London.
- Colombia Insurance Event at Lloyds on 17th June in London. Around 100 people from the City of London, mainly from insurance companies, interested in doing business in Colombia.
- Colombia Inside Out on 18th & 19th June in London. There was an amazing participation of around 300 people and the main speaker was the President of Colombia, Ivan Duque.
- Roadshows on how to work with local partners in London (20 June), Leeds (25 June) and Edinburgh (27 June)
- Five UKEF workshops on 15th & 16th  August in Bogota with participation of 76 people from UK companies, Colombian companies in the infrastructure & construction sectors, and multilaterals and commercial banks.
- Expo-Agrofuturo: three-day exhibition and conference in September where we brought 7 UK companies to attend the event.
- Early Market Engagement for Agri-insurance contracts on 24th September.
- Launch of Rail & Competitiveness projects on 27th September to an audience of 100 people.

## H: MONITORING & EVALUATION

Evidence and evaluation
The Programme had a first cycle formative evaluation this year. It had a number of key findings, which largely reflect where the Programme is in its cycle. The full evaluation will be published in the near future once internal PF transparency processes have been completed.

It found that it is too early to assess the likely contribution towards intended outputs and outcomes in the Theory of Change (ToC) as well as unintended consequences. It was positive about the umbrella ToC and its links to the Fund level ToC, making it more likely to achieve positive outcomes. The Programme’s alignment to national and regional plans increases the likelihood of interventions and benefits being sustained beyond the life of the Programme. This is supported by Programme activities including conditions on financial and environmental sustainability.

The initial assumption that international companies would be interested in partnering with the Programme has started to be tested, as they have encountered hurdles including contextual knowledge, language skills, and cost differences between international and Colombia firms.

The PF Team has undertaken both formal and on-the-job learning, including with delivery partners. They have made adaptions based on the lessons learnt, including on the logframe and ToC. The PF Team actively engages in sharing lessons with other Fund stakeholders across both Latin America and other PF regions.

Monitoring progress throughout the review period
The PF Team monitors Programme progress through the governance structures (IPRG, SG and PSAP); the AR process; the quarterly and annual reports received from IPs; project and official visits; early market engagement events and non-ODA activities (covered elsewhere); and through media reports.

Internal Progress Review Group (IPRG) meetings involve a full review of Colombia PF Programme activities, primary and secondary benefits, risks, finances and future plans with a wide range HMG stakeholders in London. IPRG meetings were held on 14 March and 8 August 2019. Topics commented on by London colleagues this year included supplier management, risks and financial forecasting.

The Stakeholder Group (SG) met on 14 February and 30 September 2019. This group composes the Colombia PF IPs and all our government stakeholders at national level. The main issues discussed this year were about building links and sharing lessons learned between the IPs and improved use of government networks, including the Presidency, to address programmatic bottlenecks.

The Private Sector Advisory Panel (PSAP) met on 14 December 2018 and on 1 October 2019, but in practice the group has met many times for early market engagement events and other Embassy commercial activities. The PSAP comprises the 10 PF CF companies with a presence in Colombia plus those other UK companies working close with PF and the Embassy. The PSAP conversations resolve almost solely on the PF contract opportunities and how to improve UK company access to them.

The AR process involved a review of documentation and work conducted to date, followed by a week of site visits, beneficiary interviews, and reviews of progress with implementers. Two independent reviewers were part of the AR Team. The Programme is continuing to work on baselines, milestones and targets for the umbrella programme-level logframe at intermediate outcome level and above. It is important that this work is complete for the next AR, so that the Programme can more accurately assess its likelihood of success and effectiveness in the future.

The PF Team has visited six of the seven Agri Tech projects over the past six months; sites of all of the Regional Competitiveness, Rail Rehabilitation and Urban Development projects; and attended a number of OCP activities. Agri-insurance and corporate governance reform of ANI do not yet require site visits. The overwhelming main takeaway from site visits is how much public officials and local communities appreciate the support of the UK government and the PF Programme. In almost every case, the UK is the only country working directly with departmental and municipal authorities to improve the lives of their most vulnerable populations through the introduction of UK innovations and technologies.

As the Colombia PF Programme has moved from planning to implementation phase for five of the seven activities, positive media coverage has similarly increased. The Programme has received good coverage on several occasions especially for its rail and AeroCafe investments. With our new Ambassador (and SRO), ambitions have increased to more comprehensively cover PF good news stories and to do so through more outlets including social media. The PF Agri Tech Luisa Vegan Chocolate story, tweeted by the DFID Secretary of State on 4 November 2019, is an example of how PF investments (in this case UK innovation improving chocolate quality and incomes for very poor, rural women) humanises and brings to life PF primary and secondary benefit objectives.

Recommendation
The PF Team to work with IPs to complete the remaining baselines, milestones and targets in the Programme-level logframe before the next Annual Review in November 2020.