Annual Review - Summary Sheet

PROGRAMME TITLE: Supporting Counter-Extremism Programme in Somalia
Country and Region:	Somalia / East Africa
IATI Unique ID:	CSSF-03-000026
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO)
Total Budget:	ODA: £19.20m			Non-ODA:
Budget FY18/19	ODA: £5.10m			Non-ODA:
Spend FY 18/19	ODA: £5.85m			Non-ODA:
Original Programme Start Date: March 2015		Planned End Date: March 2021
Outputs					Score
Rehabilitation: Beneficiaries develop / enhance knowledge, skills and attitudes in an environment conducive to positive change					A
Support to reintegration: Beneficiaries enhance their prospects for sustained socio-economic reintegration					A
Support to FGS: FGS enhances its capacity to deliver the National Programme					B
Overall output score					A
Outcome Assessment: The programme has made great progress in improving conditions at the Serendi rehabilitation centre and developing its operations and education offer. However, the theory of change (ToC) needs to be revisited to assess the rationale that encouraging defections through a rehabilitation offer can meaningfully weaken Al-Shabaab.
Outcome Score: B			Risk: High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	N/A	A	A	A	A	B
Risk Rating - low/medium/high	N/A	High	High	High	Medium	High
*output/outcome scores
How has the programme changed during this period? Two projects ended during the period paving to new CEP programme strategy was developed

What support did the UK provide in FY 18/19?
The Counter Extremism Programme (CEP) aims to weaken Al Shabaab (AS) and undermine its appeal by encouraging people to permanently (and where appropriate, publicly) leave the organisation. The programme intends to achieve its objectives by:
1. Funding a low-level defector rehabilitation centre to provide a means by which rank and file fighters looking to leave Al Shabaab (AS) can defect and reintegrate into their home communities, and
2. Continuing to support the Federal Government of Somalia (FGS) to implement its National Programme for Treatment and Handling of Disengaged Combatants.

The rehabilitation is co-managed by the Defectors Rehabilitation Programme (DRP) under FGS Ministry of Internal Security (MoIS), and by an implementing partner.

Key results for FY 18/19:
- Continued to deliver capacity building to the DRP, rehabilitation centre staff, and the FGS across all Pillars of the Federal Government of Somali National Programme.
- Supported DRP in facilitating a pilot peer-to-peer defection mechanism.
- Supported the introduction of a dedicated phone line intended to encourage defections through family connections.
- Started the final phase of upgrading physical infrastructure at the Serendi centre.
- Supported more than 250 beneficiaries who left the Serendi centre having successfully completed the formal rehabilitation process. In addition, more than 160 beneficiaries who left the rehabilitation centre received a Reinsertion Support Grant to assist their reintegration into their respective communities.
- Developed a payment incentives scheme to replace reinsertion support grants (the incentives scheme is intended to provide financial support to beneficiaries during their stay at the rehabilitation centre while incentivising beneficiaries to complete their rehabilitation and care package).

Summary of progress and lessons learnt/actions taken since last review
- One of the keys lessons learnt was in 17/18 was that the approaches used by different rehabilitation centres in Somalia, suggest that there are multiple pathways for the rehabilitation and reintegration of former combatants.
- Formal defections to the FGS are not the primary means of defection from Al Shabaab, nor do all defections follow a single pathway. Notably monitoring reports indicate that there are informal defections and reintegration occurring at community levels.
- Mechanisms to enhance coordination between international actors, including donors, and implementing partners, have been set up. There are plans to further improve coordination;
- The management of the DPR are now more willing to engage proactively and take more responsibility for the rehabilitation centre and the National Programme.

Summary of recommendations for the next year
1. Consider revising the programme theory of change to take in to account new data which suggests that disengagement and defection from Al-Shabaab are not primarily driven by an individual’s access to a formal rehabilitation process.
2. Set value for money (VfM) benchmarks for the rehabilitation centre to ensure future resource allocation is linked to maximising the impact of the centre with the largest number of defectors.
3. Carry out research on informal defection and a make comparative analysis of the best approach for rehabilitation and reintegration, e.g. residential rehabilitation vs. community-based rehabilitation, or a blended approach. In addition, also carry out a VfM analysis of community-based rehabilitation versus residential centres to ascertain which one will offer better value for money.
4. Strengthen gender analysis across the CEP programme to understand the gender dimension of rehabilitation and reintegration. In particular, CEP should ascertain the value of community-based rehabilitation versus residential rehabilitation its potential to be more inclusive.
5. Prepare for the hand-over of the management of the rehabilitation centre to the FGS under the DRP of the National Programme for Treatment and Handling of Disengaged Combatants. The hand-over would ideally happen at the end of FY 2019/20.
6. Consider different options for delivering payments to the DRP, including output-based payments which would be based on the numbers of rehabilitated disengaged combatants.
7. Consider whether the rehabilitation centre should focus on mid-level rank disengaged combatants, or alternatively, act primarily as a referral centre for at-risk defectors who are not able to defect to their communities.
8. Ensure that there is conclusive evidence that vocational training provided at the rehabilitation centre increases defectors’ employability.
9. Carry out a conflict-sensitivity analysis on the use of the reinsertion grants, given the Third Party Monitor had identified that around a third of defectors report experiencing resentment from fellow community members due to receiving a reinsertion grant.
10. Continue to implement recommendations from last year to set up a job placement scheme with potential employers.