Annual Review - Summary Sheet

PROGRAMME TITLE: Somalia Human Rights and Vulnerable Persons’ Programme
Country and Region:	Somalia
IATI Unique ID:	CSSF-03-000025
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO)
Total Budget :	ODA: £3.0m			Non-ODA: N/A
Budget this FY	ODA: £1.3m - Amended to £0.5m			Non-ODA: N/A
Spend this FY	ODA: £0.5m			Non-ODA: N/A
Original Programme Start Date: April 2017		Planned End Date: March 2020
Outputs					Score
Promoting awareness of and understanding of human rights issues and abuses in the broader security context					C
Support effective prevention and response to all forms of sexual and gender based violence against women and children across the Federal Member States					C
Overall output score					C
Outcome Assessment: Despite some evidence of positive results from the programme, it was not possible to identify evidence of progress against the programme’s outcome indicators. The review team could not establish whether the programme is making a contribution towards a ‘stronger protective environment for children and those vulnerable to sexual and gender based violence, and improved access to quality services for survivors’ due to a lack of evidence, and a theory of change and results framework that have not been updated to reflect significant programme cuts. Additionally, results were only available for implementation that took place between October 2018 and January 2019. Nevertheless, the evidence available for activity delivered to date demonstrated some positive results
Outcome Score: C			Risk: Medium

Summary of Programme Performance
Year	2016/17*		2017/18*		2018/19*
Programme Score	A	A	(PCR)	(PCR)	C	C
Risk Rating - low/medium/high	Medium		Medium		Medium
*output/outcome scores
How has the programme changed during this period? / The Somalia Human Rights & Vulnerable Persons’ Programme was established in April 2017 as a result of a review that was undertaken of a previous CSSF human rights programme conducting similar activities since 2015. The review recommended an amended programme continue to be implemented, taking into account possible synergies in delivery and exploiting collective gains with other international actors who have a greater presence in Somalia. The implementation of activities in the exit phase of the original programme ended in September 2017, although an extension period was granted to complete desk-related activities and enhance sustainability (an impact evaluation was conducted in January 2018). During FY 2018/19, the current programme began funding activity through United Nations International Children’s Emergency Fund (UNICEF) for an interim period. This was done with current measures to combine the programme with the Somalia Stabilisation programme in FY 2019/20 in mind, and re-set this programme to run until March 2020.

What support did the UK provide in FY 18/19?

The Human Rights and Vulnerable Persons’ programme intended to strengthen the UK response to human rights concerns stemming from Somalia’s insecurity. In particular, the programme was aligned with the UK National Action Plan for Women, Peace and Security (WPS) 2018-2022, in which Somalia is a priority country, and the Preventing Sexual Violence Initiative (PSVI).
The programme originally intended to contribute towards two principle Outcomes:
1. The institutional framework for enforcing human rights and holding perpetrators to account in Somalia is strengthened, the Federal Government (FGS) demonstrates a growing independent capability to consider human rights issues and take appropriate action to respond to them and key legislation (for example on child protection, sexual violence) provide adequate protection and reflect international law.
2. Community-based protection for vulnerable people – particularly women and children – is strengthened; reducing instances of gender-based violence and making it easier for survivors to access support and advocate against sexual and gender based violence.
However, originally planned interventions that contributed to Outcome 1 were removed from the programme in the autumn of 2018 and funds diverted. The programme’s funding allocation was therefore reduced from £1.3million to £0.5million

Key results for FY 18/19:

The programme experienced significant in-year changes and a reduction in funding by two-thirds, therefore key results were measured against output (2) and relate to activity implemented between October 2018 and January 2019. These include:
1. The programme carried out project activities aimed at providing a holistic Gender Based Violence (GBV) prevention, mitigation and response services. Through this the programme was able to achieve the following ;
  1. Trained service providers in nine districts across the five states of Somali to ensure minimum quality services to respond to GBV, including support to 120 justice actors.
  2. Provided technical and financial support to service providers working on clinical, psychosocial, legal and safety services throughout Somalia (in total the programme supported 82 women, 73 girls, 6 boys and 3 men).
  3. The provision of GBV and protection from sexual exploitation and abuse mainstreaming training to 40 humanitarian workers from Somalia.
2. Enhanced child protection systems:
  1. Worked with Somali representatives to support the establishment of a federal-level social work programme, including a social welfare architecture by training of social workers and carrying out piloting activities in programme areas, and at the same time worked with Mogadishu University in establishing a professional and accredited social work training.
  2. Carried out a pilot of a schools-based protection programme, an innovative empowerment and transformation training programme for girls and boys in nine primary schools in Mogadishu and reaching an estimated 1,111 (596 boys and 515 girls).
  3. Reviewed existing community-based child protection structures and support partners to standardise minimum standards of care and referral procedures.
  4. Expanded the reach of ‘Communities Care’, a programme that provides community level support systems to women who are victims of rape, and removing stigma related to FGM. This was achieved by; supporting local organisations in the delivery and scaling up of Communities Cares interventions in nine locations in Somali. As a result 120 community members (60 male and 60 female) participated in the training on the programme, including service providers, to strengthen the referral mechanisms at the community-level.

Summary of progress and lessons learnt/actions taken since last review

The programme made progress against one strand of activity despite challenging circumstances (caused by delays in implementation and a reduction in programme scope and funding). The programme builds upon earlier UK support and provides sufficient resources to ensure the UK can leverage multilateral delivery partners and deliver innovative support that complements existing UK interventions. Through UNICEF, the programme worked towards improving safety for women, girls and children by supporting protective attitudes and behaviours, and improving the capacity and policy framework available for responding to survivors of abuse and for providing professional support. The programme also provided capacity building to civil society organisations in nine regions of Somalia, developed a sustainable and community-based approach to preventing gender-based violence and protecting children, built the state-level competence of wider service providers and maintained pressure at the national level to deliver appropriate legislation that formalises protection for these groups. Alongside interventions, the programme helped to fund key research and evaluation activities of community level impact through John Hopkins University, contributing to valuable lessons on innovative social norms change programming.

Due to the new nature of the programme team’s partnership with UNICEF in order to deliver activities, as well as the significant changes the programme underwent this financial year, it has not been possible to meaningfully evaluate key lessons learnt from previous reviews.

Summary of recommendations for the next year

1. A comprehensive review of the theory of change should be undertaken, including a review of any new evidence and rationale that may influence programme design (as part of the Somalia Stabilisation Programme). As part of this, the team would benefit from articulating why that intervention model has been chosen and how it interacts with other interventions.
2. A mapping exercise of UK and external interventions in Somalia relating to or complementing efforts on human rights should be undertaken to avoid possible duplication and ensure opportunities for collaboration are not overlooked; the programme team have already initiated activities to implement this through their external Monitoring, Evaluation and Learning (MEL) partner and should ensure recommendations are implemented. The John Hopkins research lends itself well to lesson-learning and sharing activity, and the team should consider using this to create an opportunity for knowledge sharing in the sector, such as with the DFID SNaP programme.
3. The programme team should look to significantly improve their use of programme management tools and documentation (with support from the MEL partner where necessary). This includes:
  1. adapting the objectives, theory of change, and results framework to changes occurring in the programme design in a timely and accurate manner during the year, with documented version control;
  2. having a complete and meaningful results framework with all milestones and targets established, jointly agreeing any updates to these with implementers;
  3. revising all output and outcome indicators to better align with currently agreed programme activity and objectives, with accurate weightings, and disaggregated by sex, age, disability and location where possible.
1. Requirements of implementing partners’ reporting should be clarified with UNICEF and explicitly tied to the needs of the programme team and CSSF reporting cycle. This should include progress and end-of-year reporting that aligns with the programme’s results framework. The programme team should introduce an annual review recommendation tracker to ensure valuable and relevant recommendations from annual reviews are implemented in a timely manner.
2. In merging the Human Rights and Stabilisation programmes, the team should workshop a revised theory of change to explore areas of complementarity, including for example the locations in which interventions occur, the broader gender-sensitising of early recovery initiatives, and the possibility of doing additional work on preventing the recruitment of children in armed conflict.
3. Update Somalia Stabilisation programme risk register to reflect new human rights activity and consider potential new mitigation strategies, including learning from UNICEF’s approach to risk for the existing programme.