Annual Review - Summary Sheet

PROGRAMME TITLE: CSSF SOMALIA STABILISATION PROGRAMME
Country and Region:	Somalia
IATI Unique ID:	CSSF-03-000028
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Ministry of Defence (MoD).
Total Budget:	ODA: £6.2 million			Non-ODA: £0
Budget FY 18/19	ODA: £1.5 million			Non-ODA: £0
Spend FY 18/19	ODA: £1.5 million			Non-ODA: £0
Original Programme Start Date: April 2016		Planned End Date: March 2020
Outputs					Score
Government finds favourable conditions for the establishment and continuation of effective district councils					A
Gender and conflict sensitive approaches to grassroots reconciliation and political negotiations are developed by ERI (Early Recovery Initiatives) in collaboration with AMISOM (African Union Mission to Somalia), SNSF (Somalia National Security Forces), FGS (Federal Government of Somalia) & other stabilisation actors					A
Community driven activities identified and delivered through inclusive participatory processes (community, AMISOM, SNSF, MoIFAR [Ministry of Interior, Federal Affairs & Reconciliation] and FMS [Federal Member States]), supported with a combination of programme funds and assistance of other partners					A
Overall output score					A
Outcome Assessment: / The programme outcomes are on course to meet expectations. The programme has also continued to demonstrate flexibility in its ability to intervene at short notice. It has developed close linkages with both the civilian administration and the military, and can play a catalytic role bringing together civilian and military actors in a dialogue with communities that have been excluded from the political settlement. However, the outcomes and outputs have been changed several times which has made progress difficult to track. The programme now has a stronger MEL component, and it is expected that in FY19/20 the programme will be able to provide more robust evidence to show that outcomes have met expectations.
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	A	A	A	A	A	A
Risk Rating - low/medium/high	H	H	M	M	M
*output/outcome scores
How has the programme changed during this period?: The programme’s theory of change remains relevant and now has a stronger monitoring, evaluation & learning (MEL) component with a third-party monitor. More robust evidence against outcomes will be expected in FY 19/20.

What support did the UK provide in FY 18/19?
The programme aims to reduce local drivers of conflict in areas of Somalia recently recovered from al-Shabaab control and provide foundations for enduring local political settlements and stability that will allow the FGS & FMS to establish a sustained presence. The programme delivers improved community cohesion through inclusive community engagement and a set of upstream interventions, with both local and international actors that enhance civil-military coordination and build the capacity of relevant government institutions.

Key results for FY 18/19:
- A technical advisor was embedded in the Community Recovery Extension of State Authority/Accountability (CRESTA/A), a department within the United Nations Mission in Somalia (UNSOM), to support work on stabilisation transition planning between FGS, AMISOM and other partners.
- Through CSSF support to CRESTA/A, the Fragility Index & Maturity Model (FIMM) was developed which produced quarterly analyses for 16 districts used by FGS, FMS and donors to measure the districts’ performance, and plan for development and stabilisation interventions.
- The programme worked with the MOD to implement its Gender and Human Rights (G&HR) compliance training for soldiers. This training demonstrated the SNSF ability to train, adopt and deliver a training of trainer (ToT) approach towards (G&HR) training in the armed forces.
- The programme brokered stronger relationships with FGS members resulting in better political access and influence with close partners and other international donors demonstrating the UK’s unique approach to early recovery stabilisation. As a result;

  - AMISOM included stabilisation activity into their mandate & the AMISOM Concept Of Use (CONOPS);
  - The Somali Ministry of Defence (MOD) and the Somalia National Army Head Quarters (SNA HQ) adopted a more systematic approach to managing human resources and to the delivery of basic soldier training;
  - Relationships with the US and EU Training Mission were improved which resulted in the two missions agreeing to support the Civil Military Cooperation (CIMIC) team in the SNA.
  - The Office of Prime Minister and MoIFAR have also taken ownership of stabilisation planning and delivery in newly recovered areas.

The programme supported institutional capacity building for AMISOM Troop Contributing Countries (TCCs) and the SNSF, aimed at reducing potential violations and to enable them to respond more effectively to survivors of abuse.

Summary of progress and lessons learnt/actions taken since last review
- The programme has improved synergies between upstream and downstream partners by developing systems to track the various sets of trainings provided to SNA, AMISOM, FGS, FMS, MOIs, civilians and other Somalis.
- The programme has expanded early recovery initiatives by hiring Community Outreach Officers (COOs) to support the Community Based Liaison Officers (CBLOs) who work in partnership with AMISOM. Additionally, the programme uses local implementers to allow for expanded ERI coverage to more remote regions of the two target states.
- The programme has continued to use the Fragility Index & Maturity Model (FIMM) as a tool to determine which districts the ERI project should engage, and develop a research methodology for conflict analysis to complement data generated by FIMM.
- The programme results framework has ‘strengthened programme outcomes’ and ‘conflict sensitivity markers’.
- In response to recommendations in the 17/18 annual review, the programme moved away from implementing Quick Impact Projects (QIPS). The ERI project is now conducting community reconciliation and community dispute resolution work in Jubbaland and South West States.
- The team has improved gender sensitivity across the programme. To ensure women are meaningfully included in decision making process, women have been included in the recently formed Conflict Dispute Resolution (CDR) committees.
- Through the MEL partner the team has started developing a system to map out trained trainers and stakeholders who would be supportive of community reconciliation on the ground. This is expected to be completed in FY 19/20.

Summary of recommendations for the next year
1. Building on the experience of engagement in Newly Recovered Areas (NRAs) in Lower Shabelle (Bariire and Sabiib villages), scale up the ERI project and expand the programme coverage to other NRAs;
2. Develop an “Operations Manual” for the overall Stabilisation Programme in order to better guide the work of the implementing partners;
3. Continue to improve operational synergies between the programme upstream and downstream work;
4. Continue to improve synergies with Counter Extremism Programme (CEP) in order to enhance the assumptions underpinning CEP Theory of Change;
5. Ensure that ERI activities directly contribute to the process of district council formation under the government-led Wadajiir framework for local governance;
6. Clarify the aim of the conflict resolution component of the ERI project - that is, whether it should deal with any conflict that can potentially generate instability, or rather focus on improving social cohesion between government-affiliated sub-clans and sub-clans that are excluded from the political settlement and/or have a history of grievances against majority clans and/or government authorities;
7. Ensure that there is an exit strategy for conflict resolution activities by establishing partnerships with other actors who will take over and will support parties that have been affected by conflict to agree on rules on how to share resources, to avoid the risk of resurgence of new violence;
8. Establish clear criteria for targeting and ensure that prioritization of areas is based on analysis of sub-clans stance vis-à-vis the government and Al-Shabaab;
9. Establish clear criteria for phasing out as soon as early stabilisation has been achieved and other stabilisation actors have engaged;
10. Improve synergies with the human rights work and the Security Sector Reform programme to ensure that SNSF are accountable to the communities that they are meant to protect and are able to provide services to the population (e.g. first aid or engineer work);.
11. Commission the Third-Party Monitor to produce a quantitative assessment of whether the programme continues to represent value for money. Following this, the MEL unit could undertake a final evaluation of the current phase of the programme, which will include recommendations on exit strategy and sustainability.