Annual Review - Summary Sheet

PROGRAMME TITLE: CSSF Ukraine
Country and Region:	Ukraine, Eastern Europe and Central Asia
IATI Unique ID:	CSSF-05-000004
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DfID), Ministry of Defence (MoD), National Crime Agency (NCA) and Her Majesty’s Revenue and Customs (HMRC).
Total Budget	ODA: £33.2m			Non-ODA: : £11.9m
Budget this FY	ODA: £10.01m			Non-ODA: £4.04m
Spend this FY	ODA: £10.4mm			Non-ODA: : £3.866m
Original Programme Start Date: April 2017		Planned End Date: March 2020
Outputs					Score
Conflict Management & Peace Building					A+
Military Capacity Building - Operation ORBITAL					B
Defence Institutions & Governance - SDAs					B
Organisation for Security and Cooperation in Europe					B
Anti-Corruption: Institutions more effective operationally & developed Institutionally					A+
Overall output score					A
Outcome Assessment:
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	B	B	B	B	A	A
Risk Rating -		Medium	Medium	Medium	Medium	Medium
*output/outcome scores
How has the programme changed during this period? / This was a turbulent year witnessing escalating conflict tensions, the imposition of martial law, autocephaly[1] and a presidential election. The uncertain security and political situation placed demands on the Programme. There was an unexpected request to provide funding to the monitoring mission for the Presidential elections in March. The CSSF met this need by re-allocating £120K. The UK was the second largest contingent to the Organisation for Security and Cooperation in Europe’s (OSCE) Office for Democratic Institutions and Human Rights’ (ODIHR) monitoring mission. Also in 2018 the CSSF funded a pilot project by CMCoord (Humanitarian Civil - Military Coordination) in response to high level requests. There were also adjustments made in the financial plans throughout the year.
[1] Autocephaly: On 5 January 2019, Bartholomew I, the Ecumenical Patriarch of Constantinople, signed the tomos that officially recognised and established the Orthodox Church of Ukraine and granted it autocephaly (self-governorship) making it independent from the Russian Orthodox Church.

What support did the UK provide in FY 18/19?

The CSSF programme continued to provide support to the UK Government’s Ukraine strategy which is ambitious and complex, effectively combining CSSF, Good Governance Fund (GGF), development and humanitarian resources, to deliver effect. The purpose is to deliver the UK strategic objective of a united, stable, sovereign and resilient Ukraine. The programme delivers a wide range of projects, including some that are the result of political commitments, (e.g. Operation ORBITAL and the Organisation for Security and Cooperation in Europe’s Special Monitoring Mission to Ukraine OSCE SMM). The UK continued to help Ukraine implement economic, governance and defence reforms, build resilience and deal with humanitarian needs. In the financial year 2018/19, the UK government provided over £35 million of support through over 70 project initiatives in seven priority areas: anti-corruption; governance and reform; communications; education and culture; conflict, stability and security; human rights; and humanitarian.

Headline results for FY 18/19:

The CSSF extended its support to conflict affected communities. The rights of conflict affected people have been increasingly secured as a result of the UK funded network of 23 Liaison Officers which has aided over 111,000 Internally Displaced Persons (IDPs) this FY.
- The UK continued to develop the capacity and resilience of the Ukrainian Armed Forces through the Operation ORBITAL training mission, the Special Defence Advisor (SDA) Office, UK representation on the Defence Reform Advisory Board (DRAB) and contributions to NATO. Operation ORBITAL has adapted to developments, including to naval requirements, and trained around 17,000 Ukrainian Armed Forces troops since 2015.
- Ukrainian state institutions strengthened through seconded ministerial advisors (Ministry of Foreign Affairs, Defence and Ministry of Temporarily Occupied Territories) and support to anti-corruption law enforcement agencies.
- CSSF investment in supporting humanitarian mine action successfully strengthened legislation and raised it up the agenda.
- CSSF funding also enabled the UK to be the second largest contingent of the ODIHR monitoring mission during the presidential elections, strengthening public trust in the democratic process.
- The UK is the largest donor to the United Nations Populations Fund UNFPA project to address gender-based violence. It has supported the development of a national multi-sectoral response mechanism with a specialist network of shelters, police, psychological support, correction programmes and national hotline.

In sum, the UK through the CSSF programme is leveraging influence within Ukraine and amongst international partners. The ability of the programme to anticipate and respond to political and security developments in an effective and agile manner has enabled UK assistance to flex and to meet priority needs in support of policy objectives.

Summary of progress and lessons learnt/actions taken since last review

The CSSF team has responded to a number of reviews during the last year (the Independent Commission for Aid Impact ICAI, Gender audit, the Annual Review 2017-18, conflict sensitivity review, CSSF Review of UK contribution to Defence in Ukraine and FCO audit). It has made good efforts to improve relationships with key implementers, donors and stakeholders within the Ukrainian government. The CSSF programme delivered tangible results which made a difference to the population and provided leverage for political access and influence within the Ukrainian government. The programme team in Kyiv has increased in size from 9 to 13 people. Programme management has benefited from the additional personnel and this is reflected in stronger programme and project management skills, and more robust results demonstrated through improved Monitoring and Evaluation (M&E) and Value for Money (VfM). There is evidence of an improved understanding and application of CSSF programmatic requirements expected by the Joint Funds Unit (JFU), delivery agencies and contracted supporting implementers. Despite the fact that a significant percentage of the programme is not reporting directly in CSSF format for spend or impact, which makes the task of the programme team more challenging, the review team determined that the programme merited an ‘A’ score for outputs and outcome, having met expectations, or being on course to do so. This is based on good evidence of impact against the theory of change and the strong active management of delivery of the CSSF[2] element against the UK Government’s strategy for Ukraine.
[2] The programme document includes both Conflict Stability and Security Fund (CSSF) and Good Governance Fund (GGF) funded projects, and other funding streams are applied alongside CSSF (e.g. Multilateral Policy Directorate funding to the Organisation for Security and Cooperation in Europe’s Special Monitoring Mission to Ukraine)

Summary of recommendations for the next year

UK Government Strategy for Ukraine
1. That the contribution made by the CSSF programmes to delivery of the UK Government’s Ukraine strategy, both directly and indirectly, is communicated more clearly to all stakeholders.
2. A clearer articulation of the programme’s strategic fit against the UK Government Ukraine and Eastern Europe Strategies would streamline project management. (The current complex mix, spread, and sustainability of projects needs to be constantly monitored against a dynamic environment for realistic impact and delivery.)

Conflict Management & Peacebuilding

The scale of the programme’s success in Conflict Management and Peacebuilding should be captured and exploited more systematically, (perhaps using a modified version of a Political Assessment & Influence (PAI) tool), in order to maximise impact and influence and increase international coordination.

Military Capability (Operation ORBITAL)

MoD should ensure that timelines for accounting and reporting are brought into line with the CSSF framework requirements, and that secondary benefits are measured.

Defence Reform (SDAs)

There is limited understanding of the broad remit of work conducted by the SDA’s office.  Clearer communications of the project’s workstreams would significantly enhance stakeholder engagement.

OSCE

1. A clearer delineation of departmental project management roles and responsibilities for the OSCE is required to ensure VfM.  Visible systematic procedures to monitor and evaluate the SMM project are currently not in place.
2. A review should take place to assess the impact of the UK contribution to the OSCE SSM (It should assess the extra effect that CSSF funding achieves, on top of the £10m from the Multilateral Policy Directorate Fund.)

Anti-Corruption

The next CSSF tranche should consider how to continue to provide training to Ukrainian law enforcement officers and to encourage inter-agency cooperation. Support to the Ukrainian law enforcement agencies remains central to UK objectives.

Programme Management

To continue the solid improvements in programme management. In particular:
1. Engage with the National Security Council Ukraine strategy review to ensure a rationalised programme document.
2. Rationalise and streamline the programme results frameworks and risk registers.
3. Ensure that outcome indicators, milestones and targets are coherent, qualitative and time bound.
4. Explore how the CSSF reporting requirements might be lightened and simplified.
5. Continue to strengthen the links and synergies between policy and programmes in country.