Programme Completion Review - Summary Sheet

PROGRAMME TITLE: WESTERN BALKANS PROGRAMME
Country and Region:	Western Balkans – Albania, Bosnia and Herzegovina, Kosovo, Montenegro, North Macedonia and Serbia
IATI Unique ID:	CSSF-10-000001
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Home Office (HO), Ministry of Defence (MoD), Crown Prosecution Service (CPS), National Crime Agency (NCA) and Her Majesty’s Revenue and Customs (HMRC)
Total Budget	ODA: £54.61m			Non-ODA: £13.94m
Budget this FY	ODA: £22.35m			Non-ODA: £5.65m
Spend this FY:	ODA: £22.56m			Non-ODA: £5.14m
Original Programme Start Date: April 2015		End Date: March 2019
Outputs					Score
Peacekeeping/ Conflict Deterrence					A
Security Sector Reform					B
Reconciliation					A+
Governance					A+
Rule of Law					A
Countering Organised Crime, Fiscal Crime, Terrorism / Extremism threats and Illegal Migration					B
Preventing and Countering Violent Extremism					A
Defence Deployments and Capacity Building Programme					B
Countering Organised Crime					A
Bosnia and Herzegovina					A
Kosovo					A
Macedonia*					A
Serbia					A
Albania					A
Montenegro					A
Western Balkans Summit Activity					B
Stability					A
Serious and Organised Crime					B
Engagement					No score**
*Output pre-dates the referendum, now North Macedonia / **For FY18/19 the Engagement Results Framework was still being developed so the review team felt unable to score outputs but commented that evidence collected during the review suggests that Engagement is on track to achieve its outputs to a measurable degree in FY19/20.
Overall output score					A
Outcome Assessment:
Final Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	B	A	A	B	A	B
Risk Rating - low/medium/high	L/M	M/L	M		M
*output/outcome scores

What support did the UK provide in FY 18/19?
The single regional Western Balkans Programme started in FY15/16 and closed at the end of FY18/19. It consisted of three regional strands: Engagement, Serious and Organised Crime, and Stability. This single regional Western Balkans Programme will be succeeded in FY19/20 by a Western Balkans Portfolio, consisting of three regional programmes (which will replace the three aforementioned strands) and activity delivered through the Good Governance Fund (GGF) and other UK funding in the region. Unless otherwise stated, all references henceforth to ‘The Programme’ apply to the single regional Western Balkans Programme which closed at the end of FY18/19.

At the Western Balkans Summit in July 2018, the Prime Minister announced a further expansion to £80m by 2021. The uplift reflects Ministers’ wish for the UK to have a high level of ambition, including programming, in the region.

The programme was underpinned by the findings and recommendations of the Western Balkans Regional Joint Analysis of Conflict and Stability (JACS) (May 2017) and set out in the revised National Security Council Strategy (June 2017 – now known as the HMG Strategy). The programme was divided into three strands which grouped the priority drivers of instability in the region identified by the JACS. These strands were: (i) Engagement covering threats to the region’s EU and NATO direction of travel and UK engagement, including the UK-hosted Western Balkans Summit in July 2018, military and civilian secondments and our Defence Engagement programme; (ii) Serious and Organised Crime including delivery of capacity building training to improve countries’ fight against organised crime; and (iii) Regional Stability covering the ongoing legacies of the wars of the 1990s and vulnerabilities within the region (e.g. state capture, rule of law, corruption).

Key results for FY 18/19
There was some evidence of innovative programming across the region allowing the UK to punch above its weight in important areas including anti-corruption, social inclusion, transitional justice and accountability of institutions. Strong policy positions were backed up by programming which could be accessed quickly and used more flexibly when compared to other internationals. Results included:

- An anti-corruption project supported 47 recruitment processes for senior positions in public institutions in Kosovo, facilitating processes which prevent nepotism and corruption and support technical expertise. It also exposed institutions not willing to recruit through these open processes.
- UK funded projects worked to increase access to justice for conflict-related sexual violence (CRSV) survivors. In Bosnia and Herzegovina the UK supported the development and implementation of a new Law on Protection of Victims of Wartime Torture passed by the Republika Srpska National Assembly in June 2018. This law has enabled CRSV survivors to apply for the status of victim of wartime torture and have access to a set of rights including financial compensation and health insurance for the first time. As of August 2019, 86 CRSV survivors had applied for recognition of status and rights.
- A transitional justice project supported the International Commission on Missing Persons in establishing an operational group, made up of technical leads from governments across the region, for the Harmonized Database of Active Missing Persons Cases from Former Yugoslavia in the 1990s. Collaboration on these cases increased and 664 new cases were added to the database between January and March 2019.
- In support of tackling serious and organised crime and building on the commitments made at the Western Balkans London Summit in July 2018, there is now a UK-instigated and supported regional platform for intelligence sharing between customs administrations, involving all six countries of the region. Training and delivery of CSSF-funded equipment led to successful joint operations. Charges were brought against two companies and 24 persons, including eight customs officers.
- The UK continued to contribute to maintaining a safe and secure environment in the region through commitments to international peacekeeping operations in Bosnia and Herzegovina (Operation ALTHEA) and Kosovo (NATO-led Kosovo Force).

Summary of progress and lessons learnt/actions taken since last review
The programme has operated in its current format for the last three financial years (FY16/17, FY17/18 and FY18/19). Over that time it has consistently acted on recommendations from annual reviews and improved governance, programme structures, and in areas such as financial management. The recruitment of conflict advisers, a gender adviser and an M&E adviser, plus the work by the team to contract an externally provided Monitoring, Evaluation and Learning provider, will put next year’s Western Balkans Portfolio in a strong position to capture and embed learning in a more systematic and robust way.

When the programme started in FY15/16 there was an awareness of the need to reduce the breadth of the areas covered by the programme and increase depth in order to maximise opportunities for greater impact. Over subsequent years, larger regional initiatives have started to be developed (for example on political participation and rule of law) and there are already plans to look at this further over the coming financial year (FY19/20).

In FY18/19 the strands gradually introduced the structures needed to transition from being three strands under a single programme to becoming three programmes under a portfolio. This has included work to develop Theories of Change and Results Frameworks for each of the three strands. During the lifetime of the single Western Balkans Programme, there has been an awareness of the need to address shortfalls in M&E which are no fault of the programme team. The programme has been managing with short-term support from Stabilisation Unit Deployable Civilian Experts on M&E for many years which has hampered addressing previous years’ M&E recommendations and for this programme completion review meant that the final stages of development of the Results Frameworks were not completed. As a consequence, as a matter of urgency in FY19/20 each of the three programmes (formerly strands) must strengthen their Results Framework with appropriate indicators and milestones. The aforementioned new portfolio M&E adviser and commercial Monitoring, Evaluation and Learning contract will be essential for the strengthening of the Results Frameworks.

In addition each strand has developed a risk register and the portfolio risk register has been updated and significantly improved. Discussions every two months at the Portfolio Advisory Board and the Regional Strategy Board are a welcome development given the increased risk resulting from the scale and speed of the uplift over the next two years (FY19/20 and FY20/21).