Annual Review - Summary Sheet

PROGRAMME TITLE: Pakistan Rule of Law Programme (RoL)
Country/Region:	Pakistan
HMG Partners	Department for International Development (DFID), Ministry of Defence (MOD), Foreign and Commonwealth Office (FCO), Home Office (HO), National Crime Agency (NCA), Crown Prosecution Service (CPS)
Total Budget	ODA: £30.6m			Non-ODA: Not for disclosure
Budget this FY (post Supps)	ODA: £7.15m			Non-ODA: Not for disclosure
Spend this FY	ODA: £7.26m			Non-ODA: Not for disclosure
Original Programme Start Date: April 2016 (some components were already in place prior to this)		Planned End Date: March 2020
Outputs					Score
Improved cross-institutional standards to support safer security and justice outcomes					A
Strengthened internal mechanisms driven by results-based monitoring and resource allocation					A
Rights violations are prevented, and rights promoted and increasingly protected, of victims, witnesses, defendants and convicted persons, especially women and juveniles					A
Transparent, inclusive and data-driven public engagement and communication strategies to drive increased accountability of security and justice institutions					A
Overall output score					A
Outcome Assessment: Foundations laid for rule of law reforms with evident government and judicial ownership and tangible benefits for women and children. The programme is on course to meet its targets, so long as the new systems, rules and regulations, and the Roadmap approach can scale up implementation.
Outcome Score: A			Risk: High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	A+	A	A	B	A	A
Risk Rating - low/medium/high	High	High	High		High
*output/outcome scores
How has the programme changed during this period?: A number of projects have closed, commenced or transitioned to different implementing partners. The Gesellschaft für Internationale Zusammenarbeit (GIZ) component ended; Promoting Child Rights and Participation in Juvenile Justice System Reform Programme (PCRPP) started; United Nations Office on Drugs and Crime (UNODC) assumed responsibility for Sindh as well as Balochistan Rule of Law (RoL) Roadmaps; the MOD-led Counter Improvised Explosive Device (C-IED) component is beginning to diversify its approach and stakeholder engagement with an increased focus on extraction of forensic evidence; Serious Organised Crime (SOC) programme designed and piloting work to tackle Illicit Financial Flows (IFF) and Organised Immigration Crime (OIC).

What support did the UK provide in FY 2018/19?

1. DFID: Justice System Support Programme (JSSP) in Punjab and Khyber Pakhtunkhwa (KP), helping institutions improve their performance, deliver priority legal, regulatory and institutional reforms and strengthen the justice sector’s ability to coordinate and plan.
2. DFID: Justice programme in Sindh developing a Rule of Law Roadmap and quality assurance in the Karachi Forensic Science Laboratory (GIZ support ended December 2018).
3. DFID: UNODC in Balochistan and Sindh supporting roadmaps and quality assurance in the Balochistan Forensics Science Laboratory (Began February 2019).
4. DFID: Strengthening Accountable Justice Programme (SAP) supporting the implementation of child-sensitive justice in line with Pakistan’s 2018 Juvenile Justice Act (Began January 2019).
5. FCO: Counter-Terrorism project in Punjab increasing Pakistan’s civilian capacity to investigate, detain, prosecute and try terrorists in line with international standards and human rights norms.
6. MOD: Counter-Improvised Explosive Device (C-IED) project improving military and civilian capacity to disarm IEDs and collect forensic evidence for criminal investigations.
7. Home Office and NCA: Financial and immigration crime professionalisation project improving Pakistan’s capability to address illicit financial flows and immigration crime that affects the UK and Pakistan.
8. CPS: Support on extradition and mutual legal assistance - building Pakistan’s capability to use mutual legal assistance and extradition to address international criminality.

Key results for FY 2018/19:

- With GIZ support to develop a high-quality Sindh Rule of Law Roadmap in 2018, all four provinces now have Roadmaps, which are data-driven, provincially specific assessments of current performance, and will now be used to set strategic targets for reform. Under JSSP, Punjab and KP Roadmaps have developed implementation architecture, and with UNODC’s continued support, Balochistan Roadmap moves towards implementation.
- Government of Sindh took over funding the Quality Assurance Manager post in Sindh Forensic Science Laboratory, which was previously RoL programme financed. This demonstrates commitment to continue the initiative and be part of a national approach to upscale use of forensics.
- With the appointment of a Quality Assurance Manager in Balochistan, all four provincial forensic laboratories now have mentors driving up performance against nationally agreed standards.
- 1,793 potentially releasable prisoners were identified in four prisons in KP and Punjab - some 200 of these prisoners have been released to date.
- The Punjab Centre for Professional Development (CPD) is fully functional, delivering relevant and focussed training thereby strengthening capabilities of the prosecution service.
- Use of Special Measures, under the UK supported Punjab Witness Protection Act, begins to protect vulnerable witnesses, including children.
- Under the ‘UK-Pakistan Justice and Accountability Partnership’ announced in Sept 2018, the new SOC component has piloted projects for scale up in 2019 to mitigate IFF and OIC - two prime threats affecting the UK and Pakistan.

Summary of progress and lessons learnt/actions taken since last review

The programme has a much stronger line of sight to the programme outcome since the 2018 Annual Review, with new work on juvenile justice, and increased emphasis in the Roadmaps on citizen engagement, including developing Roadmap targets which will contribute to building citizen trust.

The RoL Roadmaps have secured provincial and federal government buy in and helped increase institutional cooperation and coordination. The quality has progressively improved with the latest Sindh Roadmap enabling civil society, the executive and judiciary to jointly own the strategic priorities. A key lesson is that international technical assistance, backed by a vision, strong strategic policy intent, and accompanying operational tools can help address challenges to joint working between Pakistani institutions.

Solid and sustainable foundations have been laid through policies, standards and inspection protocols governing the programme’s target crimes, including terrorism, homicide, and serious sexual violence. The UK has driven up the quality of 3 of the 4 provincial forensic laboratories to date (with support to a fourth, Balochistan, started in March). The UK is now also supporting the development of national medico-legal standards, using standard scientific criteria and collection methods, to help ensure that DNA evidence is admissible in court more broadly, and not just in cases of serious sexual violence as at present.

Significant progress has been made in a short period of time to further Child Justice and Child Rights, with the programme supporting Special Measures to protect vulnerable witnesses coupled with the engagement of children in setting the course of reforms. The British High Commission has seen that trialling justice system reform in a less disputed area, such as child rights, can open the door to wider engagement on more complex issues, using lessons learnt and systems developed in that space.

Cross programme learning has increased significantly over FY 2018/19 helping to bolster a growing sense of common purpose for the one programme. Improved linkages are noted between the forensics work and JSSP on how to improve evidential standards and between C-IED and other projects on the use of forensics in investigations.

BHC has started to draw lessons from its current focus on the criminal justice system and is recognising the need to understand the civil justice system too, as well as the complex interactions between Pakistan’s formal and informal systems. Learning from this is being used to inform the direction and priorities for future work.

Summary of recommendations for the next year

Support Counter-Terrorism and C-IED components as well as the new Serious Organised Crime (SOC) programme to strengthen and develop their Programme Management Framework (PMF) documentation aligned to the overarching CSSF RoL framework to enable them to evidence achievements and lessons learned.

Update the C-IED component for increased focus on strengthening civilian capability, without losing the clear gains achieved through support to Pakistan’s military.

Ensure that gender and social inclusion issues are mainstreamed more systematically across all programme components, looking at women and excluded populations such as people with disabilities as witnesses, victims and offenders.

As part of planning for future work on RoL, increase understanding of linkages in the wider political economy between formal and informal justice systems, and review what has and has not worked well over the past three years.