Annual Review - Summary Sheet

PROGRAMME TITLE: Egypt CSSF Programme
Country and Region:	Egypt, Middle East and North Africa
IATI Unique ID:	CSSF-06-000002
HMG Partners (LEAD in bold)	Foreign and Commonwealth Office (FCO), Ministry of Defence (MoD)
Total Budget:	ODA: £27.9m			Non-ODA: £0.4m
Budget this FY:	ODA: £10m			Non-ODA: £0.4m
Spend this FY:	ODA: £9.6m			Non-ODA: £0.3m
Original Programme Start Date: April 2016		Planned End Date: March 2021
Outputs					Score
Economic 1 - Support to the World Bank Trust Fund increases government capacity for structural reforms essential for inclusive growth, job creation and Economic participation					B
Economic 2 - Support to make financial policy and budget formation more transparent and accountable (Technical Assistance Facility)					A
Economic 3 - Provide financial, legal and advisory support to improve/actualise businesses.					A
Economic 4 – The Egyptian Centre for Economic Studies (ECES) to engage policy makers in high quality Economic research findings					A
Education 1 – World Bank - Capacity building and technical advice for development of the Project Operations Manual by the Ministry of Education and Technical Education (MoETE)					A
Education 2 – World Bank - Technical advice to help MoETE develop a communication strategy and communication plan for the reform program.					A
Education 3 - UNICEF - MOETE increasing its capacity to improve the quality of education across Egypt					A
Education 4 - UNICEF- Children in targeted communities are more actively taking part in formal & non-formal education, relating to each other more constructively & learning more effectively.					B
Education 5 - UNICEF- MoETE and development partners are using evidence produced by the project to inform and improve ongoing rollout of Education 2.0					B
Education 6 – Global Partners Governance (GPG) expertise provided to the Education Parliamentary Committee to improve policy processes					A
Equality 1 - Support Government of Egypt in strategic reform of Social Development policy					A
Equality 2 - Kvinna till Kvinna’s partner organisations (POs) have increased capacity to operate effectively and sustainably and have increased access to relevant networks (KtK)					A
Equality 3 - Kvinna till Kvinna (KtK) and POs advocate for changes to law, policy and practice that promote women’s rights and gender equality and an enabling environment for Women Human Rights Defenders (WHRD) (POs & KtK)					B
Equality 4 - Women’s rights organisations contribute effectively to the prevention of and protection against gender-based violence (GBV)					A
Equality 5 - Women’s rights organisations contribute to increase women’s participation in all aspects of decision-making					A+
MEL 1 - Increased capacity of CSSF Egypt staff and programme implementation partners (IPs) to use evidence					B
MEL 2 - A more accountable programme portfolio that captures lesson learning					A
MEL 3 - Evidence gaps within the embassy are addressed high relevant and high quality research					B
Migration - Egyptian authorities at national level are provided with UK international support to implement stronger migration management systems.					A
Security 1 - £250,000 contribution to Multilateral Force and Observers (MFO) costs of employing members of the local Bedouin population					A
Security 2 – 2x personnel subsistence costs					A
Overall output score					B
Outcome Assessment: B	Outcome Score: B		Risk: Medium/High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	A	B	A	A	B	B
Risk Rating - low/medium/high	Medium/ high	Medium/ high	Medium/ high		Medium/ High
*output/outcome scores
How has the programme changed during this period? The programme has largely remained the same, with the exception of a new expanded education project in Sinai being setup and splitting the World Bank Trust Fund into three different strands; mainly Economic, but also Education and Equality.

What support did the UK provide in FY 18/19?
The UK provided over £10m in financial support across themes linked to long-term drivers of fragility, namely economy, education, equality, local employment support in Sinai, and a monitoring, evaluation and learning project. Support was provided through a range of implementing partners including a number of international and local NGOs, International Financial Institutions, the UN and the direct provision of technical assistance. The programme was implemented by a core team of eight staff, including three technical advisors.

Key results for FY 18/19:
- Setting up and launching an education project in Sinai within nine months.
- Setting best practice on Monitoring Evaluation and Learning (MEL) by identifying strengths and weaknesses of project and programme design and the information systems underpinning the programme.
- Funded important and original research to inform policy making, such as the World Bank study on Women’s Economic Empowerment.
- The Establishment of the Eastern Mediterranean Gas Forum.
Summary of progress and lessons learnt/actions taken since last review
- Progress has been mixed at both output and outcome level. Those outputs that were broadly unchanged from last year (Economy 2 and 3, Migration, most of Equality) have continued to deliver against or exceed expectations, but some key outputs (Economy 1 and Education 4 and 5) have fallen slightly short of expectations, due to failure to deliver or set-up delays.
- The programme team have taken a methodical and robust approach to the last annual review recommendations, tracking and monitoring progress. The 2018 Annual Review made 21 recommendations; 13 of which have been acted on, one adapted (but which this review recommends again), but seven remain ongoing. More progress is needed (explained in part by staff turnover) and this year’s recommendations build on this transition.
- However, the number of project components has continued to expand since last year, risking stretching the programme too far for quality oversight or catalytic results.
Summary of recommendations for the next year:
1. A thorough review of the programme should continue to be undertaken – informed by a refreshed Joint Analysis of Conflict and Security (JACS) (the context) and the evaluability assessment (the evidence links) – to establish the fundamental balance, structure and content of the portfolio programme. This involves:
  1. Articulating a programme strategy: Defining a prioritised set of objectives that once established will inform how or if projects can be better aligned.
  2. Refreshing the Theory of Change (especially for the World Bank Trust Fund) to better align the projects to the portfolio aims: The evaluability assessment serves as a useful basis for resetting the Theory of Change, with space for testing ideas, and identifying where exit strategies need to be employed.
  3. Develop a threshold test for new project proposals, to ensure the programme remains focussed on strategic priorities and results; incorporating the level of support for cross-government objectives, plausibility of achieving outcomes, management capacity, risk, and exit strategies.
2. Continue to develop Value for Money (VfM): A VfM Conceptual Framework should define what VfM means for the programme in outputs/efficiency and outcomes/effectiveness to inform trade-offs between objectives.
3. Improve the evidence base and use reporting from partners to monitor programme-level results. British Embassy Cairo should consider changing reporting requirements, to include e.g. interim outcomes/milestones, to build a consolidated view of programme results are achieved over time.