Libya Annual Review - Summary Sheet

PROGRAMME TITLE: Libya CSSF Programme
Country and Region:	Libya, Middle East and North Africa
IATI Unique ID:	CSSF-06-000006
HMG Partners (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID), Ministry of Defence (MoD), Home Office(HO)
Total Budget:	ODA: £22.3m			Non-ODA: £0.2m
Budget this FY	ODA: £11.5m			Non-ODA: £0.2m
Spend this FY	ODA: £11.7m			Non-ODA: £0.2m
Original Programme Start Date: April 2017			Planned End Date: March 2021
Outputs					Score
Support for de-mining organisations, stabilisation initiatives and local conflict resolution actors to increase community peace, security and safety					A
Support for women and men, potential political parties, municipal councils and government actors to increase participation in political processes.					A
Support for improvements in the functioning of the Libyan economy at all levels: from macro and meso, (Public Financial Management) to micro-finance for entrepreneurs.					A
Support for political access & influencing by the UK Government (political engagement, strategic communication, lesson learning, programme incubation & adaptations)					A+
Overall output score					A
Outcome Assessment: A		Outcome Score: A			Risk: Medium FY 18/19

Summary of Programme Performance
Year	2015/16	2016/17	2017/18		2018/19*
Programme Score	A	A	A	B	A	A
Risk Rating (low/medium/high)	High	High	Medium		Medium
How has the programme changed during this period? Recommendations were actioned from last year’s annual review in respect to cutting the number of components in the programme.

*output/outcome

What support did the UK provide in Financial Year (FY) 2018/2019?
The CSSF provided over £11.5m in financial support across three pillars of work, seeking to address underlying causal factors of instability in Libya: a political pillar, a security and stabilisation pillar and an economic and governance pillar. Support was provided through a range of implementing partners including international and local NGOs, the UN and the direct provision of technical assistance. The programme was implemented by a core team of eight staff overseen by a Head of Programmes (HoP).

The context changed considerably during and immediately after the FY. Fighting broke out in Tripoli in August 2018 and then in April 2019 General Haftar’s Libyan National Army (LNA) launched an assault on Tripoli. Intensified fighting led to the cancellation of the UN national conference, delayed national elections and the withdrawal of many international staff. The conflict has significant implications for both the programme and the recommendations in this annual review.

Key results for FY 2018/2019:
- Peaceful Change Initiative (PCi) has achieved increased and more effective voices at the local level through the expansion of its Social Peace and Local Development (SPLD) model, adopted in 38 new communities through a trainer-mentor approach. Some 10 partnerships are now wholly locally funded.
- 10 initiatives implemented by women’s organisations promoting female economic and political participation, alongside further work on capacity building for women on entrepreneurial and business skills, were undertaken in the last year.
- 40 communities were reached directly with a variety of stabilisation interventions to improve their wellbeing and economic viability.
- The economic pillar of work has enjoyed good progress on public financial management, with new initiatives on private sector development making good advances with their design and set up.
- Some 70 interventions were completed supporting the development of effective, accountable and more inclusive political processes (i.e. elections, political parties etc.).
- Programmes were adapted and approaches altered in direct response to increasing tensions and outbreaks of violence, although further adaptation is required to respond to more recent violence.

Summary of progress and lessons learnt/actions taken since last review
- The programme team have taken a very considered, methodical and robust approach to the last annual review recommendations and have used them to help define their workplan for this year, tracking and monitoring progress of last year’s recommendations.
- Significant progress has been made on Monitoring, Evaluation and Learning (MEL) since the last review, including using an external consultancy to rework the results framework.
- In response to the last annual review, there has been a welcome reduction in the number of project components and a downgrading of one staff slot. The addition of a new full-time Conflict Adviser post is welcome but does increase costs. Plans were underway during the FY to scope work in three new thematic areas (justice, education, sub-national governance) which might stretch the programme team too much to be able to deliver catalytic results given time and expertise requirements in order to sustain the impact.
- Governance of CSSF at post has improved, including re-instating regular board meetings and revising the board Terms of Reference (ToRs).
- An implementer’s workshop was held to improve buy-in to CSSF higher-level objectives, to seek greater coordination and synergies between partners, and to improve implementing partner’s skills in running a CSSF-funded project. Evaluation of this welcome initiative appear positive, whilst offering ideas for more bespoke offerings for partners next time around.

Summary of recommendations for the next year:

1. A thorough review of the programme should be undertaken – informed by a refreshed Joint Analysis of Conflict and Stabilisation (JACS).
2. North Africa Joint Unit (NAJU) / the Libya desk should provide more regular strategic direction and engagement on significant programme decisions, particularly politically-sensitive ones.
3. Clarity should be provided on the threshold for when risk needs to be escalated to the HoP or the Senior Responsible Owner (SRO) / country board.
4. Implement the recommendations of the conflict sensitivity marker assessment.
5. Assess how to adapt the mine action programme in the current context.
6. The gender strategy should ensure that it sufficiently references and sets objectives for men and boys.
7. Continue to build capacity of implementing partners on gender sensitivity and begin to look for more sophisticated targets that would better articulate how to really embody progress on gender inequality.
8. An assessment should be made of MEL support requirements, given the ongoing revision of the results framework and the increased capacity within the team.
9. Improve consistency in partner reporting and ensure sufficient challenge by the programme staff to partners.
10. Implementing partner workshops should be designed to ensure they are of equal utility to all partners, and further bespoke options on capacity development are made available to those partners who require it.
11. When assessing the merits of implementing partners’ responses to the current crisis, Value for Money (VfM) metrics should continue to be considered
12. Work should continue on a programme wide VfM strategy, which should include scrutiny of key unit cost drivers such as consultancy costs.