Annual Review - Summary Sheet

PROGRAMME TITLE: Middle East Peace Process (MEPP) CSSF Programme
Country and Region:	Occupied Palestinian Territories (OPTs), Middle East and North Africa
IATI Unique ID:	CSSF-06-000023
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID), Ministry of Defence (MoD)
Total Budget :	ODA: £30.27m			Non-ODA: £2m
Budget this FY	ODA: £8m			Non-ODA: £0.4m
Spend this FY	ODA: £7.7m			Non-ODA: £0.4m
Original Programme Start Date: April 2015		Planned End Date: March 2019
Outputs					Score
More capable Palestinian Authority Security Forces, able to: deliver and oversee security services; design and deliver effective training; and coordinate with other agencies, the local community, and the international community					A
Increased pro-peace interventions from key constituencies					A+
Physical viability of a two-state solution preserved					A
Overall output score: A
Outcome Assessment: In FY 18/19 it is likely the CSSF made a contribution towards core UK objectives; improving the lives of Palestinians, reinforcing our relationships with key stakeholders and providing demonstrable support for our position on a two-state solution. Although delivering in challenging conditions, the programme was able to achieve and in many cases exceed, its project objectives, making a tangible difference to the lives of beneficiaries. However prospects for a return to formal MEPP negotiations remain low, and polling suggests that belief in the viability of a two-state solution is reducing in both Israel and the OPTs. Thus, whilst the projects have been well designed and delivered, and are in themselves worthwhile, external forces place ever greater pressure on the prospects for a negotiated settlement and widen the gap between success at the project level and successfully delivering programme outcomes.
Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	A	A	A	B	A	B
Risk Rating - low/medium/high	Medium	Medium	Medium		Medium
*output/outcome scores
How has the programme changed during this period? The programme has undergone substantial refinement over the review period. Programme approach and objectives have been adjusted significantly albeit within the three main thrusts of activity: state building with the Palestinian Authority; pursuing political conditions which support a progress towards a two-state solution; and conflict prevention, humanitarian and security. Projects have been streamlined for a more coherent programme. For example, the MoD delivered programme of support the Palestinian Authority Security Forces (PASF) and DFID managed security sector project working with the Ministry of Interior (MoI) to improve oversight of the security sector, have been unified for FY 19/20 to create a new three-year Capability, Accountability, Sustainability and Inclusivity Programme (CASIP). Following recommendations from Annual Review 17/18 MEPP CSSF has recruited two additional staff; including a Conflict Adviser to provide support to the programme team and oversee the newly created CASIP.

What support did the UK provide in FY 18/19?

- Support to the Palestinian Authority Security Sector including: providing the PASF with the capability and capacity to address their own training needs; strengthening mechanisms for decision making, coordination and resource management (in support of PASF administrative reform programme alongside the US Security Coordinator);
- Support to key constituencies in Israel and the OPTs to pursue the political conditions which support progress towards resolution of the Israeli-Palestinian conflict;
- Mitigating the impact of the conflict on the most vulnerable and working to uphold International Humanitarian Law.

Key results for FY 18/19:
- Provision of support to PASF resulted in progress towards a coherent training system / methodology within the West Bank and improved Palestinian-led security sector mechanisms for decision-making, coordination and resource management in security plan implementation.
- Project presenting pro-peace themes in the framework of a two state solution to key constituents in both Palestinian and Israeli communities greatly exceeded expected outputs (target 200 beneficiaries, achieved 820). Female beneficiaries of the project interviewed for the review all reported an increased interest and sense of agency in engaging with political themes they would previously have considered outside their domain. The project remains challenged in translating output to outcome by the prevailing (and deteriorating) political and security situation.
- The range of projects aimed at mitigating the worst impacts of the occupation on vulnerable Palestinian communities achieved all their objectives except in mine clearance activities in Jenin (due to cessation of US funding). The projects were notable for the significant benefit they provided to women, boys and girls.
- Overall project outputs met, and often exceeded, expectations but the deteriorating operating environment makes it difficult to assess the extent to which the programme will be able to translate that operational success into delivery at the outcome level.

Summary of progress and lessons learnt/actions taken since last review

This has been a year of change for the MEPP CSSF. Progress against project outcomes has been steady, given the operating context. The programme team have worked hard to implement recommendations made by numerous reviews, evaluations and visits throughout the year. Key actions taken include:

Strategy revision. The Strategy Board has reviewed project portfolio against the extant strategy and contextual developments. This has informed Theory of Change (ToC) revision, providing a more realistic impact level than in previous years, and helped focus programme design/project rationalisation.

Changes to staffing and roles. The programme team has added a Conflict Adviser, who will also programme manage the DFID/MoD CASIP and has also created additional staff time to focus on Gaza. This has added technical expertise to a complex programme. Political officers in both British Consulate-General Jerusalem and British Embassy Tel Aviv have been appointed leads in CSSF project design, helping improve policy-programme coherence during 18/19 programme development. The British Support Team (BST) has recruited a Monitoring and Evaluation (M&E) Adviser to review their Theory of Change (ToC) and results framework. While more a case of re-framing the military contribution to align with CSSF practice, the process has undoubtedly resulted in a more coherent ToC and realistic results framework. To overcome the strain between MoD mandated tour lengths and the need for continuity, the BST has given contracted consultants a more prominent role, particularly in sustaining stakeholder relationships.

Driving Value for Money (VfM). During programme design for FY 18/19, MEPP CSSF has taken steps to deliver better VfM, achieving economies in the Legal Aid project, efficiencies in the Polling Project, and closing projects where they were not achieving HMG objectives.

Lessons Learned.
- Financial Management. The profile of MEPP CSSF spend makes it incredibly difficult to meet Quarter 3 spending targets, despite close and effective management by the team;
- The programme team has actively sought external challenge and support. This has made a valuable contribution to portfolio and programme design and management;
- The Programme is right to be ambitious, but has to be realistic about the scope to influence outcomes when the wider prospects for the MEPP are deteriorating.

Summary of recommendations for the next year

- Seek to quantify the total (second and third order) benefits of MEPP CSSF projects to the UK Government. Particularly in terms of access and influence, understanding the volatile political and conflict situation, and demonstrating UK support for our position on a two state solution to the MEPP;
- Review the stretch between outputs and outcomes and ensure they are realistic. Given the vulnerability of projects to the prevailing political and security conditions it is important to have realistic ambitions for UK Government programming;
- Ensure a consistent approach to project risk management. Set risk levels for each output and monitor regularly with implementing organisations;
- Consider sustainability and contingency plans for early exit if required. Common to two outcome pillars of the MEPP CSSF approach is the variable duration and nature of MEPP projects. The programme team should develop detailed sustainability plans and early exit contingency plans to achieve the greatest possible impact even after UK Government support has ended.