Annual Review - Summary Sheet

PROGRAMME TITLE: North Africa CSSF Technical Assistance Facility (TAF) Programme
Country and Region:	North Africa Regional, Middle East and North Africa
IATI Unique ID:	CSSF-06-000022
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID), Home Office (HO), Ministry of Defence (MoD)
Total Budget:	ODA: £6.4m			Non-ODA: £0
Budget this FY	ODA: £4.7m			Non-ODA: £0
Spend this FY	ODA: £4.7m			Non-ODA: £0
Original Programme Start Date: April 2018		Planned End Date: March 2020
Outputs					Score
High quality, relevant, demand-led, conflict- and gender-sensitive Technical Assistance is delivered through the TAF					A
The TAF generates learning on how TA can bring about change and shares this across North Africa Good Governance Fund (NAGGF) programmes					B
Overall output score:					A
Outcome Assessment: Insufficient/unreliable/incomplete evidence to demonstrate likely contribution to outcome
Outcome Score: B			Risk: Moderate

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	N/A	C	A	A/B	A	B
Risk Rating - low/medium/high	N/A	Medium-High	Medium/Low (Moderate)		Moderate
*output/outcome scores
How has the programme changed during this period? / A new Theory of Change and a Results Framework were developed in May 2018, and there has been a refresh of the Programme Document in January 2019. There has been a shift from internal facing analysis to external facing TA.

What support did the UK provide in FY 18/19?

The TAF is a component of the NAGGF. It provided short term technical assistance inputs in support of NAGGF and regional National Security Council (NSC) objectives. The outcome statement for the TAF is: “Institutions in partner countries commit to, invest in and start to implement reform, and HMG scales up programmes and increases its political access and influence.”

Technical assistance projects were delivered to support Algeria, Egypt, Libya, Morocco and Tunisia and to a lesser extent regional objectives. They comprise research, advice and scoping work on behalf of Posts; and technical assistance to partner governments, including through multilaterals.

Technical assistance was provided by the TAF supplier, Coffey, using either its own personnel or through sub-contracts, including singleton consultants embedded in partner institutions.

Key results for FY 18/19:

A major World Bank loan will build on TAF support for banking reform in Tunisia, and funding from other donors has been secured for the Libyan Ministry of Planning.

A number of new relationships have been built with regional governments, notably in Egypt and Tunisia, and with civil society in Algeria.

TAF technical assistance has helped progress economic and education sector reforms in Tunisia and Egypt, and supported improved Libyan coordination of donors.

Trade and Investment studies in several countries are being used by the Department for International Trade (DIT) to inform its future work.

Summary of progress and lessons learnt/actions taken since last review

The TAF theory of change and results framework have undergone substantial revision since the last Annual Review; a new results framework has been in place since May 2018. A May 2018 review of monitoring, evaluation and learning (MEL) led to a new MEL strategy and strengthened MEL systems, including institution of bi-annual reviews by Coffey, and strengthened regular reporting. Linkages to the NAGGF MEL component have been strengthened and the TAF is to be included in thematic reviews.

There has also been a change in emphasis from internally facing work commissioned by Posts towards technical assistance to partner governments. A refresh of the programme document was also undertaken in early 2019 and approved by the North Africa Working Group (NAWG) in March 2019. This will govern activities in 2019/20. It includes a new approach to managing the budget, introduction of key performance indicators to drive value for money, and a streamlined approvals process for decision making.

The level of ambition on gender has decreased. The programme team felt, in line with Coffey’s January 2019 biannual programme review, that the demand led nature of the Fund made it unrealistic to expect transformative gender equality activities to form a substantive part of the project portfolio. This was reflected in removal of an output indicator for ambition to exceed minimum standards on gender sensitivity. This decision is currently under-review as the programme team relook at how gender sensitivity is recorded and prioritised within this programme, in line with CSSF policy on mainstreaming gender equality within all programmes.

A key open action from the last Annual Review is for a governance adviser to undertake a review of the prospects for sustained reform resulting from TAF work. That is now planned for 2019/20. It is not clear why this was postponed. Under the new MEL strategy Coffey will gather beneficiary feedback.

After a slow start Morocco has developed a number of promising activities for delivery in 2019/20. The environment in Algeria remains difficult. Communications between Posts and Coffey, although generally improved, remain a work in progress requiring continued North Africa Joint Unit (NAJU, responsible for managing the TAF) attention.

Summary of recommendations for the next year

Greater rigour in monitoring and reporting, including country visits during the next annual review to facilitate access to a greater range of stakeholder perspectives, and give increased attention to learning across TAF themes and to inform the NAGGF more broadly.

Strengthened governance oversight to ensure alignment with strategic objectives for the Fund. Improve communications between Coffey, Posts and NAJU.

Engagement with the North Africa MEL component to NAGGF to develop indicators across the different dimensions of value for money. Strengthen financial management, including timeliness and accuracy of forecasting.

Improve clarity of risk reporting and establish an issues log.

Secure specialist social development advice to review the approach being taken to gender.