Programme Completion Review - Summary Sheet

PROGRAMME TITLE: Syria CSSF: Community Support in North Western Syria Programme
Country and Region:	Syria, Middle East and North Africa
IATI Unique ID:	CSSF-06-000024
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID)
Total Budget:	ODA: £15.3m			Non-ODA: £0m
Total Spend:	ODA: £16.09m			Non-ODA: £0m
Original Programme Start Date: April 2018		End Date: March 2019
Outputs					Score
Basic community policing, security and justice services provided					A
Emergency search and rescue support provided to communities					B
Quality learning opportunities available in formal and non-formal education spaces					A
Livelihoods opportunities maintained and developed					A
Increased capacity and ability of local councils to deliver services and increased engagement between communities and local councils					A
Overall output score					B
Outcome Assessment: / The programme largely delivered against outcome targets as recorded in the results framework. Moreover, we assess that the withdrawal of the North-West Syria CSSF programme was managed responsibly in the circumstances, by the CSSF programme team as well as implementers. Reputational costs to UK Government were modest, but could have been mitigated further by engaging implementer and international partners earlier, allowing the impression of a consultative process.
Final Outcome Score: A			Risk: High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*	2018/19*
Programme Score	N/A			B	A
Risk Rating -	N/A			High
*output/outcome scores
Elements of this programme continued from the 17/18 Syria Resilience and Syria Security Programmes, including continued support to the Syria Civil Defence (SCD), service delivery and local governance.

What support did the UK provide?

Over the course of 18/19, the UK withdrew CSSF support provided to moderate communities in Idlib, Aleppo and Eastern Ghouta over the previous six years in four sectors: community policing and access to justice, education, governance and service delivery, livelihoods and economic development.

The decision in June 2018 for withdrawing the majority of programme activity from the North West was in response to change in the operational environment. The rationale being re-alignment of delivery of services under CSSF against the political and policy realities while maintaining humanitarian type activities supporting the Syrian Civil Defence (White Helmets) project. The UK sought to withdraw in a responsible manner that did least harm and avoided a hard stop in support for moderate communities. A responsible withdrawal also meant avoiding exacerbating the conflict, protecting the UK’s reputation among moderate Syrian communities, preserving the UK’s reputation as a responsible donor, and avoiding donor flight.

The UK continues to provide support in the form of funding, training, capacity building and equipment to the White Helmets who play a critical role in responding to needs, acting as a first responder and providing essential search and rescue facilities.

What results did the programme deliver? Will they be sustained?

The programme largely delivered against outcome targets as recorded in the results framework. Moreover, the withdrawal of the North Western Syria CSSF programme was managed responsibly in the circumstances by the CSSF programme team as well as by implementers, although these efforts were not formally measured. Results achieved, and whether they will be sustained, varied across the sectors supported by the programme.

Education support exceeded targets for numbers of students enrolled in supported formal schools and for teachers and staff supported across Syria with approximately 260,500 students (50%) female and 12,165 teachers and staff. The programme is expected to continue until February 2021 with DFID and EU funding.

The support to livelihoods was found to have generated demonstrably sustainable projects and helped to improve the economic inclusion of almost 12,000 individuals with 427 Small and medium-sized enterprises breaking even three months after support ended.

The UK announced its decision to draw down support to community policing and access to justice in June 2018. Third party monitors found that when support ended in October 2018, the Free Syria Police were providing policing services to around 1.1 million people, including significant numbers of women, children and Internally Displaced Persons (IDPs).

The Tatweer governance programme achieved its aim of a responsible withdrawal, as it was re-purposed into a humanitarian relief programme, which delivered tangible improvements to the daily lives of beneficiaries in target areas (reaching over 700,000 individuals in the final quarter). It also made progress in engaging significant numbers of women in decision-making.

Syria Civil Defence Urban Search and Rescue teams each conducted an average of 49 operations in quarter three, while a survey-based study from February 2019 concluded “communities perceived SCD to be a valuable actor in providing essential support” and generally viewed SCD as capable and responsive.

What lessons have been learned?

Responsible withdrawal is a legitimate objective – and the efforts to achieve it among CSSF teams and implementers warrant as much result framework attention as more traditional outcomes and outputs. Implementers should be encouraged to include withdrawal preparations and effects in their log frames, and third party monitors could be utilised to monitor cross-programme withdrawal indicators and risks, e.g. perceptions among communities, implementing partners, and even among other donors.

Communication and advance planning may mitigate the negative impacts of withdrawal on recipient populations, but will not avoid them altogether. Anecdotal reports noted sudden unannounced drawdowns from other donors that provoked greater negative reactions and consequences than the UK withdrawal. However, it was also reported that there was a perception in communities served by the Free Syrian Police that the donor group had abandoned them at a time when they faced great physical danger.

There is benefit in engaging implementers and partners early in a decision-making process that is likely to result in programme closure. Implementer input, including the opportunity to propose mitigating programme adaptations, may help elaborate proposals for timelines and handling. It is arguably unfair to feign a consultative decision-making process whose outcome is already given.

Joint programming with other international donors, as well as informal coordination, can multiply programme impact and scope. It can also risk the creation of projects that are too big to fail. In a potential withdrawal situation, engagement with international partners must weigh the risk of provoking donor flight before a decision to withdraw has actually been made, against allowing other stakeholders a voice, which can help to mitigate the reputational costs to HMG, even where the final decision runs counter to other stakeholder preferences.

While formal coordination between stabilisation and humanitarian activities may not be possible, in part for reasons of principle, communication often is possible. Information and data sharing can help humanitarian and stabilisation actors understand needs and respond accordingly. Stabilisation-humanitarian coordination (and cross-departmental cooperation more generally) was greatly helped by co-locating teams in the same office in Istanbul. Continuous, informal communications and relationships between FCO and DFID staff helped bridge the silos of security and politics vs resilience and humanitarian aid.

Remote programming presents significant challenges and requires intensive management but can achieve impressive results. Clarity on risk ownership and appetite are particularly important given the significant risks involved.