[1]Annual Review - Summary Sheet
[1] The current merged Iraq Programme reflects the combined programme value of the former programme strands Security and Justice and Governance and Resilience Programmes 18/19 that extend a number of projects under the Governance and Resilience Programme from previous years.

PROGRAMME TITLE: Iraq CSSF Programme
Country and Region:	Iraq, Middle East and North Africa
IATI Unique ID:	CSSF-06-000029
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID), Ministry of Defence (MOD)
Total Budget:	ODA: £72.2m[2]			Non-ODA: £4.35m
Budget this FY	ODA: £32.9m			Non-ODA: £0.4m
Spend this FY	ODA: £32.6m			Non-ODA: £0.3m
Original Programme Start Date: April 2018		Planned End Date: March 2019
Outputs					Score
Job generating rehabilitation of damaged infrastructure and economic markets is government-led, and takes place in all HMG target provinces except Basra.					A
Sub-national governance actors in Basra, Ninewah and Anbar better understand citizen’s needs (men and women) and have increased ability to develop the plans and strategies needed to respond to them.					C
Security sector leadership (National Security Advisor, Ministry of Peshmerga Affairs and police) are better able to pursue reform					B
Civil society and target communities (men and women) empowered and enabled to advocate for their needs from government, and critically appraise government delivery					A
Target communities and audiences (men and women) brought together to identify and address drivers of conflict, and build social cohesion - offline, online, and on-air					A+
Overall output score					B
Outcome Assessment:
Outcome Score: B			Risk: High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Governance and Resilience	A	A	A	A	n/a	n/a
Security and Justice	A	A	B	B	n/a	n/a
Iraq CSSF Programme	n/a	n/a	n/a	n/a	B	B
Risk Rating – / Low/medium/high	High	Medium-High	High		High
*output/outcome scores
During the past financial year, a single programme has been created through merging the previous two CSSF programmes. This has yielded efficiencies in project management and reporting. The merger means however that it is not possible to compare scoring with previous reviews. The separate reviews in 17/18 were scored as A (Governance and Resilience), and B (Security and Justice).

What support did the UK provide in FY 18/19?

Against a context of continuing political instability and insecurity, in 2018/19 the UK Government spent £32.8m through the CSSF in Iraq. This was spread across a number of projects that sat on FCO, DFID and MOD baselines. The activity delivered ranged from providing strategic security reform advice, through to contributing with fellow donors to the rehabilitation of damaged infrastructure in areas that had previously been under Daesh control.

Key results for FY 18/19:

Contribution to the return of 4.1m displaced persons in newly liberated areas, and benefit to 5.58m Iraqis through essential service provision, facilitating reintegration of Iraqi citizens back into local communities. The related outputs scoring A and A+ were driven by strong performance of the Implementing Partners and commendable oversight by the CSSF Iraq Team.

Improvement of provincial government technical planning skills was limited.  However, activities to strengthen target governorates outreach/needs assessment of communities provided high quality analysis of political, conflict situation and gender issues.

Intractable politics surrounding the security sector and further length of time to develop trust and good relationships hampered full achievement of this output.  But there was notable progress of security sector leadership engagement with key Iraqi security institutions and apparatus, with technical advice and reform projects supporting both the Government of Iraq and Kurdistan Regional Government.

Summary of progress and lessons learnt/actions taken since last review

Overall, the picture is one of progress, notwithstanding the need to be mindful of the need for realism about what the CSSF can achieve. The team worked hard to undertake a CSSF programme merger – bringing together the previously separate programme pillars. The team also demonstrated commendable flexibility – for example, taking actions to close the Sub National Governance project before the end of the financial year due to it no longer meeting UK Government objectives.

The main lessons identified through 18/19 include: the need to allocate enough staff time to ensure work on the programme documentation following the merger is completed to ensure coherence and usefulness. Although much creditable work has been done, the team realise that the scale of the change was beyond original expectations. An example was where indicators were amended without a corresponding change in the Results Framework (RF). Undertaking the merger mid-year was ambitious. Identifying such a change as a priority that must be resourced sufficiently to reach full completion would be a top lesson from the past year.

In total, thirty recommendations were made in previous Annual Reviews in 17/18. It is noted that the clear majority of these have been completed, were not applicable, or are no longer relevant due to projects having ended.

In 17/18, Annual Review recommended developing the result framework guaranteeing relevance to the Theory of Change, NSC Objectives and the Iraq Joint Analysis of Conflict & Stability (JACs) with input from a Monitoring and Evaluation advisor. This was completed in 18/19 but will require a continual refresh for future programmes. The review team found that further development could be made towards a more robust set of indicators for gender and conflict sensitivity. Work also should continue to assign risk ratings to programme outputs in results frameworks and ensure that results and activities generated by all implementing partners and advisors are captured in the results framework appropriately.

The Iraq CSSF team to utilise additional support to improve distribution of Monitoring and Evaluation data under a Monitoring, Evaluation and Learning plan to establish more formalised systems for dissemination and coordination of messaging across platforms, staff and implementers.

The need to refresh and carry out a JACs that should offer a proportionate coverage of conflict risks and the issue of inter-tribal conflict (rather than inter-sectarian conflict as a source of instability). The programme should also have conducted a conflict sensitivity audit which is due to take place in May 2019.

Summary of recommendations for the next year

The CSSF portfolio has been the subject of significant change during the reporting period, all designed to improve the efficiency of managing the programme, and to make adjustments that would deliver a better impact. There is evidence that further improvements can be achieved in the following areas of recommendation: having a clearer vision of the CSSF’s purpose, putting in place ways to share information clearly and in a timely fashion, ensuring that conflict sensitivity/gender/safeguarding are well integrated across the portfolio, building the coherence of UK Government activity by maximising CSSF linkages, keeping processes and documentation (including monitoring & evaluation tools/methods) updated in line with the portfolio changes, and ensuring that the information being collected is a reasonable reflection of the scope of the programme.